## Checklist Templates
Id | Type | Name | Values | Prompting Name
e547b5b1-d0a1-4cec-bfbb-544dc85da65d | checklist | ITP - Flood Recovery Combined |  | ITP - Flood Recovery Combined
a8f09b49-d702-416a-8383-25113eff35ac | section | Preliminaries - Project Management Responsibility
83347f70-cd0d-4a71-8673-269330b38407 | checkpoint | Possession of Site
deec7287-f45f-503b-b8ef-d0ca3247f6c0 | textbox | Date of possession:
b70ba7f3-dd1b-46fd-8983-5b4f3b788a29 | checkpoint | Dial Before You Dig (DBYD) and Permit to Excavate completed and signed onto by personnel - HOLD POINT REQUIRED
8d048e8e-2245-4c96-a09e-03411caea7b5 | signoff | Confirmation of DBYD uploaded to CONQA and acknowledged by RCC PM and Supervisor
74b80535-a657-485c-ac49-ae3758ccf9b9 | checkpoint | TSC Scope Agreed
5a0831a4-26d4-5cce-acb8-d48dbd6495dd | textbox | (Upload scope doc here)
7157baa8-92cf-4549-b69e-66d0036664df | signoff | Confirmation of Scope and Extent of Works with Project Team, including RCC and TSC
65756d7b-e275-4edd-9720-c5b9bfca6ed9 | checkpoint | Variations to Scope
cfa006d3-348e-5083-9409-5ab64fcbd67f | textbox | Details any Variations below and confirm if these have been uploaded to Assigner:
b4c738fd-5b90-4d35-997f-5ddebfedb073 | signoff | Confirmation of any variations to scope of work
7fd88817-f76a-4a0b-a290-9e845dba3913 | checkpoint | Testing required for the scope:
d6072286-1a93-53b1-ab84-7385f69a526c | textbox | Concrete testing
88d1b87d-1609-5b0a-84bd-684e59ae1ddf | textbox | Density Testing
d0f33317-0445-55bd-a953-e62174841e29 | textbox | Gravel Testing Other
077d7b80-c958-5311-ba3f-be1734362d79 | textbox | Other
bb5e820b-4218-4834-bdf6-09044bcc5426 | checkpoint | Traffic Control – TGS approved and appropriately selected for the works
44faa37c-cabe-4042-8cf2-862b05fefc87 | checkpoint | TGS No
84e3c3b3-78d4-424a-a1d4-69c10c6709fe | checkpoint | Erosion and Sediment Control:
df89c83d-8e69-5328-b6de-8f997e9a9e77 | textbox | Silt Boom Earth Bund
b8452f3f-0925-5881-b9ea-0097631a7ca2 | textbox | Sediment Fence
9d4719f8-ea05-58b7-8a3b-dddbd5f1104f | textbox | Other
9abbc2e0-e059-46fc-aab9-20c1f818f8e3 | section | C213 Earthworks
748d7293-2b10-4781-aabf-343cbc996965 | checkpoint | Minor clearing of vegetation undertaken – where applicable.
4499ec1f-8313-414a-80fd-7e559408969e | checkpoint | Demolition works / Spoil Removal undertaken and spoil removed from site to Quirks Quarry - HOLD POINT REQUIRED
826175d6-2821-55cd-851b-8e12828d6018 | note | TSC Direction
1c9bce0d-29d4-4eda-bc3a-ea26892720df | checkpoint | Is subgrade or sub base suitable
1af0709a-622f-46f8-96e7-53a86986d9b2 | signoff | HOLD POINT: If unsuitable is encountered TSC to be notified prior to works continuing
13829375-1942-42d1-887d-8d3f5e6f3314 | checkpoint | Table drains shaped to allow water to flow freely and best marry into existing surfaces.
27f6be8d-f4e4-489d-8360-0daf52390f89 | section | C242 Flexible Pavements
9b3a76d0-db17-46ef-a579-eaed9e59271e | checkpoint | Proof roll subgrade: If foundation fails TSC to be notified and to site instruction required - HOLD POINT REQUIRED
3045f108-f4ae-5ddb-a8d1-825d8d602377 | note | TSC Approval
e4247952-5028-4716-8ba6-4c35a0e494bf | signoff | HOLD POINT
daa9681d-d8a8-4d0b-8011-7b6e27686363 | checkpoint | Road base Material: Material source along with conforming material NATA test certificates have been submitted and approved by the Principal (Material Stockpile Lot)
82351fd0-7695-46b1-9a40-20d3706c142f | checkpoint | If testing required - Layers compacted to 100% Standard compaction for full formation width. Compaction testing to be done 1 test per 500m2, minimum of 3 test taken at a time (per lot) or as directed otherwise.
f9a49572-a28e-4a8f-b410-869907bff6ef | checkpoint | Levels of gravel marry into existing and deviation does not exceed 12mm over the length of a 3m straight edge.
682915e8-6be0-4480-b7b2-9e4f250dc02b | signoff | HOLD POINT – Carry out a proof roll of finished pavement where applicable
44b96ee5-07bc-44e6-ad9b-08af1bab6814 | section | Rock Revetment
434142de-6c79-4e13-b082-8a98259bb0c9 | checkpoint | Geotextile – A34 Geotextile separator placed prior to rock placement IF DIRECTED or WITHIN SCOPE
e2b57e31-a6cd-423e-8f97-5926e67fbe87 | checkpoint | Rock Placement - Rock to be placed in completed drain profile as per agreed scope. Correct Rock Size Placed
db56694c-4f9e-5b67-95b3-81bb8a05f89f | textbox | 40-70mm - Quantity
f277fbdc-96c9-5518-a47b-35d374b7af3a | textbox | 150-250mm - Quantity
c4974332-1556-5786-ada6-151fc20c47d3 | textbox | 300-500mm - Quantity
9ec1a032-2c78-5437-89ce-af19b490ce9e | textbox | 600-900mm - Quantity
9866f571-fb56-5d8f-8db8-e6d083fb9283 | textbox | Other
4e126908-31e7-4dfc-8da9-6c2b62ceb774 | section | Grouted Rock Pitching
cba87760-c691-4da0-9438-640543ba1052 | checkpoint | Existing rock to be grouted as per agreed scope
fb78ba51-f918-5ec6-9eaa-dd8fce0a5bac | textbox | Approx m2
376b41c9-f347-42d1-9c56-4b108c5dcda0 | checkpoint | Rocks to be cleaned down at end of grouting for neat finish
d30db0c4-9c61-4ecd-91b2-ca49840e6ad9 | section | Concrete Works
a4b39cf5-a0b0-4dd2-bd50-dc5feed15352 | checkpoint | Excavation & Preparation - Suitable subgrade material and prepared to suitable surface
3709a941-e59c-4223-a98c-1f060a46d780 | checkpoint | Formwork & Reinforcement - Dimensions and positions of forms shall be carefully checked after the forms are erected. Forms shall be aligned accurately and the location of all fittings, hold formers etc. checked prior to placing of concrete.
40412a65-f284-4e42-be7f-3a5ee073eacc | checkpoint | Formwork & Reinforcement - Placing of reinforcement as per agreed scope, with reference to Typical Construction Details. Reinforcement to maintain a 50mm vertical and horizontal cover unless directed otherwise.
ab4c65f7-1a0c-55d8-aa85-0ded6be607f8 | textbox | TSC Approval
34b028fb-66ed-42e8-9cb5-a14e57f8b06d | signoff | HOLD POINT – PRE-POUR INSPECTION The formwork shall be inspected by the Superintendent, and the placing of reinforcement in the spaces formed, where specified, shall not commence until the formwork is approved by the Superintendent.
875b1a54-6f90-4ec3-8a47-a34fc3dfd604 | checkpoint | Ready Mix Concrete - The concrete shall be mixed and delivered in accordance with the requirements of AS 1379 - PLEASE ATTACH OR TAKE PHOTOS OF LAST DOCKETS FROM EACH POUR
ba254f67-baa5-5973-aced-0d79d08bc581 | textbox | Concrete Mix Used:
b002126e-9cd4-5055-a65c-f013de92fc4b | textbox | 20/20/80
ab94d363-52c8-5e1a-8924-1d21f742b628 | textbox | 25/20/80
d85c42d0-d698-540f-8f2d-2824d50098d9 | textbox | 32/20/80
724669f4-81a7-5548-ad29-6cefb2cbd8c1 | textbox | 32/20/100
fafd4d73-4c8b-502c-a5d0-4510b48d4b75 | textbox | 40/20/80
b261ab8d-fb88-5e47-b978-5774c2ed7bf7 | textbox | Grout
2ea9a3cf-8628-57e6-8105-cb43b44d30f2 | textbox | Shotcrete Shotcrete w/ poly-fibre
67c58a2a-ce95-599a-9551-c286ef433107 | textbox | Other
df406511-0a14-434b-85bc-642e112e3cb0 | checkpoint | Concrete Placement - Concrete finished to TSC Standard
a0250777-c3a4-4fc3-9a9c-31bc5153487a | checkpoint | Two pairs of test specimens shall be moulded for each 15 cubic metres of concrete, or part thereof, one pair being intended for the 7-day test if required and the other pair for a 28-day test.
28da5238-7b5e-4c95-9165-992eae19c9bc | signoff | WITNESS POINT: Concrete test specimens to be taken in presence of Superintendent or Superintendent’s representative
caf86df7-c8e6-40a2-9d59-ab422d303aff | section | Stormwater Drainage
6589e29f-6aee-4e22-8d6a-84d1034b8aa0 | checkpoint | Stormwater components installed as per scope of works - HOLD POINT REQUIRED
979ac19f-73cc-5a80-86ad-1e500310a5e9 | textbox | Size & quantity of pipe & pits installed
893b0e0c-e4e2-5d53-8308-45ce6ad9920f | textbox | Other
ff7bfe5c-1b0d-4c27-ae4f-0e105d32ee2b | signoff | HOLD POINT: Inspection prior to backfill
0ba69685-6ea2-412c-ab89-5010c50f0111 | checkpoint | Density testing of pipeline required if within roadway:- 100% compaction to be achieved
130d2b12-0472-43f5-af6c-01f3f8a957b1 | section | Demobilisation
9688c3c0-d2a4-489d-8cc7-08d75b328534 | checkpoint | Site left tidy & DM spray mark removed
1db51bf5-0574-4bde-ba11-8dd581b63eff | section | Close Out
b59bfe74-8758-4371-ab0d-b1210a53c849 | checkpoint | Site Handover: All works complete, demobilised and site handed back to TSC
45097fcd-2c9a-594e-b19d-3058f3f26768 | textbox | Date of handback
0fef3379-59d9-4215-8d3b-3b0601cebeb1 | signoff | TSC Signature
966fbd6c-efc7-48fa-94f1-87f164e0d3ee | checkpoint | Verify conformance including close out of NCR’s
5885fb03-6f69-5c06-8bf9-2bc75018cbc7 | textbox | NCR NO:
93c4a92f-233a-5c02-9690-b0a949e187f5 | note | NATA Certificates
81a62b56-6729-5c84-bd64-b0053197ea7e | note | Survey Report
ef604807-0a18-5333-8f35-adfa3ea2015e | note | Geotechnical testing reports
05774f72-b919-5a32-a1da-21042c2a4880 | note | Concrete test reports
d5a75f28-0c81-526c-a2bb-dd68be86fc04 | note | Proof of works report
b87c0249-7aa3-5815-9fbb-baeec2b84a49 | note | Photographs of completed work
eafdfaac-0b67-4185-b6f4-743b7f700772 | checkpoint | Damage No. (DM) signed off and closed by PM or representative
594f50a2-ab52-469c-95e6-831977af456f | signoff | Signatures
84547920-a74c-4ece-b188-4ee26828e461 | checklist | ITP-001 - Installation Of Stormwater Drainage |  | ITP-001 - Installation Of Stormwater Drainage
cb94caea-bd31-482b-8511-cd652d7d468d | section | Pre-Construction
abc8bbde-8f2d-4aa0-bc10-df523f7f303c | checkpoint | Are approved "For Construction" plans available?
d4ac7a61-b635-4c8e-8331-ca2bfe3359da | checkpoint | Are Earthworks completed to Finished Level?
750ca514-2521-43db-b3eb-e093107661e3 | checkpoint | Has the Client been advised of start date?
22ea6f2d-1369-5dee-bd76-b1f6af1b4c12 | textbox | Pit / Line Information:
c93655f9-7d0d-5a33-ad4b-a021e4974d4e | textbox | Date Works Commenced:
7b76357f-b80f-483f-b7e5-106f58ad9fc6 | checkpoint | Existing services located and clearly marked (attach DBYD if applicable)
1473847f-0d23-4d12-afdd-6e9ddb307e63 | checkpoint | All materials delivered to site have been inspected thoroughly and: a) Are free of damage/cracks b) Pipe class, type and size matches plans. (upload images of damaged materials here)
4d324994-4a89-4ef0-af74-7ab074f3ed3c | signoff | HOLD POINT - Clients representative to acknowledge materials have been inspected and are free of damage/cracks.
ff130204-b5ba-4448-8876-a33379016e01 | section | Construction
ce15851d-c1ad-4f3d-9f5d-bcefc500d450 | checkpoint | Excavation Permit Completed
0315e98d-f93a-47a6-a669-a205ef3b1d21 | checkpoint | Pits/Trenches set out clearly & accurately
ddb0b98c-b9bb-416c-bb89-67478c8b4627 | checkpoint | Pits excavated to depth and checked with laser (allowed for 100mm bedding)
3b9c70fd-65c3-4707-a6e5-e75db0b34a05 | checkpoint | Pits exceeding 1.5m are correctly battered or compliant shoring installed
67309e00-5227-43b2-ac41-b803c91e481b | checkpoint | Pits Installed at correct height and orientation
6372a54d-6b46-4339-ab6e-8aace1acda57 | checkpoint | Trenches excavated to depth and checked with grade laser (allowed for 100mm bedding)
c15a3ff4-9078-4b0e-9e01-d71a758569cb | checkpoint | Trenches exceeding 1.5m are correctly battered or compliant shoring installed
50e8fd1a-2b7f-4c7e-8669-51ee79090641 | signoff | HOLD POINT - Presence of groundwater or contaminated material authorisation to proceed Requested & Approved (If Applicable)
202ea3f2-d935-40da-9309-f8dee1750ec9 | checkpoint | Trench bedding material installed as per specification
8db7362d-fcdc-41df-af19-8c1d3755efc9 | checkpoint | Pipe laid to grade (as per drawings) ensuring socket faces upstream and is free of foreign materials prior to installation of adjoining pipe
4e60f8d5-5f3a-471b-845d-466deb3fc608 | checkpoint | Each joint visually inspected (rubber rings, witness marks, etc) and lifting holes plugged
44184048-fa72-4a64-8662-233bf6d26a69 | signoff | HOLD POINT - Clients representative to acknowledge compliant Pipe/Pit Installation
96c18bbd-f8aa-4576-8e7c-e14a37c0e28e | section | Backfill
75600bb9-c18f-4d6c-a64e-134ffa288510 | checkpoint | Suitable material backfilled in layers not exceeding 150mm compacted thickness
ed276ddd-0931-4604-8024-7c3d81b089b1 | signoff | HOLD POINT - Clients representative to acknowledge Bedding, Haunching & backfill compliance
161305c1-b457-4106-976c-9f9d7e2e5d65 | checkpoint | Compaction testing Completed and Complies (attach compaction test results)
b406617d-6ae7-4a8d-b960-9c14c2ece076 | checkpoint | CCTV Carried out upon completion of works (If applicable)
c6a85456-2463-5054-b9cf-cd62d14b3879 | textbox | Date Section Completed
43cd04c8-f0e2-5c3f-832d-051fe8f49f71 | textbox | Additional Comments
9d39f5c5-f7a1-5a62-8cc5-bebc92d02c74 | note | Concrete Dockets attached
9bc45165-8474-5525-ab37-68740e7204d0 | note | Concrete Test Reports Attached
dd6e6dd1-1fe6-56ea-8648-34c93aa84853 | note | Images of works
46f6858a-7fe4-4d36-a82b-4c3f28dd7f99 | signoff | Signatures
e32ab440-910f-4957-ac5d-2f3a39d4d08f | checklist | SYS - ITP - Flood Recovery Combined (archived) |  | SYS - ITP - Flood Recovery Combined (archived)
da4291ba-661e-4495-8845-d5df5142ea97 | section | Preliminaries - Project Management Responsibility
12fef82b-aa37-40db-8a68-c2e17c22fd63 | checkpoint | Possession of Site
deec7287-f45f-503b-b8ef-d0ca3247f6c0 | textbox | Date of possession:
0534d861-d593-4b99-9bc7-9da5c8c7ff3c | checkpoint | Dial Before You Dig (DBYD) and Permit to Excavate completed and signed onto by personnel - HOLD POINT REQUIRED
278162db-9fb7-5294-8972-c053a93b0254 | textbox | TSC Scope Agreed:
58ebee3a-5ec6-417d-a581-49abbc36666c | signoff | Confirmation of Scope and Extent of Works with Project Team, including RCC and TSC
5d39d263-115a-46b8-b34a-1029c7009479 | checkpoint | Testing required for the scope:
5a0831a4-26d4-5cce-acb8-d48dbd6495dd | textbox | Concrete testing
b2deff86-2233-5b47-8e9f-5d4a0b87ad91 | textbox | Density Testing
7a044b24-753f-50bd-a442-306cd8f56748 | textbox | Gravel Testing Other
2516ec8b-6a1c-5bb6-baee-065abc6a4483 | textbox | Other
ca1cf830-9def-4294-a07f-85424cadda6d | checkpoint | Traffic Control – TGS approved and appropriately selected for the works
92abbbe1-e569-4193-9f54-0a44b053cc45 | checkpoint | TGS No
58ce92e1-6fb2-4953-a09d-c05cd8fedcd9 | checkpoint | Erosion and Sediment Control:
71113da9-5057-5e21-9ba1-4e6d9fbf936c | textbox | Silt Boom Earth Bund
eeea725e-199a-5c8e-9efe-1f306ad7607c | textbox | Sediment Fence
a565e387-c2dc-52c1-b58b-aae948045caa | textbox | Other
40eb814e-ee89-4dc1-a3c0-e5da98a3537d | section | C213 Earthworks
7f08798c-5769-4b0b-9fb9-7918ee3f7abf | checkpoint | Minor clearing of vegetation undertaken – where applicable.
b3be097f-bc68-434e-9f9d-5ee3635905e8 | checkpoint | Demolition works / Spoil Removal undertaken and spoil removed from site to Quirks Quarry - HOLD POINT REQUIRED
826175d6-2821-55cd-851b-8e12828d6018 | note | TSC Direction
ff9314af-f695-4f47-991e-283b036e8a4b | checkpoint | Is subgrade or sub base suitable
1f11c6a9-a206-4322-a87d-310f8ac8e580 | signoff | HOLD POINT: If unsuitable is encountered TSC to be notified prior to works continuing
68ab0341-16a6-44ab-a8b9-8a3be471e33c | checkpoint | Table drains shaped to allow water to flow freely and best marry into existing surfaces.
6f1956ee-2178-4eb9-9829-433edefe0dab | section | C242 Flexible Pavements
eb29b47f-1a5f-4150-be91-f18b925db32b | checkpoint | Proof roll subgrade: If foundation fails TSC to be notified and to site instruction required - HOLD POINT REQUIRED
3045f108-f4ae-5ddb-a8d1-825d8d602377 | note | TSC Approval
d21d4fb0-e74a-499d-845c-685f92807ad6 | signoff | HOLD POINT
c816d9d0-a6a8-4d98-878f-76f8bc5cf68b | checkpoint | Road base Material: Material source along with conforming material NATA test certificates have been submitted and approved by the Principal (Material Stockpile Lot)
5980ff9c-95b6-473e-be34-6b65f9530ab0 | checkpoint | If testing required - Layers compacted to 100% Standard compaction for full formation width. Compaction testing to be done 1 test per 500m2, minimum of 3 test taken at a time (per lot) or as directed otherwise.
e25652b4-1956-45a9-ba57-9c314d414a46 | checkpoint | Levels of gravel marry into existing and deviation does not exceed 12mm over the length of a 3m straight edge.
12b702b0-12b3-4083-b090-009a1b20f153 | signoff | HOLD POINT – Carry out a proof roll of finished pavement where applicable
1dcf00a7-7334-4188-ae4b-fec2462df913 | section | Rock Revetment
39a479ca-6c9f-44a4-9e0d-e79dede65113 | checkpoint | Geotextile – A34 Geotextile separator placed prior to rock placement IF DIRECTED or WITHIN SCOPE
f3ea1c10-e1a0-463e-b2a0-3a6f03d3248b | checkpoint | Rock Placement - Rock to be placed in completed drain profile as per agreed scope. Correct Rock Size Placed
db56694c-4f9e-5b67-95b3-81bb8a05f89f | textbox | 40-70mm - Quantity
f277fbdc-96c9-5518-a47b-35d374b7af3a | textbox | 150-250mm - Quantity
c4974332-1556-5786-ada6-151fc20c47d3 | textbox | 300-500mm - Quantity
9ec1a032-2c78-5437-89ce-af19b490ce9e | textbox | 600-900mm - Quantity
9866f571-fb56-5d8f-8db8-e6d083fb9283 | textbox | Other
17bae73b-a42f-4938-b4d9-4ea181101e5d | section | Grouted Rock Pitching
1b63938f-6520-41f7-a6e1-a011515958b5 | checkpoint | Existing rock to be grouted as per agreed scope
fb78ba51-f918-5ec6-9eaa-dd8fce0a5bac | textbox | Approx m2
61589245-1400-404c-bda8-0104ef058750 | checkpoint | Rocks to be cleaned down at end of grouting for neat finish
f73c29b6-5d1c-4d2f-89db-f6f13d5eae10 | section | Concrete Works
d555056b-d199-41df-b1ea-a4b0f1100572 | checkpoint | Excavation & Preparation - Suitable subgrade material and prepared to suitable surface
ccf327dc-a0f4-41b7-9649-6e4d4f5666b2 | checkpoint | Formwork & Reinforcement - Dimensions and positions of forms shall be carefully checked after the forms are erected. Forms shall be aligned accurately and the location of all fittings, hold formers etc. checked prior to placing of concrete.
8846ea92-8a53-4322-af35-05318552fad7 | checkpoint | Formwork & Reinforcement - Placing of reinforcement as per agreed scope, with reference to Typical Construction Details. Reinforcement to maintain a 50mm vertical and horizontal cover unless directed otherwise.
ab4c65f7-1a0c-55d8-aa85-0ded6be607f8 | textbox | TSC Approval
16ffb3a9-4bd3-4bf4-886f-613dfeb47dad | signoff | HOLD POINT – PRE-POUR INSPECTION The formwork shall be inspected by the Superintendent, and the placing of reinforcement in the spaces formed, where specified, shall not commence until the formwork is approved by the Superintendent.
aa2370d7-db83-44be-a271-97c188ee661d | checkpoint | Ready Mix Concrete - The concrete shall be mixed and delivered in accordance with the requirements of AS 1379 - PLEASE ATTACH OR TAKE PHOTOS OF LAST DOCKETS FROM EACH POUR
ba254f67-baa5-5973-aced-0d79d08bc581 | textbox | Concrete Mix Used:
b002126e-9cd4-5055-a65c-f013de92fc4b | textbox | 20/20/80
ab94d363-52c8-5e1a-8924-1d21f742b628 | textbox | 25/20/80
d85c42d0-d698-540f-8f2d-2824d50098d9 | textbox | 32/20/80
724669f4-81a7-5548-ad29-6cefb2cbd8c1 | textbox | 32/20/100
fafd4d73-4c8b-502c-a5d0-4510b48d4b75 | textbox | 40/20/80
b261ab8d-fb88-5e47-b978-5774c2ed7bf7 | textbox | Grout
2ea9a3cf-8628-57e6-8105-cb43b44d30f2 | textbox | Shotcrete Shotcrete w/ poly-fibre
67c58a2a-ce95-599a-9551-c286ef433107 | textbox | Other
7bc48803-5b0b-4ecf-8fe7-6868142e1e59 | checkpoint | Concrete Placement - Concrete finished to TSC Standard
2cfa392b-1901-4b9a-8ef0-cb9a5945fc28 | checkpoint | Two pairs of test specimens shall be moulded for each 15 cubic metres of concrete, or part thereof, one pair being intended for the 7-day test if required and the other pair for a 28-day test.
11830ecf-eef0-4e57-b288-5dc3a07719ba | signoff | WITNESS POINT: Concrete test specimens to be taken in presence of Superintendent or Superintendent’s representative
d7b00c04-06eb-4856-bad9-b7627df90fb7 | section | Stormwater Drainage
5ee0cfe8-c88a-4f6a-9589-86de9cf411c0 | checkpoint | Stormwater components installed as per scope of works - HOLD POINT REQUIRED
979ac19f-73cc-5a80-86ad-1e500310a5e9 | textbox | Size & quantity of pipe & pits installed
893b0e0c-e4e2-5d53-8308-45ce6ad9920f | textbox | Other
26181ee9-7fee-4498-b8e4-54d1eff14ae4 | signoff | HOLD POINT: Inspection prior to backfill
0a6643d0-3cce-4655-ae81-1501220c7b4c | checkpoint | Density testing of pipeline required if within roadway:- 100% compaction to be achieved
2e08b46a-9dc2-40c7-ac2b-9f0fa6bd45b9 | section | Demobilisation
a74183f3-ab44-4ad3-9e23-60c78f3de5d1 | checkpoint | Site left tidy & DM spray mark removed
739c0bfa-e29f-45c8-8dac-92e765a3ebd7 | section | Close Out
d292ead3-5e10-4eee-8164-01f6d781e88a | checkpoint | Site Handover: All works complete, demobilised and site handed back to TSC
45097fcd-2c9a-594e-b19d-3058f3f26768 | textbox | Date of handback
cb6782ad-077b-4580-9704-d6a994c5d17b | signoff | TSC Signature
bd1b73ea-563d-4970-921f-49464fe364f6 | checkpoint | Verify conformance including close out of NCR’s
5885fb03-6f69-5c06-8bf9-2bc75018cbc7 | textbox | NCR NO:
93c4a92f-233a-5c02-9690-b0a949e187f5 | note | NATA Certificates
81a62b56-6729-5c84-bd64-b0053197ea7e | note | Survey Report
ef604807-0a18-5333-8f35-adfa3ea2015e | note | Geotechnical testing reports
05774f72-b919-5a32-a1da-21042c2a4880 | note | Concrete test reports
d5a75f28-0c81-526c-a2bb-dd68be86fc04 | note | Proof of works report
b87c0249-7aa3-5815-9fbb-baeec2b84a49 | note | Photographs of completed work
a1693cb2-82f4-4735-a67b-7fe6fef38dd2 | checkpoint | Damage No. (DM) signed off and closed by PM or representative
1d2f6bc6-733a-4a61-b03c-1b120f00eb00 | signoff | Signatures