## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
56ee6d91-a8fd-4368-9c8d-e5fb6ea1c395 | checklist | Ceiling Lifter (Post Sheeting) |  | Ceiling Lifter (Post Sheeting)
983aeda0-58d5-4d7b-a218-c6558e04c38e | section | Installation
5ff2ba06-73c8-4f35-b4cf-44f3dfc92b15 | checkpoint | Inspect Ceiling Integrity (Verify that the ceiling sheeting around the patient lifter tracks is intact and free of any damages and irregularities)
dc772f19-2387-475c-978a-5e4ef465efff | checkpoint | Verify Track Alignment (Ensure that the patient lifter tracks remain correctly aligned and secured after sheeting has been installed)
68a16d0c-bbea-499a-b309-dbd1e8efb077 | checkpoint | Check for obstructions (Confirm that no obstructions are present on or around the tracks post-sheeting)
095594db-f66c-4b6d-acd4-9c0705204da5 | checkpoint | MLC U1000 Checks
4162cd0b-e9d4-497e-86d2-a0d332ee5c77 | checkpoint | Track System Check
0ed8428c-c1ee-4c18-b329-b1cd7c70eaf7 | checkpoint | Load Testing, only to be completed once section 1 and 2 are checked
40397906-0fab-4982-bb9b-8ba276f7364d | section | Start-Up Test
6f6911f8-ee0f-415d-9012-f68890b377a1 | checkpoint | Structural Engineering Certificates Received
81b500eb-c1da-4452-8272-d6ef6d894333 | section | Final Checks
3b7384fd-b557-4208-9dce-04a2d82fc2a3 | checkpoint | Verify system functionality
2cafeb1d-3b0e-4686-9ea1-6335c1280bd8 | checkpoint | Ceiling Lifters checked against shop drawings
8f57cad7-d416-4c6b-ba4f-db2ed8f954cc | checkpoint | Inspection verification. Attach TekMed Engineer signature + position
1fba293e-1bdd-4d5a-b141-86b9c5b09f0b | checklist | Ceiling Lifter (Pre Sheeting) |  | Ceiling Lifter (Pre Sheeting)
9abcf61a-f37d-4569-8932-fbd376eda107 | section | Installation
9d2fb5bd-e17e-4fe0-b201-ba364df99a72 | checkpoint | Verify Approved Shop Drawing Revision (Include photo of title block with drawing number and revision)
2ba77a8c-7ac4-4b4d-a451-6f2dcba20720 | checkpoint | Mark up and drill Hilti Anchors into concrete as per shop drawings
f98924f1-63d5-4374-b427-d9739d525489 | checkpoint | Ensure lateral bracing and sway bracing rods have been fixed to hilti anchor as per relevant shop drawing
c932970f-2d5b-491e-a137-73f19a18f7c9 | checkpoint | Ensure monorail has been fixed to bracing rods as per relevant shop drawings
63dd3a53-0cda-4133-860d-d0d11b4f0b67 | checkpoint | Ensure monorails have been installed at the correct ceiling height
de870a94-cea6-4a20-bc4b-5a9288a2f34c | checkpoint | Ensure all securing bolts are tightened with correct torque
3e26b663-5215-4798-a59f-876391fd0d2a | checkpoint | Post Installation Checks (After the patient lifter installation, verify that TekMed has completed final checks, including any ceiling installtion, to ensure there are no clashes or obstructions)
12a0492f-97bf-4098-84fd-ceab8574183d | section | Final Checks
b2e31de0-685c-42bd-a6a7-721119bd23a6 | checkpoint | Verify documentation (Ensure the operator manual and any other necessary documentation are present, complete and accessible)
dc5dbedf-21eb-4e17-ab43-f63331aac9fa | checkpoint | Steel certifcations attached
63e77091-a73d-456b-b86b-3617561b4802 | checkpoint | Inspection verification. Attach TekMed Engineer signature + position
0cbe0149-9d60-4388-8e02-ce1aa477bd6b | checklist | Equipment Commissioning |  | Equipment Commissioning
0993a3ba-1a17-484b-ae5d-5cdde6741e9b | section | Installation
71fb65e8-ddf2-4702-af1c-2cf087a01436 | checkpoint | Carry out all testing and safety checks as per commissioning report
a2de8b1f-c616-46ea-b645-d53657fb07d5 | checkpoint | Remove protective measures
9e329833-557a-436f-8312-4b41bfac0346 | checkpoint | Clean all surfaces
2523f134-1b86-4ff3-8c78-b814a112fbd4 | section | Final Checks
f3055923-20df-4f04-9f79-dffac6265b24 | checkpoint | Final inspection to confirm conforming
33862a80-bf69-4390-8065-ff6eba5b0cc3 | checkpoint | Remove all rubbish and clean up area
d9279de7-d711-47dd-adbc-9a8490eecca7 | checklist | Equipment Installation |  | Equipment Installation
3a49b8f4-58b2-43b7-a22f-f9e5e309ae83 | section | Site Readiness
7fa36b12-820c-48f0-94b9-59ecb39c6b5f | checkpoint | Preliminary order activies
60b576f7-05d0-47e9-9e70-3ec4e8f7fb15 | checkpoint | Order Kugel/Mortuary Lift equipment
7b809ad9-b068-4e9c-8ff3-dad1bb516fba | section | Delivery
a983af3b-17ee-436f-b8e0-c39c2cac99fe | checkpoint | Preliminary site activites completed. Add details in comments
171fb5db-8dff-4849-b3fe-f0b666499d5c | section | Installation
1c070e19-0243-495d-ab44-20770b233544 | checkpoint | Pre-start
601820f1-649c-4014-b976-f9846d194795 | checkpoint | Carry out work
f8343d87-dd35-425d-a512-2d2eeb92551c | section | Final Checks
bd3211f6-52b2-4621-8927-e5dc4334f728 | checkpoint | Pre-handover activities
293291c2-6c33-4753-9e87-064c9973aae3 | checkpoint | Handover
e9df5ac8-bbb7-41f2-beeb-dae03d474b70 | checkpoint | TekMed Engineer sign off