## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d6c5738a-af51-4bef-b16a-d779349d5954 | checklist | Balconies |  | Balconies
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9820f728-231c-44e8-a420-76d1f553d32f | checkpoint | Inspect, clean and prepare the surface before commencement of waterproofing as per application guide
9992db25-7747-499e-b582-77c132da49da | checkpoint | Prime substate with appropriate primer as per guidelines
927cfd41-56fe-4bdd-a518-a285e0b92a48 | checkpoint | Seal all joints penetrations with Polybit hydraflex as per data sheet & application guidelines
70e355d4-6352-4c3c-aef7-d1be2a79fe58 | checkpoint | Apply first coat of Polybit hydraguard at the recommended WFT as per data sheet & application guidelines
61871fd4-c6b9-4c8d-9421-bd67874e3d84 | checkpoint | Apply second coat of Polybit hydraguard at the recommended WFT as per data sheet & application guidelines
f9c9520f-1d5e-4968-9134-a92083ec6651 | checkpoint | Final sign off- All general waterproofing work completed as per the above ITP
e2f2d1b2-2f58-4069-942a-a2e6a4aac867 | checklist | Internal Wet Areas |  | Internal Wet Areas
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b974d642-faac-424d-8af3-3de7210681c3 | checkpoint | Inspect, clean and prepare the surface before commencement of waterproofing as per application guide
a58908ef-b602-4abc-9624-248623a55707 | checkpoint | Prime substate with appropriate primer as per guidelines
9c8d442d-dc1f-4ec6-919d-8d499f6130d4 | checkpoint | Install aluminium water stops to door entries and shower as per Dascoâ€™s FFL
bfe09286-8619-4869-8713-e5c196c92fd8 | checkpoint | Seal all joints & gaps with Polybit hydraflex as per data sheet & application guidelines
6316cef6-e688-448d-99cc-bb9167640e63 | checkpoint | Apply first coat of Polybit hydraguard at the recommended WFT as per data sheet & application guidelines
719b179b-c8bd-42f9-8314-93f2ccd80543 | checkpoint | Apply second coat of Polybit hydraguard at the recommended WFT as per data sheet & application guidelines
a69b66b7-83c7-4d03-8399-56fd40d90bcd | checkpoint | Apply Polybit hybrid 150 to shower walls up to 1.8 and to vanity walls at the recommended thickness as per data sheet & application guidelines
597af177-adef-5a41-8715-c0c2a9fbe28d | tickbox | Allow membrane to dry
59fe4ad3-97de-4de3-9b36-081350f8f676 | checkpoint | Flood test for 24 hours
1b216673-1977-4d74-ab97-58e87b155e6a | checkpoint | Final sign off- All general waterproofing work completed as per the above ITP
97c0df1c-e897-44c1-9f1d-ff15473849fa | checklist | Planter Boxes |  | Planter Boxes
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
245f79c3-ef91-4c83-bfec-d85e7033bb07 | checkpoint | Inspect, clean and prepare the surface before commencement of waterproofing as per application guide
a2f7c488-4c88-4c9d-a2f0-8a0ebd6e25ca | checkpoint | Prime substate with appropriate primer as per guidelines
19b0c066-60a1-43c6-a7dc-20d7524bbd5a | checkpoint | Seal all joints & gaps with Polybit hydraflex as per data sheet & application guidelines
4334cdd8-5769-4262-9cab-c409d8c9aea9 | checkpoint | Apply first coat of Polybit hydraguard anti-root as per data sheet & application guidelines
bd1d3f6c-2000-43e1-b780-c4247f525b5b | checkpoint | Apply second coat of Polybit hydraguard anti-root as per data sheet & application guidelines
66aeec4e-2e25-48bc-aa11-89f6abc03f48 | checkpoint | Final sign off- All general waterproofing work completed as per the above ITP
0f180d0a-f251-49cc-a489-616ed95cfa6c | checklist | Roof |  | Roof
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
279ba38e-bf54-4e13-9c1f-a3f8796c82c1 | checkpoint | Inspect, clean and prepare the surface before commencement of waterproofing as per application guide
bff13cd0-7bdd-4d5a-bf3a-6e638b10770a | checkpoint | Prime substate with appropriate primer as per guidelines
0d2600ad-aa5a-4c4a-ab53-c9bccf6594ca | checkpoint | Seal all joints & gaps with Polybit hydraflex as per data sheet & application guidelines
b89ade6c-f38e-4f4f-a8ef-a37d2a6a20bc | checkpoint | Apply first coat of Polybit hydraguard as per data sheet & application guidelines
89a6b37b-65c3-4bc7-a1a5-e0288e1a9589 | checkpoint | Apply second coat of Polybit hydraguard as per data sheet & application guidelines
cc0215af-1bea-4ce5-a8df-1e2ed520c9d8 | checkpoint | Apply Polybit polyguard protective UV topcoat as per data sheet & application guidelines
7fbdd54e-7c54-4093-9eea-4c5345e8c5d9 | checkpoint | Final sign off- All general waterproofing work completed as per the above ITP
7a65e4d5-a65e-4b7f-80d4-0e5752d18e4e | checklist | Step Downs To Awnings & External Permitter |  | Step Downs To Awnings & External Permitter
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
448d9989-c887-4687-8ffd-fadbf60b6f28 | checkpoint | Inspect, clean and prepare the surface before commencement of waterproofing
23c96b22-fbcb-44f5-98ac-24db42e94fb1 | checkpoint | Apply Hydrapoxy primer to substrate, including aluminium angles
de35d76b-0622-5cf6-97a1-07d00be262ef | tickbox | Allow curing time
a5c3c1d0-864c-40e1-bd78-0270b1428336 | checkpoint | Apply Hydraguard Hybrid sealant on all joints
6014ed8c-db77-47c8-9386-15e983ad8287 | checkpoint | Apply first coat of Hybrid 150 as per data sheet and application guidelines
fdb5d1ca-2138-4ed8-9724-769981cd019c | checkpoint | Apply Second Coat of Hybrid 150 as per data sheet and application guidelines
d3544c4f-289c-4c22-ac00-0ae63f8bc0f7 | checkpoint | Final sign off- All general waterproofing work completed as per the above ITP
ac33b8cc-38a7-4fe5-bf8a-25d1b9c0337a | checklist | Step Downs To Balconies |  | Step Downs To Balconies
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
14a1f49c-1e13-454b-b583-41a48f64f506 | checkpoint | Inspect, clean and prepare the surface before commencement of waterproofing
715ee9aa-a1eb-4b26-920e-0e672faebf69 | checkpoint | Apply Hydrapoxy primer to substrate, including aluminium angles
fde11510-d452-5efc-8e77-1968100e44e7 | tickbox | Allow curing time
f8977deb-2281-4fa6-8163-7e24f748a135 | checkpoint | Apply Hydraguard Hydraflex on all joints, gaps & cracks as per datasheet & application guidelines
f7f03847-22d9-4e80-8082-2ba05e80cdd1 | checkpoint | Apply a coat of Polybit Hydraguard as per datasheet & application guidelines
9aa288b2-b584-4132-ab7e-0f1c9726b1c2 | checkpoint | Final sign off- All general waterproofing work completed as per the above ITP