## Format
BD (Pharmacy) - Conqa Format
Tier 1 | Tier 2 | Tier 3 | Tier 4 |  |  |  | 4 ITPs
Building | Level | Room number | Item Number: Imaging Equipment | Description | Equipment Installation | Equipment Commisioning | 2 x Rowa
Building B | Lower Ground | LG.B.022 | MMGE-053 | MEDICATION DISPENSER: automated |  |  | 2 x ADC
|  | LG.B.038 | MMGE-053 | MEDICATION DISPENSER: automated
|  | LG.B.096 | MMGE-053 | MEDICATION DISPENSER: automated
|  | LG.B.210 | MMGE-053 | MEDICATION DISPENSER: automated
|  | LG.B.245 | MMGE-053 | MEDICATION DISPENSER: automated
|  | LG.B.303 | MMGE-053 | MEDICATION DISPENSER: automated
|  | LG.B.398 | MMGE-053 | MEDICATION DISPENSER: automated
|  | LG.B.455 | MMGE-053 | MEDICATION DISPENSER: automated
| Ground Floor | GF.A.026 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.A.126 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.A.158 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.B.148 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.B.241 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.B.258 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.B.293 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.B.337 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.B.356 | MMGE-053 | MEDICATION DISPENSER: automated
|  | GF.B.548 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 1 | 01.B.066 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 01.B.196 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 01.B.479 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 2 | 02.A.233 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.140 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.149 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.154 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.161 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.163 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.235 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.242 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.247 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.255 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.273 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.281 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.285 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.294 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.296 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.454 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.455 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.456 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 02.B.481 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 3 | 03.A.107 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 03.A.208 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 03.A.244 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 03.A.262 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 4 | 04.A.096 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 04.A.108 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 04.B.245 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 04.B.368 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 5 | 05.B.132 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 6 | 06.B.029 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 06.B.131 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 7 | 07.B.052 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 07.B.120 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 07.B.173 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 07.B.240 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 8 | 08.B.051 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 08.B.116 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 08.B.227 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 08.B.246 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 9 | 09.B.051 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 09.B.115 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 09.B.225 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 09.B.235 | MMGE-053 | MEDICATION DISPENSER: automated
| Level 10 | 10.B.051 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 10.B.115 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 10.B.225 | MMGE-053 | MEDICATION DISPENSER: automated
|  | 10.B.235 | MMGE-053 | MEDICATION DISPENSER: automated
Building B | Level 1 | 01.B.233 | MMGE-522 | ROWA

## Equipment Staging - ADC
Equipment Staging and Server Connection - ADC
TBC
Checkpoint | Installation | Criteria
Button | Staging of Pyxis Main Devices | Equipment Confirmation Form | Yes / No / N/A
Button | Syncronising of Pyxis Main to Production Server | Pyxis ES Report attached | Yes / No / N/A
Checkpoint | Final Checks
Button / Drop Down Box | Sign off of staging and server connection by MPX and BD | Staging and Server connection complete | Yes / No / N/A

## Equipment Installation - ADC
Equipment Installation - ADC
Checkpoint | Site Readiness | Criteria
Button | Final Physical Installation | Excel checklist i.e. quanitites, serial numbers, and date of install | Yes / No / N/A
Checkpoint | Final Checks
Button | Verify equipment installed in locations as per RLS drawings: | Visual Inspection | Yes / No / N/A
Textbox | BD sign off: | Signature: | Position:

## Equipment Installation - Rowa
Equipment Installation - Rowa
Checkpoint | Delivery | Criteria
Button | Delivery of all Rowa components completed - sign off by BD | German packing list attached | Yes / No / N/A
Button | Delivery Dockets sign off - sign off by MPX | Delivery dockets attached. | Yes / No / N/A
Checkpoint | Installation | Criteria
Button | Rowa VMax & External Prolog Installation | Photos attached | Yes / No / N/A
Button | Conveyor and Box System Installation | Photos attached | Yes / No / N/A
Checkpoint | Final Checks
Button | Verify equipment installed in locations as per RLS drawings. | Visual Inspection and Document | Yes / No / N/A
Textbox | BD Sign Off: | Signature: | Position:

## Equipment Commisioning - Rowa
Equipment Commisioning - Rowa
TBC
Checkpoint | Installation | Criteria
Button | Rowa VMax & External Prolog Commissioning | Commissioning Checklist | Yes / No / N/A
Button | Conveyor and Box System Commissioning | Commissioning Checklist | Yes / No / N/A
Checkpoint | Final Checks
Button / Drop Down Box |  |  | Yes / No / N/A