## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Equipment Staging and Server Connection - ADC
section | Details
checkpoint | Installation
button | Staging of Pyxis Main Devices | Yes,No,N/A
label | Criteria - Equipment Confirmation Form
button | Synchronising of Pyxis Main to Production Server | Yes,No,N/A
label | Criteria - Pyxis ES Report attached
checkpoint | Final Checks
button | Sign off of staging and server connection by MPX and BD | Yes,No,N/A
label | Criteria - Staging and Server connection complete
checklist | Equipment Installation - ADC
section | Details
checkpoint | Site Readiness
button | Final Physical Installation | Yes,No,N/A
label | Criteria - Excel checklist i.e. quanitites, serial numbers, and date of install
checkpoint | Final Checks
button | Verify equipment installed in locations as per RLS drawings: | Yes,No,N/A
label | Criteria - Visual Inspection
holdpoint | BD sign off:
checklist | Equipment Installation - Rowa
section | Details
checkpoint | Delivery
button | Delivery of all Rowa components completed - sign off by BD | Yes,No,N/A
label | Criteria - German packing list attached
button | Delivery Dockets sign off - sign off by MPX | Yes,No,N/A
label | Criteria - Delivery dockets attached.
checkpoint | Installation
button | Rowa VMax & External Prolog Installation | Yes,No,N/A
label | Criteria - Photos attached
button | Conveyor and Box System Installation | Yes,No,N/A
label | Criteria - Photos attached
checkpoint | Final Checks
button | Verify equipment installed in locations as per RLS drawings. | Yes,No,N/A
label | Criteria - Visual Inspection and Document
holdpoint | BD sign off:
checklist | Equipment Commisioning - Rowa
section | Details
checkpoint | Installation
button | Rowa VMax & External Prolog Commissioning | Yes,No,N/A
label | Criteria - Commissioning Checklist
button | Conveyor and Box System Commissioning | Yes,No,N/A
label | Criteria - Commissioning Checklist
checkpoint | Final Checks