## struct
resource | resource | resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
|  |  |  | step |  |  | Tier 1: Building B
|  |  |  | step |  |  | Tier 2: Lower Ground
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: LG.B.022; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: LG.B.038; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: LG.B.096; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: LG.B.210; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: LG.B.245; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: LG.B.303; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: LG.B.398; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: LG.B.455; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Ground Floor
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.A.026; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.A.126; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.A.158; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.B.148; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.B.241; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.B.258; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.B.293; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.B.337; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.B.356; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: GF.B.548; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 1
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 01.B.066; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 01.B.196; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 01.B.233; Tier 4: MMGE-522 - ROWA
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 01.B.479; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 2
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.A.233; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.140; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.149; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.154; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.161; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.163; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.235; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.242; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.247; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.255; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.273; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.281; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.285; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.294; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.296; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.454; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.455; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.456; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 02.B.481; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 3
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 03.A.107; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 03.A.208; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 03.A.244; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 03.A.262; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 4
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 04.A.096; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 04.A.108; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 04.B.245; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 04.B.368; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 5
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 05.B.132; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 6
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 06.B.029; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 06.B.131; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 7
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 07.B.052; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 07.B.120; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 07.B.173; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 07.B.240; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 8
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 08.B.051; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 08.B.116; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 08.B.227; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 08.B.246; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 9
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 09.B.051; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 09.B.115; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 09.B.225; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 09.B.235; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
|  |  |  | step |  |  | Tier 2: Level 10
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 10.B.051; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 10.B.115; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 10.B.225; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated
Equipment Installation - ADC | Equipment Staging and Server Connection - ADC | Equipment Installation - Rowa | Equipment Commisioning - Rowa | folder-with-checklists |  |  | Tier 3: 10.B.235; Tier 4: MMGE-053 - MEDICATION DISPENSER: automated