## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-000 - Client Pre-Construction Checklist | itp |  |  |  |  | ITP-000 - Client Pre-Construction Checklist
section | Design and Submissions
checkpoint | 1.1 Submission & approval of concrete mix design prior to commencement of project
label | FREQUENCY: Prior to first concrete pour
label | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
label | ○ Mix grade shall be VR 400/40.
label | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600, AS3600 & AS 1379
label | REFERENCE DOCUMENTS: DN S002 P&S IFC
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Mix Design ITP
label | HP
label | RESPONSIBILITY: FH Engineer / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 Submission & approval of epoxy adhesive product prior to commencement of project
label | FREQUENCY: Prior to first epoxy pour
label | ACCEPTANCE CRITERIA: Ensure product adheres to notes specified in the P&S DRG S004
label | REFERENCE DOCUMENTS: DN S004 P&S IFC
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 Submission & approval of high-strength non-shrink mortar prior to commencement of project
label | FREQUENCY: Prior to first grout pour
label | ACCEPTANCE CRITERIA: Ensure product adheres to notes specified in the P&S DRG S005
label | REFERENCE DOCUMENTS: DN S005 P&S IFC
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-025 - Structural Concrete Construction | itp |  |  |  |  | ITP-025 - Structural Concrete Construction Rev2
section | Design and Submissions
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PMP, EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Approval of concrete mix design
label | FREQUENCY: Prior to the first concrete pour
label | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
label | REFERENCE DOCUMENTS: 610.07 P&S IFC
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Reinforcement
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
label | REFERENCE DOCUMENTS: 611.04
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction/Erection of Formwork
checkpoint | 2.1 Excavation / Jackhammering
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Demolition shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Construction Methodology
label | FREQUENCY: Prior to erection
label | ACCEPTANCE CRITERIA: Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
label | REFERENCE DOCUMENTS: 614.04, 614.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Pre-Pour Planning and Inspection
checkpoint | 3.1 Formwork Design and Construction
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | REFERENCE DOCUMENTS: IFC Drawings 614.04, 614.05, 614.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | SCP, HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.2 Reinforcement
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Projecting reinforcement is the correct length and location.
label | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | REFERENCE DOCUMENTS: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Fulton Hogan / Yarra Trams
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Monitoring weather
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
label | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
label | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 3.4 Pre-pour Inspection
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | ○ All foreign material has been completely removed from the forms.
label | REFERENCE DOCUMENTS: IFC Drawings 610.18 (a) (ii) & (iii)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP Signed, Pre Pour checklist completed
label | HP
label | RESPONSIBILITY: Fulton Hogan / Yarra Trams
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Placing and Finishing Concrete
checkpoint | 4.1 Carry out sampling of concrete
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
label | REFERENCE DOCUMENTS: 610.16
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.2 Discharge time
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 60 minutes from batch time unless approved otherwise.
label | REFERENCE DOCUMENTS: 610.13 (f)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.3 Placement & Compaction
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
label | ○ Concrete shall not be moved horizontally by vibrators
label | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
label | REFERENCE DOCUMENTS: 610.18
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
section | Post-Pour Details and Inspection
checkpoint | 5.1 Curing
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
label | REFERENCE DOCUMENTS: 610.23
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.2 Formwork removal
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
label | REFERENCE DOCUMENTS: 610.25
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
label | REFERENCE DOCUMENTS: AS3600 Cl 17.5, 607.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.4 Concrete Sampling and Testing
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
label | REFERENCE DOCUMENTS: 610.16
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.5 As Built Drawings
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Recorded of as-built drawings
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-026 - Structural Grout | itp |  |  |  |  | ITP-026 - Structural Grout Rev1
section | Design and Submissions
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Activities
checkpoint | 2.1 Formwork Design and Construction
label | FREQUENCY: Each Element
label | ACCEPTANCE CRITERIA: Dimensions in plan as per drawings to achieve the desired grout profile.
label | ○ Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | SCP, HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Pre-pour Inspection
label | FREQUENCY: Each Element
label | ACCEPTANCE CRITERIA: Concrete substrate surface moisture condition as per the Product's TDS, with no ponding of water.
label | ○ Formwork location and RLs comply.
label | ○ Where applicable, any reinforcement is clean and has the required cover.
label | REFERENCE DOCUMENTS: IFC Drawings, Fosroc Conbextra EP65 Plus TDS 610.20
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Fulton Hogan / Yarra Trams
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Weather Conditions
label | FREQUENCY: Each Element
label | ACCEPTANCE CRITERIA: Grouting may be carried out without conditioning at ambient temperatures between, 5°C to 25°C. Pot life will be reduced when temperature exceeds 20°C.
label | REFERENCE DOCUMENTS: Fosroc Conbextra EP65 Plus TDS
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 2.4 Mixing Product
label | FREQUENCY: Each Batch
label | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | ○ Only whole bags to be mixed with potable water.
label | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | ○ Product poured into the mixer slowly.
label | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
label | REFERENCE DOCUMENTS: Fosroc Conbextra EP65 Plus TDS 610.28
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 2.5 Product Testing - Compressive Strength Cubes
label | FREQUENCY: Each Element
label | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds.
label | ○ Testing is be in accordance with the following frequencies:
label | — First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | — Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | REFERENCE DOCUMENTS: 610.28, 610.33
label | INSPECTION/TEST METHOD: Test
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan / Tester
textbox | Date Completed:
checkpoint | 2.6 Placement & Compaction
label | FREQUENCY: Each Element
label | ACCEPTANCE CRITERIA: All batches are traceable.
label | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | ○ Product should flow to all areas and self consolidate.
label | ○ Product that stiffens or is showing signs of stiffening shall not be used.
label | REFERENCE DOCUMENTS: Product TDS
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 2.7 Curing
label | FREQUENCY: Each Element
label | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations. Epoxy shall not be distrubed while curing occurs.
label | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | REFERENCE DOCUMENTS: Curing Methodology 610.23 Table 610.231
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
section | Post-Pour Details and Inspection
checkpoint | 3.1 Concrete Sampling and Testing
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Grout sampled and tested for Compressive Strength.
label | REFERENCE DOCUMENTS: IFC Drawings, Product TDS 610.28, 610.33
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 3.2 As Built Drawings
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Recorded of as-built drawings
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: