## Table 1
[9 empty] | Inspection and Test Plan - Template - AU | [9 empty] | Doc ID: FH-927-QU-ITP004 Rev: 0
Client: Australia Pacific Airports Melbourne | [9 empty] | Contract No: CP1024 | [6 empty] | Prepared By: James Kremers
Project: Runway 09/27 Overlay | [13 empty] | Reviewed By: | [6 empty] | Date:
Construction Process: Cold Planning | [13 empty] | Approved By: | [6 empty] | Date:
Specifications: Volume 1 – Standard Specification for Airside Works Rev 0.1
Structure / Component: Pavements
Lot No: |  |  | Lot Details: |  |  |  |  | Lot size/Quantity: | [6 empty] | Date:
Item No. |  | Task/Activity Description |  |  |  |  | Inspection/Test | [7 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsib ility Project Engineer Superint endent Surveyor Foreman | Checked by:
[7 empty] | Frequency | Acceptance Criteria |  | Reference Documents | Inspection/ Test Method |  | Record of conformity |  |  |  |  | Client |  | Fulton Hogan | GHD | Date
1 |  | Plant and equipment
1.1 |  | All cold planing works |  |  |  |  | At least ten (10) working days prior to commence ment of cold planing operations | List, including details, of all plant and equipment to be used for the cold planing work. |  | Volume 1: HP 3903-1 | Notification |  | Aconex Submission / This ITP signed by Contract Administrator |  | HP |  | Quality Engineer
1.2 |  | Contractor's check that cold planing plant in full working order |  |  |  |  | Prior (60 minutes) | 1. Notice of the commencement time of the Contractor's cold planing plant verification process |  | Volume 1: HP3903- 2.1 | Verify |  | This ITP signed by Contract Administrator |  | HP |  | Quality Engineer
1.3 |  | Cold planing plant in full working order |  |  |  |  | Prior (60 minutes) | 2. Copy of Contractors’ cold planing verification checklist at the completion of check prior to commencement of each work period |  | Volume 1: HP3903- 2.2 | Notification |  | Submission of Daily Prestart Records / This ITP signed by Contract Administrator |  | HP |  | Quality Engineer
2 |  | Cold Planing in Advance of Asphalt Work
2.1 |  | Cold planing in advance of asphalt overlay work: Area closed to aircraft traffic. |  |  |  |  | Prior (10 working days) to commence ment of planing works | Proposal to Contract Administrator to texture, profile and mill in advance of asphalt work including complete program and plan of texturing, profiling and milling and asphalt overlay work proposed in the work area. |  | Volume 1: HP 3904-1 | Notification |  | Submission of Shift Plan / This ITP signed by Contract Administrator |  | HP |  | Quality Engineer
2.2 |  | Cold planning in advance of asphalt overlay work: Area open to aircraft traffic. |  |  |  |  | Prior (10 working days) to commence ment of planing works | 1. Proposal to Contract Administrator to texture in advance of asphalt overlay work including date of demonstration and detailed program of texturing and asphalt overlay work in the work area |  | Volume 1: HP3904- 2.1 | Notification |  | This ITP signed by Contract Administrator |  | HP |  | Quality Engineer
2.3 |  | Removal of cold planing and asphalt paving equipment from work area |  |  |  |  | Before textured surface is opened to aircraft traffic | Inspection between Contractor and Contract Administrator of textured area. |  | Volume 1: HP3904-3 | Verify |  | This ITP signed by Contract Administrator |  | HP |  | Quality Engineer
3 |  | Restrictions on Cold Planing
3.1 |  | Commencement of cold planing works |  |  |  |  | Before the commence ment of each working period | Written notification to the Contract Administrator that all plant, equipment and labour, including that required for the placing, compaction and finish of asphalt, are available and ready on- site and supply of asphalt for the work is confirmed even in the event of an unexpected breakdown of the asphalt mixing plant. |  | Volume 1: HP3905-1 | Notification |  | This ITP signed by Contract Administrator |  | HP |  | Quality Engineer
4 |  | Performance Check at Commencement of Work Period
4.1 |  | Check that planing machines producing compliant surface |  |  |  |  | Prior (30 minutes) | Notice to the Contract Administrator of the commencement time of cold planning |  | Volume 1: WP3906 -1 | Notification |  | Submission |  | WP |  | Quality Engineer
5 |  | Texturing
4.1 |  | Commencement of application of tack coat and asphalt paving |  |  |  |  | Prior (30 minutes) | 1. Notice to the contract Administrator of the scheduled commencement time of Contractor's inspection and checking of the textured surface of the texturing trial. 2. Statement of compliance signed by the Contractors’ PQR that the textured surface in the texturing trial complies with the specified requirements |  | Volume 1: HP3907- 2.1 | Notification |  | This ITP signed by Contract administrator |  | HP |  | Quality Engineer
4.2 |  | Commencement of application of tack coat and asphalt paving |  |  |  |  | Prior to application of tack coat | Written agreement by Contractor, including photograph and typical measurements of the Texture Reference Area |  | Volume 1: HP3907-3 | Notification |  | This ITP signed by Contract administrator |  | HP |  | Quality Engineer
4.3 |  | Removal of application of cold planing and asphalt paving equipment from work area |  |  |  |  | Prior (minimum 60minutes ) | Notice to the Contract Administrator of Contractor's Inspection of completed textured surface and, statement of compliance of textured surface with specified requirements signed by contractor’s PQR |  | Volume 1: HP3907-4 | Notification |  | This ITP signed by Contract administrator |  | HP |  | Quality Engineer
5 |  | Profiling, Miling and Cleaning of Cold Planed Surfaces
5.1 |  | Removal of planing and cleaning equipment from site |  |  |  |  | Prior (minimum 60minutes ) | Notice to the Contract Administrator of Contractor's Inspection of completed profiled surface and, statement of compliance of profiled surface with specified requirements signed by contractor’s PQR |  | Volume 1: HP3908- 1 | Notification |  | This ITP signed by Contract administrator |  | HP |  | Quality Engineer
5.2 |  | Removal of cold planing and asphalt paving equipment from work area |  |  |  |  | Prior (minimum 60minutes ) | Notice to the Contract Administrator of Contractor's Inspection of completed milled surface and, statement of compliance of milled surface with specified requirements signed by contactor’s PQR |  | Volume 1: HP3909- 1 | Notification |  | This ITP signed by Contract administrator |  | HP |  | Quality Engineer
5.3 |  | Cleaning of entire cold planned surfaces of asphalt |  |  |  |  | Prior (minimum 30minutes ) | Notice to the contract Administrator of commencement of cleaning of cold planed surfaces of asphalt |  | Volume 1: WP3911-1 | Notification |  | This ITP signed by Contractor |  | WP |  | Quality Engineer
5.4 |  | Tack coat and placement of asphalt over cold planed surfaces of asphalt |  |  |  |  | At completion of each cleaning working period | Statement signed by the Contractor's PQR that the whole of the cold planed surfaces of asphalt have been cleaned as specified |  | Volume 1: HP3911-1 | Notification |  | This ITP signed by Contract Administrator |  | HP |  | Quality Engineer
5.5 |  | Removal of Waste |  |  |  |  | As required | All asphalt removed from pavements by cold planing will become the property of the Contractor and must be removed from the site and disposed of by the Contractor. Stockpiling and material disposal requirements to be confirmed and authorized with Contract Administrator |  | Volume 1: 3912 and Volume 2 SP3912 | Inspection |  | This ITP signed by Contractor |  | IP |  | Quality Engineer
7 |  | Survey of Cold Planed Asphalt Surfaces
7.1 |  | Placing of asphalt over cold- planed asphalt surfaces |  |  |  |  | Prior (30 minutes) | Survey of cold planed asphalt surfaces and determination of overlay thicknesses for asphalt thickness control, and Notice to the contract Administrator of commencement of survey |  | Volume 1: HP3913- 1 | Notification |  | This ITP signed by Contract Administrator / Submission of Survey Records. |  | HP |  | Quality Engineer
5.9 |  | Lot Submission for Cold Planning |  |  |  |  | Per shift | Submit detailed information for each shift. Details include location, test certificates etc. |  | Method Stateme nt | Review of Lot Submission details |  | Lot Submission documents submitted to Contract Administrator |  | WP |  | Site Engineer
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / / .
Legend:
| HP |  |  | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent | [5 empty] | IP | Inspection point |  |  | Formal Inspection to be done and recorded
| HP* |  |  | Fulton Hogan Hold Point |  | Work shall not proceed past the HP* until released by Fulton Hogan | [5 empty] | TP | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  |  | Witness Point |  | An inspection which must be witnessed by the Superintendent | [5 empty] | SCP | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
[9 empty] | Inspection and Test Plan - Template - AU | [9 empty] | Doc ID: FH-927-QU-ITP004 Rev: 0
Client: Australia Pacific Airports Melbourne | [9 empty] | Contract No: CP1024 | [6 empty] | Prepared By: James Kremers
Project: Runway 09/27 Overlay | [13 empty] | Reviewed By: | [6 empty] | Date:
Construction Process: Cold Planning | [13 empty] | Approved By: | [6 empty] | Date:
Specifications: Volume 1 – Standard Specification for Airside Works Rev 0.1
Structure / Component: Pavements
AP |  |  | Approval Point |  | Written or verbal approval given by the Superintendent
Notes