## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 006 FF&E Installation |  |  |  |  | Yes | ITP 006 FF&E Installation | 08ca46ea-87be-47c2-89fb-f482a3774242
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | c2abbd2b-d4f6-571c-9984-9e6948ac37d6 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | cdea156b-6e64-5fb1-b681-b91dfd2f15f0 |  | note | Buildup Inspection Code: W
label | 980d5aa4-82ed-5e52-b203-7a7288cead5c |  | note | Lendlease Inspection Code:
label | 3c41905e-c207-5f67-a938-658bf2485f2f |  | note | Lendlease Sign/Date:
label | f338ce94-7878-5fa1-8cb4-7a5c7a3980a3 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | FFE Installation
checkpoint-status |  |  | checkpoint | All of FFE Products must approved by Lendlease
label | 7b941512-a948-52e6-a239-fa44f2b86e94 |  | note | Acceptance Criteria: Sample Form Approval Finish Schedule
label | 2476dde4-901d-5315-b446-b991352e4e4e |  | note | Series: BR3ADL2-Internal Architectural Details
label | 2eba437b-70ef-5522-b383-cb4a56854bc0 |  | note | Buildup Inspection Code: W
label | 4437e369-66eb-5e64-9c91-7c519ba42d13 |  | note | Lendlease Inspection Code:
label | 89d32fcf-2742-5990-8709-36d25d0bebde |  | note | Lendlease Sign/Date:
label | afe6db77-25da-5108-821f-ef0bf37a3c2f |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | All of FFE products have to supported by Noggins
label | d8788752-c124-5d1a-a9a0-b69427392a7c |  | note | Acceptance Criteria: Noggin Markup Plan
label | 5210f45f-d20a-5472-91b6-59971d2b555c |  | note | Buildup Inspection Code: W
label | 830b6ebc-a10b-560e-9287-3462a5b3086c |  | note | Lendlease Inspection Code:
label | 1a4909eb-61a0-5f4b-a518-49d53182655e |  | note | Lendlease Sign/Date:
label | 3b02f4a1-2066-510b-a5e7-be5f34766ae6 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | No unreasonable gap or holes on the wall
label | 986e03fa-ca5e-517a-811d-8bb6ae807fce |  | note | Acceptance Criteria: Eye Inspection
label | 67e58164-ecf1-5d39-b7a6-d3d3f2990d98 |  | note | Buildup Inspection Code: W
label | 259b4e7c-afe8-5374-8ac6-29e590bb7359 |  | note | Lendlease Inspection Code:
label | 838e04e2-1556-5354-971e-9ff8dce427ce |  | note | Lendlease Sign/Date:
label | 4a882c14-1ada-542d-9cbb-7f9cff49f8b2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Height and location must follow the requirement
label | ac65213f-9b9d-5da2-b2da-b648bc4cb4e3 |  | note | Acceptance Criteria: Noggin Markup Plan
label | 8475da4a-1e91-58e2-a596-210dd552bbd1 |  | note | Series: Series: BR3ADL2-Internal Architectural Details
label | 98331a6a-60d7-5c3c-a8a6-00b605eab0ab |  | note | Buildup Inspection Code: W
label | c0b67e02-fa98-50ec-bc59-1eec84112fdb |  | note | Lendlease Inspection Code:
label | 9f80e201-7971-51b7-8b45-4887c997ad17 |  | note | Lendlease Sign/Date:
label | eab2375b-8f0b-57c9-a6e6-bae18874f1f8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | FFE installation should not affect the wall finish. The wall with good patching as well
label | f0fb56bb-bf84-5047-93b3-cd1728b5a6e4 |  | note | Acceptance Criteria: Eye Inspection
label | 8cc2db58-904f-5a05-8bfd-ae379749800f |  | note | Buildup Inspection Code: W
label | 05caedf7-ac78-5780-9890-b875af2c3399 |  | note | Lendlease Inspection Code:
label | ac3a2cb2-75fa-5252-bbf4-726bfd519759 |  | note | Lendlease Sign/Date:
label | 90d23d2b-4e7e-5d14-83ea-51d1e0389e88 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | e89047ff-97c4-59ea-a5c1-f5da1d49dc85 |  | note | Buildup Inspection Code: W
label | 0a70d048-2224-5748-afbb-1b895bf8310d |  | note | Lendlease Inspection Code:
label | 1b6b92f5-4c1b-52a5-adc2-3f7110e541b2 |  | note | Lendlease Sign/Date:
label | ce46cd0e-1de2-5a83-993d-3b20b9076e2f |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 004 Door and Door Hardware Installation |  |  |  |  | Yes | ITP 004 Door and Door Hardware Installation | 0c672970-0fa6-4c38-811b-70dcc78847b4
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 079f1112-3dab-5166-9032-b34d1851e645 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 1d417e47-3d76-588e-b45d-6bbd63550dde |  | note | Buildup Inspection Code: W
label | 4bacbea9-05ce-5d43-817f-8fea16687f3a |  | note | Lendlease Inspection Code:
label | fbfa84e4-1964-5782-a2dc-f736a6da97f2 |  | note | Lendlease Sign/Date:
label | cee7f272-3617-5cef-b4b8-28bc0dcb3e51 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Opening dimension checked against drawings and Setout, Door types and leaf size confirmed against partition plan
label | d4d3e4aa-09b6-5528-8086-30875d826a75 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | dd9402a0-7ac4-5a58-ac3a-c72276aa4fed |  | note | Series:BR3ADB2-Wall Setout Plans Door Schedule - BR3AT1332[C2]
label | 7744bfcf-bdc9-5773-890d-9495b59be50f |  | note | Buildup Inspection Code: W
label | bfa4b46a-5e52-547a-a95f-17542b1467c2 |  | note | Lendlease Inspection Code:
label | 291c6628-f1f2-5683-a367-72e2ed7d8357 |  | note | Lendlease Sign/Date:
label | 5313176f-2f62-593a-b75b-f2a3b3a161f2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door frame installed as manufacturer's specification to Top, bottom and both sides
label | 84dbf7cc-2ccb-51c0-805b-b8e2ac939dde |  | note | Straight and plumb and square, no sharp edge, gap less than 20mm, sealed with silicone
label | d1a25443-b62a-5318-a913-cad0a4996da8 |  | note | Buildup Inspection Code: W
label | 3de69013-951f-5b70-94aa-d87bfa861435 |  | note | Lendlease Inspection Code:
label | beb7b193-c072-53d1-861e-f1c26448cb10 |  | note | Lendlease Sign/Date:
label | db50b057-b4e7-55fd-bd0b-3637c92cd5bb |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door Hardware Installation and Check
label | df10ef95-1f84-5134-b943-2c6fd71b8cdd |  | note | Correct Hardware type followed as shop drawings. All of door hardware followed the finish Schedule
label | 590f4940-cebd-5a2f-97c2-9c8444a8803b |  | note | Buildup Inspection Code: W
label | dae28c75-73c7-5dce-8fb8-a70373d64b74 |  | note | Lendlease Inspection Code:
label | e013579c-73ab-5a05-8cba-cc8cdff23cf9 |  | note | Lendlease Sign/Date:
label | fb0a7ae2-ed69-5986-8eeb-fcf83310d943 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door Smoke sealed cabinet
label | 4d1d4426-8737-5d0b-a2c3-769368c14f83 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | 77012489-62ea-5d7f-a7c7-3c5c204e346c |  | note | Buildup Inspection Code: W
label | b2f4f504-fc55-59ce-a20b-b9b8d80848e6 |  | note | Lendlease Inspection Code:
label | d9cda0ae-4c34-5ecb-9e46-2fe5002675a8 |  | note | Lendlease Sign/Date:
label | b0ebfa4a-36bd-5805-846d-5aa7fa1622e8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | b9015113-9735-5e31-8feb-555878035277 |  | note | Buildup Inspection Code: W
label | 63748b82-7903-58d6-a7d2-eaec6cf483f0 |  | note | Lendlease Inspection Code:
label | e55964b9-de8b-5764-bb5d-e1ea31395b53 |  | note | Lendlease Sign/Date:
label | e46b8b7f-b943-5047-9c77-a2d6638d7176 |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 005 Installation of Ceiling System |  |  |  |  | Yes | ITP 005 Installation of Ceiling System | 84b627c3-f0ff-4451-a68d-c6a9df2d5929
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 8ccb6fb9-e176-51a1-9930-647eb93019c7 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | d10cdab7-0ac7-543d-98cc-da1170e92335 |  | note | Buildup Inspection Code: W
label | 1d5f4c46-27a8-534c-9c65-d86867d052cd |  | note | Lendlease Inspection Code:
label | 461b89ad-4ac1-559b-a7a6-a18698c58f37 |  | note | Lendlease Sign/Date:
label | 47a9b1be-9676-522f-a097-b2b72f1d307f |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Ceiling Framing
checkpoint-status |  |  | checkpoint | Ceiling framing dimension and FCL checked against drawings and Setout, Ceiling types confirmed against RCPs
label | b47ba2ae-6cf2-5b1e-acd4-c5b8a2100ff7 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | f91730ae-a7d6-5a4e-90df-a976147c9990 |  | note | Series: BR3ADG1-Reflected Ceiling Plans
label | 84dd0955-7c99-5d95-aab6-2029b75a28fa |  | note | Buildup Inspection Code: W
label | d0e1b751-7525-5555-b9fe-6de462cf9db4 |  | note | Lendlease Inspection Code:
label | 8642ee87-d18e-59c6-8e97-d48dde74add6 |  | note | Lendlease Sign/Date:
label | 69863c43-a4f1-574e-ab0e-465b91063e2c |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | All above-ceiling services are installed and ready for ceiling framing
label | bac8ce2e-4bab-5815-bac3-8490b56cc58e |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough ins have been completed and approved prior to sheeting
label | 47a435c8-32a3-5668-b663-3a69e1f44810 |  | note | Buildup Inspection Code: W
label | 7371e358-967e-557b-a5b2-15e7e77d7b93 |  | note | Lendlease Inspection Code:
label | 6824b749-e87f-54cf-a2de-872fdf222187 |  | note | Lendlease Sign/Date:
label | 4a059410-91f6-5f1a-84ab-f9f0af4ad9db |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Ceiling framing completed as Rondo designs
label | 64a9a753-2207-5093-a4f0-e991417bb654 |  | note | Acceptance Criteria: Suspending point max 1200mm*1200mm Grid, TCR @max 600 space and max200 from wall, FC @max 600 space and max 100 from wall. Correctly braced. Two sides fixed and two sides free
label | 9a2b1d45-a1d8-510d-a63c-2be05849ed39 |  | note | KEY-LOCK Suspended Seismic Ceiling Specification
label | 99819f3f-fffc-55f1-bd14-18e2ecf6a266 |  | note | Buildup Inspection Code: W
label | ef01c26b-61fa-5c97-95e6-d7300f507de1 |  | note | Lendlease Inspection Code:
label | cc9c4d0c-ad5b-5298-aed3-fd97b7d86c5f |  | note | Lendlease Sign/Date:
label | 5c636e52-ce79-5548-af61-428b957394e9 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Bulkhead and Bracing completed as Kanuf designs
label | abf14f5e-1c52-539b-ab59-fc2985c7e277 |  | note | Acceptance Criteria: Anchor used with Load sharing washer
label | efdbc049-5225-5d92-a29b-95c1e0162b9d |  | note | KEY-LOCK Suspended Seismic Ceiling Specification
label | 800451f3-3023-5905-8833-7fd6dd43115e |  | note | Buildup Inspection Code: W
label | 8e929a99-35e2-526b-a87b-a86844371f9f |  | note | Lendlease Inspection Code:
label | a98afffc-7fe2-5265-a655-cc361f52c4c7 |  | note | Lendlease Sign/Date:
label | 2b8c5d9b-25cd-5b11-ad2d-e2099c1a35b9 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Allowance for access panels and service penetration (Lights and Grill)
label | 2858c92a-1d0b-57cc-83a3-0e98e5581ff0 |  | note | Acceptance Criteria: Framing not in the way of services or AP
label | 362a2779-2ffd-5cc3-a34b-594902b894a9 |  | note | Coordinated RCP drawing series
label | 2857d139-a4ed-5ad2-b143-47d9b7314cc0 |  | note | Buildup Inspection Code: W
label | 6e3721c7-91aa-575a-a414-598dc033283f |  | note | Lendlease Inspection Code:
label | ebae31c8-b6ee-56c4-89d6-605ba63785bb |  | note | Lendlease Sign/Date:
label | 4ae037d0-d35f-5abf-a5f1-831be1da1516 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber Noggins and Ceiling support installed as required
label | 14b3a256-5abe-5739-9760-628d293e6748 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | e464e523-93fe-5dd0-8435-c325263caa6e |  | note | Buildup Inspection Code: W
label | 9713f7fc-98cb-5acf-a5ad-795fb0a1032b |  | note | Lendlease Inspection Code:
label | e9ed30a1-a5c2-52b5-936f-5d303f1a4891 |  | note | Lendlease Sign/Date:
label | e2484d69-1cec-5545-b3e3-dcb3dea73250 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Close Ceiling
checkpoint-status |  |  | checkpoint | Check all services roughed in and not using ceiling frame as a support, all seismic supports have been installed for service by others, ceiling closeout checklist received by Lendlease
label | 0f8736d5-982c-5ae2-b395-cd414b5f54d1 |  | note | Acceptance Criteria: Minimum 3mm gap kept from ceiling frame
label | 08a95d04-cc0c-5114-8a7f-44fc4e146b76 |  | note | KEY-LOCK Suspended Seismic Ceiling Specification
label | 43fdadd0-06f6-59eb-b2e6-0f4ce31ee91c |  | note | Buildup Inspection Code: W
label | 58d07f9b-9e07-509c-ae86-5cc153847f73 |  | note | Lendlease Inspection Code:
label | e58637b2-6bbf-5890-ab2d-05287c2da1e3 |  | note | Lendlease Sign/Date:
label | 3981e080-67f9-5aeb-81d7-764d5c157c2d |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Installation of acoustic insulation to the ceiling
label | 81aff81c-6fc1-5adf-a5f0-cef7f92d7530 |  | note | Acceptance Criteria: acoustic insulation must extend 900mm from acoustic wall
label | 442564ea-bd6f-5a30-822a-d69f4c17c4ca |  | note | Series: BR3ADS2-Insulation Ceiling Plans
label | 2def8a40-fadc-5f90-9b0d-787a04037d3a |  | note | Buildup Inspection Code: W
label | 22b1b47e-4499-5b67-8be6-df8345fcf66a |  | note | Lendlease Inspection Code:
label | 80a9d84e-a346-5ffd-ad9c-68f21a65b231 |  | note | Lendlease Sign/Date:
label | 6915005f-897e-5331-be29-ea4e2eb9f0d3 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as pec
label | eb138e17-445d-598d-801b-35b3a3bfbfde |  | note | Acceptance Criteria: Staged Fixing @200mm max centre at edges, fixing @300mm max centre in field, Staged butt joint by 600mm min. Back blocking battens used on butt joints
label | fd008660-083c-5a31-adee-89f9e54b6192 |  | note | BCA Report 210721: 1740 R1.0
label | 1c10d24c-8c2a-5c6d-ab8f-bd7235f4bf7b |  | note | Buildup Inspection Code: W
label | dbbb369c-a57c-5065-9bc8-2137c6a43775 |  | note | Lendlease Inspection Code:
label | 981b4a73-1046-5cdf-b198-9e6aafc1a3a2 |  | note | Lendlease Sign/Date:
label | b9de9516-6c46-53f9-8d2c-a0f964f79488 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Access panel installed as required
label | 381e9365-30c1-5f31-9911-9af5317712c0 |  | note | Acceptance Criteria: Correct location, square with wall or bulkhead
label | a52ac08e-47a7-5e5b-9491-53ad23dfcdf4 |  | note | BCA Report 210721: 1740 R1.0
label | 4ab56bb0-e094-5b4d-90a5-f34d1f4b94e0 |  | note | Buildup Inspection Code: W
label | 90645b15-fd70-5f41-a9e7-43453d18fd4b |  | note | Lendlease Inspection Code:
label | b1c1b48a-abe2-53d6-9faa-3415b6e2704f |  | note | Lendlease Sign/Date:
label | 7f9d52d4-ee42-5fb7-80a2-8d6ad73e6876 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | 422434b7-258a-55e8-8a65-83edce8e9343 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | cad379e2-ec02-5510-8506-3fb8f41a8811 |  | note | BCA Report 210721: 1740 R1.0
label | 5e033fe6-82cb-505e-a202-fb24eab332ac |  | note | Buildup Inspection Code: W
label | 47fd9242-746a-51b7-978a-357dd4001931 |  | note | Lendlease Inspection Code:
label | 4c104619-e873-54ef-a6e3-a10af52d5f52 |  | note | Lendlease Sign/Date:
label | abb19fd6-5daf-5a9c-a718-6b1c89abbe49 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set and sand ready for painting
label | 54c3e6f3-5bd2-56a8-9824-90a7dcf64ea3 |  | note | Acceptance Criteria: No bubbles, no lump, square, not over sanded
label | 96b4257a-8222-5fbd-986a-685815fd527e |  | note | BCA Report 210721: 1740 R1.0
label | d75d5fdb-a49c-58df-8d32-549a466e761d |  | note | Buildup Inspection Code: W
label | d5b45041-8403-5462-a72e-e834b197ee06 |  | note | Lendlease Inspection Code:
label | 6896b5b4-c197-5e9d-a373-c0d8db40c9ec |  | note | Lendlease Sign/Date:
label | 67b0a7d6-104a-50e9-b86e-9143a8a305c0 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 37609a90-dfa1-5a54-93b6-f370008aba13 |  | note | Siniat&Rondo Inspection
label | 9bedb68a-1df9-5d81-afb8-a95263c18cd8 |  | note | Buildup Inspection Code: W
label | e5a06a6c-1e7b-55b9-ace6-a248fb78f248 |  | note | Lendlease Inspection Code:
label | 0db4dc05-7bfa-513f-8e29-af87a573cdcc |  | note | Lendlease Sign/Date:
label | c8f63e6e-29bd-5169-953f-8f0cd8191c36 |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 002 Installation of Soffit Insulation |  |  |  |  | Yes | ITP 002 Installation of Soffit Insulation | 998c62c8-5cbf-4998-8a1b-341ddc1c30dc
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | c01c324e-ca5a-5d5a-82e4-7309b4f37079 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 84764a4a-1380-5a3d-bccc-cfde4673bb78 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1.
label | 431a92d4-4ec9-5b7e-a5d9-03cc38e9d7e4 |  | note | Buildup Inspection Code: W
label | 5952a1c3-5743-5cbf-bcab-70c7f386869c |  | note | Lendlease Inspection Code:
label | 19df4c2a-ac1d-5444-bf28-8f8d960c4321 |  | note | Lendlease Sign/Date:
label | 43b69f2d-b2dc-52ac-a8a5-b0f71f774fbb |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Under Slab Insulation
checkpoint-status |  |  | checkpoint | Insulation dimension checked against drawings and Setout; Insulation types confirmed against Insulation set out plans
label | 67664a62-2bf9-5ef1-ad7a-20f84dbbbf23 |  | note | Acceptance Criteria: Latest drawing revision checked
label | 344e5c82-1a2a-5c22-a35c-cf94fc78c7fa |  | note | Series: BR3ADS2-Insulation Ceiling Plans
label | 7865c40c-2757-57ba-9c94-3aa4b0b85421 |  | note | Buildup Inspection Code: W
label | d5bd0423-9804-59b3-a1b7-18a29a202974 |  | note | Lendlease Inspection Code:
label | b168d9c4-743b-506b-8959-ef959822fb0b |  | note | Lendlease Sign/Date:
label | 1d046bce-3af5-5dca-84c1-5ed422c0f01b |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | The foil surface of the insulation board should face down
label | 68e12c8e-65a7-5693-bf6c-c9486cd14a67 |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | d54ca48e-ecc9-529b-8899-88d2ebb93f07 |  | note | Buildup Inspection Code: W
label | ef3f997d-51e1-55ce-b958-164f03baa952 |  | note | Lendlease Inspection Code:
label | cf9fddac-d8f8-57a7-a7e0-b51b1ceea54f |  | note | Lendlease Sign/Date:
label | e4e71d62-3a6f-512d-9a08-8232254e57bc |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Fix insulation panel to concrete soffits with minimum 5 No. Appropriate insulation fasteners with a minimum head diameter of 35 mm
label | d63db5e2-9eb8-5d64-8382-65e1fd573105 |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 719903b8-dc99-58bb-ba3f-77474d8f26e5 |  | note | Buildup Inspection Code: W
label | baa30174-d804-56d5-9e54-bf73c2e2e479 |  | note | Lendlease Inspection Code:
label | a62ab3a9-6a07-5b87-862b-b52e3a78280d |  | note | Lendlease Sign/Date:
label | 892120b6-d132-5c11-a5ef-7bf742d7462a |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Tape board joints with a minimum 96mm wide appropriate aluminium foil tape, detail as per attached Installation Instructions
label | d374de79-4435-535d-9002-ac73933ca79b |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 17c064b3-c91b-5609-b2f8-5c837bbf3352 |  | note | Buildup Inspection Code: W
label | d93bab89-4635-5434-9435-e2a6257f8714 |  | note | Lendlease Inspection Code:
label | 8a88a2e3-38f5-5437-a247-dfcfc9c666d6 |  | note | Lendlease Sign/Date:
label | 557e26d3-6cff-53ae-a469-277bb20cfffe |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Exposed board edge covered with foil tape lapped 48mm on to underside
label | 60bccecf-89e2-5099-a540-0371807a933c |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 7fa786ae-8d4b-56e7-a06c-59ff49568be3 |  | note | Buildup Inspection Code: W
label | 32199de6-1dba-5cc4-a1a6-3a06b5a4b377 |  | note | Lendlease Inspection Code:
label | d0225112-0552-5b63-b5b3-5adc32efec40 |  | note | Lendlease Sign/Date:
label | 808139a0-0149-5769-90a6-13b7cb3fa68e |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Check against cast-in penetrations. All penetrations/collars/dampers to be fully exposed
label | 842fc341-348b-5a04-acbc-9b194866d5b6 |  | note | Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 4cf13bae-3427-5b99-ac2a-8d9a5a6965bf |  | note | Buildup Inspection Code: W
label | 38637e23-ed5f-517d-8a1d-9c481bf2c216 |  | note | Lendlease Inspection Code:
label | ddf155b7-5950-54cc-81e3-f4ad8698637e |  | note | Lendlease Sign/Date:
label | 91890264-d785-5181-b077-7ce6489eed6f |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 007 Skirting Installation |  |  |  |  | Yes | ITP 007 Skirting Installation | c47f575a-98b5-488b-8d16-136a1b146f70
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 2058b252-d911-565f-a69f-16423a69bf28 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 73ee2e30-1d0f-5b3e-8b4a-82b050c0dfdc |  | note | Buildup Inspection Code: W
label | 65cbccbb-5a2e-5d2b-95d1-b1cff001e83d |  | note | Lendlease Inspection Code:
label | 59eba635-5cbe-577e-be29-d07716bfa2ba |  | note | Lendlease Sign/Date:
label | 0332f8f4-f30d-5b62-b5d7-bfd1a5678d5b |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set out Timber skirting size & type as per wall finish set out plan
label | 43b1d786-6fce-5b30-bc23-6b19c75d65ff |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | a1cc546e-8ba5-551f-a31a-a3ef6f6fbbd1 |  | note | Series: BR3ADL2-Internal Architectural Details BR3ADB2-Wall Setout Plans
label | 3adac091-ec2e-5e45-acbe-f817785ac2c6 |  | note | Buildup Inspection Code: W
label | b9aabbc4-7e20-566a-94be-5b62cb66d254 |  | note | Lendlease Inspection Code:
label | 4cbffd8b-dc32-59fb-a850-aa66e3ab3913 |  | note | Lendlease Sign/Date:
label | 7eca43b0-d8ad-5c50-bd36-ca8c6de13cd8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber skirting installed as manufacturer's specification to Top, bottom side
label | 4936f854-7ded-5ac5-a9da-9323fdd1ed00 |  | note | Acceptance Criteria: Straight and plumb and square, no sharp edge, gap less than 3mm, sealed with silicone Ref
label | 34c3463f-26d1-58b8-9b06-eea58dfdeadb |  | note | Buildup Inspection Code: W
label | ec631d1e-e65f-55bc-b668-a9987d4f5cba |  | note | Lendlease Inspection Code:
label | 87119f2a-2b6d-5e74-a040-642392d876e8 |  | note | Lendlease Sign/Date:
label | 1dd8ec1e-8f28-5c16-97f7-54f739459639 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | No unreasonable gap or holes on the wall
label | 83b0b825-56e8-5a4c-92ba-c6656d8a29fc |  | note | Acceptance Criteria: Eye Inspection
label | 1143549d-ecad-59d5-868e-e78a0c9d1413 |  | note | Buildup Inspection Code: W
label | 80ab6abf-280a-521a-a1d2-cef1fcf76738 |  | note | Lendlease Inspection Code:
label | c6fdaa16-75e0-5898-acad-5ec8a19dc929 |  | note | Lendlease Sign/Date:
label | b583eb85-c10a-58c4-8ea5-b04b69ee6a1c |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Timber skirting fixing and inspect for damage prior to hand over
label | eee90216-f251-5476-9797-c735ba4540f3 |  | note | Acceptance Criteria: Inspected and approved
label | 80c63d5a-1cf6-518c-aff6-ceeb89fc8756 |  | note | Buildup Inspection Code: W
label | 138e049a-3b60-5c71-ac05-a45128cf169c |  | note | Lendlease Inspection Code:
label | 6813e8fc-c750-53b3-af04-1988e0e0b68b |  | note | Lendlease Sign/Date:
label | 0a06ffeb-9004-53ac-872b-293a24e314ef |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 6ea47192-1939-5466-a098-8ee6eaea055d |  | note | Buildup Inspection Code: W
label | 779b72da-71eb-5ecc-8a95-f5a2c9689388 |  | note | Lendlease Inspection Code:
label | 38583753-7d9f-5b92-885a-0dae65accc7a |  | note | Lendlease Sign/Date:
label | c053e79e-ec61-5d28-8c50-d80c7f261444 |  | note | Lendlease Comment/Result:
checklist-flat |  |  | checklist | ITP 001 Speed Panel |  |  |  |  | Yes | ITP 001 Speed Panel | c5180ef2-7f9f-4896-ae8f-1aa92423c386
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | 8e24d5cd-ef03-5334-8145-6b0a2e38a581 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 94f3436a-1f7f-5430-aae7-0e1282c7714d |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | 0b1ceb7a-e8a4-5bdd-ad5a-f20f36bce9a1 |  | note | Buildup Inspection Code: W
label | 6fa01492-440f-5711-a227-e8369ca383df |  | note | Lendlease Inspection Code:
label | 812c5813-bf1b-5bd3-bca2-6f20181e4f7c |  | note | Lendlease Sign/Date:
label | 28b48b71-6fb7-509e-8d88-b40d965335e2 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | 062d1ddf-2f98-54aa-a91b-11e843ce2e71 |  | note | Acceptance Criteria: Latest drawing revision checked
label | 7e8d1535-1841-54e4-b945-ec49a1f26bb4 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | 301cfe28-301f-5364-b6ba-8e716f739ded |  | note | Buildup Inspection Code: W
label | 87a44666-9082-572f-84e2-ecd8aae56dc4 |  | note | Lendlease Inspection Code:
label | 2ee0bc45-84c2-5a38-b3d3-2152ec7ad1ff |  | note | Lendlease Sign/Date:
label | 144b97c8-a67d-5dbd-b571-2c8490f8533a |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | a0751e1b-18d6-5332-94f4-c330a1fe2fd3 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | d2e3aeba-95d6-5eae-958d-8edb7ad3f94a |  | note | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | 97450deb-3dac-5af6-8f50-20ffba3bcae8 |  | note | Buildup Inspection Code: W
label | a4bbd3eb-bee1-5624-9c83-ce234029a28d |  | note | Lendlease Inspection Code:
label | 6146f5f4-2ab7-55a4-9a7b-0dcc950492a3 |  | note | Lendlease Sign/Date:
label | 6a3b3020-2d5a-5ff1-97f4-fa8f0bcf2eb8 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Panels installed as manufacturer's specifications
label | 0f5ae4bb-721a-54fe-a1a5-2cbd490884bf |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 633cd53b-9530-54d5-8026-8041b5ad2089 |  | note | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | e47d1349-2acc-5ec3-abad-46151ad9c097 |  | note | Buildup Inspection Code: W
label | 1d27e422-86d5-52f3-8587-0be079f5e040 |  | note | Lendlease Inspection Code:
label | f8f0f50b-7718-548c-bf73-340c41fc03ff |  | note | Lendlease Sign/Date:
label | e617cc63-96c3-5a8c-b6d8-9b4066e57a6c |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Comprehensive first of type inspection
label | 5f18ecfd-40c6-527f-8db9-82e928697d80 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | d407e042-d2bb-5cc6-af7c-6b73a2a90fa1 |  | note | Buildup Inspection Code: W
label | 23955e3c-9b8a-5eb3-bcb4-55ae656dfb55 |  | note | Lendlease Inspection Code:
label | 40fb006c-a3a9-5592-b9ba-f484b4915280 |  | note | Lendlease Sign/Date:
label | 0006cae8-e483-521c-bb98-28fcdb9866c2 |  | note | Lendlease Comment/Result:
checklist-sectioned |  |  | checklist | ITP 003 Installation of Internal Partitions |  |  |  |  | Yes | ITP 003 Installation of Internal Partitions | ef6f2698-0b89-4dbc-8f39-391ff3fc32b6
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | Materials Inspected upon delivery
label | e2aef0d4-0b60-5db8-af66-1f8d981a3696 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | af7cabba-94fe-5233-9279-04d7cd377b6a |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | d0df392b-e109-55bb-87aa-a4d434f44b3d |  | note | Buildup Inspection Code: W
label | 493388d7-c8b0-5e4e-aa1f-699619b387ff |  | note | Lendlease Inspection Code:
label | 9d239220-e801-5615-af30-f8e916306d84 |  | note | Lendlease Sign/Date:
label | b687bb69-c8b9-5d7d-bb08-ef8c8c3d85a2 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Wall Framing
checkpoint-status |  |  | checkpoint | Wall framing dimension checked
label | 9943d771-e801-5a1a-972a-eff94af52e19 |  | note | Slotted Deflection Track used; additional noggin installed for onside sheeting frame
label | ebaf8bc6-a965-57a9-8a3a-c957f8bcd22f |  | note | Series: BR3ADB2-Wall Setout Plans
label | 3bca9619-45d6-57c3-ba89-8110fd3f38ed |  | note | Buildup Inspection Code: W
label | 866dbe68-c41b-5f88-b65e-31cb0f5827ad |  | note | Lendlease Inspection Code:
label | 0ede35d8-3042-539f-bc0c-45dd4189c60c |  | note | Lendlease Sign/Date:
label | 02874717-1b18-5604-9fc3-9c70cec1839f |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Allowance for access panels and service penetration
label | 3ef4865a-9df9-56da-9582-1b216aaf6ca1 |  | note | Acceptance Criteria: Bridging Track supported by offcut studs
label | 8bbcd3a0-8767-5bb6-a324-5d6572ef2419 |  | note | Internal partition designs: 10246-22-001 -SK00 - 10246-22-001 -SK15
label | 8b379e89-f9b9-5afb-a8bd-d22cf82692f8 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 8567e648-c220-54ab-92d6-f4113934b5aa |  | note | Buildup Inspection Code: W
label | 14e039f2-6705-564c-bfb0-5cc2dbd47c42 |  | note | Lendlease Inspection Code:
label | 2fbfe656-c759-593a-b5a3-486fbf5c9623 |  | note | Lendlease Sign/Date:
label | 3de960a9-e363-5460-b0c2-60ba0d0217fa |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Openings (Including doors, windows, removable parts) installed to correct position and height, with right opening towards, plumb and square, as per Rondo designs
label | 5e9c85c0-7023-5110-806f-0c78dc656d46 |  | note | Acceptance Criteria: Jamb header or sill used correct components
label | 2d0ab5b4-1b10-5cb8-82a0-c08c72959b4d |  | note | Internal partition designs: 10246-22-001 -SK00 - 10246-22-001 -SK15
label | c51e7ec8-e389-560b-952d-6454a9dde7a9 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 80428c71-85d9-5c4a-9a9f-fb07f6d1ece3 |  | note | Buildup Inspection Code: W
label | 8fde32dc-bb85-51d4-b134-7bc642ba73d1 |  | note | Lendlease Inspection Code:
label | d597d094-66b2-53fc-99f1-40796beaa4a8 |  | note | Lendlease Sign/Date:
label | b194411a-6c3c-5f6a-8df7-414fdde4b56c |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Plywood Noggins and structural stud installed for all fixtures
label | f5c5d73d-510d-5a8e-ac74-b7ab9a978a06 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | 45c12722-6ca6-52d2-b2fb-73d2eb042b25 |  | note | Internal partition designs: 10246-22-001 -SK00 - 10246-22-001 -SK15
label | b9b822f8-bcae-5e79-8476-402600f22af4 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 9b6c8c08-42be-5014-96aa-866ad5dadaff |  | note | Buildup Inspection Code: W
label | 514f70e1-ef7b-5379-b42f-2156b385dcee |  | note | Lendlease Inspection Code:
label | 209295b4-8de8-56e3-9bb4-a98c22477c91 |  | note | Lendlease Sign/Date:
label | 415f1ca7-a155-5a32-845d-b5e18b192247 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Door and window Frame installed as per manufacturer's specification stud installed for all fixtures
label | 0427c906-1929-55e0-88ba-4166a4752f25 |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | 3581032e-14ed-5cab-91be-189f988e1f10 |  | note | Internal partition designs: 10246-22-001 -SK00 - 10246-22-001 -SK15
label | 71aa2cf8-2dc2-5515-b568-ab3c98a9bd46 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 4592128e-8326-59f2-a9a1-314659febdf0 |  | note | Buildup Inspection Code: W
label | 380cb038-d578-5ef3-a5cb-19773645ed02 |  | note | Lendlease Inspection Code:
label | cb649b6e-5aa0-5a16-bce4-c2c899ec6185 |  | note | Lendlease Sign/Date:
label | 07081622-f51e-5ede-889c-65afd056c8a2 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Sheeting (One Side)
checkpoint-status |  |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as specification
label | dc3c429c-b981-5776-8b1f-8bec016aca1b |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | 0c3107ca-eaad-5b38-be1e-ecdb1d723184 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 51ceebac-27fd-516b-aa82-0aa9020750ab |  | note | Buildup Inspection Code: W
label | 76b8352b-8228-55fe-809b-537f59bd9629 |  | note | Lendlease Inspection Code:
label | 3685800b-c7c9-5c83-a13e-d379bc810c55 |  | note | Lendlease Sign/Date:
label | f81a1207-a1a7-5b05-a1e8-908c1e9b64f7 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | a9408b2b-c354-54c1-9074-b588d00dedf1 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | 4bea2370-f9b3-511a-9f44-9705d4da30c4 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | c41427b5-297c-57f5-bbdd-6bb0b3b7e211 |  | note | Buildup Inspection Code: W
label | 4e599fd2-e633-5845-af92-de72cf20d5fa |  | note | Lendlease Inspection Code:
label | 4d7c8434-7ac8-5df5-8b68-395c956685e4 |  | note | Lendlease Sign/Date:
label | b63f59f1-a282-57fc-b2c0-d01665850b12 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Penetration sheeted and sealed as per builder's drawings
label | 50747465-0c76-5314-8655-3d22908c401f |  | note | Acceptance Criteria: Opening square and flush, fully sealed
label | bbbf86c1-87de-5b67-845a-539fcd054c31 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | 1e59e90c-1e72-569c-bbb7-871bcad14eda |  | note | Buildup Inspection Code: W
label | 65f182e6-8b78-5f09-ad8c-8213540b341d |  | note | Lendlease Inspection Code:
label | 1cf7f24a-f68b-50f6-81c8-38074659e548 |  | note | Lendlease Sign/Date:
label | ae8dc7d6-dfbc-5030-a162-042eb8093b48 |  | note | Lendlease Comment/Result:
checkpoint-group |  |  | section | Sheeting (Close Wall)
checkpoint-status |  |  | checkpoint | All in wall Services signed off by other trades, wall closeout checklist received by Lendlease
label | eff795cd-3630-50c6-bb08-867ee7ccfc2d |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough in have been completed and approved prior to sheeting
label | c51bf7d1-cc14-5c7e-8f17-926d9b9317d5 |  | note | Buildup Inspection Code: W
label | 6197a0a5-bdf5-53c4-ae8c-c54546d87fe4 |  | note | Lendlease Inspection Code:
label | 163fdc55-715c-5c11-95ef-ac8b4b3272c0 |  | note | Lendlease Sign/Date:
label | cf8d4008-a75d-5489-aefc-8f4d2963c0cb |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Insulation completed as per acoustic report, partition plans and spec
label | 97aa7043-055b-5a70-ba0a-f04215d81122 |  | note | Acceptance Criteria: As required Insulation, no gap can be seen
label | e78d5cda-82aa-5978-9af1-d96bffcfbbee |  | note | Series: BR3ADL1-Wall Type
label | e8eb522d-11c7-52f4-8a1d-0f55667ad4b7 |  | note | Buildup Inspection Code: W
label | d08091ae-d318-517e-b714-a977b14e4c48 |  | note | Lendlease Inspection Code:
label | baa93725-d080-5c32-9f8a-b13645bb078d |  | note | Lendlease Sign/Date:
label | a681190e-45a9-506c-b0fd-46c8304b36ba |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Plywood Noggins and structural stud installed for all FFE
label | 9554d882-8350-5de0-b822-d52e7f42bab4 |  | note | Acceptance Criteria: Checked against current RLS
label | 80e15c0c-9d81-507b-8931-2343edfa3cd8 |  | note | Series: BR3ADL2-Internal Architectural Details
label | f8ca0bbc-0f7d-5259-98d0-45ff3bec4ece |  | note | Buildup Inspection Code: W
label | 2de2c4a6-4d1c-5b03-a16e-62b7ca299a01 |  | note | Lendlease Inspection Code:
label | 186456a8-b64f-511c-b2d0-0658c52858ec |  | note | Lendlease Sign/Date:
label | f8fa23fd-9391-56e7-a6f8-fb1cc0d1983b |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Close wall
label | c11109d1-5e75-54d9-896a-be21075416ec |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | 4b599c37-6a69-5ea4-8e0b-39b0756eab37 |  | note | Series: BR3ADB2-Wall Setout Plans And BR3ADL1-Wall Type
label | dcfe2e31-1335-5c19-9c37-6f6a9ff1bb4f |  | note | Buildup Inspection Code: W
label | 8beafecc-9f0b-5576-b333-507c231d5338 |  | note | Lendlease Inspection Code:
label | 9de927bf-09e8-5743-bc01-3cbbfbf975ad |  | note | Lendlease Sign/Date:
label | a945601a-9568-55ae-82ae-d3e56bd54174 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Caulking to acoustic / fire / smoke/ details
label | 7f580262-1beb-511a-bb33-2dbfc089212a |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | ef7679f0-3b71-540c-82fc-858f29ab54b0 |  | note | Buildup Inspection Code: W
label | 073610b3-ffc7-5180-a9af-6a8e629f7a36 |  | note | Lendlease Inspection Code:
label | 964c2a12-8ae5-5e09-a6c3-56131dedbc4d |  | note | Lendlease Sign/Date:
label | 27e879bf-b723-5f48-84bb-e42118223954 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | Set and sand ready for painting
label | b2b9821b-202f-5e52-ac86-4a25cd8df678 |  | note | Acceptance Criteria: Meet Level 4 of finish requirement
label | 7e8a6dae-f662-5725-ac67-b404a883eea1 |  | note | Buildup Inspection Code: W
label | fbe923fe-8d68-5d10-b672-abb3c5820444 |  | note | Lendlease Inspection Code:
label | eebe4794-5925-5a5b-9b8f-a1d469c87dac |  | note | Lendlease Sign/Date:
label | e9dfad96-ffdf-5bc5-86f5-c8c5d23b7388 |  | note | Lendlease Comment/Result:
checkpoint-status |  |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 3fc9c7d0-1ae8-579f-84e6-3b2fc81c0772 |  | note | Acceptance Criteria: Siniat & Rondo Inspection
label | 02497322-3532-5e74-8175-6aab9ca7031b |  | note | Buildup Inspection Code: W
label | 5ea48d04-1c00-508b-83f6-6397493c0b49 |  | note | Lendlease Inspection Code:
label | 41e56e37-ff59-55f7-90b8-319f4a1313da |  | note | Lendlease Sign/Date:
label | 656dafc0-26ac-5152-912c-6967d7ebc7a7 |  | note | Lendlease Comment/Result: