## QA Folder Structure
QA
Substructure
Foundations
Columns
Shear Walls
Slab
Ramp slab
Other
Superstructure
Level 1
Slab
Columns
Shear Walls
Ramp slab
other
Level 2
Slab
Columns
Shear Walls
Ramp slab
other
Level 3
Slab
Columns
Shear Walls
Ramp slab
other
Level 4
Slab
Columns
Shear Walls
Ramp slab
other

## Tools Inventory
Tools & Equipment
| Section | Stihl Cut-Off Petrol Saw
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Electric (7") Angle Grinder
| Checkpoint |  | CR Number
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Electric (5") Angle Grinder
| Checkpoint |  | CR Number
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Electric (5") Angle Grinder Cordless
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Cordless Impact Driver
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Portable Stick Welder
| Checkpoint |  | CR Number
| Checkpoint |  | Welding Gloves
| Checkpoint |  | Welding Helmet
| Checkpoint |  | Photo
| Section | Electrical Leads
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Bolt Cutter
| Checkpoint |  | Photo
| Section | Dog Bars
| Checkpoint |  | Quantity
| Checkpoint |  | Photo
| Section | Cutter Bender
| Checkpoint |  | Photo
| Section | Ramset Epoxy Gun Electric
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Ramset Epoxy Gun Manual
| Checkpoint |  | Photo
| Section | Pipe Wrench
| Checkpoint |  | Quantity
| Checkpoint |  | Photo
| Section | Sledge Hammer
| Checkpoint |  | Photo
| Section | Spirit Level
| Checkpoint |  | Photo
| Section | 25/30m Measure Tape
| Checkpoint |  | Photo
| Section | Face Shield
| Checkpoint |  | Photo
| Section | Fire Extinguisher 3kg
| Checkpoint |  | Photo
| Section | Bar Stands
| Checkpoint |  | Photo

## Crane Base Insitu
Job
Reinforcing Installation
Crane Base
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Piles
| Checkpoint |  | Starters perpendicular
| Checkpoint |  | Piles - Cut off height & linished
| Checkpoint |  | Flange nuts fixed and epoxied
| Checkpoint |  | Hoops/spiral installed with correct diameter/grade/spacing
| Section | Bottom bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Top bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Side bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | All bars adequately tied
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | All bars adequately tied
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Sufficient protruding lap
| Section | Miscellaneous
| Checkpoint |  | Cast-ins/Crane legs
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy

## Lift Pit
TH01
Reinforcing Installation
Lift Pit
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Base slab top & bottom
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Section | Ground beams
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section |  | Stirrup diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Sump
| Checkpoint |  | Location
| Checkpoint |  | Trimmers
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Sufficient protruding lap
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Foundations
TH-01
Reinforcing Installation
Foundations
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Pile cap
| Checkpoint |  | Stirrups/links diameter/spacing
| Checkpoint |  | U-bars diameter/spacing
| Section | GB top bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section | GB bottom Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section | GB Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Checkpoint |  | Penetration thickening
| Section | GB Side bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Set out
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Drossbach template installed for panel starters
| Checkpoint |  | Starters braced and perpendicular
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy
zASQ

## Column Insitu
TH-01
Reinforcing Installation
Columns
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Set out
| Checkpoint |  | Starters perpendicular
| Section | Column
| Checkpoint |  | Starter height, bar diameter and correct lap
| Checkpoint |  | Main bar diameter/quantity, and lap
| Checkpoint |  | Stirrups diameter/spacing
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Stirrups to top of concrete
| Checkpoint |  | Holding stirrup at top of column
| Checkpoint |  | All bars and stirrups adequately tied
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy
\

## PT Beams
TH01
Reinforcing Installation
PT Beams
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe & accessible
| Section | Top bars
| Checkpoint |  | Bar diameter/spacing
| Checkpoint |  | Lap
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Not obstructing PT
| Checkpoint |  | Eye bars
| Section | Bottom bars
| Checkpoint |  | Bar diameter/spacing
| Checkpoint |  | Lap
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Not obstructing PT
| Checkpoint |  | Eye bars
| Section | Side bars
| Checkpoint |  | Bar diameter/spacing
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Bar diameter/spacing
| Checkpoint |  | Lap
| Checkpoint |  | Correct dimensions
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Correct dimensions
| Section | Starter bars
| Checkpoint |  | Set out
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Sufficient protruding lap with holding stirrup
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Miscellaneous
| Checkpoint |  | Penetrations trimmers
| Checkpoint |  | Pan trimmers
| Checkpoint |  | U-bars over anchors
| Checkpoint |  | Terminators/Couplers installed correctly
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## PT Slab
TH-01
Reinforcing Installation
PT Slab
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Slab
| Checkpoint |  | Distribution Steel B1. Bar diameter/spacing
| Checkpoint |  | Distribution Steel B2. Bar diameter/spacing
| Checkpoint |  | T1/T2. Bar diameter/spacing
| Checkpoint |  | Laps B1,B2/T1,T2
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Stagger
| Checkpoint |  | Saddle bars over beams
| Checkpoint |  | Starters thru CJ
| Checkpoint |  | Protruding lap length past CJ
| Checkpoint |  | Penetration trimmers
| Checkpoint |  | Pan trimmers
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Shear Wall
TH-01
Reinforcing Installation
Shear Wall
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Wall verticals
| Checkpoint |  | Starter height, bar diameter
| Checkpoint |  | Main bar diameter/quantity, and lap
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Staggered laps
√ | Checkpoint |  | All bars adequately tied
| Section | Wall horizontals
| Checkpoint |  | Bar diameter/spacing
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Section | Stirrups/Links
| Checkpoint |  | Bar diameter/spacing
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Section | Cage
| Checkpoint |  | Cage Correct Overall Length
| Checkpoint |  | Cage Correct Overall Width
| Checkpoint |  | Cage Correct Overall Height
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | 1st handover for cast-ins
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy
| Section | Final review
| Checkpoint |  | All reinforcing tied back correctly
| Checkpoint |  | All starters postioned correctly
| Checkpoint |  | Cover blocks/chairs/spacers

## Panel Stitches
TH-01
Reinforcing Installation
Panel Stitches
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Starters from protruding from panels as per drawings/no re-bending
| Section | Verticals NF/FF
| Checkpoint |  | Bar diameter/spacing
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Checkpoint |  | Correct length
| Checkpoint |  | Correct laps
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Top cover where returns terminate
| Checkpoint |  | Trimmers to penetrations/openings
| Section | Horizontals/stirrups/links
| Checkpoint |  | Bar diameter/spacing
| Checkpoint |  | Correct grade 300 or 500 noted in comments with photos
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| section | Review & Handover
| checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint |  | Area left clean & tidy

## Slab on Ground
Job
Reinforcing Installation
Slab Ground
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Underside of slab levels correct
| Checkpoint |  | Correct laps
| Section | Slab reinforcing
| Checkpoint |  | B1/B2 bar diameter/grade/spacing
| Checkpoint |  | Additional/drag bars bottom mat
| Checkpoint |  | Slab orientation EG: B1 East-West B2 North-South
| Checkpoint |  | T1/T2 bar diameter/grade/spacing
Additional/drag bars top mat
| Checkpoint |  | Saddle bars over beams and walls
| Checkpoint |  | Correct laps
| Checkpoint |  | Chair height
| Checkpoint |  | Vertical starters diameter/grade/spacing & cover allowing for horizontals
| Checkpoint |  | Trimmers to penetrations/openings
| Checkpoint |  | Nibs - note location
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Suspended Slab
TH-01
Reinforcing Installation
Suspended Slab
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Slab Comflor
| Checkpoint | C80/250 | H16-200 CRS-EW and SE62 Mesh
| Checkpoint | C80/180 | H12-200 CRS-EW and SE62 Mesh
| Checkpoint | C80/200 | H16-200 CRS-EW
| Checkpoint |  | Trough bars 30mm bottom cover
| Checkpoint |  | Typical trimmers at slab edge and openings
| Checkpoint |  | Diaphragm/Drag bar reo
| Checkpoint |  | Saddle bars running E-W
| Checkpoint |  | Edge hairpins and nosing bar
| Checkpoint |  | T1 Connections
| Checkpoint |  | Bar laps
| Checkpoint |  | Mesh laps
| Checkpoint |  | Correct laps at step
| Checkpoint |  | Nibs - note location
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## PC Beam Stitch
BTR
Reinforcing Installation
PC Beam Stitch
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Starters from protruding from PC Beams as per drawings/no re-bending
| Section | Longitudinal T/B & sides
| Checkpoint |  | Correct laps
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| section | Review & Handover
| checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint |  | Area left clean & tidy

## Ground Beams
Job
Reinforcing Installation
Ground Beams
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Prestart/area acceptance
| Checkpoint |  | Safe access
| Checkpoint |  | Edge protection
| Checkpoint |  | Workface ready and clear
| Checkpoint |  | Blinding level surveyed
| Checkpoint |  | Waterproofing
| Checkpoint |  | Setout
| Section | Cover spacer blocks
| Checkpoint |  | Correct type/size
| Checkpoint |  | Staggered
| Checkpoint |  | No punctures to waterproofing
| Checkpoint |  | Sufficient spacing to avoid sagging
| Section | Top bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | Development length into pile cap
| Checkpoint |  | Returns 90 degrees
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | Bottom Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | Development length into pile cap
| Checkpoint |  | Returns 90 degrees
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Checkpoint |  | Cover top, bottom and sides
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Checkpoint |  | Trimmers to penetrations/openings & additional stirrups
| Checkpoint |  | All bars adequately tied
| Section | Side bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Returns 90 degrees
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | Starter bars
| Checkpoint |  | Setout correct
| Checkpoint |  | Template if required
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Couplers flush at concrete face
| Checkpoint |  | Couplers capped or taped
| Checkpoint |  | Footplates fixed
| Checkpoint |  | Setout correct
| Section | Miscellaneous
| Checkpoint |  | Penetrations/trimmers
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy

## Capping Beam
Job
Reinforcing Installation
Capping Beam
| Section | Delivery/Material Check
| Checkpoint |  | Material delivered to site correct
| Section | Workface Acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Piles
| Checkpoint |  | Orientation
| Checkpoint |  | Correct height
| Checkpoint |  | Hoops bar diameter/grade/spacing
| Checkpoint |  | Hoops welded laps
| Section | Top Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | All bars adequately tied
| Section | Bottom Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Side Bars
| Checkpoint |  | NF/FF Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | 40mm IMBMS couplers fitted and aligned
| Section | Stirrups/Links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Footpath Starters
| Checkpoint |  | Setout correct
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Miscellaneous
| Checkpoint |  | Penetrations/trimmers
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy