## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Subsoil Drainage - Rev C | itp |  |  |  |  | ITP - Subsoil Drainage - Rev C
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
note | Standard / Specification - Downer
note | Verifying Document - Construction Pack
note | Frequency - Submit 10 days prior to commencement of works
note | Activity - H
note | By - PE
checkpoint | 3.01.02 - Survey Setout
note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
note | Standard / Specification - Downer
note | Verifying Document - Survey Records
note | Frequency - Prior to Works
note | Activity - H
note | By - SV
checkpoint | 3.01.03 - Approved Construction Drawings
note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
note | Standard / Specification - Downer
note | Verifying Document - IFC Drawings
note | Frequency - Prior to works start
note | Activity - H
note | By - PE
checkpoint | 3.01.04 - Topographic surveys for measurement
note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
note | Standard / Specification - PS 2.2.12
note | Verifying Document - As-built
note | Frequency - Prior to works and Post Works
note | Activity - H
note | By - PE
checkpoint | 3.01.05 - Permits
note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
note | Standard / Specification - ITP Register
note | Verifying Document - ITP Sign Off
note | Frequency - Prior to commencement of construction activity
note | Activity - R
note | By - SE
checkpoint | 3.01.06 - Stakeholder Management
note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
note | Standard / Specification - Project Stakeholder Management Plan
note | Verifying Document - ITP Sign Off
note | Frequency - Prior to Construction with continue updates throughout the works
note | Activity - R
note | By - SE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Subsoil Pipes
note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
note | Standard / Specification - GWS 3.2.1
note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
note | Frequency - Every Delievery to Site
note | Activity - C
note | By - SE
checkpoint | 4.01.02 - Subsoil Drainage Aggregate
note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11
note | • Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
note | • App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
note | Test Sieve Aperture (mm) Percentage Passing (%)
note | 53 100
note | 13.2 10 (max)
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Standard / Specification - GWS 3.2.2 & 3.4
note | Verifying Document - PSD, CR
note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
note | Activity - C
note | By - SE
checkpoint | 4.01.03 - Filter Cloth
note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
note | Standard / Specification - GWS 3.2.3
note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
note | Frequency - Every Delievery to Site
note | Activity - C
note | By - SE
checkpoint | 4.01.04 - Securing Pins
note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
note | Frequency - Every Delievery to Site
note | Activity - C
note | By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench.
note | • Cloth must fully encapsulate the aggregate.
note | • Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6).
note | • Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement).
note | • Verifying document, photos of trench prior to backfill, every line.
note | Standard / Specification - GWS 3.2.2
note | Verifying Document - Every line
note | Frequency - Photos of trench prior to backfill
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Trench Backfill
note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
note | Standard / Specification - GWS 3.3
note | Verifying Document - Site Record
note | Frequency - Each trench
note | Activity - I
note | By - SE
checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
note | Standard / Specification - GWS 3.6
note | Verifying Document - Site Records
note | Frequency - Each Subsoil Line
note | Activity - I
note | By - SE
checkpoint | 5.01.04 - Subsoil Flushing
note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
note | Standard / Specification - GWS 3.6
note | Verifying Document - Site Records
note | Frequency - On completion of earthworks
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.05 - Survey
note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SV
checkpoint | 5.01.06 - Excavation
note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Prior to laying filter cloth
note | Activity - I
note | By - SE
checkpoint | 5.01.07 - Bedding
note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Prior to laying Novacoil
note | Activity - I
note | By - SE
checkpoint | 5.01.08 - Joining Pipes
note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
note | Frequency - Every join
note | Activity - I
note | By - SE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SE
checkpoint | 6.01.02 - Survey Records
note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - As-builts taken every 10m prior to backfill
note | Activity - H
note | By - SV
checkpoint | 6.01.03 - Redline Drawings
note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
note | Standard / Specification - Downer
note | Verifying Document - Redlines
note | Frequency - Post construction
note | Activity - H
note | By - PE
checkpoint | 6.01.04 - Defect, Snag and Punch List
note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
note | Standard / Specification - Downer
note | Verifying Document - Register
note | Frequency - Post construction
note | Activity - H
note | By - PE
checkpoint | 6.01.05 - Photos
note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
note | Standard / Specification - Downer
note | Verifying Document - Photo Records
note | Frequency - Post construction
note | Activity - H
note | By - SE