## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-063-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0063 - PERMANENT LINE MARKING
section | Lot Information
checkpoint | 1.0 Lot Information
text | Lot Created On
text | Lot Opened On
text | Work Commenced On
select | Lot Type | CIL - Civil Lot
text | From and To Chainage
select | Construction Element | SIGN - Signage and Pavement Marking
select | Activity | LINE - Line Marking
select | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | Engineer Responsible
text | comments
section | 1 - Preliminary Works
checkpoint | 1.1 Inductions
label | Frequency: Prior to Commencing linemarking works
label | - - - - - - - - -
label | Acceptance Criteria: All personnel on site have been inducted to the CRU Site.
label | - - - - - - - - -
label | Reference Documents: Inductions Register
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of Conformity: ITP signed, Site induction signed.
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.2 Safety measures are in place, SWMS undertaken
label | Frequency: Prior to Commencing linemarking works
label | - - - - - - - - -
label | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | - - - - - - - - -
label | Reference Documents: Health and Safety Co-Ordination Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: ITP signed, SWMS(s) signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.3 Check that current revision drawings are being used
label | Frequency: Prior to Commencing linemarking works
label | - - - - - - - - -
label | Acceptance Criteria: Issued For Construction (IFC) drawings, & latest available revision used.
label | - - - - - - - - -
label | Reference Documents: IFC Project Drawings.
label | • PS3070.04, PS3070.06
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of Conformity: ITP signed, Latest revision IFC drawings
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.4 Confirm understanding of current EMP related to the work area and that all prescribed environemental controls are in place
label | Frequency: Prior to Commencing linemarking works
label | - - - - - - - - -
label | Acceptance Criteria: All environmental measures to be implemented as per construction environmental management plan
label | - - - - - - - - -
label | Reference Documents: CEMP, Site induction, PS1200.03
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.5 Traffic Management (When required)
label | Frequency: Prior to Commencing linemarking works
label | - - - - - - - - -
label | Acceptance Criteria: Approved TMP and MOA in use
label | - - - - - - - - -
label | Reference Documents: Applicable TMP, PS1160.012
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | • Approved TMP & MOA
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
section | 2 - Linemarking Works
checkpoint | 2.1 Verification of line marking material
label | Frequency: Prior to commencing site preparation
label | - - - - - - - - -
label | Acceptance Criteria: Line marking material to comply with minimum requirements as specified in VicRoads Spec 721.A05, VR721.A13, VR721.A14, & PS3070.05
label | - - - - - - - - -
label | Reference Documents: PS3070.05, VR721.A05
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of Conformity: ITP signed, Material compliance
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 2.2 Site preparation
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: Site to be prepared by removing any foreign materials and debris within reasonable limits.
label | - - - - - - - - -
label | Reference Documents: PS3070.07C
label | • VR721.A06
label | • VR721.A08
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 2.3 Removal of unsuitable/redundant markings (If required)
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: If redundant/unsuitable pavement markings to be removed, removal methodology to be approved by superintendent
label | - - - - - - - - -
label | Reference Documents: PS3070.07C
label | • VR721.A06
label | • VR721.A08
label | • VR721.A12
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Set out of line markings; dimensions and spacings
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: Painting/application of material shall not commence until the Superintendent has inspected the setout and installation timeframes are adherred to.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings
label | • PS3070.07D
label | • PS3070.07H
label | • PS3070.07J
label | • VR721.A09
label | • VR721.B05
label | • VR721.B04
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | • Consent to proceed by Superintendent OR written exemption granted
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Painted pavement marking application (if required)
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: If required, painted pavement marking is to be applied by a self propelled machine, with the minimum requirements for paint and glass to be as per table 721.D021
label | - - - - - - - - -
label | Reference Documents: VR721.D01, VR721.D02
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 2.6 Long life pavement marking application
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: all line marking shall be applied using a self propelled ride-on machine including statcon marking unless otherwise approved, with the minimum requirements for long life materials and glass beads to be as per table 721.E021
label | - - - - - - - - -
label | Reference Documents: VR721.E01, VR721.E02
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 2.7 Protection of works
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: Work to be protected by appropriate means until it is trafficable.
label | - - - - - - - - -
label | Reference Documents: VR721.A11
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
section | 3 - Testing
checkpoint | 3.1 Acceptance of retroflectivity
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: Contractor to measure level of retroflectivity, with the average of six test site retroflectivity values for each lot.
label | - - - - - - - - -
label | Reference Documents: VR721.A13
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed, Test report
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 3.2 Acceptance of colour
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: Colour match tests for white & yellow markings to be conducted as per 721.A14, with results forwarded to the superintendent no later than 5 days from testing.
label | - - - - - - - - -
label | Reference Documents: VR721.A14
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed, Test report
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 3.3 Acceptance of tolerances
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: Survey conformance report to show line marking applied as per tolerances shown in table 721.A101.
label | - - - - - - - - -
label | Reference Documents: VR721.A10, VR721.A101
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed, Survey report
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 3.4 Acceptance of work
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: Work to comply with specified requirements as detailed in VR721.A12
label | - - - - - - - - -
label | Reference Documents: VR721.A12
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint | 3.5 Records & reporting
label | Frequency: Per lot
label | - - - - - - - - -
label | Acceptance Criteria: All new markings to have job completion report forwarded to the superintendent, with a retroflectivity report completed and forwarded to the superintendent showing the retroflectivity for each test lot.
label | - - - - - - - - -
label | Reference Documents: VR721.B06
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of Conformity: ITP signed, Reports
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
text | Work Completed On
checkpoint-group | Lot Verification
checkpoint-status | Lot Verification.
select | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | Other:
select | Lot Status | OUTSTANDING, CLOSED
text | Lot Closed On
text | comments