## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP-022-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS | itp |  |  |  | Yes | ITP-022-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS | 8b3c83f4-9492-4b34-974e-01c36b4b52b5
checkpoint-group | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS
label | ITP Description: BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 28/02/2023
label | ITP created by: Jason Lee
label | ITP approved for use by: Jon De Castro
checkpoint-status | 1.1 - Non Dependent
label | Reference - VicRoads Section 204
checkpoint-status | 1.2 - Non Dependent
label | Reference - VicRoads Section 173
checkpoint-status | 1.3 - Non Dependent
label | Reference - IFC Drawings
checkpoint-group | 2. Preliminaries - Materials
checkpoint-status | 2.1 - Non Dependent
label | Reference - N/A
label | Acceptance Criteria - N/A
label | Method - N/A
label | Frequency - N/A
label | Category - N/A
label | Responsibility - N/A
label | Verifying Documents - N/A
checkpoint-group | 3. Preliminaries - Procedures & Documentation
checkpoint-status | 3.1 - Non Dependent
label | Reference - N/A
label | Acceptance Criteria - N/A
label | Method - N/A
label | Frequency - N/A
label | Category - N/A
label | Responsibility - N/A
label | Verifying Documents - N/A
checkpoint-group | 4. Pre-construction Activities
checkpoint-status | 4.1 - Survey Set-Out
label | Reference - IFC Drawings
label | Acceptance Criteria - The Area of Excavation has been set out in accordance with the drawings.
label | ○ IFC Drawings with work lots marked-up attachment required
label | Method - Verify
label | Frequency - Prior to Commencement of Excavation
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP
checkpoint-status | 4.2 - Material Classified as Silt
label | Reference - Section 204.04 (b) - Table 204.041
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
label | ○ Type A Material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | ○ Superintendent satisfied with stabilisation
label | ○ Attach: TeamBinder Material Approval Ref No.
label | Method - Document Review
label | Frequency - Prior to Commencing
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 5. Construction Activities
checkpoint-status | 5.1 - Subgrade Material Properties Inspection
label | Reference - IFC Drawings
label | ○ Section 204.06 (c)
label | ○ Section 204.06 (e)
label | Acceptance Criteria - Section 204.06 (c)
label | • Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04 and Table 204.041
label | ○ Section 204.06 (e)
label | • In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | • Assigned CBR not less than Type A material and shall have swell less than 2.5%.
label | • If parameters are met, rip and re-compact to a depth of 150mm.
label | • If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | ○ Attach: Laboratory testing Verification
text | Type A fill Lot Number:
label | Method - Verify - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.2 - Acceptance of Rock Subgrade (where applicable)
label | Reference - Section 204.06 (f)
label | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | Method - Site Inspection/Document Review
label | Frequency - Prior Construction of the regulating layer
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.3 - Unsuitable Material
label | Reference - Section 204.07 (d)
label | Acceptance Criteria - Where unsuitable material is encountered, proposed in-situ treatment or extent of excavation must be submitted to the Superintendent for review.
label | Method - Visual Inspection
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.4 - Groundwater
label | Reference - Section 204.06 (h)
label | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Method - Visual Inspection
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.5 - Fill Construction
label | Reference - IFC Drawings
label | ○ Section 204.10 (b)
label | ○ Section 204.11 (b)
label | Acceptance Criteria - No Fill to be commenced on prepared areas until area has been reviewed by the Superintendent.
label | ○ As per the notes in the IFC drawings, excavation is required until natural clay is exposed with a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement.
label | ○ No Fill placed against or within 3m of a structure until the foundation for fill has been reviewed by the Superintendent.
label | Method - Site Inspection
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.6 - Proof Roll
label | Reference - Section 173
label | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.7 - Compaction Testing
label | Reference - Table 204.131 IFC Drawings
label | Acceptance Criteria - As per IFC Drawings Notes:
label | 7. SCALE A MAY BE ASSUMED FOR THE PURPOSES OF ALL MATERIAL TESTING EXCEPT WHERE APPROVED BY THE DESIGNER
label | ○ Attach: Compaction Test Result:
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Test Records, Lot Register
checkpoint-status | 5.8 - Post Compaction Material Property Testing
label | Reference - Table 204,041
label | ○ Table 204.141
label | ○ Section 204.14 a) or b)
label | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | • CBR ≥ 8% and Swell ≤ 1%
label | • Max Permeability = N/A
label | ○ Grading: 75.0mm 100%
label | • 37.5mm 50-100%
label | • 4.75mm 25-65%
label | • 0.425mm 10-25%
label | • 0.075mm <20%
label | • Max. PI x%Passing 0.425mm = 1000 , PI = <25
label | ○ Scale A:
label | • CBR & Swell
label | Initial - 1 Lot Test to determine Assigned CBR and swell
label | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | • Max Permeability
label | Initial - 1 test per 2 lots
label | Reduced - 1 test per 4 lots
label | • Grading:
label | Initial - 1 test for each lot tested for compaction
label | Reduced - 1 test for every second lot tested for compaction
label | • Max. PI x%Passing 0.425mm & PI
label | Initial - 1 test per 2 lots
label | Reduced - 1 test per 4 lots
label | ○ Scale B:
label | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | • Attach: Post compaction test results:
label | Method - Review Document
label | Frequency - Refer to Section 204
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Sign ITP, Attach Material Property Test Report
checkpoint-group | 6. Post-construction Activities
checkpoint-status | 6.1 - Survey Conformance
label | Reference - VicRoads 204.03 (f,g,h) Section 173.05
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances (Scale A):
label | • Range x = +5, -15mm
label | • Max S = 12 mm
label | • 80 measurements per lot
label | ○ Level tolerances (Scale B):
label | • Range x = +5, -25mm
label | • Max S = 15 mm
label | • 40 measurements per lot
label | ○ Level tolerances (Scale C):
label | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | Method - Review Document
label | Frequency - Each lot
label | Category - SP
label | Responsibility - SE/Surveyor
label | Verifying Documents - Sign ITP, Attach Survey Report
checkpoint-status | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint-status | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checklist-sectioned | ITP-023-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS | itp |  |  |  | Yes | ITP-023-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS | 5135b347-e346-4d44-9786-99f7d9d757f4
checkpoint-group | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS
label | ITP Description: BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 28/02/2023
label | ITP created by: Jason Lee
label | ITP approved for use by: Jon De Castro
checkpoint-status | 1.1 - Non Dependent
label | Reference - IFC Drawings
checkpoint-status | 1.2 - Non Dependent
label | Reference - VicRoads Section 173
checkpoint-status | 1.3 - Non Dependent
label | Reference - VicRoads Section 204
checkpoint-status | 1.4 - Non Dependent
label | Reference - VicRoads Section 176
checkpoint-group | 2. Preliminaries-Materials
checkpoint-status | 2.1 - Material Conformance
label | Reference - Section 204.04 (b) Table 204.041
label | ○ IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848)
label | Acceptance Criteria - REPLACEMENT MATERIAL (Type A) TO MEET THE REQUIREMENTS IN TABLE Note 1 of IFC Drawing MRP-089-C-ACD-DRG-30-BFD-CBR-2848, AND OTHERWISE CONFORMING TO TYPE A FILL REQUIREMENTS IN ACCORDANCE WITH VICROADS STANDARD SPECIFICATION SECTION 204 and Table 204.041
label | ○ Table Note 1:
label | • Assigned CBR ≥ 8%
label | • Swell ≤ 1%
label | ○ Grading:
label | • 75.0mm 100%
label | • 37.5mm 50-100%
label | • 4.75mm 25-65%
label | • 0.425mm 10-25%
label | • 0.075mm <20%
label | ○ Reference: Material approval in Teambinder
label | Method - Document Review
label | Frequency - Once, for each material type
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 3. Preliminaries-Documentations
checkpoint-status | 3.1 - Pre-Commencement of Fill Works
label | Reference - Section 204.10 (b)
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | ○ Reference: Subgrade Preparation Lot Number:
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 4. Pre-construction / Pre-installation Activities
checkpoint-status | 4.1 - Survey Set Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | Method - Visual Inspection
label | Frequency - Each lot prior to commencement
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - This ITP
checkpoint-status | 4.2 - Flora and Fauna
label | Reference - Section 176.I1 IFC Drawings
label | Acceptance Criteria - Prior to removing any vegetation, an on site inspection with the Superintendent and other relevant authorities to confirm, identify and mark trees, vegetation to be removed. Any removal shall be consistent with the IFC drawings and any relevant permits.
label | Method - Visual Inspection
label | Frequency - Each lot prior to commencement
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - This ITP
checkpoint-group | 5. Type A Fill Activities
checkpoint-status | 5.1 - Placing of Fill
label | Reference - Section 204.10 (d)
label | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | Method - Visual Inspection
label | Frequency - Each Lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
checkpoint-status | 5.2 - Fill at Structures
label | Reference - Section 204.11 (b)
label | Acceptance Criteria - No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent
label | ○ In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
label | Method - Site Inspection
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
checkpoint-status | 5.3 - Test Roll
label | Reference - Section 173.03, Section 204.12
label | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | ○ Superintendent to be present during all test rolling
label | ○ Attach: Test/Proof Roll Checklist
label | Method - Visual Inspection
label | Frequency - Each Lot/Layer
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.4 - Compaction Testing
label | Reference - Table 204.131
label | ○ Section 204.14 (c)
label | ○ Table 204.142
label | Acceptance Criteria - Testing as per 204.13. Ensure testing is tracked and reports available.
label | ○ Standard Compactive Effort
label | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | ○ Compaction and Moisture content
label | • Scale A: Characteristic Density Ratio 99%.
label | • Scale B: Characteristic Density Ratio 98%.
label | • Scale C: Mean Value of Density Ratio: 100%
label | ○ Lot size - the leser of one day's production or 4000sqm
label | ○ ATTACH: COMPACTION TEST RESULTS
label | Method - Review Document
label | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work, subject to Superintendent satisfaction
label | Category - HP*
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
checkpoint-status | 5.5 - Preparation of final surface
label | Reference - Section 204.15
label | ○ Section 204.03 (g)
label | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | Method - Measure
label | Frequency - Top layer
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
checkpoint-status | 5.6 - Post Compaction Material Property Testing
label | Reference - Table 204,041
label | ○ Table 204.141
label | ○ Section 204.14 (a) or b)
label | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | • CBR ≥ 8% and Swell ≤ 1%
label | • Max Permeability = N/A
label | • Grading: 75.0mm 100%
label | • 4.75mm 25-65%
label | • 0.075mm <20%
label | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ○ Scale A:
label | ○ CBR & Swell
label | • Initial - 1 Lot Test to determine Assigned CBR and swell
label | • Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | ○ Max Permeability
label | • Initial - 1 test per 2 lots
label | • Reduced - 1 test per 4 lots
label | ○ Grading:
label | • Initial - 1 test for each lot tested for compaction
label | • Reduced - 1 test for every second lot tested for compaction
label | • Max. PI x%Passing 0.425mm & PI
label | • Initial - 1 test per 2 lots
label | • Reduced - 1 test per 4 lots
label | ○ Scale B:
label | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | ○ Attach: Post compaction test results:
label | Method - Review Document
label | Frequency - Refer to Section 204
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
checkpoint-group | 6. Post-construction Activities
checkpoint-status | 6.1 - Survey Conformance - Asbuilt
label | Reference - VicRoads Section 204.03 (f), (g) and (h)
label | ○ Table 204.031
label | ○ Section 173.05
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173. The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
label | ○ Level tolerances Scale A:
label | • Range x = +5, -15mm
label | • Max S = 12 mm
label | • 80 measurements per lot
label | ○ Level tolerances Scale B:
label | • Range x = +5, -25mm
label | • Max S = 15 mm
label | • 40 measurements per lot
label | ○ Level tolerances Scale C:
label | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | ○ Attach: As-built conformance report/data
label | Method - Document Review
label | Frequency - Top of Type A
label | Category - HP*
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint-status | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint-status | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP