## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-035-STR-Brunt-CFA Piling | itp |  |  |  | Yes | ITP-035-STR-Brunt-CFA Piling
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-035-STR-Brunt-CFA Piling
label | ITP Description: CFA Piling
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 5/05/2023
label | ITP created by: Yasna Naicker
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 607 March 2015
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 610 June 2019
checkpoint | 1.3 - Non Dependent
label | Reference - VicRoads Section 611 November 2018
checkpoint | 1.4 - Non Dependent
label | Reference - AS2159-2009
checkpoint | 1.5 - Non Dependent
label | Reference - AS3810.1-2015
checkpoint | 1.6 - Non Dependent
label | Reference - AS5100.3-2017
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Concrete Mix
note | Reference - 610.07, Table 610.071
note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - ACRS Certification (for Reinforcement)
note | Reference - 611.05 (a)
note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Once for each supplier, 14 days of award of contract
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bar Chairs/Aspros Certification
note | Reference - 610.26 (a)
note | Acceptance Criteria - Wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads.
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Working Platform certification
note | Reference - Piling platform design
note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement.
note | ATTACH: Piiling Platform Certificate
note | Method - Document Review
note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
note | Category - HP
note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Concrete CFA Pile Design
note | Reference - 607.01, IFC Drawings
note | Acceptance Criteria - Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
textbox | Enter: Teambinder Approval number
note | Method - Document Review
note | Frequency - Where applicable, once, 4 weeks prior to the commencement of piling
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Piling Operations Work Procedure
note | Reference - 606.03 (a)
note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | Method - Document Review
note | Frequency - Once, 4 weeks prior to the commencement of piling
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Casting Under Water Procedure
note | Reference - 607.04
note | Acceptance Criteria - Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
note | Method - Document Review
note | Frequency - Where applicable, once, prior to placement of concrete
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Dynamic Pile Testing Procedure
note | Reference - 607.07
note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | Note: Attach Superintendent Dispensation/Approval if not undertaking this test.
note | Method - Document Review
note | Frequency - Once, prior to testing
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Pre-qualified Pile Testing Consultant
note | Reference - 607.07
note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
note | Details of the consultant to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | Method - Document Review
note | Frequency - Once, 2 weeks prior to testing
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Reinforcement Welding Specifications & Qualifications
note | Reference - 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
note | Method - Document Review
note | Frequency - Where applicable, once, prior to welding
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - IFC Drawings
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
note | Method - Document Review
note | Frequency - Prior to starting Works and at regular intervals
note | Category - HP*
note | Responsibility - All
note | Verifying Documents - This ITP Signed Off
checkpoint | 4.2 - Survey Set-out / Set-out of Piles
note | Reference - IFC Drawings 607.06 (a)
note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
note | • Ensure Pile Set-out is correct and working area is clear.
note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
note | Method - Measure, Visual
note | Frequency - Each pile
note | Category - IP
note | Responsibility - Surveyor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 4.3 - Protection of Adjacent Piles
note | Reference - 607.05
note | Acceptance Criteria - Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
note | • Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 MPa.
note | Attach: concrete compressive strength test results, and Lot maps to show pile strength, locations and sequence of piling works to ensure pile protection requirements are met in accordance with VR 607.05
note | Method - Measure, Visual
note | Frequency - Each pile
note | Category - HP*
note | Responsibility - SPE/PE
note | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Reinforcement - Inspection
note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
note | • Projecting reinforcement is the correct length and location.
note | • Splice lengths achieve the minimum length and are in contact for this length.
note | • The reinforcement surface condition is free from dirt, debris and damage.
note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
note | • The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
note | Attach: Prepour Inspection Checklist
note | Attach: Steel delivery dockets, checked if correct to steel / cage design, fabrication checked as acceptable, cage/splice lengths matches design.
note | Method - Measure, Visual, Document Review
note | Frequency - Each pile
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.2 - Reinforcement - Electrical Continuity
note | Reference - IFC Drawings 610.29 (d), 610.43
note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage, and Prepour Inspection Checklist.
note | Method - Measure, Visual
note | Frequency - Where applicable, each pile
note | Category - IP
note | Responsibility - Earthing Engineer, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.3 - Augering Operations
note | Reference - IFC Drawings 607.04
note | Acceptance Criteria - Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
note | • The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
note | • Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
note | Method - Measure, Visual
note | Frequency - Each pile
note | Category - IP
note | Responsibility - Surveyor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.4 - Inspection of Excavated Material
note | Reference - 607.04
note | Acceptance Criteria - Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
note | Attach: Geotechnical Field Sheet or Report
note | Method - Measure, Visual
note | Frequency - Each pile
note | Category - HP
note | Responsibility - Geotechnical Engineer
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Increase in Depth Beyond Design
note | Reference - 607.04 (a - d), Piling Operations Work Procedure
note | Acceptance Criteria - Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
note | • A full account of the changes shall be submitted for approval to the Nominated Authority:
note | Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
note | Method - Measure, Document Review
note | Frequency - Where applicable
note | Category - HP
note | Responsibility - Geotechnical Engineer
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Weather Conditions & Evaporation Limits
note | Reference - Hot and/or Cold Weather Concreting Procedure, 610.17, 610.17 (a) & (e), Table 610.171
note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
note | Record: Required information on the Concrete Pour Record.
note | Method - Measure, Visual
note | Frequency - Each pile
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.7 - Concrete Testing - Sampling Frequency
note | Reference - Site Sampling & Testing Procedure 610.16 (b), Table 610.161
note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
note | • 0m³ to 10m³ = 1 sample
note | • 10m³ to 25m³ = 2 samples
note | • 25m³ to 50m³ = 3 samples
note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
note | • For each additional 50m³ and additional sample shall be taken.
note | • where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
note | Attach: Concrete Pour Record
note | Attach: Concrete Dockets
note | Method - Test
note | Frequency - Each pile
note | Category - IP
note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.8 - Concrete Testing - Spread, Passability & Viscosity
note | Reference - 610.13 (b)
note | Acceptance Criteria - Spread range = 550mm to 750mm
note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
note | • Passability = ≤10mm (aggregate height differential)
note | Attach: Concrete Pour Record
note | Attach: Concrete Dockets
note | Method - Test
note | Frequency - Each sample of Self-compacting Concrete
note | Category - IP
note | Responsibility - Concrete Tester
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.9 - Concrete Testing - Compressive Strength Cylinders
note | Reference - Site Sampling & Testing Procedure 610.16
note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample in accordance with VR 610.16.
note | Attach: Concrete Pour Record
note | Attach: Concrete Dockets
note | Method - Test
note | Frequency - Each sample
note | Category - IP
note | Responsibility - Concrete Tester
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.10 - Concrete Placement & Compaction
note | Reference - Piling Operations Work Procedure 610.18 (a) & (b), 610.18 (d) (i), 607.04
note | Acceptance Criteria - All concrete batches are traceable.
note | • The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
note | • The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
note | • Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
note | • Concrete shall not be dropped freely from a height exceeding two metres
note | Record: Required information on the Concrete Pour Record.
note | Attach: Concrete Pour Record
note | Attach: Concrete Dockets
note | Method - Visual
note | Frequency - Each load
note | Category - SP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - Foreman, SE/PE/SPE
checkpoint | 5.11 - Reinforcement - Placement
note | Reference - IFC Drawings 607.04
note | Acceptance Criteria - The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
note | Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
note | • If the cage cannot be positioned into its final level, the pile shall be rejected.
note | Method - Measure, Visual
note | Frequency - Each pile
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.12 - Cast-in Items
note | Reference - IFC Drawings
note | • 610.46 (a), Table 610.462 (November 2018)
note | • 610.47 (a), Table 610.472 (March/June 2019)
note | • AS3810.1 Table 3.3.6.2
note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
note | ii. Running dimensions of a group of the above = ±6mm
note | iii. Ducts and conduit location = ±12mm
note | iv. Diameter of ducts and conduits = ±3mm
note | Method - Measure, Visual
note | Frequency - Where applicable, each pile
note | Category - IP
note | Responsibility - Foreman, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Pile Trimming
note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 607.04
note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
note | • Any weak or damaged concrete shall be removed back to sound concrete.
note | Method - Measure, Visual
note | Frequency - Where applicable, each pile
note | Category - IP
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Compressive Strength Test Results
note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
note | Attach: Compressive Strength Test Results
note | Method - Document Review
note | Frequency - Each cylinder
note | Category - IP
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.3 - Pile Integrity Testing
note | Reference - 607.07, AS2159 Clause 8.8
note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
note | • Cross-sectional area = ≥90%
note | Note: To help ensure the Pile Integrity Testing is done properly, proper planning on site activities are to be considered, i.e. plan for PIT to be undertaken with minimal works around the area to avoid induced vibrations that may affect testing results.
note | Attach: Pile Integrity Test Report
note | Method - Document Review
note | Frequency - Each pile
note | Category - IP
note | Responsibility - Testing Consultant, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.4 - Dynamic Pile Testing
note | Reference - 607.07 (b), AS2159 Clause 8.7
note | Acceptance Criteria - Where applicable, Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
note | • Measured Ultimate capacity = ≥ values on IFC drawings
note | Attach: Dynamic Pile Test Report
note | Method - Document Review
note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
note | Category - IP
note | Responsibility - Testing Consultant, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.5 - As-built Survey
note | Reference - IFC Drawings 607.06 (a & b), AS2159 Clause 7.2.2
note | Acceptance Criteria - The following tolerances apply to piles:
note | i. Centre of pile head plan location = ±75mm
note | ii. Variance from vertical or rake = 1:50
note | iii. Irregularities in straightness = 1:100
note | iv. RL = ±25mm
note | Attach: Survey As-builts / Survey Report
note | Method - Document Review
note | Frequency - Each pile
note | Category - IP
note | Responsibility - Surveyor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.6 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP