## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-123-STR-CPD-Steel Structures Installation
ITP Description: |  | Steel Structures Installation
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2023-01-19
ITP created by: |  | Andrew Carlini
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Calder Park Drive Project
Inspection & Test Plan - Steel Structures Installation (Anti-throw Screens)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-01-19
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VR Section 610 Feburary 2020 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VR Section 630 July 2022 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VR Section 631 June 2017 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 | Non Dependent | AS4100 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.6 | Non Dependent | AS5131 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Structural Steel Components | IFC Drawings MRPA Quality Management Plan | Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. Typically this consists of but not limited to: i. Certificate of Compliance ii. Completed Fabrication ITP iii. Weld Procedure Specifications iv. Weld Procedure Qualifications v. Welder Qualifications vi. Material Certificates and traceability vii. Quality Assurance check sheets viii. Welding Consumable batch certificates ix. Coating certificate(s) x. Non-destructive Testing (NDT) Reports xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot. Enter: Teambinder Material Approval number [free text box] | Document Review | Each component | HP | Nominated Authority | Conqa HP Release
2.2 | Fasteners | Section 630.20 IFC Drawing | Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112 Enter: Teambinder Material Approval number [free text box] | Document review | Each component | HP | Nominated Authority | Conqa HP Release
2.3 | Base Plate Structural Grout or Mortar | IFC Drawings Section 610.33 | Product to be selected based on the following criteria: i. either a single component, self consolidating and dual shrinkage compensating cementitious grout ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum iii. have a flowable consistency iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of product | HP | Nominated Authority | Conqa HP Release
3 | Preliminaries - Procedures
3.1 | Handling, Transport and Erection of Structural Steel Element | Section 630.09 AS5131 | Methods of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. An installation methodology and ITP in accordance with AS 5131 shall be submitted prior to installation. As a minimum, the installation methodology shall include the following procedures below, when appropriate: (a) Lifting procedures for each component; transport to and handling on site (b) Bolt tightening procedures for snug tight bolting (c) Procedures for grouting of base plates (d) Procedures for ensuring that components are erected in the correct sequence and position. Attach: Subcontractor Installation ITP and Procedures Enter: Teambinder Approval number [free text box] | Document Review | 4 weeks prior to installation | HP | Nominated Authority | Conqa HP Release
4 | Pre-installation Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP Signed Off
4.2 | Materials Inspection Checklista | IFC Drawings Section 630 | General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
4.3 | Materials Inspection Checklist | IFC Drawings Section 630 | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Where bolted faces are sloping at 1:20 or greater, tapered washers must be used. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
4.4 | Materials Inspection Checklist | IFC Drawings Section 631 | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
4.5 | Materials Inspection Checklist | IFC Drawings Section 631 | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5 | Installation Activities
5.1 | Bearing / Mounting Surface Preparation | IFC Drawings Product TDS | Ensure the bearing surface is clean and free from any loose particles that will prevent solid seating of the parts. | Measure Visual | Where applicable, each installation location | IP | SE/PE/SPE | This ITP Signed Off
5.2 | Structural Steel Handling | Section 630.09 Section 631.14 | The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. | Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.3 | Structural Steel Erection | AS4100 AS5131 Section 630.12 | Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.4 | Fastener Tightening - Snug Tight Condition | IFC Drawings Section 630.09 Section 630.21 | Place bolts, washers and nuts as detailed on the IFC Drawings. For posts base plates, the arrangement is to be (from the base plate): - Base Plate - Washer as specified - Lock Nut as specified - Nut - Bolt protrusion (1 clear tread) | Measure Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP Signed Off
5.5 | Fastener Tightening - Snug Tight Condition | IFC Drawings Section 630 | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter. Tapered washers shall be positioned if specified. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. | Measure Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP Signed Off
5.6 | Survey Conformance | IFC Drawings AS4100 AS5131 | Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from plan position = ±6mm Departure from alignment = ±6mm Irregularities in alignment = 25mm in 30m Projection of bolt = +25mm, 5mm Location of beam = ±3mm Location of column = height/500, 10mm max. | Measure Visual | Each element | HP* | SE/PE/SPE Surveyor | This ITP Signed Off
5.7 | Base Plate Formwork Construction & Placement | IFC Drawings | Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks. | Measure Visual | Each post location | IP | SE/PE/SPE | This ITP Signed Off
5.8 | Pre-soaking Concrete Surface | Product TDS | Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS. Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower. | Visual | Each post location | IP | SE/PE/SPE | This ITP Signed Off
5.9 | Weather Conditions | Section 610.17 VR Table 610.171 | Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected. The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Record: Required information on the Grout Pour Record. | Measure Visual | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.10 | Mixing Product | Product TDS Section 610.28 | Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained. Enter: Required information on the Grout Pour Record. | Measure Visual | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.11 | Product Testing - Compressive Strength Cubes | Section 610.28 Section 610.33 | Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is to be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Enter: Required information on the Grout Pour Record. | Test | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.12 | Placement & Compaction | Product TDS | All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used. Enter: Required information on the Grout Pour Record | Visual | Each post location | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.13 | Surface Finishes & Protection of Works | IFC Drawings Section 610.17 | If shaping of the unformed surface is required, shape prior to the product fully hardening. All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. | Visual | Where applicable, each post location | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.14 | Curing | Curing Methodology 610.23 Table 610.231 | Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS. | Visual | Where applicable, each post location | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.15 | Architectural Steel Erection | AS4100 Clause 15.2.3 AS5131 Clause 11.5.7 630.12 | Place steel component into position, ensuring that it is plumb, level and square Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.16 | Architectural Steel Erection-Fasteners | IFC Drawings Section VR 630 | Place bolts, washers and nuts as detailed on the IFC Drawings. For architectural/Security screens, the arrangement is to be (from themounting post): - Post - Washer (s) as specified - insulating washer - insulating bush - Insulating washer - washer as specified - Lock nut - Nut - Bolt protrusion (1 clear tread) | Measure Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP Signed Off
5.17 | Installation of Electrical Isolation Materials | IFC Drawings | Installation of Electrical Isolation Material in locations specified on the IFC drawings (where applicable). | Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
6 | Post-installation Activities
6.1 | Inspection of Coating | IFC Drawings Section 630 | After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure. | Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
6.2 | Compressive Strength Test Results | IFC Drawings Product TDS Section 610 | 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly. 28 day compressive strength per sample comply with the design strength. Attach: Compressive Strength Test Results | Document Review | Each Sample | IP | SE/PE/SPE | This ITP Signed Off
6.3 | As-built Survey | IFC Drawings AS5131 | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from plan position = ±6mm Departure from alignment = ±6mm Irregularities in alignment = 25mm in 30m Projection of bolt = +25mm, 5mm Location of beam = ±3mm Location of column = height/500, 10mm max. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP Signed Off
6.4 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /