## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-124-STR-CPD-Precast Super T Installaton
ITP Description: |  | CPD-Precast Super T Installaton
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2024-01-19
ITP created by: |  | Andrew Carlini
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Calder Park Drive LXRP
Inspection & Test Plan - Bored Piling
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-01-19
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VR 652 June 2010 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VR 656 June 2010 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VR 610 February 2020 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | VR 620 May 2009 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Epoxy bedding | IFC Drawings | Product to be selected based on the following criteria: i. minimum compressive strength requirement as the Expoxy beeding is used to ensure the taper plate fullyengaes with the Girder. ii. Can be applied in IFC specified nominal thickness (1mm) Enter: Teambinder Material Approval number [free text box] | Document Review | When applicable | HP | Nominated Authority | ConQA Hold Point Release
2.2 | Bolts | IFC Drawings | M16 property calss 12.9 Zinc Coated countersunk socket cap screw Enter: Teambinder Material Approval number [free text box] | Document Review | When applicable | HP | Nominated Authority | ConQA Hold Point Release
3 | Preliminaries - Procedures & Documentation
3.1 | Precast Elements | IFC Drawings 610.47 (a) Table 610.473 (Feburary 2020) 620.03 | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Pre-stressing check sheet / ITP vi. Post-pour check sheet / ITP vii. Covermeter check record viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates Note: Different revisions of 610 have different clause numbers Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder Enter: Teambinder MDR Lot number [free text box] | Document Review | Each element | HP* | PE/SE/SPE | This ITP
3.2 | Elastomeric Bearings | IFC Drawings 652.02 652.03 652.04 AS5100.4 Appendix C and D | Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4. Tolerances: Dimensions in plan = +4mm, -2mm Thickness = ≤100mm = ±2mm >100mm ≤ 150mm = ±3mm > 150mm = ±4mm Testing: Each bearing tested under compression Batch tested for shear stiffness Attach: Elastomeric Bearing Test Reports Attach: Elastomeric Dimensional Records | Document Review | Each element | HP | PE/SE/SPE | This ITP
3.3 | Tapper plates | VR 620.05 | Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm. Enter: Teambinder MDR Lot number [free text box] | Document Review | Each Plate | IP | SE/PE | This ITP
4 | Pre-construction Activities
4.1 | Bearing Plates-Check | IFC Drawing | Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders. Ensure the plate and plate orientation are correct | Visual | Each Tapper plate | IP | SE/PE | This ITP
4.2 | Crosshead / Pedestal Tolerances | Survey As-builts / Survey Report | Re-check that the As-built dimensional tolerances comply with the requirements below: Reduced level ±2.5mm Variation from grade across the width of individual pedestals shall not exceed 1 in 200 Deviation from flat surface ±1mm | Document Review | Each element | IP | PE/SE/SPE | This ITP
5 | Construction Activities
5.1 | Falsework Design and Certification | 613.04 Temporary Works Design | The Falsework drawings submitted shall state all design assumptions and shall include a statement of the loads and any dimensional changes due to loading in all members of the falsework. The drawings shall be fully detailed including all member sizes and materials, dimensions, levels, erection procedures and other relevant details including bracing, connections and foundations, to ensure that erection and inspection of the falsework can be undertaken without reference to any other documentation. Attach: Temporary Works Design | Document Review, Visual, Measure | Each element | HP | Temporary Works Designer, Proof Engineer | This ITP
5.2 | Flasework Certification - Falsework Inspection | 613.04 Temporary Works Design | The application of any permanent load shall not proceed until the signed Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed and accepted by the Nominated Party. Attach: Temporary Works Permit to Construct, Apply Load and Remove | Document Review, Visual, Measure | Each element | HP | Temporary Works Designer, Proof Engineer | This ITP
5.3 | Precast Handling | 620.07 Crane Lift Study | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. | Visual | Each element | IP | SE/PE/SPE | This ITP
5.4 | Elastomeric Bearing Placement | IFC Drawings VR 656.05 | Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances. Tolerances: Plan position: ±2mm in any direction Level: ±2mm Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report | Measure Visual | Where applicable, each bearing location | IP | Surveyor SE/PE/SPE | This ITP
5.5 | Precast Placement | IFC Drawings 610.27 | Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings. The nominal gap between elements is as per the IFC Drawings. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.6 | Precast Traceability | 620.09 | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report | Visual | Each element | IP | SE/PE/SPE | This ITP
6 | Post-construction Activities
6.1 | As-built Survey | IFC Drawings 610.47 (a) Table 610.472 (Feburary 2020) | Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
6.4 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /