## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-121-STR-CPD-Grout Pedestals & Bearings | itp |  |  |  |  | ITP-121-STR-CPD-Grout Pedestals & Bearings Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-STR-CPD-Grout Pedestals & Bearings
label | ITP Description: CPD-Grout Pedestals & Bearings
label | ITP Number: 121
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 19/01/2024
label | ITP created by: Andrew Carlini
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 610 Feb 2020
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Product Selection
label | Reference - IFC Drawings 610.28, 610.33
label | Acceptance Criteria - Product to be selected based on the following criteria:
label | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | ii. have the required strength at 28 days as noted on the IFC drawings.
label | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
label | Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of product
label | Category - IP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.2 - Curing Compound
label | Reference - 610.23 (d)
label | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | Note: This may be the same product used for the concrete curing
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of product
label | Category - IP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Curing Methodology (for Concrete, Grout and Mortar)
label | Reference - 610.23 (a)
label | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | Note: This may be the same document used for the concrete curing.
textbox | Enter: Teambinder Correspondence Approval number
label | Method - Document Review
label | Frequency - Once, 4 weeks prior to placement of product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Survey Set-out
label | Reference - IFC Drawings 610.46 (a), Table 610.462 (Nov 2018), 610.47 (a) Table 610.472 (March/June 2019)
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
label | Note: Different revisions of 610 have different clause numbers
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Construction Joint
label | Reference - IFC Drawings 610.20 Fosroc Renderoc BB TDS
label | Acceptance Criteria - Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment.
label | ○ Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Construction Activities
checkpoint | 5.1 - Formwork Construction & Placement
label | Reference - IFC Drawings
label | Acceptance Criteria - Dimensions in plan as per drawings (typically +50mm all around).
label | ○ Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | ○ Any cast in componentry (ferrules, conduit etc.) secure.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Pre-pour Inspection
label | Reference - IFC Drawings 610.18
label | Acceptance Criteria - Formwork location and RLs comply.
label | ○ Any reinforcement has the required cover.
label | ○ Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Weather Conditions
label | Reference - 610.17 610.17 (a) & (e) Table 610.171
label | Acceptance Criteria - All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | Record: Required information on the Grout Pour Record.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Mixing Product
label | Reference - Product TDS 610.28
label | Acceptance Criteria - Size of mixer should match the application.
label | ○ Only whole bags to be mixed with potable water.
label | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | ○ Product poured into the mixer slowly.
label | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
textbox | Enter: Required information on the Grout Pour Record.
label | Method - Measure, Visual
label | Frequency - Each batch
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Product Testing - Compressive Strength Cubes
label | Reference - 610.28, 610.33
label | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | ○ Testing is be in accordance with the following frequencies:
label | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
textbox | Enter: Required information on the Grout Pour Record.
label | Method - Test
label | Frequency - Each element
label | Category - IP
label | Responsibility - Tester, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Placement & Compaction
label | Reference - Product TDS
label | Acceptance Criteria - All batches are traceable.
label | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | ○ Product should flow to all areas and self consolidate.
label | ○ Product that stiffens or is showing signs of stiffening shall not be used.
textbox | Enter: Required information on the Grout Pour Record
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.7 - Surface Finishes
label | Reference - 610.28
label | Acceptance Criteria - Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.8 - Curing
label | Reference - Curing Methodology 610.23 Table 610.231
label | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Compressive Strength Test Results
label | Reference - IFC Drawings, Product TDS
label | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength per sample comply with the design strength.
label | Attach: Compressive Strength Test Results
label | Method - Document Review
label | Frequency - Each cube
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.2 - Surface Inspection - Cracks
label | Reference - 610.24
label | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
label | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | Method - Visual, Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.3 - Surface Inspection - Surface Finish
label | Reference - IFC Drawings 610.31 (a) - (n), 610.32
label | Acceptance Criteria - Comply with the IFC drawings and specifications.
label | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.4 - Measurement of Concrete Cover
label | Reference - 610.34
label | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | ○ Minimum 10 no. measurements recorded in each area.
label | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | Attach: Covermeter Check Record
label | Method - Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.5 - As-built Survey
label | Reference - IFC Drawings 610.47 (a), Table 610.472
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
label | ○ Reduced level ±2.5mm
label | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | ○ Deviation from flat surface ±1mm
label | Note: Different revisions of 610 have different clause numbers
label | Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.6 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP