## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-124-STR-CPD-Precast Super T Installation | itp |  |  |  |  | ITP-124-STR-CPD-Precast Super T Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-124-STR-CPD-Precast Super T Installaton
label | ITP Description: CPD-Precast Super T Installaton
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 19/01/2024
label | ITP created by: Andrew Carlini
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1.1 - Non Dependent
label | Reference - VR 652 June 2010
checkpoint | 1.2 - Non Dependent
label | Reference - VR 656 June 2010
checkpoint | 1.3 - Non Dependent
label | Reference - VR 610 February 2020
checkpoint | 1.4 - Non Dependent
label | Reference - VR 620 May 2009
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Epoxy bedding
label | Reference - IFC Drawings
label | Acceptance Criteria - Product to be selected based on the following criteria:
label | i. minimum compressive strength requirement as the Expoxy beeding is used to ensure the taper plate fullyengaes with the Girder.
label | ii. Can be applied in IFC specified nominal thickness (1mm)
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Bolts
label | Reference - IFC Drawings
label | Acceptance Criteria - M16 property calss 12.9 Zinc Coated countersunk socket cap screw
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Precast Elements
label | Reference - IFC Drawings 610.47 (a) Table 610.473 (Feburary 2020), 620.03
label | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Pre-stressing check sheet / ITP
label | vi. Post-pour check sheet / ITP
label | vii. Covermeter check record
label | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
label | Note: Different revisions of 610 have different clause numbers
label | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
textbox | Enter: Teambinder MDR Lot number
label | Method - Document Review
label | Frequency - Each element
label | Category - HP*
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Elastomeric Bearings
label | Reference - IFC Drawings 652.02, 652.03, 652.04 AS5100.4 Appendix C and D
label | Acceptance Criteria - Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
label | Tolerances:
label | ○ Dimensions in plan = +4mm, -2mm
label | Thickness =
label | ○ ≤100mm = ±2mm
label | ○ >100mm ≤ 150mm = ±3mm
label | ○ > 150mm = ±4mm
label | Testing:
label | ○ Each bearing tested under compression
label | ○ Batch tested for shear stiffness
label | Attach: Elastomeric Bearing Test Reports
label | Attach: Elastomeric Dimensional Records
label | Method - Document Review
label | Frequency - Each element
label | Category - HP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Tapper plates
label | Reference - VR 620.05
label | Acceptance Criteria - Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm.
textbox | Enter: Teambinder MDR Lot number
label | Method - Document Review
label | Frequency - Each Plate
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Pre-installation Activities
checkpoint | 4.1 - Bearing Plates-Check
label | Reference - IFC Drawing
label | Acceptance Criteria - Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders.
label | ○ Ensure the plate and plate orientation are correct
label | Method - Visual
label | Frequency - Each Tapper plate
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Crosshead / Pedestal Tolerances
label | Reference - Survey As-builts / Survey Report
label | Acceptance Criteria - Re-check that the As-built dimensional tolerances comply with the requirements below:
label | ○ Reduced level ±2.5mm
label | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | ○ Deviation from flat surface ±1mm
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Construction Activities
checkpoint | 5.1 - Falsework Design and Certification
label | Reference - 613.04 Temporary Works Design
label | Acceptance Criteria - The Falsework drawings submitted shall state all design assumptions and shall include a statement of the loads and any dimensional changes due to loading in all members of the falsework. The drawings shall be fully detailed including all member sizes and materials, dimensions, levels, erection procedures and other relevant details including bracing, connections and foundations, to ensure that erection and inspection of the falsework can be undertaken without reference to any other documentation.
label | Attach: Temporary Works Design
label | Method - Document Review, Visual, Measure
label | Frequency - Each element
label | Category - HP
label | Responsibility - Temporary Works Designer, Proof Engineer
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Flasework Certification - Falsework Inspection
label | Reference - 613.04 Temporary Works Design
label | Acceptance Criteria - The application of any permanent load shall not proceed until the signed Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed and accepted by the Nominated Party.
label | Attach: Temporary Works Permit to Construct, Apply Load and Remove
label | Method - Document Review, Visual, Measure
label | Frequency - Each element
label | Category - HP
label | Responsibility - Temporary Works Designer, Proof Engineer
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Precast Handling
label | Reference - 620.07 Crane Lift Study
label | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Elastomeric Bearing Placement
label | Reference - IFC Drawings VR 656.05
label | Acceptance Criteria - Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
label | Tolerances:
label | ○ Plan position: ±2mm in any direction
label | ○ Level: ±2mm
label | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
label | Method - Measure, Visual
label | Frequency - Where applicable, each bearing location
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Precast Placement
label | Reference - IFC Drawings 610.27
label | Acceptance Criteria - Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | ○ The nominal gap between elements is as per the IFC Drawings.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Precast Traceability
label | Reference - 620.09
label | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-installation Activities
checkpoint | 6.1 - As-built Survey
label | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feburary 2020)
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
label | Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP