## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | 101C-SDC-TMP-CON-ITP-008 - 3 - Suspended Concrete Slab |  |  |  |  | Yes | 101C-SDC-TMP-CON-ITP-008 - 3 - Suspended Concrete Slab | 1639df78-2a9c-465d-9c59-469669b9f384
checkpoint-group |  |  | section | Prior to Formwork Deck Handover
checkpoint-status |  |  | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
text | 71577392-12c1-515b-a87b-92b6737e8527 |  | textbox | Architectural Drawings
text | 35391470-e1ca-5251-ae7d-50a6f778b833 |  | textbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Concrete Mix Design
text | aa0b26bf-fcf3-566e-823c-bba049b0a821 |  | textbox | Confirm Mix Design
checkpoint-status |  |  | checkpoint | Set-out - Surveyor set out slab grids to allow formwork construction
checkpoint-status |  |  | checkpoint | Survey & Set-out of formwork correct. Check correct heights for formwork soffit, Top of Concrete (TOC) and falls
label | 7e92b3f4-2de1-5ce1-87ec-7db3a674d241 |  | note | Attach Surveyor Formwork As-Built to ITP
checkpoint-status |  |  | checkpoint | Site Instructions - Copies of design changes, emails and site advices and the like to be attached.
checkpoint-status |  |  | checkpoint | Bondek (where applicable) - Back propping installed for pre pour and deflection & gaps sealed to prevent dripping
checkpoint-status |  |  | checkpoint | Structural Steel Sign off from Steel installer and Structural Engineer (where applicable for bondek slabs)
checkpoint-status |  |  | checkpoint | Formwork Sign-off - Area cleaned of all excess formwork, sawdust, reo and debris prior to pour. Safe Access to deck available.materials before handover deck
label | 41e7a28f-8521-5b18-a4e6-d67e7a5df259 |  | note | Attach formworkers ITP (referencing all hobs, steps, cast-ins, HDB's, bearing strips, polystyrene, fillets, etc… installed correctly)
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Structural Compliance - Engineers approval for concrete placement required with list of defects to be completed
label | 9e61c242-2c12-584a-ab33-a3a588135238 |  | note | Attach structural engineers inspection report and evidence of close-out
checkpoint-status |  |  | checkpoint | Formwork Engineers Sign-off - Attach Sign-off
checkpoint-status |  |  | checkpoint | Post Tensioning - Check Subcontractor ITP complete, and attach to this ITP.
checkpoint-status |  |  | checkpoint | Screen Needle Cast-in's - Inspect all screen needles are installed in accordance with relevant shop drawings
label | 528ef2fc-3f99-53f3-a276-ddcef0e4da30 |  | note | Attach sign-off from Formworker
checkpoint-status |  |  | checkpoint | Curtain Wall Bracket Cast-in's - Inspect all Curtain wall brackets/rebates are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
label | 48245463-11d7-5676-8374-8cb3d0502001 |  | note | Attach Curtain Wall subcontractors sign-off & ITP from formworker
checkpoint-status |  |  | checkpoint | Crane/Hoist Bracket Cast-in's - Inspect all hoist and crane brackets are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
label | 4c3b3f45-78b0-55bc-9628-c84b2cacceae |  | note | Hoist and Crane contractor to inspect and sign-off cast-in position.
checkpoint-status |  |  | checkpoint | Temporary Penetrations - Inspect formwork penetrations in accordance with temporary works design. Surveyor to confirm locations are correct.
label | 4e806b36-cb1b-5334-8aab-68cb0e0307f4 |  | note | Temporary Penetrations may include: formwork hoist, concrete boom, etc…
checkpoint-status |  |  | checkpoint | In-Slab Services - Electrical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | In-Slab Services - Hydraulic subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | In-Slab Services - Mechanical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | In-Slab Services - Fire Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | In-Slab Services - Security Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | Formwork Cast-ins - All timber fillets, drip grooves, Rebates, and proprietary shear connectors installed as required
checkpoint-status |  |  | checkpoint | Starter Bars - Confirm all starter bars for walls and columns installed as required per structural and architectural drawings and survey pins
checkpoint-status |  |  | checkpoint | Water Stops - Confirm installation of any proprietary water stops as required (ie; at CJ’s, etc…)
checkpoint-status |  |  | checkpoint | Reinforcement Cover - Check top RLs for all reinforcement, ensuring adequate concrete cover. Confirm with Concreter. Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits.
checkpoint-status |  |  | checkpoint | Attach Reinforcement contractors ITP
checkpoint-status |  |  | checkpoint | Concrete Falls - Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary
label | 0c708f08-397b-5649-92f4-d4d6c37335ab |  | note | Cross-check the following drawings: See Hydraulic, Architectural Concrete Outlines and Structural drawings
checkpoint-status |  |  | checkpoint | Cleaning of Deck - Clean off decks and beams prior to pour and ensure all exposed off-form soffits are free of any dust, stains, and rust marks. Hose down if necessary.
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | Concrete Placement Checklist
boolean | 7913c179-94c9-519d-a948-d0a9c94253c5 |  | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
boolean | 79922c4d-a7b3-5475-9417-7a5ba8f297fa |  | tickbox | Confirm Delivery Docket References correct mix design
boolean | 3c0e5aa6-2340-5e95-b8cf-be49dd705115 |  | tickbox | Plant and equipment checklist completed on concrete pump and lines
boolean | 931fdd79-290f-5785-802c-dba7dfd82152 |  | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
label | 248d7a4c-044f-5752-bebe-bb2ab35d27b9 |  | note | 1, 4, 7, 28 & 56 day compressive test results to be issued by batch plant
checkpoint-status |  |  | checkpoint | Concrete Finish - Ensure concrete contractor is aware of required concrete surface finish.
checkpoint-status |  |  | checkpoint | Slab Curing - Check cured when bleed water stops and able to access slab without marking and also amount used complies
checkpoint-status |  |  | checkpoint | Concrete Falls - Confirm concrete has falls to drainage points in slab.
checkpoint-status |  |  | checkpoint | Attach Concrete Place Contractors ITP
checkpoint-status |  |  | checkpoint | Trade Representatives - Ensure a representative from each of the following is on site and witnessing the pour:
boolean | 274596a9-8284-55c2-a562-3a463c31a7f4 |  | tickbox | Form Worker
boolean | 6e693d5b-96b7-5efd-a753-91817e4b9749 |  | tickbox | Electrician
boolean | 4d76e6fc-1f2c-55c3-a91d-791136188cdf |  | tickbox | Plumber
boolean | a671c5d5-4c08-5660-a9d1-8999d27af5cf |  | tickbox | Post Tensioner
checkpoint-status |  |  | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry.
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan.
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are as follows:
label | 22ed6f70-72b8-5528-9059-0ffa3d38f35d |  | note | 6mm +/- from design RL
label | 74023c59-165d-53fa-bcb2-6f6223d28ae6 |  | note | 6mm +/- from 3.0m straight edges
checkpoint-status |  |  | checkpoint | Exposed Concrete Finish - Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610 (Class 1, 2 or 3)
checkpoint-status |  |  | checkpoint | Concrete Test Results - Note test results on ITP and attach:
text | a1ddf03f-e21d-552c-b850-a1e687cafdac |  | textbox | 1 Day
text | fe30e90a-5fb4-5064-a514-5f52dfe6511f |  | textbox | 4 Day
text | 8becb43c-e7d2-5896-bc57-4c3a4c1c9126 |  | textbox | 7 Day
text | f9ca7c0a-9042-5d98-bf73-7ed0fad33737 |  | textbox | 28 Day
text | d3436848-b341-5571-8ded-d3c90f10030f |  | textbox | 56 Day
checkpoint-status |  |  | checkpoint | Initial Stressing - Concrete has achieved required strength MPa (10 MPa and confirmed by Concrete contractor)
label | c63b12e5-d21d-5ebd-a6d0-4bbcbc26a6ec |  | note | Concrete Contractor must issue Concrete test results, verbal not accepted
checkpoint-status |  |  | checkpoint | Final Stressing - Concrete has achieved required strength Mpa (22 Mpa and confirmed by concrete contractor)
label | 1188e90e-ee7d-54b8-b59d-1a0cd8f0a55d |  | note | Concrete Contractor must issue Concrete test results, verbal not accepted
checkpoint-status |  |  | checkpoint | Stressing Sign-off - Before stripping can commence final stress complete, Ducts grouted and PT supervisor issues verification records
label | fff3426b-83cc-50f5-8e4a-d67a41db9099 |  | note | Attach Post Tension Contractors ITP
checkpoint-status |  |  | checkpoint | Extension Records Approval - Engineer approval of extension records following final stress
text | 2c04992a-3395-5768-9381-56b23470d61c |  | textbox | Record date when props were removed if not given approval by engineer
checkpoint-status |  |  | checkpoint | All non-conformances closed out and accepted by Structural Engineer and Architect.
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer
checklist-sectioned |  |  | checklist | 101C-SDC-TMP-CON-ITP-007b - 3 - Stairs FRP Works |  |  |  |  | Yes | 101C-SDC-TMP-CON-ITP-007b - 3 - Stairs FRP Works | 355d3d5f-c93a-4903-b4f9-30f8ed07dbd0
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm bottom, mid & top of stair RL's on Architectural Concrete Outlines.
text | e8432eb9-d3bf-54c0-ab3c-5666ea19e365 |  | textbox | Bottom Landing RL
text | 522ca3ff-d379-52e2-a9ab-3283d628ca54 |  | textbox | Mid Landing RL
text | 1f24f4ff-b86c-5894-b788-58006e9dca4d |  | textbox | Top Landing RL
checkpoint-status |  |  | checkpoint | Confirm Re-boxes/cast-in bars are installed to correct heights at landings, based on nominated design RL's.
checkpoint-status |  |  | checkpoint | Confirm any starter bars on landings for dividing walls, etc… are installed as per Structural Drawings
checkpoint-status |  |  | checkpoint | Check for reinforcement cover as per Structural Drawings.
label | efda221b-4598-5123-8e20-9290008eb0dc |  | note | Cover requirement generally 30mm
checkpoint-status |  |  | checkpoint | Confirm all cast in elements installed (eg, stair handrails, etc…)
checkpoint-status |  |  | checkpoint | Confirm all formwork is clean and free of debris.
checkpoint-status |  |  | checkpoint | Confirm any conventional parts of stairs have been formed in accordance with the relevant shop drawings and standards.
label | 939e6cf6-de24-5941-9f7b-742819c18525 |  | note | Statutory Requirements (Dimensions in mm): Riser: Min. 115, Max. 190 Going: Min. 240, Max. 355 Ensure consistency
checkpoint-status |  |  | checkpoint | Confirm cast-in of anti-slip items if required (eg, carborundum powder, stair nosings, etc…);
checkpoint-status |  |  | checkpoint | Obtain certificate from Structural Engineer prior to concrete pour and attached completed Inspection Report.
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg. size of concrete prior to ordering.
text | cd6146d1-2ebb-56b4-9646-825e787cf64d |  | textbox | Concrete Mpa/Mix Design
checkpoint-status |  |  | checkpoint | Obtain subcontractors ITP (Steel Fixer) & attach to ITP
checkpoint-status |  |  | checkpoint | Obtain subcontractors ITP (Form Worker) & attach to ITP
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | If the stairs are being used as access to a leading deck, ensure alternative access is established prior to pouring.
checkpoint-status |  |  | checkpoint | Confirm concrete tester onsite during concrete pour, and the following tests have been requested.
label | 061bea70-3313-5d8d-aec5-01c437d7de85 |  | note | 7 Day
label | 362ef73f-a50c-537b-9a30-8b523e267b2c |  | note | 28 Day
label | cec00985-e38f-58cf-b784-74ea822c451f |  | note | Ensure concrete tester is aware of pour locations
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
boolean | 31fa7557-407d-52d8-a95f-0c8ea6e688a3 |  | tickbox | Form Worker
boolean | c3976a82-9072-5fb6-9178-4fea09025f3a |  | tickbox | Electrician
boolean | 7d8cbc69-dd58-5e21-aabf-06c1380565c3 |  | tickbox | Plumber / Fire services
checkpoint-status |  |  | checkpoint | Ensure concreters have correct finishing tools (eg, carborundum powder, etc…).
checkpoint-status |  |  | checkpoint | Ensure only rubber tipped vibrators are used to prevent formwork damage.
checkpoint-status |  |  | checkpoint | Obtain Subcontractors ITP (Concretor) & attach to this ITP
checkpoint-status |  |  | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of stairs, immediately after pour.
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces:
label | 0d39ffe8-ee98-52fa-b9f2-bc81f956f666 |  | note | 6mm +/- from design RL
label | 6ba58a59-474a-533c-8221-6387e7075c24 |  | note | 6mm +/- from 3.0m straight edges.
checkpoint-status |  |  | checkpoint | If an as-built survey is required, confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 days. Attach to ITP
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 days. Attach to ITP
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer
checklist-sectioned |  |  | checklist | Framing/Sheeting |  |  |  |  | Yes | Framing/Sheeting | 7ee86fba-b355-497a-982d-46fc7d52e5b0
checkpoint-group |  |  | section | Survey/Wall Framing
checkpoint-status |  |  | checkpoint | Confirm set-out of walls in correct locations & cross check with surveyors grids.
text | 6c528bef-34fa-54af-991e-7536fb4aee24 |  | textbox | Confirm wall set-out plan/revision used for set-out
checkpoint-status |  |  | checkpoint | Confirm that 1m benchmark has been reviewed and agreed. Ensure it is marked on most relevant permanent structure.
label | e6763fc6-305f-5f8a-9ce0-ac73604cac46 |  | note | Attach photo of 1m benchmark for reference.
checkpoint-status |  |  | checkpoint | Review wall types are installed correctly per architectural wall type details.
checkpoint-status |  |  | checkpoint | Review wet area framing to ensure square and plumb to take tiling.
checkpoint-status |  |  | checkpoint | Strengthening Requirements - Confirm all noggins, trimming blocks and struts have been appropriately installed to support the following items (Min. 12mm structural plywood). Ensure to cross check relevant drawings:
label | 90c3ce66-801a-5970-ada9-33cea8c3b373 |  | note | Appliances (Wall mounted dryers, etc…)
label | 772fbd5a-a2cf-522c-9f7c-abc9c0b7fc8a |  | note | Bathroom Accessories (Robe hooks, towel rails, shower shelves, toilet roll holders, adaptable handrails, etc…)
label | b166a7e8-bbe3-5f0a-b4bc-fcd693a2f0b8 |  | note | Bathroom Furniture (Mirror Cabinets, Vanity Basins, shower roses, etc…)
label | 830c1c25-6d0f-5b5f-bb10-ac7ebbc4b45f |  | note | Services (pendant lighting, display screens, TV areas, etc…)
checkpoint-status |  |  | checkpoint | Adaptable Apartments - Check blocking installed to cater for post adaptation layouts
checkpoint-status |  |  | checkpoint | Confirm that all framing is square at corners (check top, middle & bottom of frame junctions)
checkpoint-status |  |  | checkpoint | Confirm studs not bridging or touching hydraulic pipes, mechanical units, columns in intertenancy walls or lift shaft walls to ensure vibration is not transferred through walls
checkpoint-status |  |  | checkpoint | Deflection Requirements - Ensure gap is present (10-15mm) at top of stud inside head track
checkpoint-status |  |  | checkpoint | Joinery Openings - check gaps between framing to joinery + wall finishes will fit (5mm tolerance)
checkpoint-status |  |  | checkpoint | Stud Spacing - Spot check studwork is spaced at 600mm maximum per Architectural Specification. Check additional studwork reinforcement at openings (ie; double studwork).
label | 7887257e-2b4d-5d97-a3ea-b4aa8a92a7e8 |  | note | Staggered Studs (if required) - to be installed at 300mm centres alternating per architectural specification
checkpoint-status |  |  | checkpoint | Movement Joints - check walls are discontinued where they pass over building movement joints.
checkpoint-status |  |  | checkpoint | Services Risers - Ensure stud and trackwork is kept a minimum of 20mm away from vertical services within risers per acoustic specification
checkpoint-status |  |  | checkpoint | Engineered Designs - Spot check any engineered framing designs and attached engineers review and sign-off on system.
checkpoint-group |  |  | section | Wall Sheeting
checkpoint-status |  |  | checkpoint | Confirm acoustic/thermal insulation installed to achieve design ratings
label | c7ee05f4-1820-54c2-aafc-8fd3ec6d0a8e |  | note | Cross check product ratings against architectural insulation plans
checkpoint-status |  |  | checkpoint | Confirm there is a minimum of 45mm cavity between the residential intertenancy wall studwork per Acoustic Details/Wall type Plans
checkpoint-status |  |  | checkpoint | Confirm door frames are installed vertical and plumb and at correct height.
label | c6b6d5ce-78dc-5309-8b8a-4836446823b4 |  | note | Check metal door frames in wet areas are outside of membrane zone (ie; notched accordingly).
checkpoint-status |  |  | checkpoint | Check plasterboard sheets installed with 10-15mm gap at top and bottom to allow for deflection and fire sealant.
checkpoint-status |  |  | checkpoint | Control Joints - Ensure controls joints installed in wall runs larger than 12m in length.
checkpoint-status |  |  | checkpoint | Check correct plasterboard linings installed (type and thickness) per architectural wall types
checkpoint-status |  |  | checkpoint | Ensure sheets are staggered on multiple sheet layer walls. Stagger all sheet joints by minimum 200mm per architectural specification.
checkpoint-status |  |  | checkpoint | Confirm plasterboard lining installed to wet areas are sealed up to concrete soffit on both sides of wall where adjacent to habitable rooms.
checkpoint-status |  |  | checkpoint | Confirm all services penetrations through wet area walls adjacent to habitable rooms are sealed and caulked for acoustic performance.
label | 1e7bb1fb-b11e-516f-8ea4-09fa29e09adc |  | note | Check that mechanical flex ducts are not passing through walls - to be rigid ductwork or sleave installed over.
checkpoint-status |  |  | checkpoint | Check intertenancy walls extend to façade panels, leave 10-15mm gap and caulked with fire sealant.
holdpoint |  |  | signoff | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
checkpoint-group |  |  | section | Sheeting Ceilings
checkpoint-status |  |  | checkpoint | Confirm ceiling insulation complete where applicable
checkpoint-status |  |  | checkpoint | Confirm provisions made in ceiling framing for access panels and air grilles were required by architectural RCP
label | 82795dbf-4740-57c7-9997-b007c85022d7 |  | note | Spot check access panels installed to allow access to fire dampers and mechanical fans
checkpoint-status |  |  | checkpoint | Confirm ceiling framing bulkheads are square and level
checkpoint-status |  |  | checkpoint | Confirm furring channels do not clash with other services (eg; downlights, access panels, mechanical exhaust, sprinkler heads, etc…).
checkpoint-status |  |  | checkpoint | Control Joints - Ensure ceiling bays are not larger than 10m x 7m without a joint or wall break.
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP for the Works
checkpoint-status |  |  | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
holdpoint |  |  | signoff | Review & Sign-off by Acoustic Consultant
checkpoint-status |  |  | checkpoint | HOLD POINT - Confirm BCA consultant inspection of services penetrations through fire rated walls prior to sheeting ceilings
holdpoint |  |  | signoff | Review & Sign-off by BCA consultant
checkpoint-status |  |  | checkpoint | Final Sign-off Complete
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer
checklist-flat |  |  | checklist | SDC-TMP-CON-ITP-009 - 3 – RC Slab on Grade |  |  |  |  | Yes | SDC-TMP-CON-ITP-009 - 3 – RC Slab on Grade | 9514316c-69f4-4990-9d8f-e0a3152c40e8
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Attach Markup to confirm proposed pour zone
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Ensure detailed excavation is complete (Attach Excavation Contractor’s ITP)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm inground drainage and pit works has been completed and backfilled (Attach photos/confirmation)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm that substation earthing rods have been drilled, as AS Built red line survey (If applicable)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm min 100mm subsoil drainage has been installed as per geotechnical requirements (attach contractor’s ITP)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm Surveyor has provided set outs/ benchmarks (Attach survey)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm vapor barrier installed over subbase (Attach photos and confirm signed off by concrete place ITP)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach formwork contractor’s ITP (including setdowns, hobs, Construction/key/movement joints, ect.)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach Structural Engineers inspection report
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach Verification that structural engineer’s inspection report has been closed out to allow concrete pour (Attach Photos)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach reinforcement contractor’s ITP
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach Hydraulic ITP (inground drainage and pipework)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach Electrical ITP (Cast in conduits – if applicable)
checkpoint-status |  |  | checkpoint | During Concrete Pour: Attach Concrete place contractor’s ITP (including Ableflex)
checkpoint-status |  |  | checkpoint | After Concrete Pour: Confirm falls have been completed in concrete pour in accordance to architectural drawings
checkpoint-status |  |  | checkpoint | After Concrete Pour: Attach Concrete test results and confirm compliance with engineer requirements
checkpoint-status |  |  | checkpoint | After Concrete Pour: Confirm saw cuts installed as per engineer’s drawings
checkpoint-status |  |  | checkpoint | Signoffs: Site Engineer to signoff ITP has been completed
holdpoint |  |  | signoff | Signoff by Site Engineer
checkpoint-status |  |  | checkpoint | Signoffs: Project Engineer to review and confirm ITP has been completed
holdpoint |  |  | signoff | Signoff by Project Engineer
checklist-flat |  |  | checklist | SDC-TMP-CON-ITP-006 - 4 – Pits, Pads and Strip Footings |  |  |  |  | Yes | SDC-TMP-CON-ITP-006 - 4 – Pits, Pads and Strip Footings | aaa9ea4f-9e04-4b4c-902d-5cdffa5f8cfd
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach markup structural plan identifying footings relevant to this ITP
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm surveyor has provided setout for pad footing excavation (attach survey setout plan)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach Geotech engineer bearing certification confirming approval of substrate complying with engineer’s requirements
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm that either pre- applied membrane or Forecoin plastic has been installed to comply with electrolysis study (attach photos)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm excavation is free of debris and loose materials to walls and floor prior to handover (attach photos)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach reinforcement contractors ITP (incl AEFAC Accredited installer signoff of any drill and epoxy bars to comply with structural engineer details)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm wall starter bars have been installed in accordance with surveyor setout and architectural outline drawings.
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach signoff from CFT Column contractor inspection approval of starter bars, castins and hold down bolts
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach waterproofing contractors ITP confirm tanking waterproofing and PVC water bar has been installed(attach waterproofing ITP)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm that waterproofing consultant has inspected works and defects closed out
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach hydraulic contractor's ITP confirming completion of any cast in as per hydraulic drawings
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach formwork ITP/Signoff that all formwork to kicker has been completed (sump, hobs, edge boards etc)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach structural engineer’s inspection report
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach verification that structural engineer’s inspection report has been closed out to allow concrete pour
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm concrete place contractor's order complies with engineer's strength of concrete, waterproofing additive and testing requirements
checkpoint-status |  |  | checkpoint | Prior to Concrete Place - Attach photo of formwork setting the level for concrete place contractor
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach concrete place contractor’s ITP
checkpoint-status |  |  | checkpoint | After Concrete Pour - Confirm RL of poured footing complies with design RLs
checkpoint-status |  |  | checkpoint | After Concrete Pour - Confirm integrals falls have been completed in concrete to sump
checkpoint-status |  |  | checkpoint | After Concrete Pour - Attach concrete test results and confirm compliance with engineer requirements
checkpoint-status |  |  | checkpoint | Signoffs - Site Engineer to signoff ITP has been completed
holdpoint |  |  | signoff | Signoff by Site Engineer
checkpoint-status |  |  | checkpoint | Signoffs - Project Engineer to review and confirm ITP has been completed
holdpoint |  |  | signoff | Signoff by Project Engineer
checklist-sectioned |  |  | checklist | 01C-SDC-TMP-CON-ITP-007a - 3 - Jumpform |  |  |  |  | Yes | 01C-SDC-TMP-CON-ITP-007a - 3 - Jumpform | af2efa61-0e19-4197-9220-c65768e87a9c
checkpoint-group |  |  | section | Prior to Reinforcement
checkpoint-status |  |  | checkpoint | Confirm Jump No Seq and bottom and top RLs of proposed pour
text | fc09e239-cb41-5229-8b1b-6ae5ce6205f1 |  | textbox | Jump No Sequence
text | 75617b45-fc0d-579f-9246-d6705d97d9f2 |  | textbox | Bottom of Proposed Wall RL
text | 8179fb56-38cc-5e32-9066-d62c3cd214d9 |  | textbox | Top of Proposed Wall RL
checkpoint-status |  |  | checkpoint | Surveyor to complete survey of concrete walls below to confirm if walls need to be adjusted. Attach confirmation survey has been issued to formwork contractor via Aconex
text | acbaf781-9d79-57fa-9ed0-83bbeccd16c1 |  | textbox | Aconex Correspondence No.
checkpoint-status |  |  | checkpoint | Lift Requirements - Review formwork blockouts for lift openings and door thresholds in accordance with architectural elevations and lift shop drawings
checkpoint-status |  |  | checkpoint | Formwork Requirements - Confirm that all reboxes, couplers, shear key pockets and cast in plates to internal shutter as per structural engineer detail
checkpoint-status |  |  | checkpoint | Attach Sign Off from form worker contractor confirming all works completed and clear access for handover to steel fixers
checkpoint-group |  |  | section | Prior to Closing Shutters
checkpoint-status |  |  | checkpoint | Lift Requirements - Confirm any block out / penetrations required for lift buttons and indicators has been cast in by Form Worker
checkpoint-status |  |  | checkpoint | Confirm all outside reboxes & couplers are installed to required SSL + cover levels
checkpoint-status |  |  | checkpoint | Attach electrical contractors ITP to confirm any required conduit cast ins are completed
checkpoint-status |  |  | checkpoint | Attach reinforcement installer’s ITP
checkpoint-status |  |  | checkpoint | Reinforcement Checks (Refer Structural Engineers Drawings for Reference):
label | 3aabcaef-75b7-543f-9097-8ce3fe8da03c |  | note | Reinforcement cover sufficient
label | 5db9e275-7014-5d2c-9883-66249edf6d5d |  | note | Lap Length of bars sufficient
label | c270377a-5ff0-5bff-85ee-fcbf436be1aa |  | note | Starter bar length to next pour correct
label | 6e0fdbe0-6e0e-59e1-8ef2-ce14ae5842d5 |  | note | Lace bars installed to reboxes
checkpoint-status |  |  | checkpoint | Attach structural engineer’s inspection report
checkpoint-status |  |  | checkpoint | Attach verification that structural engineer’s inspection report has been closed out to allow concrete pour
checkpoint-status |  |  | checkpoint | Attach photos of all works completed prior to closing shutters
checkpoint-group |  |  | section | During Concrete Pouring
checkpoint-status |  |  | checkpoint | Confirm Concrete ordered is correct
text | 69fee95c-c606-5464-a090-2d97dcf397c7 |  | textbox | MPa/mix design
checkpoint-status |  |  | checkpoint | Confirm pour height with concrete Contractor prior to pouring
checkpoint-status |  |  | checkpoint | Attach form worker’s jumpform ITP
checkpoint-status |  |  | checkpoint | Attach concrete place contractor’s ITP
checkpoint-status |  |  | checkpoint | Confirm concrete tester onsite to take samples and ensure correct pour location is recorded
checkpoint-group |  |  | section | Prior to Jumping
checkpoint-status |  |  | checkpoint | Attach concrete test result to confirm min 15 MPa has been reached
checkpoint-status |  |  | checkpoint | Attach form worker’s Permit to Energise Jumpform.
label | 2ed66936-a16d-5a74-b215-f797fe5c331a |  | note | Note exclusion zone below and all penetrations to be blocked up and secure and any temporary services (hydraulic/electrical/static line) disconnected inside trailing decks
checkpoint-group |  |  | section | After Jumping
checkpoint-status |  |  | checkpoint | Form Worker to ensure that all z bar holes and jumpform pockets within the lift shaft has been patched and infilled in accordance with structural engineer drawings
checkpoint-status |  |  | checkpoint | Attach concrete test results 28d and confirm compliance with engineer requirements
checkpoint-status |  |  | checkpoint | Permit to Re-seat jumpform received (attach to ITP)
checkpoint-status |  |  | checkpoint | Surveyor to survey finished concrete walls (attach as-built to ITP)
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer
checklist-sectioned |  |  | checklist | 101C-SDC-TMP-CON-ITP-007 - 2- Concrete Columns Walls Verticals |  |  |  |  | Yes | 101C-SDC-TMP-CON-ITP-007 - 2- Concrete Columns Walls Verticals | f049abf5-edd6-416c-83b9-121dd092777f
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
text | be34bdae-f703-5862-8415-cd17d0848cba |  | textbox | Architectural Drawings
text | 98c3cdb3-0c8d-5188-bc6f-4dbea03affac |  | textbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Ensure survey of column/wall positions are completed prior to commencing formwork
label | 83678975-8dac-5a3c-9344-1bc226ae18a7 |  | note | Attach surveyors as-built records to ITP
checkpoint-status |  |  | checkpoint | Reinforcement - Check Starter bars from previous pour installed in correct position (compare against survey points)
checkpoint-status |  |  | checkpoint | Reinforcement - Check for correct bar sizes and lap lengths between starter bars (top & bottom)
checkpoint-status |  |  | checkpoint | Cast-in Services - Electrical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design. Attach Contractors ITP
checkpoint-status |  |  | checkpoint | Cast-in Services - Hydraulics subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
checkpoint-status |  |  | checkpoint | Cast-in Services - Mechanical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
checkpoint-status |  |  | checkpoint | Cast-in Services - Fire Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
checkpoint-status |  |  | checkpoint | Cast-in Services - Security Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design
checkpoint-status |  |  | checkpoint | Confirm strength and mix design of concrete ordered with subcontractor prior to pour
text | 83416d4e-588a-5834-bfc7-cca8d9297375 |  | textbox | Concrete Mix Design:
checkpoint-status |  |  | checkpoint | Structural Engineer Sign-off - Foreman and subcontractor to sign off engineer’s report to verify that all work to be rectified was checked for compliance prior to pour
label | c4b3574e-3e4d-5d2d-9f51-2682acf11262 |  | note | Attach engineers inspection report and verification of rectification items being closed out.
checkpoint-status |  |  | checkpoint | Formwork Compliance - Confirm formwork is checked to achieve Class 2 finish to concrete:
boolean | 1c7ffae4-da3d-5f41-9776-0dc689ab6e2a |  | tickbox | Formwork is clean and free of debris
boolean | 9e437d63-5f9b-56ad-849a-dc1f97c98f02 |  | tickbox | No lipping of formwork between sheets
boolean | cc5eedd9-562a-5a3c-bbf8-35089fa64818 |  | tickbox | Fillets installed at all corners
boolean | f3d9af63-113f-5fa7-a734-818ad2f60b11 |  | tickbox | Form ties are installed at even spacing
boolean | 6b22574f-5639-5df7-bb94-dd6682f5e4e7 |  | tickbox | Check for correct reo cover at shutters
boolean | c78823d8-b08f-5d92-b36a-9adb285dda2f |  | tickbox | Splayed columns are at correct degrees per Architectural/Structural drawings
checkpoint-status |  |  | checkpoint | Area cleaned of all excess formwork, sawdust at base of columns, reo, and debris prior to pour
checkpoint-status |  |  | checkpoint | Attach formworkers ITP for column and wall formworking
checkpoint-status |  |  | checkpoint | Attach Steelfixers ITP for Column and wall reinforcement
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | Concrete Placement Checklist
boolean | ef0d10f5-ca0a-5fbc-b5a2-88bcb5fc011a |  | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
boolean | 4d43f38a-5927-5625-9cee-50b55ef49554 |  | tickbox | Confirm Delivery Docket References correct mix design
boolean | 6afa1aba-7909-5a62-8e46-39ab8780b801 |  | tickbox | Plant and Equipment checklist completed on concrete pump and lines
boolean | 75c379bc-ae8f-53e8-84f9-d4849bf5d7c7 |  | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
label | 8eae3c07-4137-513b-83dc-1b73460911d1 |  | note | 7, 28 & 56 day compressive test results to be issued by batch plant
label | 0ba68840-1f2c-5ee0-8575-28464266daca |  | note | Batch plant to issue monthly dry shrinkage test results
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
boolean | cfa21684-6574-52b3-ac38-ddba1bcb52d1 |  | tickbox | Form Worker
boolean | f0f49649-9514-5fe7-8657-bb359e1b359f |  | tickbox | Electrician
boolean | aab7c095-1bf7-539c-8343-065ddf77ee46 |  | tickbox | Plumber
checkpoint-status |  |  | checkpoint | Ensure only rubber tipped vibrators are used and care is taken not to damage shutters
checkpoint-status |  |  | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of walls, immediately after pour for off form finishes.
checkpoint-status |  |  | checkpoint | Attach Concrete Place contractors ITP
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Curing - Approved curing compound to be applied to columns following removal of formwork as required.
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces:
label | bef63090-e05d-52a2-9126-1efb628a4c99 |  | note | 5mm+/- in correct position
label | 97bd183b-4da4-5ec2-82e7-5e9c5d97eab4 |  | note | 5mm +/- from 3.0m straight edges.
label | 0e3449f9-ff48-5dad-aaa5-565606e686e0 |  | note | 5mm +/- from plumb.
checkpoint-status |  |  | checkpoint | As-Built Survey - Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As Built Survey Plan
checkpoint-status |  |  | checkpoint | Concrete Test Results - Obtain all concrete test results. Confirm strength achieved after:
text | cd3ad7e9-18da-54e4-a3e6-dad00be42a1c |  | textbox | 7 Days MPa
text | 27a71ddb-793f-5e8c-a11c-83069ad213c8 |  | textbox | 28 Days MPa
text | 10ab75ae-4cdd-5660-a6b6-1d88aadbe99b |  | textbox | 56 Days MPa
checkpoint-status |  |  | checkpoint | All non-conformances closed out
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer