## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Equipment Delivery Verification |  |  |  |  | Yes | Equipment Delivery Verification | 312e7cc2-5bbe-49d5-b506-e4cbc899f19e
checkpoint-status |  |  | checkpoint | Sighted by Scentre Group
checklist-sectioned |  |  | checklist | Framing/Sheeting |  |  |  |  | Yes | Framing/Sheeting | 37102f3d-3041-437b-a7a1-a758bb233171
checkpoint-group |  |  | section | Survey/Wall Framing
checkpoint-status |  |  | checkpoint | Confirm set-out of walls in correct locations & cross check with surveyors grids.
text | bf593cf7-e545-5d09-9b0b-ec0e6373d66f |  | textbox | Confirm wall set-out plan/revision used for set-out
checkpoint-status |  |  | checkpoint | Confirm that 1m benchmark has been reviewed and agreed. Ensure it is marked on most relevant permanent structure.
label | 172e069e-c65b-54dc-b5a7-1c15435da685 |  | note | Attach photo of 1m benchmark for reference.
checkpoint-status |  |  | checkpoint | Review wall types are installed correctly per architectural wall type details.
checkpoint-status |  |  | checkpoint | Review wet area framing to ensure square and plumb to take tiling.
checkpoint-status |  |  | checkpoint | Strengthening Requirements - Confirm all noggins, trimming blocks and struts have been appropriately installed to support the following items (Min. 12mm structural plywood). Ensure to cross check relevant drawings:
label | 2c5a047b-960f-5c5f-aa3a-0cb88c8cc8cb |  | note | Appliances (Wall mounted dryers, etc…)
label | c1b1f60c-6dc9-5f9a-8745-995ef2938d45 |  | note | Bathroom Accessories (Robe hooks, towel rails, shower shelves, toilet roll holders, adaptable handrails, etc…)
label | 925b3429-826e-5c1e-b9d5-42f3bd35a048 |  | note | Bathroom Furniture (Mirror Cabinets, Vanity Basins, shower roses, etc…)
label | 3d0db52b-01eb-5cce-8cbf-3a3679aa89de |  | note | Services (pendant lighting, display screens, TV areas, etc…)
checkpoint-status |  |  | checkpoint | Adaptable Apartments - Check blocking installed to cater for post adaptation layouts
checkpoint-status |  |  | checkpoint | Confirm that all framing is square at corners (check top, middle & bottom of frame junctions)
checkpoint-status |  |  | checkpoint | Confirm studs not bridging or touching hydraulic pipes, mechanical units, columns in intertenancy walls or lift shaft walls to ensure vibration is not transferred through walls
checkpoint-status |  |  | checkpoint | Deflection Requirements - Ensure gap is present (10-15mm) at top of stud inside head track
checkpoint-status |  |  | checkpoint | Joinery Openings - check gaps between framing to joinery + wall finishes will fit (5mm tolerance)
checkpoint-status |  |  | checkpoint | Stud Spacing - Spot check studwork is spaced at 600mm maximum per Architectural Specification. Check additional studwork reinforcement at openings (ie; double studwork).
label | 39866e90-f81a-57a8-a328-13140080c264 |  | note | Staggered Studs (if required) - to be installed at 300mm centres alternating per architectural specification
checkpoint-status |  |  | checkpoint | Movement Joints - check walls are discontinued where they pass over building movement joints.
checkpoint-status |  |  | checkpoint | Services Risers - Ensure stud and trackwork is kept a minimum of 20mm away from vertical services within risers per acoustic specification
checkpoint-status |  |  | checkpoint | Engineered Designs - Spot check any engineered framing designs and attached engineers review and sign-off on system.
checkpoint-group |  |  | section | Wall Sheeting
checkpoint-status |  |  | checkpoint | Confirm acoustic/thermal insulation installed to achieve design ratings
label | 9214adb6-d2ff-5660-8c6b-148031b3d64c |  | note | Cross check product ratings against architectural insulation plans
checkpoint-status |  |  | checkpoint | Confirm there is a minimum of 45mm cavity between the residential intertenancy wall studwork per Acoustic Details/Wall type Plans
checkpoint-status |  |  | checkpoint | Confirm door frames are installed vertical and plumb and at correct height.
label | 6dd1553e-b07f-5f38-8ad6-7ad960f7ad18 |  | note | Check metal door frames in wet areas are outside of membrane zone (ie; notched accordingly).
checkpoint-status |  |  | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting walls
holdpoint |  |  | signoff | Review & Sign-off by Acoustic Consultant
checkpoint-status |  |  | checkpoint | Check plasterboard sheets installed with 10-15mm gap at top and bottom to allow for deflection and fire sealant.
checkpoint-status |  |  | checkpoint | Control Joints - Ensure controls joints installed in wall runs larger than 12m in length.
checkpoint-status |  |  | checkpoint | Check correct plasterboard linings installed (type and thickness) per architectural wall types
checkpoint-status |  |  | checkpoint | Ensure sheets are staggered on multiple sheet layer walls. Stagger all sheet joints by minimum 200mm per architectural specification.
checkpoint-status |  |  | checkpoint | Confirm plasterboard lining installed to wet areas are sealed up to concrete soffit on both sides of wall where adjacent to habitable rooms.
checkpoint-status |  |  | checkpoint | Confirm all services penetrations through wet area walls adjacent to habitable rooms are sealed and caulked for acoustic performance.
label | 2e46ccf7-7f4f-5172-a94e-48007bf168d3 |  | note | Check that mechanical flex ducts are not passing through walls - to be rigid ductwork or sleave installed over.
checkpoint-status |  |  | checkpoint | Check intertenancy walls extend to façade panels, leave 10-15mm gap and caulked with fire sealant.
holdpoint |  |  | signoff | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
checkpoint-group |  |  | section | Sheeting Ceilings
checkpoint-status |  |  | checkpoint | Confirm ceiling insulation complete where applicable
checkpoint-status |  |  | checkpoint | Confirm provisions made in ceiling framing for access panels and air grilles were required by architectural RCP
label | 7fdffaac-406b-5801-bef2-6361fc7b31f7 |  | note | Spot check access panels installed to allow access to fire dampers and mechanical fans
checkpoint-status |  |  | checkpoint | Confirm ceiling framing bulkheads are square and level
checkpoint-status |  |  | checkpoint | Confirm furring channels do not clash with other services (eg; downlights, access panels, mechanical exhaust, sprinkler heads, etc…).
checkpoint-status |  |  | checkpoint | HOLD POINT - Confirm Acoustic Consultant Inspection Completed prior to sheeting
holdpoint |  |  | signoff | Review & Sign-off by Acoustic Consultant
checkpoint-status |  |  | checkpoint | HOLD POINT - Confirm BCA consultant inspection of services penetrations through fire rated walls prior to sheeting ceilings
holdpoint |  |  | signoff | Review & Sign-off by BCA consultant
checkpoint-status |  |  | checkpoint | Confirm Plasterboard fixings are at correct intervals
label | 47cc8396-5364-55eb-8c95-5ebafa007f1a |  | note | For painted surfaces, screw fixing onto sheeted frames should be max 400mm spacing. Refer to Manufacturer’s Installation guide
checkpoint-status |  |  | checkpoint | Confirm Villaboard/FC (wet area) fixings are of the correct intervals
label | be026fdc-1154-5e26-8d0d-16328c8b72b7 |  | note | For 9mm Villaboard/FC: Tiled wall screw fixings must be max 150mm spacing. Stud centres to be 400mm. Refer to Manufacturer’s Installation guide
checkpoint-status |  |  | checkpoint | Control Joints - Ensure ceiling bays are not larger than 10m x 7m without a joint or wall break.
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP for the Works
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to painting
label | b4d64f56-0ea4-5b50-a1c8-90071a066939 |  | note | All defects completed?
checkpoint-group |  |  | section | Sign-off
checkpoint-status |  |  | checkpoint | Subcontractor Signoff
holdpoint |  |  | signoff | Subcontractor Sign-off
checkpoint-status |  |  | checkpoint | SDC Signoff
holdpoint |  |  | signoff | SDC Sign-off
checklist-sectioned |  |  | checklist | 01C-SDC-TMP-CON-ITP-007a - 3 - Jumpform |  |  |  |  | Yes | 01C-SDC-TMP-CON-ITP-007a - 3 - Jumpform | 725ada60-3628-4ac7-bbd2-0eeef0230d32
checkpoint-group |  |  | section | Prior to Reinforcement
checkpoint-status |  |  | checkpoint | Confirm Jump No Seq and bottom and top RLs of proposed pour
text | 51402eb2-ae72-5c2d-a581-6bac310dfde6 |  | textbox | Jump No Sequence
text | 02f23e48-87d6-507c-b8e9-c6a88597fc7a |  | textbox | Bottom of Proposed Wall RL
text | 8b65fcba-6344-577a-95e6-980670abccd1 |  | textbox | Top of Proposed Wall RL
checkpoint-status |  |  | checkpoint | Surveyor to complete survey of concrete walls below to confirm if walls need to be adjusted. Attach confirmation survey has been issued to formwork contractor via Aconex
text | 68b1ccb4-f460-5ab1-a75b-553c75d0fc8f |  | textbox | Aconex Correspondence No.
checkpoint-status |  |  | checkpoint | Lift Requirements - Review formwork blockouts for lift openings and door thresholds in accordance with architectural elevations and lift shop drawings
checkpoint-status |  |  | checkpoint | Formwork Requirements - Confirm that all reboxes, couplers, shear key pockets and cast in plates to internal shutter as per structural engineer detail
checkpoint-status |  |  | checkpoint | Attach Sign Off from form worker contractor confirming all works completed and clear access for handover to steel fixers
checkpoint-group |  |  | section | Prior to Closing Shutters
checkpoint-status |  |  | checkpoint | Lift Requirements - Confirm any block out / penetrations required for lift buttons and indicators has been cast in by Form Worker
checkpoint-status |  |  | checkpoint | Confirm all outside reboxes & couplers are installed to required SSL + cover levels
checkpoint-status |  |  | checkpoint | Attach electrical contractors ITP to confirm any required conduit cast ins are completed
checkpoint-status |  |  | checkpoint | Attach reinforcement installer’s ITP
checkpoint-status |  |  | checkpoint | Reinforcement Checks (Refer Structural Engineers Drawings for Reference):
label | e7e68324-bcab-5573-8e93-210cce932bd4 |  | note | Reinforcement cover sufficient
label | 2be8e629-aa9c-5e79-9054-2b740d1a57ee |  | note | Lap Length of bars sufficient
label | 48bd83df-ac5f-5da9-aaca-72bd54684c32 |  | note | Starter bar length to next pour correct
label | 43f96e07-3667-5d3d-86fd-ce324fad6495 |  | note | Lace bars installed to reboxes
checkpoint-status |  |  | checkpoint | Attach structural engineer’s inspection report
checkpoint-status |  |  | checkpoint | Attach verification that structural engineer’s inspection report has been closed out to allow concrete pour
checkpoint-status |  |  | checkpoint | Attach photos of all works completed prior to closing shutters
checkpoint-group |  |  | section | During Concrete Pouring
checkpoint-status |  |  | checkpoint | Confirm Concrete ordered is correct
text | 510cdbe8-8db7-538d-a942-980f4beefc41 |  | textbox | MPa/mix design
checkpoint-status |  |  | checkpoint | Confirm pour height with concrete Contractor prior to pouring
checkpoint-status |  |  | checkpoint | Attach form worker’s jumpform ITP
checkpoint-status |  |  | checkpoint | Attach concrete place contractor’s ITP
checkpoint-status |  |  | checkpoint | Confirm concrete tester onsite to take samples and ensure correct pour location is recorded
checkpoint-group |  |  | section | Prior to Jumping
checkpoint-status |  |  | checkpoint | Attach concrete test result to confirm min 15 MPa has been reached
checkpoint-status |  |  | checkpoint | Attach form worker’s Permit to Energise Jumpform.
label | 11f6ad46-257b-5f13-b106-6b4dfc224c03 |  | note | Note exclusion zone below and all penetrations to be blocked up and secure and any temporary services (hydraulic/electrical/static line) disconnected inside trailing decks
checkpoint-group |  |  | section | After Jumping
checkpoint-status |  |  | checkpoint | Form Worker to ensure that all z bar holes and jumpform pockets within the lift shaft has been patched and infilled in accordance with structural engineer drawings
checkpoint-status |  |  | checkpoint | Attach concrete test results 28d and confirm compliance with engineer requirements
checkpoint-status |  |  | checkpoint | Permit to Re-seat jumpform received (attach to ITP)
checkpoint-status |  |  | checkpoint | Surveyor to survey finished concrete walls (attach as-built to ITP)
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer
checklist-sectioned |  |  | checklist | 101C-SDC-TMP-CON-ITP-007 - 2- Concrete Columns Walls Verticals |  |  |  |  | Yes | 101C-SDC-TMP-CON-ITP-007 - 2- Concrete Columns Walls Verticals | 8813ca33-5c45-45f7-9eb2-acdb8e8d4176
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
text | 8212b539-cd4f-5577-8e24-cde7cadf435e |  | textbox | Architectural Drawings
text | 9525446e-d822-5373-a025-b3ff69bf5704 |  | textbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Ensure survey of column/wall positions are completed prior to commencing formwork
label | 1181ac05-c6a5-5bc7-9c93-9e35cbd517a6 |  | note | Attach surveyors as-built records to ITP
checkpoint-status |  |  | checkpoint | Reinforcement - Check Starter bars from previous pour installed in correct position (compare against survey points)
checkpoint-status |  |  | checkpoint | Reinforcement - Check for correct bar sizes and lap lengths between starter bars (top & bottom)
checkpoint-status |  |  | checkpoint | Cast-in Services - Electrical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design. Attach Contractors ITP
checkpoint-status |  |  | checkpoint | Cast-in Services - Hydraulics subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
checkpoint-status |  |  | checkpoint | Cast-in Services - Mechanical subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
checkpoint-status |  |  | checkpoint | Cast-in Services - Fire Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design Attach Contractors ITP
checkpoint-status |  |  | checkpoint | Cast-in Services - Security Subcontractor to sign off that all Conduits / block-outs are installed in accordance with the design
checkpoint-status |  |  | checkpoint | Confirm strength and mix design of concrete ordered with subcontractor prior to pour
text | e2392b00-e6cb-5a51-8a2a-2a77c8e07c4b |  | textbox | Concrete Mix Design:
checkpoint-status |  |  | checkpoint | Structural Engineer Sign-off - Foreman and subcontractor to sign off engineer’s report to verify that all work to be rectified was checked for compliance prior to pour
label | ef21bfda-3e60-5169-b596-cebf04ae4aad |  | note | Attach engineers inspection report and verification of rectification items being closed out.
checkpoint-status |  |  | checkpoint | Formwork Compliance - Confirm formwork is checked to achieve Class 2 finish to concrete:
boolean | 3a93e62d-4b35-5058-8a98-4dcd75ec50a2 |  | tickbox | Formwork is clean and free of debris
boolean | 27f9719b-8318-58ee-a64a-ba2a4f2bc4d4 |  | tickbox | No lipping of formwork between sheets
boolean | 97222634-f5b3-5bfc-a4b9-bb08014a530c |  | tickbox | Fillets installed at all corners
boolean | 93aef68f-4499-5ea3-8e2e-b386ba441593 |  | tickbox | Form ties are installed at even spacing
boolean | fda4eb4c-8d85-56c3-b72d-bf16096a64be |  | tickbox | Check for correct reo cover at shutters
boolean | 3d1004c4-dd9c-5151-9af4-4d2b3025a3c1 |  | tickbox | Splayed columns are at correct degrees per Architectural/Structural drawings
checkpoint-status |  |  | checkpoint | Area cleaned of all excess formwork, sawdust at base of columns, reo, and debris prior to pour
checkpoint-status |  |  | checkpoint | Attach formworkers ITP for column and wall formworking
checkpoint-status |  |  | checkpoint | Attach Steelfixers ITP for Column and wall reinforcement
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | Concrete Placement Checklist
boolean | 1b98de59-d17f-5afc-88c7-b191e7ce5752 |  | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
boolean | d5dfff6a-4133-5297-8624-bb4fb087cf0c |  | tickbox | Confirm Delivery Docket References correct mix design
boolean | 50bdef93-0732-56eb-9b5e-e6f5997d3539 |  | tickbox | Plant and Equipment checklist completed on concrete pump and lines
boolean | b5e23c22-d0f6-5c73-ace4-90ad93375d9a |  | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
label | d4db1014-9b4b-5670-87f1-e038c416b2c7 |  | note | 7, 28 & 56 day compressive test results to be issued by batch plant
label | f9088664-a151-577d-abf9-6d232344a425 |  | note | Batch plant to issue monthly dry shrinkage test results
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
boolean | 80f59b43-15d6-5b35-8916-516d07afe598 |  | tickbox | Form Worker
boolean | a24b20a5-b078-5691-bdf1-3a7e0310a014 |  | tickbox | Electrician
boolean | c7498df1-2e83-5f27-bbe5-5dd8c14f2062 |  | tickbox | Plumber
checkpoint-status |  |  | checkpoint | Ensure only rubber tipped vibrators are used and care is taken not to damage shutters
checkpoint-status |  |  | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of walls, immediately after pour for off form finishes.
checkpoint-status |  |  | checkpoint | Attach Concrete Place contractors ITP
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Curing - Approved curing compound to be applied to columns following removal of formwork as required.
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces:
label | 2f82a0a6-22f5-5790-8419-6e5c3ba5917b |  | note | 5mm+/- in correct position
label | 5c321c38-d145-551c-a30c-87290edfbf01 |  | note | 5mm +/- from 3.0m straight edges.
label | a1a15c84-31a4-56a0-a2b0-e39c6e15e7e6 |  | note | 5mm +/- from plumb.
checkpoint-status |  |  | checkpoint | As-Built Survey - Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As Built Survey Plan
checkpoint-status |  |  | checkpoint | Concrete Test Results - Obtain all concrete test results. Confirm strength achieved after:
text | 1f5986f6-3a4c-561f-861d-6357c8d03c6c |  | textbox | 7 Days MPa
text | b5affa46-7af9-5f5b-98b8-9f58c3a7f11c |  | textbox | 28 Days MPa
text | 32f818c2-e3c3-5979-8176-de537e4796de |  | textbox | 56 Days MPa
checkpoint-status |  |  | checkpoint | All non-conformances closed out
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer
checklist-flat |  |  | checklist | Drawings / Documents |  |  |  |  | Yes | Drawings / Documents | 94073e7f-4220-4ecb-ae12-616effc73097
checkpoint-status |  |  | checkpoint | Approved Drawing Available
checklist-flat |  |  | checklist | Fit Off |  |  |  |  | Yes | Fit Off | c4d8be49-fdab-409b-885a-43ab825336fa
checkpoint-status |  |  | checkpoint | Approved for Sheeting/Closure
checkpoint-status |  |  | checkpoint | Fit Off Complete
checklist-flat |  |  | checklist | SDC-TMP-CON-ITP-006 - 4 – Pits, Pads and Strip Footings |  |  |  |  | Yes | SDC-TMP-CON-ITP-006 - 4 – Pits, Pads and Strip Footings | d79cedb5-5790-4f7b-9118-3138e4f9e9ec
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach markup structural plan identifying footings relevant to this ITP
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm surveyor has provided setout for pad footing excavation (attach survey setout plan)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach Geotech engineer bearing certification confirming approval of substrate complying with engineer’s requirements
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm that either pre- applied membrane or Forecoin plastic has been installed to comply with electrolysis study (attach photos)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm excavation is free of debris and loose materials to walls and floor prior to handover (attach photos)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach reinforcement contractors ITP (incl AEFAC Accredited installer signoff of any drill and epoxy bars to comply with structural engineer details)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm wall starter bars have been installed in accordance with surveyor setout and architectural outline drawings.
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach signoff from CFT Column contractor inspection approval of starter bars, castins and hold down bolts
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach waterproofing contractors ITP confirm tanking waterproofing and PVC water bar has been installed(attach waterproofing ITP)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm that waterproofing consultant has inspected works and defects closed out
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach hydraulic contractor's ITP confirming completion of any cast in as per hydraulic drawings
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach formwork ITP/Signoff that all formwork to kicker has been completed (sump, hobs, edge boards etc)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach structural engineer’s inspection report
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach verification that structural engineer’s inspection report has been closed out to allow concrete pour
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Confirm concrete place contractor's order complies with engineer's strength of concrete, waterproofing additive and testing requirements
checkpoint-status |  |  | checkpoint | Prior to Concrete Place - Attach photo of formwork setting the level for concrete place contractor
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour - Attach concrete place contractor’s ITP
checkpoint-status |  |  | checkpoint | After Concrete Pour - Confirm RL of poured footing complies with design RLs
checkpoint-status |  |  | checkpoint | After Concrete Pour - Confirm integrals falls have been completed in concrete to sump
checkpoint-status |  |  | checkpoint | After Concrete Pour - Attach concrete test results and confirm compliance with engineer requirements
checkpoint-status |  |  | checkpoint | Signoffs - Site Engineer to signoff ITP has been completed
holdpoint |  |  | signoff | Signoff by Site Engineer
checkpoint-status |  |  | checkpoint | Signoffs - Project Engineer to review and confirm ITP has been completed
holdpoint |  |  | signoff | Signoff by Project Engineer
checklist-flat |  |  | checklist | Rough In |  |  |  |  | Yes | Rough In | dadb4428-a37d-4c96-802a-f970bfe6a95c
checkpoint-status |  |  | checkpoint | Rough In Complete
checklist-sectioned |  |  | checklist | 101C-SDC-TMP-CON-ITP-008 - 3 - Suspended Concrete Slab |  |  |  |  | Yes | 101C-SDC-TMP-CON-ITP-008 - 3 - Suspended Concrete Slab | e9298d8b-f232-4509-92d7-86cfa2c57e91
checkpoint-group |  |  | section | Prior to Formwork Deck Handover
checkpoint-status |  |  | checkpoint | Current Drawing Status - Refer Aconex Document Register for latest approved Shop Drawings. Record drawings used at time of pour on ITP.
text | 414a16c9-2639-5e6c-a7e0-d5bd95d1a1b2 |  | textbox | Architectural Drawings
text | 64b36330-3896-594a-8a03-fea7244cd31d |  | textbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Concrete Mix Design
text | d2a3248f-b14a-5d59-99dc-49bd2ea3a66d |  | textbox | Confirm Mix Design
checkpoint-status |  |  | checkpoint | Set-out - Surveyor set out slab grids to allow formwork construction
checkpoint-status |  |  | checkpoint | Survey & Set-out of formwork correct. Check correct heights for formwork soffit, Top of Concrete (TOC) and falls
label | f4cce657-83ef-543b-8341-1965af65a402 |  | note | Attach Surveyor Formwork As-Built to ITP
checkpoint-status |  |  | checkpoint | Site Instructions - Copies of design changes, emails and site advices and the like to be attached.
checkpoint-status |  |  | checkpoint | Bondek (where applicable) - Back propping installed for pre pour and deflection & gaps sealed to prevent dripping
checkpoint-status |  |  | checkpoint | Structural Steel Sign off from Steel installer and Structural Engineer (where applicable for bondek slabs)
checkpoint-status |  |  | checkpoint | Formwork Sign-off - Area cleaned of all excess formwork, sawdust, reo and debris prior to pour. Safe Access to deck available.materials before handover deck
label | caca8116-cf42-5015-b1a0-9143a8395eb9 |  | note | Attach formworkers ITP (referencing all hobs, steps, cast-ins, HDB's, bearing strips, polystyrene, fillets, etc… installed correctly)
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Structural Compliance - Engineers approval for concrete placement required with list of defects to be completed
label | da6340f8-c775-55da-95ed-ff85d07b1b95 |  | note | Attach structural engineers inspection report and evidence of close-out
checkpoint-status |  |  | checkpoint | Formwork Engineers Sign-off - Attach Sign-off
checkpoint-status |  |  | checkpoint | Post Tensioning - Check Subcontractor ITP complete, and attach to this ITP.
checkpoint-status |  |  | checkpoint | Screen Needle Cast-in's - Inspect all screen needles are installed in accordance with relevant shop drawings
label | 90bcdc10-a2cb-5816-8a8f-646586fefef7 |  | note | Attach sign-off from Formworker
checkpoint-status |  |  | checkpoint | Curtain Wall Bracket Cast-in's - Inspect all Curtain wall brackets/rebates are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
label | 3b8ee292-84cf-53f9-b316-0ba3bccd1b41 |  | note | Attach Curtain Wall subcontractors sign-off & ITP from formworker
checkpoint-status |  |  | checkpoint | Crane/Hoist Bracket Cast-in's - Inspect all hoist and crane brackets are installed in accordance with relevant shop drawings. Surveyor to confirm locations are correct.
label | 7af1ed1e-1c1b-57d0-b260-f29d39cfedfc |  | note | Hoist and Crane contractor to inspect and sign-off cast-in position.
checkpoint-status |  |  | checkpoint | Temporary Penetrations - Inspect formwork penetrations in accordance with temporary works design. Surveyor to confirm locations are correct.
label | 0c469f09-ebc8-59d0-b762-2ae84293d11d |  | note | Temporary Penetrations may include: formwork hoist, concrete boom, etc…
checkpoint-status |  |  | checkpoint | In-Slab Services - Electrical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | In-Slab Services - Hydraulic subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | In-Slab Services - Mechanical subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | In-Slab Services - Fire Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | In-Slab Services - Security Subcontractor to sign off that all penetrations are installed in accordance with the design. Attach contractors ITP
checkpoint-status |  |  | checkpoint | Formwork Cast-ins - All timber fillets, drip grooves, Rebates, and proprietary shear connectors installed as required
checkpoint-status |  |  | checkpoint | Starter Bars - Confirm all starter bars for walls and columns installed as required per structural and architectural drawings and survey pins
checkpoint-status |  |  | checkpoint | Water Stops - Confirm installation of any proprietary water stops as required (ie; at CJ’s, etc…)
checkpoint-status |  |  | checkpoint | Reinforcement Cover - Check top RLs for all reinforcement, ensuring adequate concrete cover. Confirm with Concreter. Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits.
checkpoint-status |  |  | checkpoint | Attach Reinforcement contractors ITP
checkpoint-status |  |  | checkpoint | Concrete Falls - Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary
label | b46d41a8-a2f6-5a67-a3cb-589bf5128ea3 |  | note | Cross-check the following drawings: See Hydraulic, Architectural Concrete Outlines and Structural drawings
checkpoint-status |  |  | checkpoint | Cleaning of Deck - Clean off decks and beams prior to pour and ensure all exposed off-form soffits are free of any dust, stains, and rust marks. Hose down if necessary.
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | Concrete Placement Checklist
boolean | a8cc6a45-5839-5efc-8114-c275f597ccd4 |  | tickbox | Structural Engineer & Formwork Engineer Sign-off Received
boolean | cc282e2e-0a8a-53d7-8509-60b3247b8396 |  | tickbox | Confirm Delivery Docket References correct mix design
boolean | 70a5305c-d905-57b1-9576-84907c01aa12 |  | tickbox | Plant and equipment checklist completed on concrete pump and lines
boolean | fd542543-8855-5fc8-9478-f16a999c8b62 |  | tickbox | Confirm concrete tester on-site and correct location of concrete pour provided to them for test results
label | efd491ba-0a05-58ff-87af-b27f9097431b |  | note | 1, 4, 7, 28 & 56 day compressive test results to be issued by batch plant
checkpoint-status |  |  | checkpoint | Concrete Finish - Ensure concrete contractor is aware of required concrete surface finish.
checkpoint-status |  |  | checkpoint | Slab Curing - Check cured when bleed water stops and able to access slab without marking and also amount used complies
checkpoint-status |  |  | checkpoint | Concrete Falls - Confirm concrete has falls to drainage points in slab.
checkpoint-status |  |  | checkpoint | Attach Concrete Place Contractors ITP
checkpoint-status |  |  | checkpoint | Trade Representatives - Ensure a representative from each of the following is on site and witnessing the pour:
boolean | 158e4fe0-f043-5003-8978-c52840fb3055 |  | tickbox | Form Worker
boolean | 9b437c7e-a121-5e39-82d9-f3da15ff1195 |  | tickbox | Electrician
boolean | 281e0d71-ebf6-5950-8500-3260adc89826 |  | tickbox | Plumber
boolean | 81f29997-bbcc-5986-aece-fa078c429731 |  | tickbox | Post Tensioner
checkpoint-status |  |  | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry.
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan.
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are as follows:
label | face7fb6-ab6d-5c94-837f-569ba0859243 |  | note | 6mm +/- from design RL
label | a2342f2a-44dd-5caf-9dae-727bb7d88ed6 |  | note | 6mm +/- from 3.0m straight edges
checkpoint-status |  |  | checkpoint | Exposed Concrete Finish - Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610 (Class 1, 2 or 3)
checkpoint-status |  |  | checkpoint | Concrete Test Results - Note test results on ITP and attach:
text | e21d473f-6711-5330-b779-31ec2e2d4259 |  | textbox | 1 Day
text | 16cd5736-3c0d-5d08-9e27-1df61d0cb2f4 |  | textbox | 4 Day
text | a9ec48f5-2664-5170-8410-9484e3767dcd |  | textbox | 7 Day
text | 4ba85b4c-7e76-5cb7-8b48-b59b3a6f79e7 |  | textbox | 28 Day
text | 3d932226-c9fa-5f7a-b3ab-393eef268526 |  | textbox | 56 Day
checkpoint-status |  |  | checkpoint | Initial Stressing - Concrete has achieved required strength MPa (10 MPa and confirmed by Concrete contractor)
label | 3fde47b1-83ee-5b0d-a635-1aeaaf6e5f29 |  | note | Concrete Contractor must issue Concrete test results, verbal not accepted
checkpoint-status |  |  | checkpoint | Final Stressing - Concrete has achieved required strength Mpa (22 Mpa and confirmed by concrete contractor)
label | fb420cbd-4d1c-531a-b340-8329ceb1ceb0 |  | note | Concrete Contractor must issue Concrete test results, verbal not accepted
checkpoint-status |  |  | checkpoint | Stressing Sign-off - Before stripping can commence final stress complete, Ducts grouted and PT supervisor issues verification records
label | b0d0a74d-cc56-5c59-a817-3330d3757394 |  | note | Attach Post Tension Contractors ITP
checkpoint-status |  |  | checkpoint | Extension Records Approval - Engineer approval of extension records following final stress
text | 82c227c8-9b47-50fb-a877-577c22bf013c |  | textbox | Record date when props were removed if not given approval by engineer
checkpoint-status |  |  | checkpoint | All non-conformances closed out and accepted by Structural Engineer and Architect.
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer
checklist-flat |  |  | checklist | SDC-TMP-CON-ITP-009 - 3 – RC Slab on Grade |  |  |  |  | Yes | SDC-TMP-CON-ITP-009 - 3 – RC Slab on Grade | ee793663-d8bf-4be5-9b25-38983bf84229
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Attach Markup to confirm proposed pour zone
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Ensure detailed excavation is complete (Attach Excavation Contractor’s ITP)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm inground drainage and pit works has been completed and backfilled (Attach photos/confirmation)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm that substation earthing rods have been drilled, as AS Built red line survey (If applicable)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm min 100mm subsoil drainage has been installed as per geotechnical requirements (attach contractor’s ITP)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm Surveyor has provided set outs/ benchmarks (Attach survey)
checkpoint-status |  |  | checkpoint | Prior to Reinforcement: Confirm vapor barrier installed over subbase (Attach photos and confirm signed off by concrete place ITP)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach formwork contractor’s ITP (including setdowns, hobs, Construction/key/movement joints, ect.)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach Structural Engineers inspection report
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach Verification that structural engineer’s inspection report has been closed out to allow concrete pour (Attach Photos)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach reinforcement contractor’s ITP
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach Hydraulic ITP (inground drainage and pipework)
checkpoint-status |  |  | checkpoint | Prior to Concrete Pour: Attach Electrical ITP (Cast in conduits – if applicable)
checkpoint-status |  |  | checkpoint | During Concrete Pour: Attach Concrete place contractor’s ITP (including Ableflex)
checkpoint-status |  |  | checkpoint | After Concrete Pour: Confirm falls have been completed in concrete pour in accordance to architectural drawings
checkpoint-status |  |  | checkpoint | After Concrete Pour: Attach Concrete test results and confirm compliance with engineer requirements
checkpoint-status |  |  | checkpoint | After Concrete Pour: Confirm saw cuts installed as per engineer’s drawings
checkpoint-status |  |  | checkpoint | Signoffs: Site Engineer to signoff ITP has been completed
holdpoint |  |  | signoff | Signoff by Site Engineer
checkpoint-status |  |  | checkpoint | Signoffs: Project Engineer to review and confirm ITP has been completed
holdpoint |  |  | signoff | Signoff by Project Engineer
checklist-sectioned |  |  | checklist | 101C-SDC-TMP-CON-ITP-007b - 3 - Stairs FRP Works |  |  |  |  | Yes | 101C-SDC-TMP-CON-ITP-007b - 3 - Stairs FRP Works | f21bfd5d-e387-4b11-b326-5460f624620a
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm bottom, mid & top of stair RL's on Architectural Concrete Outlines.
text | 3c333b2e-8c59-5cea-9bd6-995e5e5278dd |  | textbox | Bottom Landing RL
text | 6268699c-bbf8-5b2d-b60b-6c91d3b7d452 |  | textbox | Mid Landing RL
text | 7200af5a-dbde-5e1e-a6fb-251f67252f38 |  | textbox | Top Landing RL
checkpoint-status |  |  | checkpoint | Confirm Re-boxes/cast-in bars are installed to correct heights at landings, based on nominated design RL's.
checkpoint-status |  |  | checkpoint | Confirm any starter bars on landings for dividing walls, etc… are installed as per Structural Drawings
checkpoint-status |  |  | checkpoint | Check for reinforcement cover as per Structural Drawings.
label | 3d315b18-7758-50f8-989c-6e7a2fee29cb |  | note | Cover requirement generally 30mm
checkpoint-status |  |  | checkpoint | Confirm all cast in elements installed (eg, stair handrails, etc…)
checkpoint-status |  |  | checkpoint | Confirm all formwork is clean and free of debris.
checkpoint-status |  |  | checkpoint | Confirm any conventional parts of stairs have been formed in accordance with the relevant shop drawings and standards.
label | d5770c7b-4996-5b2a-b994-b3894dd14abf |  | note | Statutory Requirements (Dimensions in mm): Riser: Min. 115, Max. 190 Going: Min. 240, Max. 355 Ensure consistency
checkpoint-status |  |  | checkpoint | Confirm cast-in of anti-slip items if required (eg, carborundum powder, stair nosings, etc…);
checkpoint-status |  |  | checkpoint | Obtain certificate from Structural Engineer prior to concrete pour and attached completed Inspection Report.
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg. size of concrete prior to ordering.
text | b8c2026a-2175-5b8d-aff1-5efde45b01d8 |  | textbox | Concrete Mpa/Mix Design
checkpoint-status |  |  | checkpoint | Obtain subcontractors ITP (Steel Fixer) & attach to ITP
checkpoint-status |  |  | checkpoint | Obtain subcontractors ITP (Form Worker) & attach to ITP
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | If the stairs are being used as access to a leading deck, ensure alternative access is established prior to pouring.
checkpoint-status |  |  | checkpoint | Confirm concrete tester onsite during concrete pour, and the following tests have been requested.
label | 1df64493-478e-5d8e-9f03-72aebec291be |  | note | 7 Day
label | 672a0c94-2891-5426-a6cd-ac2ccde9cdba |  | note | 28 Day
label | 4856696c-b869-5e48-9b65-241e9f43325b |  | note | Ensure concrete tester is aware of pour locations
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
boolean | cc4294a7-8a69-5f86-8f2d-974e66cea6ae |  | tickbox | Form Worker
boolean | 86538ad7-9fc1-5b9b-a13e-ec09b8a2f4de |  | tickbox | Electrician
boolean | 0488c9dd-4037-5d80-a06f-5237a5736306 |  | tickbox | Plumber / Fire services
checkpoint-status |  |  | checkpoint | Ensure concreters have correct finishing tools (eg, carborundum powder, etc…).
checkpoint-status |  |  | checkpoint | Ensure only rubber tipped vibrators are used to prevent formwork damage.
checkpoint-status |  |  | checkpoint | Obtain Subcontractors ITP (Concretor) & attach to this ITP
checkpoint-status |  |  | checkpoint | Ensure Form Worker labour is available to clean up any slurry runs at bottom of stairs, immediately after pour.
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces:
label | b56e6619-857a-5c66-8962-bf3d63a08444 |  | note | 6mm +/- from design RL
label | c499d97b-f322-5fb7-993d-8cbbe0ad1873 |  | note | 6mm +/- from 3.0m straight edges.
checkpoint-status |  |  | checkpoint | If an as-built survey is required, confirm Surveyor is out next day to carry out survey of finished concrete. Attach As built Survey Plan
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 days. Attach to ITP
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 days. Attach to ITP
holdpoint |  |  | signoff | Final ITP Review & Sign-off by Project Engineer