## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Tahunanui Back Beach Remediation |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | To be confirmed |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Nelson City Council |  |  |  |  | B | Report by Breach | CM | Construction Manager | Wayne Oldfield | WO
Contract Number: | 151991 |  |  |  |  | C | Check | NCC | Nelson City Council | Ajith Rajmohan | AR
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | SUB | Subcontractor | Nelmac | NM
[6 empty] | E | Examine |  | Subcontractor | Civil Engineering Labs | CELS
ITP Number: | 1 |  | Version: | 1 |  | H | Hold Point | CE | Civil Engineering Cadet | Tyler Peppin | TP
ITP Description: | Inspection and Test Plan for the Tahunanui Back Beach Remediation. |  |  |  |  | I | Inspection | PM | Project Manager | Jaco van Noordwyk | JVN
Discipline: | Civil Construction, Earthworks. |  |  |  |  | M | Monitor on Random Basis | PS | Project Supervisor | Lawrence McCarthy | LM
Specification: | [5 empty] | O | Operation | SV | Surveyor | Mark Frost | MF
[6 empty] | R | Review | ENG | Engineer | Tonkin + Taylor | T+T
Drawings: | 1006675.5130-00 - 10 |  |  |  |  | S | Subcontractor | STMS | STMS | Downer | /
[6 empty] | V | Visual Verification
Prepared By: (Name) | Tyler Peppin |  | Date: | 2024-09-09 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
1.1 | Pre Construction
1.2 | Vegetation Clearance | Removal of trees, and other plants within the area of works | Trees and plants removed in the area of works | Visual | Pre Construction | Operation, Hold point | SUB | Nelmac
1.3 | Traffic Management | Implementation of Traffic Management | Traffic Management set up in accordance with approved TMP | Visual | Constant monitoring | Visual verification, Hold point | STMS | Downer
1.4 | Survey and Set out | Pre construction survey and site set out | Set out follows provided coordinates | Visual | Pre Construction | Inspection, Hold point | SV, ENG | Downer, T+T
2 | Zone A Excavation
2.1 | Final Excavation Level | Testing for contamination | Excavation free of contaminants | Engineer approval | Every 25m of the completed excavation | Inspection, Visual, Hold point | ENG | T+T
3 | Zone B Excavation
3.1 | Final Excavation Level | Testing for contamination | Excavation free of contaminants | Engineer approval | Every 25m of the completed excavation | Inspection, Visual, Hold point | ENG | T+T
4 | Carpark Construction
4.1 | AP40 Compaction | NDM Testing | Mean Value ≥98%, Min Value ≥95% | Lab Report | 1 lot ( 5 tests) | Testing | SUB | Civil Engineering Labs
4.2 | AP40 Compaction | Beam Testing | Maximum Deflection 2.0mm | Lab Report | Every wheel track at 20m intervals | Testing | SUB | Civil Engineering Labs

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: