## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Tahunanui Back Beach Remediation ITP | itp |  |  |  |  | Tahunanui Back Beach Remediation ITP
section | 1.1 - Pre Construction
checkpoint | 1.2 - Vegetation Clearance
label | Inspection Point: Quality Control Activity - Removal of trees, and other plants within the area of works
label | Acceptance Criteria - Trees and plants removed in the area of works
label | Verifying Document - Visual
label | Frequency - Pre Construction
label | Inspection Type (Visual, other) - Operation, Hold point
label | Inspection: Key - SUB
label | Inspection: By (Role Key) - Nelmac
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Traffic Management
label | Inspection Point: Quality Control Activity - Implementation of Traffic Management
label | Acceptance Criteria - Traffic Management set up in accordance with approved TMP
label | Verifying Document - Visual
label | Frequency - Constant monitoring
label | Inspection Type (Visual, other) - Visual verification, Hold point
label | Inspection: Key - STMS
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey and Set out
label | Inspection Point: Quality Control Activity - Pre construction survey and site set out
label | Acceptance Criteria - Set out follows provided coordinates
label | Verifying Document - Visual
label | Frequency - Pre Construction
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: Key - SV, ENG
label | Inspection: By (Role Key) - Downer, T+T
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Zone A Excavation
checkpoint | 2.1 - Final Excavation Level
label | Inspection Point: Quality Control Activity - XRF Contamination Testing
label | Acceptance Criteria - Excavation free of contaminants
label | Verifying Document - Engineer approval
label | Frequency - Every 25m of the completed excavation
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: Key - ENG
label | Inspection: By (Role Key) - T+T
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Zone B Excavation
checkpoint | 3.1 - Final Excavation Level
label | Inspection Point: Quality Control Activity - XRF Contamination Testing
label | Acceptance Criteria - Excavation free of contaminants
label | Verifying Document - Engineer approval
label | Frequency - Every 25m of the completed excavation
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: Key - ENG
label | Inspection: By (Role Key) - T+T
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Carpark Construction
checkpoint | 4.1 - AP40 Compaction
label | Inspection Point: Quality Control Activity - NDM Testing
label | Acceptance Criteria - Mean Value ≥98%, Min Value ≥95%
label | Verifying Document - Lab Report
label | Frequency - 1 lot ( 5 tests)
label | Inspection Type (Visual, other) - Testing
label | Inspection: Key - SUB
label | Inspection: By (Role Key) - Civil Engineering Labs
checkpoint | 4.2 - AP40 Compaction
label | Inspection Point: Quality Control Activity - Beam Testing
label | Acceptance Criteria - Maximum Deflection 2.0mm
label | Verifying Document - Lab Report
label | Frequency - Every wheel track at 20m intervals
label | Inspection Type (Visual, other) - Testing
label | Inspection: Key - SUB
label | Inspection: By (Role Key) - Civil Engineering Labs