## ITP COVER PAGE
Ducting & Pit Inspcection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - DN1211-ITP-003 - Rev IFC-01
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Wellesley St Bus Interchange - WSBI |  |  |  |  | ITP Number: |  |  | DN1211-ITP-003
Project Number: |  |  | DN1211 |  |  |  |  | ITP Status: |  |  | For Review
ITP Description: |  |  | Earthworks (Excavation, Subgrade and Sub-Base) |  |  |  |  | Revision: | 1000 |  | IFC-01
Contract Number: |  |  | WSBI |  |  |  |  | Drawing Sets:
Customer: |  |  | Auckland Transport |  |  |  |  | Specification:
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | For Review | 2024-08-29 |  | R.Collier |  | Compiled draft |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | IFC | 2024-09-09 |  | R.Collier |  | For construction |  |  |  | C | Check |  | DES | Designer
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer CM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) |  | AT/MSQA | [5 empty] | Client (If Applicable) |  | AT/MSQA

## ITP
[7 empty] | ITP- | Earthworks (Excavation, Subgrade and Sub-Base)
[7 empty] | Project- | WSBI - 1211
[7 empty] | ITP No.- | ITP-003
[7 empty] | Revision- | Rev-01
Item No. | Inspection and Test Point | Acceptance/Conformance criteria | Standard/Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Engineer Rep Signature (Blank as req.) | MSQA (Blank as req.) | Comments/Closeout Details
SECTION 3 - PRE CONTRUCTION (P&G/ESTABLISHMENT)
3.1 | Pre- construction | Site Clearance and service location completed. Before U Dig, GPR service locate and pilot holing as required. Protect existing services and liaise with utility providers as necessary | Aurecon Civil Spec 19.5 | Service Locate or Asbuilts / Sample Dig permit | Prior excavation | H | SE | H |  | I
SECTION 4 - MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.1 | Aggregate MAR | Sub-Base to be ATAP40 and comply with TNZ M/4 specification for aggregate properties - At least seven working days prior to delivery of Sub-Base course the contractor shall deliver to the engineer the results of production property tests carried out by an IANZ accredited lab in accordance with the relevant NZ standards | Aurecon Spec 7.5.1 | Approved MAR / IANZ test report | Once prior Sampling rate as per civil 6.5.1 | H | DES | H |  | R | I
SECTION 5 - CONSTRUCTION ACTIVITY
5.1 | Excavation | Set- out position completed RL marked. For excavation level | Aurecon Civil Spec Section 19.11.2 | ITP sign off | In Process Check | V | SV | V |  | I
Site Clearance
5.2 | Site Clearance (Cut to Subgrade) | Area of work Cleared in accordance with Resource consent andlocal authority requirements. Discovery of unsuitable materials to be advised to the engineer and disposed of or repalced as directed. | Aurecon Civil Spec; Section 3.3 and 3.6 | ITP Sign off | In Process Check | W | SE | V |  | I
5.3 | Discovery of antiques and valuables (If applicable) | Arcaheology: Works to be completed as per CMP Archaeoligical discovey protocol, records in site diary and Aconex sent to the Engineer. Antiques: Owners must contact the Heritage New Zealand for authority to proceed. | Aurecon Spec 3.10 and Heritage New Sealand | ITP Sign off | Upon Discovery (May not be Applicable) | H | PE | H |  | I
Removal of Structures and Obstructions
5.4 | Discovery of Contaminated or Hazardous Material (May not be Applicable) | Contaminated material or Waste exhibitning hazardous characteristics handled and removed asper work safe guidnlines and taken off site to be tested. Hazardous or contaiminted materials disposed at approved landfills only. Volume or any disposed hazardous or contaminated materials to be recorded. | Arecon Civil Spec 4.5.6 and management plan | Disposal dockets (If applicable) /Site Diary (If applicable) | Upon Discovery (May not be Applicable) | H | PE | H |  | H
5.5 | Disposal of materials | Demolished Materials sorted as required and disposed of correctly. Materials or item salvaged for re-use as appropriate | Aurecon Civil Spec 4.5.7 | Daily Diary (If applicable) | In Process Check | I | SE | I
5.6 | Demolition and removal of obstructions | Submit works over approvlas for Relevant NUO's where utilities found. Confirm approval to remove structure or protection requirements as per Aurecon DRG's | Aurecon Civil Spec 4.5.5 | Email confirmation where applicable or works over permit algining with the consent | Upon Discovery (May not be Applicable) | H | PE | H |  | I
5.7 | Tree Removal (If applicable) | Refer to Tree Management Plan, Tree Management plan certification and relevant resource consents/approvals | Resource Consent | Resource consent | Each Tree (If applicable) | W | PE/DES/ENG | W |  | I | R
5.8 | Services/Sun Surface infrastrucure removal | Existing services and drainage structures to be located where possble or as agreed with the Engineer. Pilot hole, disconnect or isolate live services prior to demolitions as required. Services or pipes to be abandoned are to be completely removed or grout filled as per drawing or approval by assest owner if different. | Aurecon Civil Spec 4.5.4 and 4.5.5 | Service As built | As Encountered | H | PE/ENG | H |  | R
Excavation
5.9 | Subgrade Testing | Contractor to Confirm subgrade strength and report to Engineer via Inspection. Clegg to CBR correlation to be confirmed and Clegg hammer results to be undertaken on Subgrade | Aurecon Civil Spec 5.6.11 | QA sheet | Every 20m or as agreed by the Engineer | H | SE | H |  | R | I
5.10 | Line and Level of subgrade | Pavement Subgrade tolerance +/-10mm from design subgrade level (or as applicable with existing services). Excavation depth must be at least the design pavement depth for LMC locations. Subgrade shape as per survey set out. To be verified on site. | Aurecon Civil Spec 5.6.9 | As builts | Each Subgrade section | H | PE | H |  | R | W
Sub-Base
5.11 | Sub-Base Level and Shape | Construct lifts between 2.5 to 5X maximum stone size to ensure good compaction (100-200m). Surface shape, finished and tolerances shall comply with requirments of TNZ B/02- -25mm/+5mm to design FL measured between centreline and pavement edge | Aurecon Civil Spec 6.7.4 TNZ B/2 | QA cheetsb and as built survey | Every 10m for each section of basecourse | H | SE | H |  | R | I
5.12 | Sub base Compaction | Clegg testing of Sub0-base course to achieve CIV 25+ | Aurecon Spec 6.1 and GCOR-0042 | QA sheets | Every 10m for each section of basecourse | H | SE | H |  | R | R
SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.1 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | ENG | H |  | H | R
6.2 | Survey Record | Installation of works under contract completed compliant in accordance with all relevant regulations, COP and standards | Design Specification / Downer | QA Checksheet Redlines | Post Construction | H | ENG | H |  | H | R
6.3 | Redline Drawings | Ensure all items have been installed create a Redline Drawings for Asbuilt creation noting all changes with RFI numbers and departures in red pen | Downer | Redlines | Post Construction | H | ENG | H |  | H | R
6.4 | Defect, Snag and Punch List | Update the project defects, snag and punch list register | Downer | Redlines | Post Construction | H | ENG | H |  | H | R
SECTION 7 - SIGN OFF
|  | Customer Release Granted: |  | ☐ Yes | ☐ No | Date:
Certificate Number: