## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1211-003 ITP Earthworks (Excavation, Subgrade, Sub-Base) Rev1 | itp |  |  |  |  | DN1211-003 ITP Earthworks (Excavation, Subgrade, Sub-Base) Rev1
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.1 - Pre- construction
label | Acceptance/Conformance criteria - Site Clearance and service location completed. Before U Dig, GPR service locate and pilot holing as required. Protect existing services and liaise with utility providers as necessary
label | Standard/Specification - Aurecon Civil Spec 19.5
label | Verifying Document - Service Locate or Asbuilts / Sample Dig permit
label | Frequency - Prior excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | Engineer Rep Signature - I
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 - MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.1 - Aggregate MAR
label | Acceptance/Conformance criteria - Sub-Base to be ATAP40 and comply with TNZ M/4 specification for aggregate properties - At least seven working days prior to delivery of Sub-Base course the contractor shall deliver to the engineer the results of production property tests carried out by an IANZ accredited lab in accordance with the relevant NZ standards
label | Standard/Specification - Aurecon Spec 7.5.1
label | Verifying Document - Approved MAR / IANZ test report
label | Frequency - Once prior Sampling rate as per civil 6.5.1
label | Verification Activity: Activity - H
label | Verification Activity: By - DES
label | Downer Signature - H
label | Engineer Rep Signature - R
label | MSQA - I
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 - CONSTRUCTION ACTIVITY
checkpoint | 5.1 - Excavation
label | Acceptance/Conformance criteria - Set- out position completed RL marked. For excavation level
label | Standard/Specification - Aurecon Civil Spec Section 19.11.2
label | Verifying Document - ITP sign off
label | Frequency - In Process Check
label | Verification Activity: Activity - V
label | Verification Activity: By - SV
label | Downer Signature - V
label | Engineer Rep Signature - I
checkpoint | 5.2 - Site Clearance (Cut to Subgrade)
label | Acceptance/Conformance criteria - Area of work Cleared in accordance with Resource consent andlocal authority requirements. Discovery of unsuitable materials to be advised to the engineer and disposed of or repalced as directed.
label | Standard/Specification - Aurecon Civil Spec; Section 3.3 and 3.6
label | Verifying Document - ITP Sign off
label | Frequency - In Process Check
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | Downer Signature - V
label | Engineer Rep Signature - I
checkpoint | 5.3 - Discovery of antiques and valuables (If applicable)
label | Acceptance/Conformance criteria - Arcaheology: Works to be completed as per CMP Archaeoligical discovey protocol, records in site diary and Aconex sent to the Engineer. Antiques: Owners must contact the Heritage New Zealand for authority to proceed.
label | Standard/Specification - Aurecon Spec 3.10 and Heritage New Sealand
label | Verifying Document - ITP Sign off
label | Frequency - Upon Discovery (May not be Applicable)
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | Engineer Rep Signature - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Discovery of Contaminated or Hazardous Material (May not be Applicable)
label | Acceptance/Conformance criteria - Contaminated material or Waste exhibitning hazardous characteristics handled and removed asper work safe guidnlines and taken off site to be tested. Hazardous or contaiminted materials disposed at approved landfills only. Volume or any disposed hazardous or contaminated materials to be recorded.
label | Standard/Specification - Arecon Civil Spec 4.5.6 and management plan
label | Verifying Document - Disposal dockets (If applicable) /Site Diary (If applicable)
label | Frequency - Upon Discovery (May not be Applicable)
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Disposal of materials
label | Acceptance/Conformance criteria - Demolished Materials sorted as required and disposed of correctly. Materials or item salvaged for re-use as appropriate
label | Standard/Specification - Aurecon Civil Spec 4.5.7
label | Verifying Document - Daily Diary (If applicable)
label | Frequency - In Process Check
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
label | Downer Signature - I
checkpoint | 5.6 - Demolition and removal of obstructions
label | Acceptance/Conformance criteria - Submit works over approvlas for Relevant NUO's where utilities found. Confirm approval to remove structure or protection requirements as per Aurecon DRG's
label | Standard/Specification - Aurecon Civil Spec 4.5.5
label | Verifying Document - Email confirmation where applicable or works over permit algining with the consent
label | Frequency - Upon Discovery (May not be Applicable)
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | Engineer Rep Signature - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Tree Removal (If applicable)
label | Acceptance/Conformance criteria - Refer to Tree Management Plan, Tree Management plan certification and relevant resource consents/approvals
label | Standard/Specification - Resource Consent
label | Verifying Document - Resource consent
label | Frequency - Each Tree (If applicable)
label | Verification Activity: Activity - W
label | Verification Activity: By - PE/DES/ENG
label | Downer Signature - W
label | Engineer Rep Signature - I
label | MSQA - R
checkpoint | 5.8 - Services/Sun Surface infrastrucure removal
label | Acceptance/Conformance criteria - Existing services and drainage structures to be located where possble or as agreed with the Engineer. Pilot hole, disconnect or isolate live services prior to demolitions as required. Services or pipes to be abandoned are to be completely removed or grout filled as per drawing or approval by assest owner if different.
label | Standard/Specification - Aurecon Civil Spec 4.5.4 and 4.5.5
label | Verifying Document - Service As built
label | Frequency - As Encountered
label | Verification Activity: Activity - H
label | Verification Activity: By - PE/ENG
label | Downer Signature - H
label | Engineer Rep Signature - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.9 - Subgrade Testing
label | Acceptance/Conformance criteria - Contractor to Confirm subgrade strength and report to Engineer via Inspection. Clegg to CBR correlation to be confirmed and Clegg hammer results to be undertaken on Subgrade
label | Standard/Specification - Aurecon Civil Spec 5.6.11
label | Verifying Document - QA sheet
label | Frequency - Every 20m or as agreed by the Engineer
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | Engineer Rep Signature - R
label | MSQA - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.10 - Line and Level of subgrade
label | Acceptance/Conformance criteria - Pavement Subgrade tolerance +/-10mm from design subgrade level (or as applicable with existing services). Excavation depth must be at least the design pavement depth for LMC locations. Subgrade shape as per survey set out. To be verified on site.
label | Standard/Specification - Aurecon Civil Spec 5.6.9
label | Verifying Document - As builts
label | Frequency - Each Subgrade section
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | Engineer Rep Signature - R
label | MSQA - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.11 - Sub-Base Level and Shape
label | Acceptance/Conformance criteria - Construct lifts between 2.5 to 5X maximum stone size to ensure good compaction (100-200m). Surface shape, finished and tolerances shall comply with requirments of TNZ B/02- -25mm/+5mm to design FL measured between centreline and pavement edge
label | Standard/Specification - Aurecon Civil Spec 6.7.4 TNZ B/2
label | Verifying Document - QA cheetsb and as built survey
label | Frequency - Every 10m for each section of basecourse
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | Engineer Rep Signature - R
label | MSQA - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.12 - Sub base Compaction
label | Acceptance/Conformance criteria - Clegg testing of Sub0-base course to achieve CIV 25+
label | Standard/Specification - Aurecon Spec 6.1 and GCOR-0042
label | Verifying Document - QA sheets
label | Frequency - Every 10m for each section of basecourse
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | Engineer Rep Signature - R
label | MSQA - R
section | SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.1 - Construction Record Compilation
label | Acceptance/Conformance criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
label | Downer Signature - H
label | Engineer Rep Signature - H
label | MSQA - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Survey Record
label | Acceptance/Conformance criteria - Installation of works under contract completed compliant in accordance with all relevant regulations, COP and standards
label | Standard/Specification - Design Specification / Downer
label | Verifying Document - QA Checksheet, Redlines
label | Frequency - Post Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
label | Downer Signature - H
label | Engineer Rep Signature - H
label | MSQA - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Redline Drawings
label | Acceptance/Conformance criteria - Ensure all items have been installed create a Redline Drawings for Asbuilt creation noting all changes with RFI numbers and departures in red pen
label | Standard/Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
label | Downer Signature - H
label | Engineer Rep Signature - H
label | MSQA - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Defect, Snag and Punch List
label | Acceptance/Conformance criteria - Update the project defects, snag and punch list register
label | Standard/Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post Construction
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
label | Downer Signature - H
label | Engineer Rep Signature - H
label | MSQA - R
holdpoint | AUTHORITY HOLDPOINT