## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP - Foam Bitumen Stabilisation. Rev 0 | itp | ITP - Foam Bitumen Stabilisation |  | 4216c747-4808-4716-ab13-9261e9574f94
| section | 3.0. BITUMEN STABILISATION OPERATION
| checkpoint | 3.01 - Production Plan
| note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Prior to each section
| note | Inspection / Test method - Daily Report
| note | Acceptance Criteria - Points covered in NZTA B/5
| note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.02 - Weather conditions
| note | Detail of Activity / Test - Material behind stabiliser
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Prior to spreading
| note | Inspection / Test method - Measurement
| note | Acceptance Criteria - Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilsing Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 2.07 - Weather conditions
| note | Detail of Activity / Test - Wind
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Prior to spreading cement or lime
| note | Inspection / Test method - Local weather stations
| note | Acceptance Criteria - Wind speed < 25 km/hr
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilsing Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 2.08 - Weather conditions
| note | Detail of Activity / Test - Rain
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Prior to spreading cement or lime
| note | Inspection / Test method - Local weather stations
| note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilsing Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.01 - Stabilising Agents
| note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Per Batch
| note | Inspection / Test method - TNZ M/15
| note | Acceptance Criteria - Conform to Specification
| note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.02 - Stabilising Agents
| note | Detail of Activity / Test - Cement, GP
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Per Batch
| note | Inspection / Test method - NZS 3122
| note | Acceptance Criteria - Conform to Specification
| note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.03 - Stabilising Agents
| note | Detail of Activity / Test - Bitumen (130/150)
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Per Batch
| note | Inspection / Test method - M/1
| note | Acceptance Criteria - Conform to Specification
| note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.04 - Spreading of powdered stabilising agent (Cement / Lime)
| note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - every 400 m2, every 150m for a 2.4m width
| note | Inspection / Test method - Weigh mat or tray
| note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.05 - Spreading of powdered stabilising agent (Cement / Lime)
| note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - On-going measurement by computer/load cells
| note | Inspection / Test method - Measurement each run
| note | Acceptance Criteria - ± 2.5% of specified rate
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.06 - Injection of bituminous stabilising agent (FBS or BE)
| note | Detail of Activity / Test - Flow meter and operator's display readings
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
| note | Inspection / Test method - Visual display reading
| note | Acceptance Criteria - ± 5% of specified rate
| note | Record documents (QCP - Quality Control Portal) - N/A
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.07 - Injection of bituminous stabilising agent (FBS or BE)
| note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Record usage from PCU at the end of each run
| note | Inspection / Test method - Record readings at the end of each run
| note | Acceptance Criteria - ± 3% of specified rate
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.08 - Injection of bituminous stabilising agent (FBS or BE)
| note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - For each bitumen tanker load
| note | Inspection / Test method - Dip bitumen tanker before and after
| note | Acceptance Criteria - ± 2.5% of specified rate
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.09 - Injection & Mixing of Water
| note | Detail of Activity / Test - In-situ Stabilisation process
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - On-going visual assessment
| note | Inspection / Test method - Visual and hand squeeze test
| note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.10 - Depth of stabilisation
| note | Detail of Activity / Test - Depth of stabilisation
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - Every 200m
| note | Inspection / Test method - Measurement
| note | Acceptance Criteria - +15mm / -5mm from specified depth
| note | Record documents (QCP - Quality Control Portal) - Daily work Log
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - I
| note | Contractor - R
| checkpoint | 3.11 - FBS material
| note | Detail of Activity / Test - Stabilised material strength - ITS
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
| note | Inspection / Test method - NZTA T/19N: 2020
| note | Acceptance Criteria - Testing at 1mm/min:
| note | – BSM Dry ITS: 150 kPa to 400 kPa
| note | – BSM Soaked ITS: 120 kPa to 350 kPa
| note | ○ Testing at 50.8mm/min:
| note | – BSM Dry ITS: 180 kPa to 450 kPa
| note | – BSM Soaked ITS: 150 kPa to 420 kPa
| note | Record documents (QCP - Quality Control Portal) - IANZ Report
| note | Responsibility - Stabilising Contractor
| note | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
| note | Designer - I
| note | Eng. Rep - A
| note | Contractor - R
| checkpoint | 3.12 - Compaction
| note | Detail of Activity / Test - Plateau Density Test
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
| note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
| note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
| note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed.
| note | Responsibility - Stabilising Contractor
| note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
| note | Designer - I
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Compaction
| note | Detail of Activity / Test - Maximum Dry Density
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
| note | Inspection / Test method - NZS 4402.4.1.3
| note | Acceptance Criteria - For analysis of DoC
| note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squeeze test on site
| note | Record documents (QCP - Quality Control Portal) - IANZ Report
| note | Responsibility - Stabilising Contractor
| note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
| note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
| note | Designer - I
| note | Eng. Rep - A
| note | Contractor - R
| checkpoint | 3.14 - Compaction
| note | Detail of Activity / Test - Degree of Compaction (DoC)
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - 5 per 1,000m2
| note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
| note | Acceptance Criteria - Average DoC ≥ 98%, Minimum DoC ≥ 95%
| note | Record documents (QCP - Quality Control Portal) - IANZ Report
| note | Responsibility - Stabilising Contractor
| note | Designer - I
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.15 - Finished Pavement
| note | Detail of Activity / Test - Crossfall
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - every 20m
| note | Inspection / Test method - Measurement
| note | Acceptance Criteria - ± 0.5% of specified crossfall measure, 2m apart
| note | Record documents (QCP - Quality Control Portal) - Survey
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.16 - Finished Pavement
| note | Detail of Activity / Test - Stabilised width
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - 1 every 20m
| note | Inspection / Test method - Measurement
| note | Acceptance Criteria - -20mm, +100mm
| note | Record documents (QCP - Quality Control Portal) - Survey
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.17 - Finished Pavement
| note | Detail of Activity / Test - Surface Shape
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - every 20m
| note | Inspection / Test method - Measurement
| note | Acceptance Criteria - < 10mm using 3m straight edge
| note | Record documents (QCP - Quality Control Portal) - Survey
| note | Responsibility - Stabilising Contractor
| note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
| note | Designer -
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.18 - Finished Pavement
| note | Detail of Activity / Test - Surface Levels
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - every 20m
| note | Inspection / Test method - Measurement
| note | Acceptance Criteria - -5mm, +15mm
| note | Record documents (QCP - Quality Control Portal) - Survey
| note | Responsibility - Stabilising Contractor
| note | Designer -
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Finished Pavement (1)
| note | Detail of Activity / Test - Surface Finish
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - Per Lot
| note | Inspection / Test method - Visual
| note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
| note | 2. Smaller aggregate held in place by fine material
| note | 3. matrix does not displace under normal trafficking and/or sweeping
| note | Record documents (QCP - Quality Control Portal) - Survey
| note | Responsibility - Stabilising Contractor
| note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
| note | Designer -
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Finished Pavement (2)
| note | Detail of Activity / Test - Roughness
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - Before Sealing
| note | Inspection / Test method - TNZ TM 7003 v1
| note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
| note | Record documents (QCP - Quality Control Portal) - Test Certificate
| note | Responsibility - Contractor
| note | Designer -
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
| note | Detail of Activity / Test - Clegg Impact Value
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - 5 per 1000m2
| note | Acceptance Criteria - CIV ≥ 50
| note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
| note | Responsibility - Stabilising Contractor
| note | Designer - I
| note | Eng. Rep - A
| note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.21 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
| note | Detail of Activity / Test - Degree of Saturation, DOS
| note | Action (Hold, Monitor, Witness) - M
| note | Minimum Test Frequency - 5 per 1000m2
| note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
| note | Acceptance Criteria - aim for DOS ≤ 80%
| note | Record documents (QCP - Quality Control Portal) - IANZ report
| note | Responsibility - Contractor
| note | Project Specific Notes / Instructions - Report only
| note | Designer - I
| note | Eng. Rep - A
| note | Contractor - R
| section | 4.0. FINAL SIGN OFF
| checkpoint | 4.01 - Pavement Layer Signoff
| note | Detail of Activity / Test - Assessment of all test results for conformity
| note | Action (Hold, Monitor, Witness) - H
| note | Minimum Test Frequency - Each Lot
| note | Inspection / Test method - Site Inspection
| note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
| note | Record documents (QCP - Quality Control Portal) - NCR
| note | Responsibility - Engineers Representative
| note | Designer -
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
| textbox | Contractor's Rep Name:
| textbox | Engineer's Rep. Name:
| date | Date:
| signoff | Add Signature