## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-015 - Sign Installation | itp |  |  |  |  | ITP-015 - Sign Installation
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Signage Conformance
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
label | REFERENCE DOCUMENTS: Drawings, AS 1742
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Service Identification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
label | REFERENCE DOCUMENTS: DBYD, Service chart
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Post & Foundations
label | FREQUENCY: Prior to Start
label | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | REFERENCE DOCUMENTS: 714.06
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Signage Install
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
label | ○ Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
label | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | REFERENCE DOCUMENTS: AS 1742, TS 1313 Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-029 - PVC TGSI Installation | itp |  |  |  |  | ITP-029 - PVC TGSI Installation
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check Materials
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | REFERENCE DOCUMENTS: Receivable Inspection List
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
label | ○ Line and level of tactiles shall be set out according to design levels to suit new kerb height (if applicable).
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer, Client
textbox | Date Completed:
section | Construction of Access Ramp Bluestone Footpath
checkpoint | 2.1 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: TGSI should be laid in accordance with the site specific application and applicable standards before fixing
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Placement of TGSI
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure the placement of the TGSI are in accordance with IFC drawings and are compliant to AS1428.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Completion
checkpoint | 3.1 Completion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure pavement area is free of debris and waste.
label | REFERENCE DOCUMENTS: Visual Inspection
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-036 - Kerb Access Ramp Bluestone Footpath | itp |  |  |  |  | ITP-036 - Kerb Access Ramp Bluestone Footpath
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Existing Bluestone Kerb Demolition
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
label | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
label | ○ Bluestone shall be salvaged and re-used in new kerb alignment where possible
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Check Materials
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | REFERENCE DOCUMENTS: Receivable Inspection List
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
label | ○ Line and level of bluestone pavers, tactiles and inlay shall be set out according to design levels to suit new kerb heights.
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction of Access Ramp Bluestone Footpath
checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels.
label | ○ Bluestone kerb shall be placed on a bed of low slump, 20 Mpa concrete of 75mm minimum thickness.
label | REFERENCE DOCUMENTS: IFC Drawings, CoM Bluestone Paving Specification
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.1 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling
label | ○ After placing and vibration, the concrete shall be screeded and trowelled to the correct level.
label | REFERENCE DOCUMENTS: CoM Bluestone Paving Specification
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Mortar Bed
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base
label | ○ All pavers shall be coated in mortar slurry on rear face before laying
label | REFERENCE DOCUMENTS: Dwg 1P50201
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Cutting of Pavers
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.6 Placement of bluestone pavers
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402.
label | ○ Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
label | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.7 Curing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic
label | ○ Where required, ply shall be laid over area of works
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.8 Grouting
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
label | REFERENCE DOCUMENTS: Manufacturers Specifications
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.9 Installation of Versatac Granite Tactiles and Granite Inlay
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201.
label | REFERENCE DOCUMENTS: Dwg 1P50201
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Completion
checkpoint | 4.1 Completion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste
label | ○ Bluestone pavement is free of mortar stains and cleaned to satisfaction
label | REFERENCE DOCUMENTS: Visual Inspection
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: