## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
114fbf73-e64f-459a-a88c-325a9c0e0f86 | checklist | 1.01 - Drainage - Pipe Laying | itp | 1.01 - Drainage - Pipe Laying | c8446a39-d9fa-4275-83ab-d78bfabc8bd2
11933fe0-ac09-42a4-9a18-1dd1a3e4db98 | section | 1.0 Preliminary Works
b3bfdabd-af08-415a-ab6a-13a6427cb084 | checkpoint | 1.1 - Pre-commencement documentation in place.
3b47b27a-daef-5008-bb24-aeaf3d410d96 | note | Frequency - Prior to Commencing
b0ab5d77-f7e2-537c-ab3f-f8e8e8247b17 | note | Acceptance Criteria - All personnel and plant have been inducted to the K-Road project. Client has received and approved all pre-commencement documentation including SWMS, PMP, EMP, QMP, SMP and TGS plans.
5edcb883-f265-55ec-9153-3c139e17a28a | note | Reference Documents - OH&S Act 2007 FH Documents
700b6b61-7441-5c9e-8146-be490c5c98f2 | note | Inspection / Test Method - Document review
67233c73-1453-5b11-bd44-467ffd03faaf | note | Record of conformity - Personnel/Plant Inducted SWMS Signed
23321880-c667-5fbe-9b16-7fb286df41d3 | note | WP
9f8c095c-4951-5383-a0d6-cb69327fbe6c | note | Responsibility - Site Engineer / Site Foreman
1d291a81-e782-48ef-93d0-14427651809c | checkpoint | 1.2 - Relevant Permits Issued
2a48331d-d981-579d-9034-7c617406a03a | note | Frequency - Prior to Commencing
3078bab6-fcff-51f4-b4de-1fcf560b5233 | note | Acceptance Criteria - Current excavation permit is in place and signed by Site Foreman. Any excavation greater than 1.5m has an approved Trenching Notification submitted to Worksafe.
36625176-dad3-5147-b464-907bfe300c2c | note | Reference Documents - Permit Review
d6ab8906-293e-5a27-bb78-6eff441c2fc1 | note | Inspection / Test Method - Document review
88d4b158-5be2-5471-923b-1a84ca6b49c5 | note | Record of conformity - Excavation Permit
b4003526-52b2-5a4d-8cc7-53f643ec5a6c | note | WP
70c0d7a3-a07a-564f-b94f-88de542ae80b | note | Responsibility - Site Engineer / Site Foreman
0efeeae2-2535-4ffd-9399-2d4e3f4ceace | checkpoint | 1.3 - Precast Materials Inspection and Compliance
94546952-120d-542a-9792-f0626cff7b2a | note | Frequency - Each Delivery
fe3bde42-4410-543b-94db-c0d7f74f5dac | note | Acceptance Criteria - Precast materials have been inspected and are free of chips, cracks and no exposed reinforcement.Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058.
ca32be02-08ad-5592-a305-25e1ac95518c | note | Reference Documents - DTP 701.05 Engeny Water Management Specification Cl 21.2
05d8d46d-357f-5e63-ab99-5a7e8e34d9df | note | Inspection / Test Method - Visual Inspection
0ec1490d-0a38-5779-bff0-917bd54eda7b | note | Record of conformity - Signed ITP
be2096b9-7f78-5b8e-b75e-c9d3370350d7 | note | WP
2df97e16-9ffa-5b43-99f3-ef942a8779c9 | note | Responsibility - Site Engineer / Site Foreman
c505f6db-807a-408b-b17c-cd0c9604b763 | checkpoint | 1.4 - Service locating and NDD proving
c1c75c98-6305-59b9-8aa5-8613ae9a9e33 | note | Frequency - Prior to Commencing
8a619627-1ef1-539a-a8e2-402188039204 | note | Acceptance Criteria - Prior to commencement of excavation works, a BYD request will be submitted and any known services in the area will be located and physically proven every 5m interval.
56d6fbde-98a6-51d9-b1f9-9dc76f993897 | note | Reference Documents - BYD Information
aa777c9e-4239-56bc-bdfa-450a14eb3ee6 | note | Inspection / Test Method - Verify
c0a89984-9e9e-5369-b20d-bf8aa20dd16e | note | Record of conformity - Signed ITP
94ccafdc-add1-58a5-9e79-711a62272eb5 | note | WP
e7abb189-649c-53ba-82cc-9f460a0f0e08 | note | Responsibility - Site Engineer / Site Foreman
11d99066-2d38-4c54-bdce-6e17563a63c6 | checkpoint | 1.5 - Conformity with Drawings
70e3c08c-9554-5fa7-89d8-748b6c2f333c | note | Frequency - Prior to Commencing
9ebe3206-fca6-527f-8f72-7289d9733f33 | note | Acceptance Criteria - Prior to commencement of excavation for the pipes the Contractor shall confirm the position of all pipes with the Superintendent.
7304484f-c29d-50a1-9697-45987bf07873 | note | Reference Documents - DTP 701.1
9ab54ef4-3e70-5ed5-a516-eaee06a14bc1 | note | Inspection / Test Method - Site Inspection
5ec61d0a-12a9-5e59-baaa-e570d8566d09 | note | Record of conformity - Signed ITP
0eabee8e-a846-5799-bfc7-b6ade101739f | note | HP
957aa771-31d0-5a8d-8682-f4b691974d7f | note | Responsibility - Project Engineer / Site Foreman
848f43b0-1720-48a5-bb04-20a12dd1845f | signoff | AUTHORITY HOLDPOINT
9aafac52-c2a1-4c9b-9ee6-a9c3fce1363a | checkpoint | 1.6 - Material Conformance Bedding & Backfill
d7ef5399-6b21-563a-9ee1-bc8bcdc02a7e | note | Frequency - Prior to Commencing
bc64aaf7-5896-557e-b361-c852e835dca1 | note | Acceptance Criteria - Materials used for bedding and backfill shall be free from perishable mater and lumps. Grading as per table 701.081. PI max should be 20. Grading and PI tests to be carried out as per frequency nominated in Engeny Water Management Specification Appendix B.
44a2163a-5d26-59f4-8e47-3ff009147a05 | note | Reference Documents - Engeny Water Management Specification Appendix B DTP 701.09
3f6cd880-271c-5558-b341-b59f3ba133a5 | note | Inspection / Test Method - Verify
6152f85f-9552-5a4a-8629-3b82be190d46 | note | Record of conformity - Material Conformance Documents
5c08dc55-9daa-5fd1-8f40-50b542dbd690 | note | WP
715f2ec4-5584-5806-9ee9-34b24e54c802 | note | Responsibility - Site Engineer / Site Foreman
9e2fffdf-4f34-46b5-91b7-4637c4e04faa | section | 2.0 Construction Works
be5af7d2-354b-4e49-ae98-3282f362f335 | checkpoint | 2.1 - Set out of drainage
a27d2cd4-7e79-5627-bdb0-0bbd93b8dc27 | note | Frequency - Prior to Commencing
cd351c2d-a1c1-5a5a-927c-7eae27f75e9d | note | Acceptance Criteria - The position of all drainage lines are to be confirmed with the Superintendent. Survey pegs set-out at two different offsets.
ff6dcf04-e045-52c6-9149-c37e5f70da83 | note | Reference Documents - Engeny Water Management Specification Cl.11.1
54704862-3fdd-5592-aca9-1535657c9718 | note | Inspection / Test Method - Visual Inspection
5d294567-499a-5a2f-8a63-35e8d5252860 | note | Record of conformity - Signed ITP
5bfadba8-0fb9-585b-9689-a14f660c412b | note | HP
7c2e97cd-de21-527d-9115-312ea08441db | note | Responsibility - Project Engineer / Site Foreman
782f7578-6bce-4603-a225-5cbd85bf2935 | signoff | AUTHORITY HOLDPOINT
84b14e0d-f23d-4fc5-9029-74482f53db9c | checkpoint | 2.2 - Trench and Bedding Preparation
8bc96986-9436-59b5-8004-40eb864ca51d | note | Frequency - During Excavation
7a6ec10b-3d45-51d1-934c-092fef183591 | note | Acceptance Criteria - Trenches shall be inspected by the Engineer prior to the laying of pipe or placement of bedding sand within the trench. The base width and invert level of the trench shall be surveyed prior to the laying of pipe or the placement of bedding sand.
e71cd783-562d-5dab-b16f-d2e239272432 | note | Reference Documents - Engeny Water Management Specification Cl.21.4.1
d289e432-b9bd-54ec-859c-6666289d2e50 | note | Inspection / Test Method - Site Inspection
00b5bdca-f3d0-5520-b7b2-2caaf94addc9 | note | Record of conformity - Signed ITP
173331a8-d40c-5b68-82d5-605a4cc33cc3 | note | HP
b5fd5e7e-834b-5b57-a926-e6eac1d79e59 | note | Responsibility - Project Engineer / Site Foreman
d28534a7-2ccc-4cd9-9ba9-bcdb4c5250b7 | signoff | AUTHORITY HOLDPOINT
996d4577-0400-4d3f-9e68-051db91bd409 | checkpoint | 2.3 - Geotextile Wrap (where applicable)
e7c819d3-54ef-5397-b9b2-e47d983711da | note | Frequency - During Excavation
024342c7-f4cd-5ccc-9dec-eb942d6275a4 | note | Acceptance Criteria - Trench to be fully laid with Bidim 34 Geotextile where groundwater is likely to be encountered (only where determined by Engineer).
62acfe6d-b90a-5247-a47f-9c385e278606 | note | Reference Documents - DTP 702.06
a660ada8-5ee5-537e-a202-53202948d582 | note | Inspection / Test Method - Site Inspection
dc5f8139-3eb6-5c2f-bfc9-587889450e69 | note | Record of conformity - Signed ITP
36b6aa95-9581-553d-884d-ce367528141f | note | IP
a77a7487-681e-5538-a768-1065e4ef2b29 | note | Responsibility - Site Engineer / Site Foreman
67ef734c-91f8-4639-9c93-5dc32340aff7 | checkpoint | 2.4 - Place bedding material & compact
fc848566-ce80-5557-92fe-006872a5100f | note | Frequency - During Excavation
95a76716-6796-5594-9368-6a841bf4eae8 | note | Acceptance Criteria - Bedding material shall be compacted to no less than the below thickness: - 100mm where D < 600mm - 150mm where D > 600mm
da663a49-5b8b-5d9b-910c-48432ed9e92a | note | Reference Documents - MW 72551/08/419
d4f5a831-b075-529a-a6c6-6f0c5a5f9813 | note | Inspection / Test Method - Visual Inspection
eae93723-f6df-5951-808a-ebe89b2ad0fc | note | Record of conformity - Signed ITP
122c9c6e-c4db-5434-a917-024a4acdc609 | note | IP
317e042b-6157-52b2-bd06-be0891923219 | note | Responsibility - Site Engineer / Site Foreman
f46392cd-0f0a-41a7-b344-befdf174848a | checkpoint | 2.5 - Place pipes
24a313d5-7f8e-586b-9472-330980870718 | note | Frequency - During Excavation
5465bf3c-1628-5505-8a5b-26c587805d09 | note | Acceptance Criteria - Pipes to be placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied.
f9c13ead-7e3b-50e9-8131-71e078e61875 | note | Reference Documents - DTP 701.17
88647a6d-e908-5250-9a17-163fa9d0f596 | note | Inspection / Test Method - Visual Inspection
846db670-811d-5cdd-809d-abe84c7785b9 | note | Record of conformity - Signed ITP
d116313e-a8f0-5726-a859-77a1bd0810ef | note | IP
28092506-e844-59d1-a179-e145328853d2 | note | Responsibility - Site Engineer / Site Foreman
5caa024f-5761-4edd-9cbb-a59a2128f4cb | checkpoint | 2.6 - Pipe Inspection
ba8a0a47-755f-5023-94c8-93172fb8b2a4 | note | Frequency - During Excavation
87879348-885e-59e0-9685-35dded2c1e44 | note | Acceptance Criteria - Once the pipe is joined and laid to the lines and levels shown on the Drawings, the Engineer must perform an inspection.
0a6a25b6-8471-5a35-accc-e84f6ecee5de | note | Reference Documents - Engeny Water Management Specification Cl.21.4.6
10bb6195-1187-535a-83ca-59c2b90c8bc4 | note | Inspection / Test Method - Visual Inspection
1475a198-18dc-5abf-9764-b73996fbe48d | note | Record of conformity - Signed ITP
6c9008d5-315a-56f0-a5ff-188d04974051 | note | HP
e0655ad7-6eb7-51b0-bbd6-05ca0f7f46d6 | note | Responsibility - Project Engineer / Site Foreman
b523a38c-fef2-4e38-aa62-25df238c0828 | signoff | AUTHORITY HOLDPOINT
4e205917-3398-48db-843f-8647672cf481 | checkpoint | 2.7 - Pipe Backfill - Side and Overlay Zones
bb53b45a-ebb7-5eb8-a476-88741b9183a8 | note | Frequency - During Excavation
da24f26b-8269-5b14-a93b-2b3bbeea0ee4 | note | Acceptance Criteria - Side and Overlay Zone backfill shall be placed in maximum lifts of 150mm and compacted to the approved standard. Backfilling shall proceed as rapidly as construction and testing of work allows. The placed backfill material shall conform with the material and compaction properties of General Fill – Side and Overlay listed in Appendix B of Engeny Water Management Technical Specification.
026869e6-0b84-5555-8a90-2fb9510abbfe | note | Reference Documents - Engeny Water Management Specification Appendix B. IFC Design Drawings
67bc9fbe-a0f6-5dd8-8a8a-a5203c1233cf | note | Inspection / Test Method - Site Inspection
6541a67e-efd5-52bf-af18-5e5328f13859 | note | Record of conformity - Signed ITP
ecb0cee9-7f56-5191-9185-708cbed1ed84 | note | HP
e74f659c-81fc-5337-9ccc-878f7dc3a86a | note | Responsibility - Project Engineer / Site Foreman
d3a6a95a-c1d1-43ba-8cea-ffd423f8a18a | signoff | AUTHORITY HOLDPOINT
d41b8c83-1f11-4547-8e1e-4393f2f61aca | checkpoint | 2.8 - Subsoil drains (where applicable)
388a222e-3298-514a-bd8f-245a84ebc3ab | note | Frequency - During Excavation
9d7c3cde-9acf-5e69-94a2-45c7dd6eadbd | note | Acceptance Criteria - Ø100 VicRoads Class 1000 subsurface drain to be contrained within 300 x 300mm granular filter material fully wrapped in Bidim A34 Geotextile installed on road side only of trench.
cf6488bd-3156-5bcf-9dcf-053ad0448654 | note | Reference Documents - DTP 702.05
c307cc95-5eeb-5b89-a88a-7073fee7d6bc | note | Inspection / Test Method - Site Inspection
4fb1a92b-c446-5812-a984-1c5d541effff | note | Record of conformity - Signed ITP
c7cdcd52-226b-5b74-9532-dce702ddf332 | note | IP
58bf7218-beb1-5edc-8cdc-064d83723ecc | note | Responsibility - Site Engineer / Site Foreman
b8239158-af1f-4bc9-a1f3-f97736b05e6e | checkpoint | 2.9 - Repairs to damaged pipes
7683cc62-8ff8-5391-8644-44ba86c41d44 | note | Frequency - Each damaged pipe
4e41048c-93b3-5fb1-9c62-8aea7d4feb64 | note | Acceptance Criteria - No repairs shall be undertaken without the superintendents approval of the repair materials and procedures All repair procedures undertaken in accordance with Cl 701.25
3afae192-9e15-5619-bb2f-75ee21d1de45 | note | Reference Documents - 701.31
90bcb13e-cad1-5254-ab1c-4e189ecf63c7 | note | Inspection / Test Method - Verify
502cf184-6ead-5918-8ca9-90140ed8c513 | note | Record of conformity - ITP Signed
a615fee4-a312-592b-83d8-629473048e9d | note | HP
d3e26d14-364e-5ddd-b291-a8b9ebca2c73 | note | Responsibility - Project Engineer / Site Foreman
ec8a3d85-767f-4c4f-b6b5-e577a371afbe | signoff | AUTHORITY HOLDPOINT
4d4d7e4f-c472-4a81-bffa-375986a83c20 | section | 3.0 Testing & Completion
bc67870c-9b88-48ab-8fa2-866c497bc02b | checkpoint | 3.1 - Compaction testing of bedding material (Concrete pipe bedding and haunch material).
1fcabe01-ec4d-5331-bb93-c57c3c8f30ff | note | Frequency - As per Specification
816fb2ba-c022-59b7-9b69-40c2a7fd8e8d | note | Acceptance Criteria - Bedding, haunch and overlay material shall be 5-7mm "A Grade" crushed rock compacted to >95% Dry Density Ratio (RD) and 70% Density Index (ID). Compaction frequency shall be 1 test per 2 layers per 40 linear metres. PSD & Atterberg 1 test per 100m3.
d98d144a-ea39-5783-ad27-4c29712d0cb7 | note | Reference Documents - Engeny Water Management Specification Appendix B. MW 7251/08/419
c453deba-3282-5593-93f0-707e32fcc91e | note | Inspection / Test Method - Verify
396af111-b4f1-597e-aac1-861d9e26891a | note | Record of conformity - Test Reports
60395a6a-2378-5433-a9c8-a85ecf066401 | note | TP
ac8a45bd-8655-5219-89b8-0a7009ba8def | note | Responsibility - Site Engineer / Site Foreman
1d3b7fa4-678e-4658-9296-6602917a06a8 | checkpoint | 3.2 - Compaction testing of bedding material (Poly pipe bedding and haunch material).
6a178ac3-8bd5-5c16-bdc7-ebf182aaee22 | note | Frequency - As per Specification
9d7f7f20-2278-52c3-8aad-a12695046216 | note | Acceptance Criteria - Bedding and embedment material shall be 5-7mm crushed rock compacted to >95% Dry Density Ratio (RD) and 70% Density Index (ID). Compaction frequency shall be 1 test per 2 layers per 40 linear metres. PSD & Atterberg 1 test per 100m3.
3c3df960-83b6-5dff-a8df-655aef87e9ec | note | Reference Documents - Engeny Water Management Specification Appendix B.
dde282bc-d35c-5b29-945b-717a6d033bdd | note | Inspection / Test Method - Verify
d92c41e5-ca08-576a-87d5-6f95f43405a7 | note | Record of conformity - Test Reports
6bea093f-36f2-52c9-9bef-830d37dd8de1 | note | TP
7f549e55-d356-55ae-aef0-b044575b2d87 | note | Responsibility - Site Engineer / Site Foreman
41ca94e1-0a28-4832-9b02-426689bd1a64 | checkpoint | 3.3 - Compaction testing of backfill material (Pipe top backfill material - Site Won).
6804dd24-e43c-5df0-89ed-3ab1f9224d9f | note | Frequency - As per Specification
ce3655d0-a756-5de1-8946-1b54e515630f | note | Acceptance Criteria - Backfill material that is site won and classified as "General Fill" shall be compacted to >98% standard MDD. Compaction frequency shall be 1 test per 2 layers per 40 linear metres. OMC -2% to OMC +2%. PSD & Atterberg 1 test per 100m3.
e4ba102a-582b-531d-8be3-659171c95c72 | note | Reference Documents - Engeny Water Management Specification Appendix B.
06c5aee1-c7d8-5272-b9b8-0075e99d0068 | note | Inspection / Test Method - Verify
fd442592-ed2f-51a6-b052-66b434bd1c63 | note | Record of conformity - Test Reports
d035b1b1-fbee-51e6-9dee-549dec5fa90a | note | TP
e8961e58-77dc-55a7-8ea4-6d203e055dbb | note | Responsibility - Site Engineer / Site Foreman
9fa7e5ba-7f33-4d8a-b5fe-b1e45e290126 | checkpoint | 3.4 - Compaction testing of backfill material (Pipe top backfill material - Trafficable Areas).
23dc1469-8d9f-5b5c-b9e2-93cb9768bed9 | note | Frequency - As per Specification
bea89ae2-db9f-50ef-b570-7f0d217c2fa4 | note | Acceptance Criteria - Backfill material shall be 20mm FCR CL3 compacted to >98% standard MDD. Compaction frequency shall be 1 test per 2 layers per 40 linear metres. OMC -2% to OMC +2%. PSD & Atterberg 1 test per 100m3.
212c4e42-4de4-5b44-ad5a-878186282b9f | note | Reference Documents - Engeny Water Management Specification Appendix B. DTP 812
5b54e5e9-108c-550c-9a12-62bc33359c8e | note | Inspection / Test Method - Verify
4dbe324b-836f-5596-aec3-bfc456178394 | note | Record of conformity - Test Reports
941a1938-178e-53c0-995a-158e7af883e8 | note | TP
ff2220a6-609e-541a-af1b-ef9b216fff3a | note | Responsibility - Site Engineer / Site Foreman
4b337d8a-65bc-4b6f-bb0c-f9227da1b08d | checkpoint | 3.5 - CCTV Inspections
390f3dbc-f905-5d93-8cfa-7c3f7ac117b9 | note | Frequency - After Completion
ab185ff2-a61a-511f-a4d5-1c42c7499d5f | note | Acceptance Criteria - CCTV inspection of all constructed pipelines for review and approval prior to Practical Completion of the Works.
679916fb-6d51-566c-b9cd-e9523531356a | note | Reference Documents - Engeny Water Management Specification Cl.21.4.8
cd851920-f236-5576-9689-8f6d2ebdb052 | note | Inspection / Test Method - Site Inspection
d338fc42-2c90-570f-82be-752ee55322cf | note | Record of conformity - Signed ITP
802fb1d4-2d4f-5b81-94e1-3a4e1024cd03 | note | HP
3c7cc459-19e4-5652-94cf-11b014579048 | note | Responsibility - Project Engineer / Site Foreman
fe6c33a1-dfdc-4d87-8633-04aebe2d80ef | signoff | AUTHORITY HOLDPOINT
2d840424-cd51-413f-a22c-ff6562090bbc | checkpoint | Final Inspection
c74cdc04-d31e-50a6-9165-a02c891c744e | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
9dc95bf2-d9a0-50c1-970f-f95eb211d666 | textbox | Print Name:
a9070e9e-9eb1-5535-9ea5-9711167b7b38 | textbox | Position:
d5284498-d1f5-51c4-b63a-40655c0db9bb | date | Date:
4dc9c6a4-03c2-4894-bdab-f0dc8e49dd4c | signoff | Sign ITP
b2cbca49-7b7d-4166-af2f-d411ece1c209 | checklist | 1.02 - Drainage - Pits | itp | 1.02 - Drainage - Pits | e62a62e7-d2ec-49a3-8ffa-b97b1093979b
98626467-c5eb-416f-a5dd-bcf029d40187 | section | 1.0 Preliminary Works
32afb1be-c873-4be0-aa63-f15cc586492e | checkpoint | 1.1 - Pre-commencement documentation in place.
b9d64325-3c9b-53b3-b502-773e0517ca68 | note | Frequency - Prior to Commencing
dc4e1a57-0429-5541-822c-048c87e2d098 | note | Acceptance Criteria - All personnel and plant have been inducted to the K-Road project. Client has received and approved all pre-commencement documentation including SWMS, PMP, EMP, QMP, SMP and TGS plans.
d0b14d6e-6d7b-57bb-838b-001761dfb9ad | note | Reference Documents - OH&S Act 2007 FH Documents
9a358759-7430-5590-8726-2f432f278e12 | note | Inspection / Test Method - Document review
7c1a050f-eb3b-581e-9030-74446044b7f9 | note | Record of conformity - Personnel/Plant Inducted SWMS Signed
28f0350a-6a39-54c5-9c01-8a050fcf1b50 | note | WP
660dfe4f-8ce5-5130-a9ef-5e2951c471c8 | note | Responsibility - Site Engineer / Site Foreman
755c93a5-a1fb-4f73-9f23-ad7e5d6f654d | checkpoint | 1.2 - Relevant Permits Issued
9331e262-9380-569c-aca9-1796dbf0fcd7 | note | Frequency - Prior to Commencing
60686427-595f-5dea-98ad-8ef6b57a08df | note | Acceptance Criteria - Current excavation permit is in place and signed by Site Foreman. Any excavation greater than 1.5m has an approved Trenching Notification submitted to Worksafe.
7f49379e-6933-5d23-af1e-5c8644e79ca8 | note | Reference Documents - Permit Review
2e2643eb-c1c9-5ea8-86b9-57bf08274cd1 | note | Inspection / Test Method - Document review
3691e134-5627-50f6-a152-ee0a61b94b94 | note | Record of conformity - Excavation Permit
6ebaf2c5-7258-5953-a822-6a92d0434087 | note | WP
6e2193f4-d705-5408-9c63-3a4b8f3eda39 | note | Responsibility - Site Engineer / Site Foreman
a807d288-9fe4-4635-ba30-4b3f7f685b6e | checkpoint | 1.3 - Precast Materials Inspection and Compliance
426652e7-5a32-583b-9a3a-2bc728a9b0d7 | note | Frequency - Each Delivery
90530a6a-5c19-5b15-a074-316f7965cb68 | note | Acceptance Criteria - Precast materials have been inspected and are free of chips, cracks and no exposed reinforcement.Precast Reinforced Concrete Pits shall comply with requirements of DTP Section 610 and 611.
cd9f873a-44b1-5892-b8d3-0683e9e1236b | note | Reference Documents - DTP 705.04 Engeny Water Management Specification Cl 21.2
e330680a-c83d-5efd-9295-cad44181db12 | note | Inspection / Test Method - Visual Inspection
6a8d37ba-fdfc-5eb3-b9fa-95c2ee590fc9 | note | Record of conformity - Signed ITP
d9e363fb-93ea-5c21-86f5-6f04e8058091 | note | WP
db90b969-3b35-5ae9-b92f-d83582a19325 | note | Responsibility - Site Engineer / Site Foreman
ce841d82-9dd9-4a9e-b7b2-0498477f06d5 | checkpoint | 1.4 - Service locating and NDD proving
215bd97d-6a10-575c-ad67-904607cc3c37 | note | Frequency - Prior to Commencing
48f67e96-790d-5ff4-b08c-86e16d84b83f | note | Acceptance Criteria - Prior to commencement of excavation works, a BYD request will be submitted and any known services in the area will be located and physically proven every 5m interval.
e4a54901-852b-501f-8720-18a11d58b7b6 | note | Reference Documents - BYD Information
8863bc90-3285-5bb1-84db-85ebec46d280 | note | Inspection / Test Method - Verify
4b94e04d-185a-57c6-87e3-9c2728382dad | note | Record of conformity - Signed ITP
2348ffdb-f309-5254-af8d-76ae854e7237 | note | WP
e624c429-4a7e-5d6b-b5d4-5d05793e2561 | note | Responsibility - Site Engineer / Site Foreman
0d06b12c-6d8f-40f0-9a3c-99e66dc79c53 | checkpoint | 1.5 - Conformity with Shop Drawings
d67608f3-9441-55e1-a0a7-f98910f9fd88 | note | Frequency - Prior to Commencing
f9b5bfd1-e8a2-5411-8589-efaf01f64417 | note | Acceptance Criteria - Prior to casting precast concrete pits the Shop Drawings have been reviewed and approved by the Client Representative. Precast pits are to be supplied by a VicRoads certified precast concrete manufacturer producing shop drawings for individual pits.
b04c3d8f-3ab3-5b42-b80e-47641732df09 | note | Reference Documents - Supplier Shop Drawings
605a0cfb-aa94-5ce2-be67-41493b61a7d2 | note | Inspection / Test Method - Document review
87d401d5-ebcf-532d-bb33-6a9a8c09a868 | note | Record of conformity - Signed ITP
d1963911-fc87-51f0-891a-ccd5424ad2d2 | note | HP
e518156a-db04-51fd-8902-6dfd9428721d | note | Responsibility - Project Engineer / Site Foreman
47392d30-6f4f-4a95-9bf3-98fbc1b72bcf | signoff | AUTHORITY HOLDPOINT
993365d1-388b-430d-8107-10cc5ba2b89a | checkpoint | 1.6 - Concrete Mix Design
ee639c54-e818-57a0-ae15-720dd4be362f | note | Frequency - Prior to Commencing
51250284-cd61-58e1-bca6-0695eab529a8 | note | Acceptance Criteria - The Contractor shall submit their preferred mix design for each strength grade incorporated into the design to the Company’s Representative a minimum 5 working days prior to concrete placement for review and approval. Details of concrete supplier, grade N40 - Structural Concrete and N20 - Blinding Concrete, slump and types to be included.
93a2cf16-c2de-5966-a63e-14ac1176b48b | note | Reference Documents - Engeny Water Management Specification Cl24.4.1
15d749e5-b485-5f4c-a4d6-397bf92240a8 | note | Inspection / Test Method - Document review
22834964-2420-5e2d-8ace-441cc50273a8 | note | Record of conformity - Signed ITP
8baaa558-a22e-5768-9ea9-bc47926f3f83 | note | HP
029df5af-e397-556d-a919-2d1936817276 | note | Responsibility - Project Engineer / Site Foreman
7b4bb3e0-b039-444b-8da1-10eff67a5894 | signoff | AUTHORITY HOLDPOINT
c9d705e5-3fe0-49c4-89a2-30018ade5775 | checkpoint | 1.7 - Backfill Material Conformance
f34124ef-a8e9-5cfa-af51-5ac6812dc984 | note | Frequency - Prior to Commencing
3ecb976b-fabe-5c73-bf61-d64ce93a5ef0 | note | Acceptance Criteria - Materials used for backfill shall be free from perishable mater and lumps. Grading as per table 701.081. PI max should be 20. Grading and PI tests to be carried out as per frequency nominated in Engeny Water Management Specification Appendix B.
2ac851d5-f990-5de9-a7f4-a74393b25cda | note | Reference Documents - Engeny Water Management Specification Appendix B DTP 701.09
ee770951-2178-56d9-8b00-e8e46b4ff2be | note | Inspection / Test Method - Verify
5e74aae7-1c78-56a5-af9c-fdfcde74950b | note | Record of conformity - Material Conformance Documents
0c430c36-539a-5f7d-be60-44a7ee29e689 | note | WP
5f435d81-539d-500d-aa2f-bf1e22365b0e | note | Responsibility - Site Engineer / Site Foreman
744a9cfe-50de-42fc-9108-5d8ce3fba87a | section | 2.0 Construction Works
b070618f-6236-498c-b5ac-b41f804aa744 | checkpoint | 2.1 - Set out of drainage
c10ad0e5-7e3e-5ff8-a68b-c0614eae72c8 | note | Frequency - Prior to Commencing
9d7f3bcb-94a3-50fc-9ebd-7f9e354c866a | note | Acceptance Criteria - The position of all drainage pits are to be confirmed with the Superintendent. Survey pegs set-out at two different offsets.
fb59cc95-fcfb-5130-b749-3342df13a945 | note | Reference Documents - Engeny Water Management Specification Cl.11.1
0598ed28-2b30-5dd5-93a5-9836647b6b8b | note | Inspection / Test Method - Visual Inspection
b6c7173e-77ed-5885-9078-4deef34b988b | note | Record of conformity - Signed ITP
681b4f15-3e36-5015-b192-74557fb95c48 | note | HP
7aaecfe2-96bd-5569-8c81-9043b89a4815 | note | Responsibility - Project Engineer / Site Foreman
977cc845-857c-429e-94e7-80e878dc9844 | signoff | AUTHORITY HOLDPOINT
02e8f72e-a1bd-43bb-9868-5d5d3be6026c | checkpoint | 2.2 - Formwork
201ca35b-49af-592f-b037-88de79899b39 | note | Frequency - During construction
d931f48a-4cb9-5efc-8266-4ef8104cfa70 | note | Acceptance Criteria - Formwork shall comply with AS3610. Formwork shall be sufficiently ridged and strong to support all dead, live, and construction loads imposed. Formwork shall be Class 2 to AS3610. External edges of concrete work above ground shall be formed with a continuous 20 x 20 mm chamfer. Internal corners shall be formed with a continuous 20 x 20 mm fillet.
3f3eb9b6-7af0-5ba6-bad4-57535b7e3121 | note | Reference Documents - Engeny Water Management Specification Cl.24.13
64e4aed3-8ea4-500e-8c17-352b2410364f | note | Inspection / Test Method - Visual Inspection
46fdfb3b-1a0b-56d0-8137-5b446f386f69 | note | Record of conformity - Signed ITP
fa361db7-e07a-50b5-a7cd-20b0779231d3 | note | IP
41ca869a-6fd3-5083-931b-663effbd9b51 | note | Responsibility - Site Engineer / Site Foreman
41fb4342-42be-4a3b-9638-28045a665af8 | checkpoint | 2.3 - Reinforcement
0671163f-8a9d-5794-9701-e0d9fa4662b0 | note | Frequency - During construction
0046f4ac-39ce-5911-98c8-e43e99a898e6 | note | Acceptance Criteria - All reinforcing bars must be deformed steel, Grade D500N, in accordance with AS/NZS 4671-2001 unless otherwise shown on the Drawings. The reinforcement cover must be as shown on the drawings, if no dimension is shown on the Drawings, reinforcement must have minimum 50mm cover to the concrete surface.
e9bf8152-cc2f-573b-874b-5874629d594a | note | Reference Documents - Engeny Water Management Specification Cl.24.5
13d1001f-58b8-5bc2-b399-4b0ae8563032 | note | Inspection / Test Method - Visual Inspection
311de345-8a9b-533c-b9b8-94ff8cd66ed5 | note | Record of conformity - Signed ITP
a7b8e9c7-8a80-5e46-a32c-a8e354a2cbae | note | IP
d791686d-18e1-5d6b-bd0a-f37666f4a5d3 | note | Responsibility - Site Engineer / Site Foreman
cbe206e1-4a13-43dc-8563-77fa24f63b98 | checkpoint | 2.4 - Pre-pour Inspection
a19deaf7-c95e-5a4b-9ee9-6302f13b7b3c | note | Frequency - During construction
8dc4e804-7e39-582d-a5f3-825f6e952d7d | note | Acceptance Criteria - Prior to concrete placement, the formwork, steel fixing, and embedded items shall be inspected by the Engineer. A minimum 48 hours’ notice shall be given prior to the inspection. The concrete shall be placed within 48 hours following the inspection.
bd6b8ff3-07a2-5136-9bcd-58d046df23b1 | note | Reference Documents - Engeny Water Management Specification Cl.24.14
85861f6e-18ce-5f92-a69c-02f4dc45a8ef | note | Inspection / Test Method - Visual Inspection
f48b5bbd-f107-5769-aabb-d0c69ae4610c | note | Record of conformity - Signed ITP
2e206b52-e86a-5b05-b87e-8210e077cd5a | note | HP
5414d710-9229-59c1-b033-79f260b361f6 | note | Responsibility - Project Engineer / Site Foreman
3cd5178d-5f50-4e12-9fdb-a52d5d862f1d | signoff | AUTHORITY HOLDPOINT
e3a77083-43d4-43c2-b49f-6c99adf28e44 | checkpoint | 2.5 - Concrete Placement
a7eafed4-b8e7-50f4-80a5-3dbc7753affe | note | Frequency - During construction
4ad67332-f7cb-5021-9c71-429b2a1a269d | note | Acceptance Criteria - Concrete shall be deposited in a uniform manner into the forms and around the reinforcing steel, embedded items, and penetrations. Concrete shall not be dropped from a height exceeding 2m without the use of a tremmie tube.
84187500-8fa7-52ad-b68d-99737ad9dd61 | note | Reference Documents - Engeny Water Management Specification Cl.24.15.5
b398d977-c33f-5656-a33c-724d9ac6b48b | note | Inspection / Test Method - Visual Inspection
2e4aceeb-0542-56ea-bf83-9d5e854a5226 | note | Record of conformity - Signed ITP
499228a2-d7a9-5930-aa4a-548fcf76e7e8 | note | IP
a4e8d3a0-c8d5-5b34-ba2c-62454289e2b6 | note | Responsibility - Site Engineer / Site Foreman
90ddd212-199a-4419-9dcf-4fc7c3c341c4 | checkpoint | 2.6 - Finishing
75660674-6e92-582b-a23e-afc470f4506f | note | Frequency - During construction
71ca81d9-82e3-545f-b7a7-e5416db5a186 | note | Acceptance Criteria - Unformed surfaces shall be finished smooth by steel trowel, float or other suitable method approved by the Company’s Representative
f22e2896-42bb-5ddc-8cbf-4a700c9833ae | note | Reference Documents - Engeny Water Management Specification Cl.21.4.6
249bab4c-3b75-5d0c-972d-f295a17fc27b | note | Inspection / Test Method - Visual Inspection
5705b3d0-6dba-5249-a000-3c7b579c606e | note | Record of conformity - Signed ITP
42b7551a-845d-5c47-b857-ca2cd49530fb | note | HP
91b1a70e-98b1-59d1-98f2-d99a5fc1efea | note | Responsibility - Project Engineer / Site Foreman
fb296e69-d1e1-4cb8-8e1b-d92c8885cb7a | signoff | AUTHORITY HOLDPOINT
7daeaa92-7f7b-45cf-b0e5-03c627cb8c6e | checkpoint | 2.7 - Curing
b9000627-c877-55ec-bec0-bdc556f23c7e | note | Frequency - During construction
1006beb8-9643-5b80-93c2-4618c4336a7c | note | Acceptance Criteria - Immediately following finishing operations, unformed surfaces shall be coated with an approved moisture retaining compound such as aliphatic alcohol. The unformed surfaces and formwork shall be kept continuously wet for a period of 3 days using wet hessian or other suitable means followed by a gradual drying out over the following 7 days.
30b87a5e-61c3-5b2f-a5ee-da3924c02b7b | note | Reference Documents - Engeny Water Management Specification Cl.24.15.5
2b39eafd-02d7-5f58-8770-6f17d7484c4c | note | Inspection / Test Method - Visual Inspection
99b0c161-1f33-5889-926b-b768e3a11713 | note | Record of conformity - Signed ITP
52810c82-1b4f-514f-bf17-77cd9fea2a14 | note | IP
1f7fcc92-e0c4-5e15-b68b-72e99530b66f | note | Responsibility - Site Engineer / Site Foreman
810e78ca-09e0-4058-b723-3a9e88702122 | checkpoint | 2.8 - Formwork Stripping
b73c0faf-404a-5c1c-af2d-ca24eeb820a8 | note | Frequency - During construction
163d4470-5845-5fd1-9434-477cc5a9500c | note | Acceptance Criteria - Where not otherwise required as structural support forms may be struck after 24 hours but shall remain in place for at least 3 days or until a minimum compressive strength of 25 MPa (as supported by testing) is achieved.
6358c8e0-c1c5-5cd9-877e-c0aef3a6deff | note | Reference Documents - Engeny Water Management Specification Cl.24.16
d9b73344-6e94-5e19-af66-b08d94443b27 | note | Inspection / Test Method - Visual Inspection
16f2ed5a-a8ae-5d8d-80b7-7a77baf12228 | note | Record of conformity - Signed ITP
2a7cfc83-4b12-543d-b567-19c88c249928 | note | IP
d0041b5c-7ca4-5859-ada6-bee95a190128 | note | Responsibility - Site Engineer / Site Foreman
793f35c9-2547-48a9-b0b3-5e1b13ec84a7 | checkpoint | 2.9 - Stormwater drainage connections
a333a903-d2d3-5139-b0b7-f9c871354587 | note | Frequency - During construction
4b249747-e2f5-56f9-8ee7-3055b316936e | note | Acceptance Criteria - Stormwater drainage connections to pits shall be neatly made, and where necessary the ends of all drains shall be trimmed off and finished with cementitious mortar as stated in Clause 705.14. Comply in accordance with Clause 705.10 with requirements for openings, weepholes and exposed reinforcement.
db4f4e9b-5bb3-5efc-83ab-486f54e90070 | note | Reference Documents - DTP 705.10 DTP 705.14
25ad559f-09fe-5517-9998-bfda86a44512 | note | Inspection / Test Method - Visual Inspection
ce136bfc-1205-52aa-88e9-93626fbc5862 | note | Record of conformity - Signed ITP
183e407d-75d7-56f6-87b2-70e10001909d | note | WP
6dddf2c9-b11d-5d0f-acf1-217ad48f1451 | note | Responsibility - Site Engineer / Site Foreman
434d4014-6cf8-431f-ab96-67cc133f497a | checkpoint | 2.1 - Covers, Grates, Lids and Lintels
566253b5-8a86-57c8-b83e-80ef95447143 | note | Frequency - During construction
7ebb2bd6-1bd3-59a5-9106-f0077e772c25 | note | Acceptance Criteria - Covers, grates, lids and lintels shall be as shown on the drawings. Metal access covers, grates and frames shall comply with AS 3996. Covers and grates shall not dislodge or rock in their frame when subjected to traffic loading. Covers and grates shall be of the lift out type, unless otherwise specified or shown on the drawings.
4a8ccf9a-357c-5ce3-994d-0069050710dd | note | Reference Documents - DTP 705.04 (b)
1972cd04-d78f-5453-ab30-615b39427830 | note | Inspection / Test Method - Visual Inspection
6d53aad5-5c57-55d9-8dd9-3e465205c5df | note | Record of conformity - Signed ITP
5a014510-4a17-537a-a93c-f4941d942dc0 | note | WP
b014a43d-c061-5f9b-b1f8-4baaa0599162 | note | Responsibility - Site Engineer / Site Foreman
0d8956de-ac57-4da3-8a01-a39e483367c1 | checkpoint | 2.11 - Step Irons
495fb47c-ef19-5aed-bea7-8e837866dd39 | note | Frequency - During construction
fffb27e4-0ccf-5057-b7f8-fba1b9d0b2b5 | note | Acceptance Criteria - Drainage pits > 1m deep shall be fitted with step irons installed horizontal, vertically in line and shall project uniformly from drainage pit walls in accordance with design drawings and specifications.
45d2c555-3f2c-556f-bc28-2cc175fda406 | note | Reference Documents - DTP 705.04 (c)
3521db6d-a340-5b10-af40-89a81995b774 | note | Inspection / Test Method - Visual Inspection
3b90018b-c99d-5d3f-b82c-9e7b6a3debe1 | note | Record of conformity - Signed ITP
b03991b2-146e-5e87-b1ee-8afc8ea8bd88 | note | WP
4e842b0a-1fb7-5374-96c5-cb3a5488f9c4 | note | Responsibility - Site Engineer / Site Foreman
b10ec63f-7fec-4d04-8a10-b050547707d4 | checkpoint | 2.12 - Concrete repairs
6df6e786-dac2-577e-8258-6126dfed32c6 | note | Frequency - Only where required.
26605cab-6e67-552d-8991-d15ebaebd9a2 | note | Acceptance Criteria - Should concrete works be defective the Contractor shall submit to the Engineer for approval their prepared methodology to repair the defect/s.
c8f8d325-03d6-56e8-a05c-ae4d0ccd7b0e | note | Reference Documents - Engeny Water Management Specification Cl.24.19
53b7c7b1-1c4f-571a-9201-b1011a37cc98 | note | Inspection / Test Method - Visual Inspection
f93c3898-7876-5f1f-9f9c-2aba6b9ce6de | note | Record of conformity - Signed ITP
41e160c6-bc03-577e-a5bb-b6fc8a3d08e6 | note | HP
87919d29-c290-5085-8aae-00646bd84b28 | note | Responsibility - Project Engineer / Site Foreman
4ab5d9c1-6a5d-4fe9-a61f-791917c1d465 | signoff | AUTHORITY HOLDPOINT
5596e3c6-65f7-4a62-8f0a-974d74e76aef | checkpoint | 2.13 - Backfilling of Structures
eba1c354-abd7-51d1-ae95-c2aba083f4ef | note | Frequency - After completion.
dae6890c-d628-5f0b-b487-62e3e19ac4e5 | note | Acceptance Criteria - The Contractor shall place and compact backfill in even layers on either side of structures to avoid differential loading. Backfill material to consist of 20mm FCR CL3 (under roads or footpaths) or General Fill material (outside traffic areas).
8fdf5ee4-caba-5b84-a007-b909bb8933bb | note | Reference Documents - Engeny Water Management Specification - Appendix B.
c38e2a99-cf00-589c-88e5-8aef04b90dcd | note | Inspection / Test Method - Visual Inspection
85301b4e-aa5f-5824-832e-86eaaa78a142 | note | Record of conformity - Signed ITP
852d5953-303d-50a5-a784-f1fd76ad6466 | note | IP
104ab0d1-16ab-59b5-8ed5-7559a70b44b3 | note | Responsibility - Site Engineer / Site Foreman
83e4438a-d89b-445b-8f65-bde283ae3fd9 | section | 3.0 Testing & Completion
39d7455a-c2c3-487b-891e-e0e5cc9e6920 | checkpoint | 3.1 - Concrete Strength Testing
0e824946-5814-526c-bdd0-61c10e0fe200 | note | Frequency - Each Lot
b5cbe3d4-71a7-5951-ba3a-841163b33fe6 | note | Acceptance Criteria - Following initial acceptance, 4 matched concrete specimen cylinders per 6 m3 of placed concrete shall be taken, stored, cured under standard conditions, and tested at a NATA accredited laboratory in accordance with the requirements of AS1012. One cylinder tested at 3 days, one at 7 and x2 at 28 days.
eaca631f-2c8a-5098-9cdb-dc9ce165ba1c | note | Reference Documents - Engeny Water Management Specification Cl24.4.1
02387aa7-3f15-590e-bab7-aefde2d71b2a | note | Inspection / Test Method - Document review
99bf1100-a254-53da-959e-4cf9e83daf9a | note | Record of conformity - Signed ITP
667620cb-5d59-582d-bf65-8ce16d36f4f1 | note | TP
64454014-d232-54ec-ad6e-dbc9bb0d37a2 | note | Responsibility - Site Engineer / Site Foreman
caa35162-ae13-4774-99c3-0a46220933ee | checkpoint | 3.2 - Conformity with Drawings
fa442f91-c860-59dc-9d1c-39dfd17b4af8 | note | Frequency - On Completion
3512bbc4-fd75-5c17-8e32-af3fcab77eab | note | Acceptance Criteria - Survey to confirm compliance with drawings. - offset of entry pits required to match lines of kerbs or barriers ± 20mm - plan location of pits other than offsets to kerb lines or barriers ± 100mm - invert level of pipes at pits ± 50mm -departure from design grade of pipe runs ± 10mm in 10m provided minimum grade is not < 1:250.
9b5e3a5d-27d7-59fd-a5fe-cc76f9ceb939 | note | Reference Documents - DTP 701.10
54178424-06c8-5bc6-a6f1-39d64c46c050 | note | Inspection / Test Method - Visual Inspection
1981fd87-12b1-5530-aef1-c10fc0b10364 | note | Record of conformity - Signed ITP
f4202e92-d6f3-57fb-af16-4a64fe5f24cb | note | HP
06a9cda3-fafa-5c45-9629-ccfb0396af69 | note | Responsibility - Project Engineer / Site Foreman
028dd299-ced3-47d2-8588-58df27cc8b11 | signoff | AUTHORITY HOLDPOINT
a59fb1ca-bd5d-4e71-a6b7-d1aadf1d5cd9 | checkpoint | 3.3 - CCTV Inspections
07a112ed-dc51-5239-99f8-b7767daf9126 | note | Frequency - On Completion
697f0151-e63e-5abf-a89e-e379108a067d | note | Acceptance Criteria - The report and CCTV record shall be provided to the Superintendent for review of any possible damage to the pits.
e21f7dd0-8317-51ba-a1aa-7456c524a9d7 | note | Reference Documents - Engeny Water Management Specification Cl.21.4.8
eddfe267-ffe4-5f1e-9a29-acbc1d6fea12 | note | Inspection / Test Method - Site Inspection
53ff1860-2d3c-553d-a50f-27499dfb7ba4 | note | Record of conformity - Signed ITP
c36eecd1-0ef3-5e1d-8b95-11abb2d469d7 | note | HP
23bb90d7-f3e4-56a1-a45d-e09e0159f36b | note | Responsibility - Project Engineer / Site Foreman
8371b345-6db5-47a0-a091-ebfc704d040f | signoff | AUTHORITY HOLDPOINT
9331bf79-c8c8-41a9-a2eb-5946f7ce5be8 | checkpoint | Final Inspection
94d9713a-c00d-5946-ac9e-aa67c784a13c | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
5e57f315-7e8d-5140-8c1b-be87af80a139 | textbox | Print Name:
6b05c4fe-d8df-5479-a370-bff194b234ef | textbox | Position:
6afc49ad-5b94-5c7f-a2cb-dc6b47f06070 | date | Date:
63c7393a-dcbc-48c1-bb44-93f397370169 | signoff | Sign ITP
0b8009bd-8d1f-45b0-99e3-73d9fa2dfbe8 | checklist | 1.03 - Drainage - Structures | itp | 1.03 - Drainage - Structures | 5e6e6749-9efe-412c-b457-961edf79c771
b640ef1e-78f8-48ed-879a-2fb511478a7b | section | 1.0 Preliminary Works
666d272b-7211-4d52-ac0e-2dcd52d0eefd | checkpoint | 1.1 - Pre-commencement documentation in place.
d655ce3a-0583-5734-8d30-15fc1fb47150 | note | Frequency - Prior to Commencing
edea5806-e822-50d0-a28b-b72bfd0f6a66 | note | Acceptance Criteria - All personnel and plant have been inducted to the K-Road project. Client has received and approved all pre-commencement documentation including SWMS, PMP, EMP, QMP, SMP and TGS plans.
bd4cf437-77f6-5efd-a24e-621a0cf8dd54 | note | Reference Documents - OH&S Act 2007 FH Documents
41cc3cc1-a9bc-5dc6-a7e8-55ed9fe3c330 | note | Inspection / Test Method - Document review
ec41f3ba-ecdc-52f2-8560-f5aaf49b754f | note | Record of conformity - Personnel/Plant Inducted SWMS Signed
5614cc81-75f0-597a-9ed5-5a12c9d79591 | note | WP
92d12ea1-954c-5f6a-9d56-fa14752e6c48 | note | Responsibility - Site Engineer / Site Foreman
8be7a5a0-3a63-4108-872a-c1a6642ee726 | checkpoint | 1.2 - Relevant Permits Issued
112eb91a-8db6-59c5-ae97-ef533a0ed743 | note | Frequency - Prior to Commencing
b264d50b-2a5a-5ef5-a27f-8cbdfdb83e78 | note | Acceptance Criteria - Current excavation permit is in place and signed by Site Foreman. Any excavation greater than 1.5m has an approved Trenching Notification submitted to Worksafe.
cf321fb4-dd26-5b30-b3fb-d4c4698d1b8d | note | Reference Documents - Permit Review
6cb6d6e9-07c2-581d-a875-eac614f70463 | note | Inspection / Test Method - Document review
ead93f4f-32ab-5064-b5a7-dab998327bf8 | note | Record of conformity - Excavation Permit
dff12923-4bf6-54aa-9e40-238e1428641e | note | WP
2c172507-3fd8-55a1-8822-0d952c01d099 | note | Responsibility - Site Engineer / Site Foreman
edca978d-1099-4f50-9856-f2ad22b8e3c7 | checkpoint | 1.4 - Service locating and NDD proving
0315740e-b822-5490-97a4-b4000af9e656 | note | Frequency - Prior to Commencing
20554195-451f-5d4f-afb3-19d4a9c8d159 | note | Acceptance Criteria - Prior to commencement of excavation works, a BYD request will be submitted and any known services in the area will be located and physically proven every 5m interval.
07ec074d-cf86-5f0d-86db-cb9a3b15a188 | note | Reference Documents - BYD Information
782c1dfa-edae-53bd-97cc-a45be9d8f970 | note | Inspection / Test Method - Verify
584c7caf-6ec0-5618-92e8-a0bb2450587c | note | Record of conformity - Signed ITP
2223647c-8a14-5338-ba65-bf6476511337 | note | WP
1ca79215-fc0c-5f34-a052-971892d11995 | note | Responsibility - Site Engineer / Site Foreman
832b24e8-dfa9-4826-b317-b763d6b35d09 | checkpoint | 1.4 - Conformity with Drawings
2d2859ee-de04-5624-82a6-eea2caaff455 | note | Frequency - Prior to Commencing
535d820e-752e-5147-a503-480bd0ac1663 | note | Acceptance Criteria - Prior to commencement of excavation for the construction of the reinforced concrete structures the Contractor shall confirm the limits of the structures with the Superintendent.
022793c8-fb93-5204-8122-84cfb911590a | note | Reference Documents - DTP 701.1
b5372adb-da17-5292-ae93-4f624197ca42 | note | Inspection / Test Method - Verify
f939c94b-dc3a-5a8e-8bad-96ec094b7eb4 | note | Record of conformity - Signed ITP
4118b7b2-d12f-5f17-9654-293c240bbe91 | note | HP
4b156094-957c-5c6b-8b0a-1c07a157b7ae | note | Responsibility - Project Engineer / Site Foreman
71ba3f6b-229a-412a-b524-cfa91fa718a5 | signoff | AUTHORITY HOLDPOINT
83b1dcce-868e-4ffd-a21c-1126fa423784 | checkpoint | 1.5 - Concrete Mix Design
63a3d123-00f4-539c-ad5c-609b720ba957 | note | Frequency - Prior to Commencing
71b2aa67-f727-5ef4-9e4b-61e57a6deb33 | note | Acceptance Criteria - The Contractor shall submit their preferred mix design for each strength grade incorporated into the design to the Company’s Representative a minimum 5 working days prior to concrete placement for review and approval. Details of concrete supplier, grade N40 - Structural Concrete and N20 - Blinding Concrete, slump and types to be included.
b3ff20ac-92cd-5ece-80ee-eeecfbae7f6d | note | Reference Documents - Engeny Water Management Specification Cl24.4.1
f7b23e58-4ca0-50e4-b891-6fc9cea06755 | note | Inspection / Test Method - Verify
982c2885-e716-5582-9d25-8fc730611690 | note | Record of conformity - Signed ITP
e98b7ba0-aca3-551c-91d0-51d6d4217457 | note | HP
2d74fbff-7047-59a8-b422-7f0140c41190 | note | Responsibility - Project Engineer / Site Foreman
6246df75-35b4-4a9d-aa6b-e0c7d1872123 | signoff | AUTHORITY HOLDPOINT
6413b2bf-42be-4211-b29b-a8db0b0dde23 | checkpoint | 1.6 - Backfill Material Conformance
7efe355a-1d3e-52c4-b538-cc908ee9c92a | note | Frequency - Prior to Commencing
2fe29c5a-a02a-5913-90a4-d932f09b41fd | note | Acceptance Criteria - Materials used for backfill shall be free from perishable mater and lumps. Grading as per table 701.081. PI max should be 20. Grading and PI tests to be carried out as per frequency nominated in Engeny Water Management Specification Appendix B.
10a74135-f8db-5522-97bc-a0e4d30d4eb0 | note | Reference Documents - Engeny Water Management Specification Appendix B DTP 701.09
d61e28f9-898f-5394-bc8a-deebfd54d1ad | note | Inspection / Test Method - Verify
09e5c161-ee52-5a0b-9735-c89f88fd902b | note | Record of conformity - Material Conformance Documents
6a875177-0bf2-5d78-94b1-d328698ac2a6 | note | WP
2588f020-8ac2-5d31-96a6-f617dcd19437 | note | Responsibility - Site Engineer / Site Foreman
225eb892-dcc2-4b0c-bf3d-43238dc7d3d0 | section | 2.0 Construction Works
c0773fcb-a047-433c-890e-665b54c13c67 | checkpoint | 2.1 - Set out of drainage
eb0c641b-b62e-58de-89e9-6060083f7cad | note | Frequency - Prior to Commencing
1755537d-743c-56bd-914f-896b494a7b3e | note | Acceptance Criteria - The position of all structural elements are to be set out by a suitably qualified surveyor with a minimum of two offset pegs for each survey setout point.
0d5fa713-5d41-542c-9b7a-753893a3da7a | note | Reference Documents - Engeny Water Management Specification Cl.11.1
da58380d-bdc7-5569-93d5-aec4ce6b847e | note | Inspection / Test Method - Visual Inspection
307aeb3b-39a8-534b-b2c1-14b2b0729979 | note | Record of conformity - Signed ITP
b1f038c3-6550-5c85-8947-c2e365a965fb | note | HP
6c7a6e7f-1e13-5c2e-9a74-049b8337c399 | note | Responsibility - Project Engineer / Site Foreman
7be46015-c736-4b5d-b30c-ede8b859cc62 | signoff | AUTHORITY HOLDPOINT
103e8190-baa7-4ef6-9b58-8807570bbb46 | checkpoint | 2.2 - Clearing and grubbing
d3bc5e26-302e-51f4-8942-cb69e87460ae | note | Frequency - During construction
a407e447-6583-54b9-9475-13294cd36db8 | note | Acceptance Criteria - No vegetation is to be cleared without prior approval from the Company’s Representative. The Company will develop and approve clearing permits and excavation permits.
228896b6-21e4-5b54-9d9a-097beb56591d | note | Reference Documents - Engeny Water Management Specification Cl.12.3
a972efa2-030a-5ef1-a6e7-240ea4f4bfc9 | note | Inspection / Test Method - Visual Inspection
8be0f81c-fec9-5f1d-8132-42966390ba3e | note | Record of conformity - Signed ITP
4e8803cc-7527-5248-8a22-24a3f6634149 | note | HP
ddbe8c36-925c-5e12-913d-9c5bf8f08318 | note | Responsibility - Project Engineer / Site Foreman
fecc3f93-0dd6-4682-bbdf-ceac081cac14 | signoff | AUTHORITY HOLDPOINT
c212c951-62f8-4c10-9f64-78c90afdf3b7 | checkpoint | 2.3 - Tree Roots
1690e735-3bf2-59fd-8809-a22024551174 | note | Frequency - During construction
46ee66ed-20db-5040-a507-625db70062d4 | note | Acceptance Criteria - Where a major tree root is encountered the Contractor must immediately seek direction from the Company’s Representative as to what action should be taken
20e1db83-344f-5101-b4ac-b4f1b12aaedd | note | Reference Documents - Engeny Water Management Specification Cl.12.5
6fea6138-dae5-59ad-bde7-fea808b4e3f0 | note | Inspection / Test Method - Visual Inspection
9e3911d2-b9d8-5e24-af3c-1d05cf286c27 | note | Record of conformity - Signed ITP
bde00e55-a191-537c-a000-5fcddbfd380f | note | HP
8a3aad5c-340a-5347-8f4e-cefbdae44aba | note | Responsibility - Project Engineer / Site Foreman
f8648aad-bb46-4921-80ce-75711d901555 | signoff | AUTHORITY HOLDPOINT
9535e4a0-e6d5-4da4-8b82-17b785b7af91 | checkpoint | 2.4 - Topsoil Removal
4cdc50a6-e43f-54fe-8ec4-fd84442ac3e1 | note | Frequency - During construction
d8652daa-1e66-54be-8b05-b998287a0c4f | note | Acceptance Criteria - Topsoil removal to only occur following approval from the Company’s Representative. Topsoil to be stockpiled in areas nominated by Company’s Representative. Stripping and stockpiling of topsoil should be undertaken in accordance with Melbourne Water’s Specification for Soils and Landscaping of Constructed Melbourne Water Assets.
5f532297-888a-5922-bfc1-6afa97bc3d2b | note | Reference Documents - Engeny Water Management Specification Cl.12.6
f5f4b2b1-8280-5173-8e6b-ce40dbccf4d3 | note | Inspection / Test Method - Visual Inspection
df024cfe-f80e-5cd9-ba8e-e646552b8f5e | note | Record of conformity - Signed ITP
d5f5d0c6-022a-545f-8075-876d720968d1 | note | HP
4760c33b-ae67-50d2-aa3b-a0483bbe70ca | note | Responsibility - Project Engineer / Site Foreman
9ccfe689-f005-412b-923f-69d153670d9c | signoff | AUTHORITY HOLDPOINT
c79cb683-e3d9-4d96-a4f9-a3836aada22a | checkpoint | 2.5 - Excavation
78c429ce-017b-5928-ba07-3d271ee26285 | note | Frequency - During construction
36458d7c-fc60-5fb5-aa65-078a9c3dffb6 | note | Acceptance Criteria - No material shall be excavated until a joint survey of the existing surface has been performed by the Contractor and the Company’s Representative. Following excavation, the exposed surfaces shall be inspected and approved by the Engineer.
558a7aa8-bbfa-58f4-89ce-37b502cc80a1 | note | Reference Documents - Engeny Water Management Specification Cl.13.1
834eb22a-06a4-5db4-87bf-775d86be7962 | note | Inspection / Test Method - Visual Inspection
691e51b4-3e8b-5b6e-ad05-88b2c375a818 | note | Record of conformity - Signed ITP
185bcbc9-8c7c-57e6-a3c9-3b1c75534c41 | note | HP
5f2c8511-1ff2-5133-bc8c-3a9ba259921b | note | Responsibility - Project Engineer / Site Foreman
f5f50cda-c80a-4d1b-8d11-62ae92d83ea2 | signoff | AUTHORITY HOLDPOINT
93d86585-f0a0-45cd-b63d-c66175456e1d | checkpoint | 2.6 - Foundation Preparation
fe8e270b-83fe-5470-9be2-f8e582f7db35 | note | Frequency - During construction
56b6d8e0-1b01-5493-ae36-caa6653a3ee6 | note | Acceptance Criteria - The prepared foundation shall be inspected by the Engineer prior to further works and any defects rectified by the contractor.
3de4cd4c-49ca-5d35-927d-2f039bd9eb6c | note | Reference Documents - Engeny Water Management Specification Cl.14
06d18db2-227d-5523-8052-b32dfb846c65 | note | Inspection / Test Method - Visual Inspection
1c8c7702-8cf4-5af1-bceb-e46f9ddfd4ac | note | Record of conformity - Signed ITP
0e393ff6-1a1e-5072-84cd-f99ce3c4d3a1 | note | HP
42df8d4e-b7da-5877-9833-97e7ffa8eadb | note | Responsibility - Project Engineer / Site Foreman
495ef02b-de31-49ba-9958-5e6d7b9b21ea | signoff | AUTHORITY HOLDPOINT
0b9049a2-da24-47bc-82b6-d0e516c126cd | checkpoint | 2.7 - Subgrade Surface
507abed6-db0d-5623-94b6-99a6b2460610 | note | Frequency - During construction
7ba1c1d6-41c4-5ec1-9efe-525e79097175 | note | Acceptance Criteria - Construction of the D11 outfall drain headwall structure, Werribee River energy dissipation structure or trunk drainage pipes specified on the Engeny Trunk Drainage Design plans shall not commence until the Engineer has inspected and approved the subgrade surface preparation
5f283404-71f8-525f-a2af-1af87a2a9a1d | note | Reference Documents - Engeny Water Management Specification Cl.14.2
db1623bb-c021-517a-ba5f-916bd25ffa35 | note | Inspection / Test Method - Visual Inspection
dab3b0e2-90f9-5096-aa9c-ce121a3526fd | note | Record of conformity - Signed ITP
2c10ea2f-423e-57ca-bf5a-189f4d89b89b | note | HP
aafa8639-5ed2-53df-a6cf-045530d37ae5 | note | Responsibility - Project Engineer / Site Foreman
142df480-b03b-45cd-95fe-a15682442b59 | signoff | AUTHORITY HOLDPOINT
30b1e876-729c-4e1f-bf0f-cbe5348913ca | checkpoint | 2.8 - Formwork
227f900b-8387-5476-9f57-8e1eef11ae79 | note | Frequency - During construction
c55d0f8a-7473-5028-9707-42adf5c3c0b6 | note | Acceptance Criteria - Formwork shall comply with AS3610. Formwork shall be sufficiently ridged and strong to support all dead, live, and construction loads imposed. Formwork shall be Class 2 to AS3610. External edges of concrete work above ground shall be formed with a continuous 20 x 20 mm chamfer. Internal corners shall be formed with a continuous 20 x 20 mm fillet.
dddd3d14-0a3a-5416-932b-a3f4b991558c | note | Reference Documents - Engeny Water Management Specification Cl.24.13
c6a06e60-a9c1-5208-8fc1-9fea34d1f5f1 | note | Inspection / Test Method - Visual Inspection
3b46cde1-04f9-5e67-b97f-c107b41dbb32 | note | Record of conformity - Signed ITP
c7410149-1eae-5621-9a48-cafb0427fb05 | note | IP
f7db80a3-af46-5b3d-bdfd-b0886e400fa1 | note | Responsibility - Site Engineer / Site Foreman
10694e91-c7ff-4139-893e-9650dd868b45 | checkpoint | 2.9 - Reinforcement
509a8c26-aa3f-5d84-96ba-6ec7c5ae0d9d | note | Frequency - During construction
9a8900d5-6b87-548e-aee2-bd57b5c5fa3e | note | Acceptance Criteria - All reinforcing bars must be deformed steel, Grade D500N, in accordance with AS/NZS 4671-2001 unless otherwise shown on the Drawings. The reinforcement cover must be as shown on the drawings, if no dimension is shown on the Drawings, reinforcement must have minimum 50mm cover to the concrete surface.
06c86277-2b6a-5a02-bd31-79e0e5160034 | note | Reference Documents - Engeny Water Management Specification Cl.24.5
03928726-4d86-571a-8e1d-f98785968c37 | note | Inspection / Test Method - Visual Inspection
2e3fc55e-e068-5088-9fe7-c2c79badb039 | note | Record of conformity - Signed ITP
195391ee-42fe-583e-a028-fecda0567efe | note | IP
b8f7f703-7a09-549b-b20b-d62424382ddb | note | Responsibility - Site Engineer / Site Foreman
00cb341b-23b6-4bb9-8ffd-0d84de81dcf9 | checkpoint | 2.1 - Pre-pour Inspection
185857e0-9c83-5d83-921f-73546d605204 | note | Frequency - During construction
d12ad743-d044-592f-9cb3-30b8848e8ca0 | note | Acceptance Criteria - Prior to concrete placement, the formwork, steel fixing, and embedded items shall be inspected by the Engineer. A minimum 48 hours’ notice shall be given prior to the inspection. The concrete shall be placed within 48 hours following the inspection.
680570f2-b975-5755-8841-5ab23a33ad09 | note | Reference Documents - Engeny Water Management Specification Cl.24.14
132bad86-51cc-5bb3-af55-4d6c50bf149b | note | Inspection / Test Method - Visual Inspection
87d148e0-6b33-527b-beca-db256c0a9a86 | note | Record of conformity - Signed ITP
0e66d6ab-7455-58bf-975c-69fdf9303f38 | note | HP
9a439cb5-5ce4-5691-abe6-07615d7fbd07 | note | Responsibility - Project Engineer / Site Foreman
218e998e-2bf2-4b34-abc4-0d5196c5c84f | signoff | AUTHORITY HOLDPOINT
624247c0-f748-4e7f-89f4-acaca0bcba84 | checkpoint | 2.11 - Concrete Placement
296c9a99-625a-5c5b-b522-ae3586b218a7 | note | Frequency - During construction
4e07cffc-d184-5284-b72d-5b618334204c | note | Acceptance Criteria - Concrete shall be deposited in a uniform manner into the forms and around the reinforcing steel, embedded items, and penetrations. Concrete shall not be dropped from a height exceeding 2m without the use of a tremmie tube.
1de29c53-2b40-5bba-8096-b7201c23da08 | note | Reference Documents - Engeny Water Management Specification Cl.24.15.5
242a485d-abb7-5e00-a4d8-84e6e2bfb1b9 | note | Inspection / Test Method - Visual Inspection
b3d6a22f-debc-57a5-b104-32e31f06ae52 | note | Record of conformity - Signed ITP
89efb125-7156-5a42-a17b-16a7d1db71eb | note | IP
28bb1ead-e40f-579a-a4d9-6429a3903068 | note | Responsibility - Site Engineer / Site Foreman
29d4f621-157e-4704-8922-5d70e0398f1a | checkpoint | 2.12 - Finishing
e1d33ed5-7dbe-5553-a801-fee3e168521d | note | Frequency - During construction
87463cfb-4f4c-5a4e-813e-17c107f9d2a0 | note | Acceptance Criteria - Unformed surfaces shall be finished smooth by steel trowel, float or other suitable method approved by the Company’s Representative.
bc593de3-ae2e-5539-9ecd-c92b16549cff | note | Reference Documents - Engeny Water Management Specification Cl.21.4.6
571b32b2-3e6c-5488-9103-9b6a296cbb73 | note | Inspection / Test Method - Visual Inspection
4ed87680-2944-5e51-a1e5-2706cbdf5a2d | note | Record of conformity - Signed ITP
391423a7-3be3-54d9-b786-f364cab7a6cd | note | HP
0b1b4c76-f4d3-574e-8b4f-d60940de7836 | note | Responsibility - Project Engineer / Site Foreman
258423d2-5b26-4f9d-ad1f-c0f86bebebc5 | signoff | AUTHORITY HOLDPOINT
647b9a49-a79b-4064-883b-fa9f8f8abae7 | checkpoint | 2.13 - Curing
48d5d31a-0483-59f1-ab30-78e87afdd241 | note | Frequency - During construction
b87f1458-038d-5ff3-a120-a62007bbe391 | note | Acceptance Criteria - Immediately following finishing operations, unformed surfaces shall be coated with an approved moisture retaining compound such as aliphatic alcohol. The unformed surfaces and formwork shall be kept continuously wet for a period of 3 days using wet hessian or other suitable means followed by a gradual drying out over the following 7 days.
ed8ec38c-9daa-546b-b203-59c16e3909b2 | note | Reference Documents - Engeny Water Management Specification Cl.24.15.5
5dc47202-c49d-5364-afb5-7ad4c2eb2291 | note | Inspection / Test Method - Visual Inspection
5fbbcac6-614f-5917-9e2e-3c47258ecafd | note | Record of conformity - Signed ITP
c931e924-15da-50e4-9b60-a8535ce4f269 | note | IP
0f650de1-7ccf-5efe-bfaa-b10f2ab10c43 | note | Responsibility - Site Engineer / Site Foreman
4de2d6dd-136f-45f2-b6f8-662275f4f198 | checkpoint | 2.14 - Formwork Stripping
732e59bf-8dd2-5ca9-8fea-e9ff9f38cbcf | note | Frequency - During construction
22b2528e-04b4-556b-9ce5-7f57f69124a3 | note | Acceptance Criteria - Where not otherwise required as structural support forms may be struck after 24 hours but shall remain in place for at least 3 days or until a minimum compressive strength of 25 MPa (as supported by testing) is achieved.
cd480e65-7b8c-5c5a-a0c5-f890f64fbf53 | note | Reference Documents - Engeny Water Management Specification Cl.24.16
995f8aee-a35d-5a8c-9040-d251c12c59a8 | note | Inspection / Test Method - Visual Inspection
e7b4d4e2-5877-59e2-b3cd-824254967f04 | note | Record of conformity - Signed ITP
0b0795a4-c8e0-5637-994b-e3ef2f496691 | note | IP
4dfdcc27-44ed-5c95-8588-6e1447eb2f07 | note | Responsibility - Site Engineer / Site Foreman
b2e80cd9-ffd5-48b1-863a-2eb03e357150 | checkpoint | 2.2 - GPT Unit
ad737f0b-d13e-55bc-acd0-5bc2c40f43a2 | note | Frequency - During construction
643a5022-fadf-5d9e-8e4e-2607d7976606 | note | Acceptance Criteria - Offline Gross Pollutant Trap (GPT) and diversion chamber to be installed in accordance with manufacturer guidelines as per design drawings and specifications.
d7480d3f-bff2-5bda-8f11-108e9780da02 | note | Reference Documents - IFC Design Drawings
80fd66c3-d87a-5ab1-b078-f0b80cba8496 | note | Inspection / Test Method - Visual Inspection
15c37f00-3232-5f25-8750-457ff056661b | note | Record of conformity - Signed ITP
3d7d82be-a79d-518a-90b9-d06dd59ef420 | note | WP
11242215-8364-5aec-a3bb-3b8280901e22 | note | Responsibility - Site Engineer / Site Foreman
f0f4f1c2-2c4e-4a51-9f34-d2b64cc95e1c | checkpoint | 2.15 - Backfilling of Structures
094c1d92-b9c5-5f34-81e9-8c85036f9f95 | note | Frequency - After completion.
b0c1e73b-d4b9-5a7b-915c-46b9bae0541f | note | Acceptance Criteria - The Contractor shall place and compact backfill in even layers on either side of structures to avoid differential loading. Backfill material to consist of 20mm FCR CL3 (under roads or footpaths) or General Fill material (outside traffic areas).
fe7a9d26-5ef9-5be5-babc-c2f10409455a | note | Reference Documents - Engeny Water Management Specification - Appendix B.
4c19bca6-a9d9-5991-86df-d32b2c34e2b5 | note | Inspection / Test Method - Visual Inspection
a163c44e-ac42-5dcd-b539-8eaacb995167 | note | Record of conformity - Signed ITP
11680cfe-0328-54e4-bff4-8d5699b77274 | note | IP
3ac88e0b-0ed7-51db-ad46-4f10c2acd981 | note | Responsibility - Site Engineer / Site Foreman
2c602fd2-e0dd-4654-b65e-39cfec03bdb4 | checkpoint | 2.16 - Covers, Grates, Handrails and Grilles
b55f88b6-07c5-5096-b325-63ebccbaa43a | note | Frequency - During construction
12810cb5-8104-59a0-9d6b-e9eff5de95e1 | note | Acceptance Criteria - Covers, grates and grilles shall be installed as shown on the design drawings and meet the Melbourne Water specification.
9f7d81a8-3dda-52d0-8ef8-693617137771 | note | Reference Documents - MW 7251/08/423
23261bc4-21ed-5c7b-9353-bdb79f18fb14 | note | Inspection / Test Method - Visual Inspection
a956393a-1073-5555-a4eb-bef2ada3c5ba | note | Record of conformity - Signed ITP
96dff044-fea3-5314-9c0a-b6740a5a8351 | note | WP
164f6d33-7cbc-5296-9d9b-bc20650c10e2 | note | Responsibility - Site Engineer / Site Foreman
17edd021-ebc5-43c9-902e-f822ec500cb5 | checkpoint | 2.17 - Post and Rails
40b80ff3-d68f-5d29-9b0b-ebaacfef553d | note | Frequency - During construction
e6df1f78-094a-596b-a4a9-feabe17f3935 | note | Acceptance Criteria - Pedestrian post and rail protection to be installed in accordance with design drawings and Melbourne Water specification.
d4378520-f4aa-5b52-87a2-590bf7361c73 | note | Reference Documents - MW 7251/08/423
c1ead493-b26a-5517-90c3-b40ad8e2f7b8 | note | Inspection / Test Method - Visual Inspection
d164b6e5-c104-5cd6-b636-39b235dca9e9 | note | Record of conformity - Signed ITP
1b65160d-bd43-5873-9494-eadb3eeff59b | note | WP
24ae753d-0c4d-5f5a-95fb-37fb2106ca8a | note | Responsibility - Site Engineer / Site Foreman
106b8deb-357e-46c8-8aae-35a72285ebbf | checkpoint | 2.18 - Ladders
410b67f2-54c6-51c0-90e5-cb678a646122 | note | Frequency - During construction
74433cfe-6b6c-5c93-97b9-fa87a38c34eb | note | Acceptance Criteria - Drainage pits > 1m deep shall be fitted with step irons installed horizontal, vertically in line and shall project uniformly from drainage pit walls in accordance with design drawings and specifications.
d0ab32b5-3982-5028-85f8-9cbb34a8b3e5 | note | Reference Documents - MW 7251/08/423
a16f6bfc-ccaf-5301-acc9-efcccf0dac04 | note | Inspection / Test Method - Visual Inspection
4e03a313-f2be-5620-9c75-f7d16ff6956e | note | Record of conformity - Signed ITP
36571866-52d1-50ad-b330-7b8b2fd5037c | note | WP
8aa3f3f0-d474-58aa-8865-0b0c177b218c | note | Responsibility - Site Engineer / Site Foreman
55b0eb24-3774-4665-9767-42c0f537c5b7 | checkpoint | 2.19 - Rock Beaching
914319a6-beef-5c2b-a813-71781b7f875d | note | Frequency - During construction
d4881a4a-97f6-53ee-a203-41b5af126c74 | note | Acceptance Criteria - D50=300mm angular rock beaching shall be placed over 100mm depth CL3 20mm FCR base underlain with Bidim A44 geofabric at structure outlet as per design drawing and specifications. Rock material shall consist of hard, durable, roughly equi-dimensional sourced from an approved commercial quarry.
2145ef69-5346-51ad-91a6-37bb1c5ee634 | note | Reference Documents - IFC Design Drawings Engeny Water Management Specification Cl.18.1
8308765b-7a1d-5287-98ff-e06aba1771b7 | note | Inspection / Test Method - Visual Inspection
53551f65-4c97-54b1-9c56-e9bbba9d50f8 | note | Record of conformity - Signed ITP
84330483-91c9-542d-a238-a44718238e21 | note | WP
2cd80bb8-cd36-589a-9592-9e628a6932cd | note | Responsibility - Site Engineer / Site Foreman
e0ca1ecf-5344-4650-a950-b5e3bc1176c5 | checkpoint | 2.21 - Concrete repairs
85c6173e-10b2-5f8e-ba93-ae8edc29c357 | note | Frequency - Only where required.
229eab76-3e60-5c83-a0c6-1aa6d761166a | note | Acceptance Criteria - Should concrete works be defective the Contractor shall submit to the Engineer for approval their prepared methodology to repair the defect/s.
0ee41051-a8a7-543c-8f63-9168ee13fcab | note | Reference Documents - Engeny Water Management Specification Cl.24.19
1fd3c630-b9d5-5cb6-9c5e-db7bd866312e | note | Inspection / Test Method - Visual Inspection
ec880fd5-7039-5fe4-97eb-981c8bdc5b1a | note | Record of conformity - Signed ITP
ffa8e1eb-e4b9-57b0-99e7-5288fdcfd369 | note | HP
9e4408f3-dde5-5ab2-ba20-b30a34f9cdcf | note | Responsibility - Project Engineer / Site Foreman
99f31083-f009-42bd-bf7f-f4e17e04d61e | signoff | AUTHORITY HOLDPOINT
a09ca045-2e22-4d48-bc39-83844e2bb86f | section | 3.0 Testing & Completion
7aa828a9-9580-40f1-a90c-fb3090938eb1 | checkpoint | 3.1 - Concrete Strength Testing
e7a909cc-be09-5f70-a0db-cedab6a7cdb5 | note | Frequency - Each Lot
2b1e5b93-4fb0-598f-a984-df35c84e87bf | note | Acceptance Criteria - Following initial acceptance, 4 matched concrete specimen cylinders per 6 m3 of placed concrete shall be taken, stored, cured under standard conditions, and tested at a NATA accredited laboratory in accordance with the requirements of AS1012. One cylinder tested at 3 days, one at 7 and x2 at 28 days.
f25ffec4-8fab-5759-9ed9-270175830685 | note | Reference Documents - Engeny Water Management Specification Cl24.4.1
c6f41fcf-6ecc-5c04-8561-3c05b4d13611 | note | Inspection / Test Method - Document review
6c507f33-effb-5e71-a813-398201624b48 | note | Record of conformity - Signed ITP
10ed9d39-3dc2-59d7-84be-264e48160ff8 | note | TP
beff390c-bd54-537e-9c72-e7524e5cc203 | note | Responsibility - Site Engineer / Site Foreman
f5ec8c86-b8f6-4fbb-9c52-f5d1619b428c | checkpoint | 3.2 - Conformity with Drawings
8964a6df-47c9-5c18-ae12-68d865f82335 | note | Frequency - On Completion
7bb24928-e2d1-5bc8-829d-412ad282bd32 | note | Acceptance Criteria - Survey to confirm compliance with drawings. - offset of entry pits required to match lines of kerbs or barriers ± 20mm - plan location of pits other than offsets to kerb lines or barriers ± 100mm - invert level of pipes at pits ± 50mm -departure from design grade of pipe runs ± 10mm in 10m provided minimum grade is not < 1:250.
c2705d45-b0ff-5c09-87b1-de55ed8a2eb8 | note | Reference Documents - DTP 701.10
0d692dd8-b22e-5ad7-a8cc-6634db22d962 | note | Inspection / Test Method - Visual Inspection
ef688d85-c153-563b-ab1f-40a8073be0d8 | note | Record of conformity - Signed ITP
e2d79758-8f1d-5505-a367-afee692f506f | note | HP
fd1df3ec-7372-5832-aca8-7f8c26df3a73 | note | Responsibility - Project Engineer / Site Foreman
09a4e5a3-ff56-44cf-a29e-25918b7ae34c | signoff | AUTHORITY HOLDPOINT
693b9daf-5cd9-4ee1-8204-84957dcea6b7 | checkpoint | Final Inspection
8fe61893-d863-51e0-91f4-6a6905d08875 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
e44ba24f-04a9-5970-b154-db6b420002ea | textbox | Print Name:
3080be15-7036-5b4c-b4b4-54437822c180 | textbox | Position:
353134e2-a07f-5801-a36a-1ffb55b90a16 | date | Date:
abdaef58-da49-4ebc-bd27-339b060f96ac | signoff | Sign ITP
| checklist | 1.28 - River Edge Terrace | itp | 1.28 - River Edge Terrace | f3450281-3f90-42f1-b05f-af2a337bc122
| section | 1.0 Construction Works
| checkpoint | 1.1 - Induction and safety measures are in place, safe work method statement (SWMS) undertaken
81b01f12-11d4-5c1c-91cf-fa980dc209ba | note | Frequency - Prior to Commencing
1c771ff8-3d70-592e-84b3-961fcae9888e | note | Acceptance Criteria - All personnel on site have been inducted to the K Rd Project site and are informed of all relevant environmental management plans. Additionally, all necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
d2077ae8-1271-568d-a9e3-605dca4a28fa | note | Reference Documents - Inductions Register/OH&S Co-Ordination Plan
07c99e39-cb6a-5519-93bc-84670a2679d8 | note | Inspection / Test Method - Document review
126f2840-b25a-5a47-bbc0-31fae6bf7df9 | note | Record of conformity - Site Induction Signed. SWMS Signed.
66a4cb97-341a-5404-9133-f509bec28b0d | note | IP
5652da0c-2ac5-5499-a886-8bfab4b9a063 | note | Responsibility - Site Engineer / Site Foreman
| checkpoint | 1.2 - Relevant Permits Issued
06687a49-9a6a-5f56-a8fb-59a99cbd1e0a | note | Frequency - Prior to Commencing
daaa8bdd-47e5-5936-bbde-6d86890af0bc | note | Acceptance Criteria - All relevant and/or applicable permits have been submitted and approved including details of all areas to be affected by works.
c194bd2f-fbfd-5848-8c45-106caa885d17 | note | Reference Documents - Permit Review
ce335486-cb4c-5e11-b0d1-5c45346c1726 | note | Inspection / Test Method - Document review
b92dad4f-864a-53e1-9f31-97210386ef68 | note | Record of conformity - Excavation Permit #
3878c4c5-1e7e-55cb-8506-f07fbbeb2753 | note | IP
7d65436d-610b-5b16-9b03-c7298bc7c2a9 | note | Responsibility - Site Engineer
| section | 2.0 Construction Works
| checkpoint | 2.01 - Survey set-out
1421944a-ebd4-5927-8cfd-c19656e1301e | note | Frequency - Prior to Commencing Excavation
6a4aeddc-7f26-53d4-931f-233d39e5f9e5 | note | Acceptance Criteria - Survey activities undertaken to ensure all works meet level and location requirements. Establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
a4a2b8d2-1283-5703-9d8a-36a24c740dea | note | Reference Documents - Document Review
f73321cb-a375-52bc-a9ef-6af95894b23b | note | Inspection / Test Method - Site Inspection
0d8a0e30-7cf8-5fc0-a18d-dd9396898dc4 | note | Record of conformity - Survey records & pegs on the ground
eccca336-b8df-5f25-8995-76d0db6874c2 | note | IP
5a48f60a-f9c2-504d-86a4-27dd1378b937 | note | Responsibility - Site Engineer & Surveyor
| checkpoint | 2.02 - Conformity with Drawings
a2db94d6-9eb7-5f20-a85d-a86ff30d305c | note | Frequency - Prior to Commencing Excavation
edea3b3d-0dcb-57b3-a2a4-485dced3d621 | note | Acceptance Criteria - The finished surface of the river edge terrace shall conform with approved levels, lines and grades as shown on the drawings or as specified placement in accordance with section 210.
99e18eb0-ea38-5ba5-9817-c16490ec602f | note | Reference Documents - Document Review
4f315854-f43f-5f88-ac7f-25521011b7fe | note | Inspection / Test Method - Site Inspection
b4d2ee78-e282-5648-aef5-24418ad5567f | note | Record of conformity - Signed ITP
4af05dc4-d7b3-5281-ad58-982f6245692f | note | IP
418a4cf0-031b-5dd9-bae3-d29d11408f7f | note | Responsibility - Site Engineer
| checkpoint | 2.03 - Material Source Management
c55a046e-cb63-5eac-bbb7-497ddefd70ba | note | Frequency - Prior to Commencing Excavation
9774418b-fa14-515a-a0c0-9f43831e8d14 | note | Acceptance Criteria - Supply of crushed rock bedding material is from one source and will not change without first advising the Company’s Representative and agreeing with them the volume of fill to be obtained from that source.
8c6e53cc-f12f-5d12-a2bc-b5782f9961c0 | note | Reference Documents - Document Review
178b694b-6065-5687-8e67-8a2e3fc2a33b | note | Inspection / Test Method - Document Review
52abcf6c-8f67-57bc-b86c-3a20b033aadc | note | Record of conformity - Signed ITP
305a68db-939e-5b8b-954b-9c9ce4f9fbd5 | note | AP
d72ca4c4-d73a-5450-8cf5-3389f0ff38e7 | note | Responsibility - Site Engineer
| checkpoint | 2.04 - Granatic Gravel
30652c64-82ec-50ee-985c-4d36bc01b01e | note | Frequency - Prior to Commencing Excavation
0ba932a9-bc21-55a0-a240-5033d94b88e9 | note | Acceptance Criteria - Granatic gravel used for river edge terrace meets project requirements (size, type and quality).
7174d4bb-71f8-5db0-aebb-baac7556c124 | note | ○ Material sample provided to client for rview and approval
83b46b97-46e6-5d0e-a15e-dfb11e119563 | note | Reference Documents - Document Review
09d0c7f9-7731-5f88-ae07-57e5df717b18 | note | Inspection / Test Method - Site Inspection
a901492a-2264-5a67-acdc-ff0050f9159c | note | Record of conformity - Signed ITP
26d6635e-0595-56d4-99c7-77f72b1dbcdd | note | AP
c4268748-e7e8-5001-9c30-89c2e958d68c | note | Responsibility - Superintendent
| checkpoint | 2.05 - Feature Rock
7f7bc361-99f3-5a29-8a3f-64ed893be147 | note | Frequency - Prior to Commencing Excavation
6ff322d0-22c8-5f41-bf1c-3f99d9129b60 | note | Acceptance Criteria - Rock material used for river edge terrace meets project requirements (size, type and quality).
780c203d-4f52-5f59-a26c-635310a4bacc | note | ○ Material sample provided to client for rview and approval
0bf7991c-73db-5e58-a589-3a636ead6336 | note | Reference Documents - Document Review
ca8a400a-eb86-5ac3-9781-e0e680971191 | note | Inspection / Test Method - Site Inspection
16b827ff-6aec-58f5-976c-970b356825bd | note | Record of conformity - Signed ITP
3df8b66a-3710-5f7d-a484-4a07f043380a | note | AP
5f5701df-fd60-50c0-b029-f91d24300b9b | note | Responsibility - Superintendent
| checkpoint | 2.06 - Enviromental & Cultural Heritage Factors
50e5a3b9-1be7-537f-80c1-823806044cdd | note | Frequency - Prior to Commencing Excavation
6eab84be-e92d-5732-aaa7-5f9ddc256980 | note | Acceptance Criteria - Work affecting surrounding environment which is not pre-planned/approved in either Cultural heritage management plan (CHMP), Root Mapping Report, or Geotechnical reports is approved by client representative.
6f4a2388-2817-593b-a8a2-7a2902e8e319 | note | Reference Documents - CHMP, Root Mapping Report, Cliff stability Report, Geotechnical Report
09d818fd-2643-5ab2-8501-910982c1d00c | note | Inspection / Test Method - Site Inspection
a0dcf1bc-44c1-5e34-ad18-f36500723ef7 | note | Record of conformity - Signed ITP
3e70b073-fe25-5713-aa6d-aaba68563f9d | note | HP
899bad0b-e922-57ff-9367-92b51529775e | note | Responsibility - Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.07 - Preperation of underlying surface
2b8abbba-af2c-532b-80ba-c9e39bd47aec | note | Frequency - Prior to Commencing Excavation
ddb87e3e-3a7d-5719-ad8a-db9196aa1616 | note | Acceptance Criteria - Areas on which feature rocks & granetic gravel are to be placed shall be compacted and trimmed as required to provide a finished surface level in accordance with the drawings.
ab8ccd5c-97e0-5f7b-8b8b-d311371e73c5 | note | Reference Documents - Document Review
816c9601-9536-5e8f-b516-f680303a0d95 | note | Inspection / Test Method - Site Inspection
fe07d7b1-d970-5225-828e-d647cb1dfb0d | note | Record of conformity - Signed ITP
5e0a5b93-c132-5cb8-bbed-7c0f8dbe5ee1 | note | IP
62d65f97-eb4c-5471-8cb4-966d171d2f5b | note | Responsibility - Site Engineer
| checkpoint | 2.08 - Geofabric & Bedding
c4487a60-3287-5f2e-b1ee-edfad576bfc2 | note | Frequency - During Excavation
7c13da86-2f9f-55ed-9372-4cd6052d94e0 | note | Acceptance Criteria - Geofabric to be placed on excavated surface, followed by 100mm (compacted) crushed rock bedding as per design drawings.
5c9bfbc6-15ae-570b-a4ce-46eb2132b0a9 | note | Reference Documents - Document Review
444d75ca-d20e-5357-b166-136881df5eac | note | Inspection / Test Method - Site Inspection
c8eea92e-e4ad-5fbb-ae7a-260236198418 | note | Record of conformity - Signed ITP
89dda445-3284-5ffb-b3b1-dd1d03fea270 | note | IP
422ffeb5-4843-5529-a41f-6e9e04e1a6c2 | note | Responsibility - Site Engineer
| checkpoint | 2.09 - Feature Rock Placement
92e36948-c6d9-5fa0-b357-f2898aa79f2f | note | Frequency - During Excavation
8706fa4a-c6f3-5663-aaba-5198273194d2 | note | Acceptance Criteria - Feature rocks are placed as per design drawings.
3d341311-266d-569c-a9eb-117b33b77e0f | note | Reference Documents - Document Review
09cc5b70-e2b0-5d6e-8279-1a2c23af2a17 | note | Inspection / Test Method - Site Inspection
6b6c5a5a-5e8b-5a25-8cb6-2b0c770747ea | note | Record of conformity - Signed ITP
476f374c-4427-5700-8e38-652e4cfb0de3 | note | IP
bafbe85c-6c35-50ed-a47e-9d25b57e0ffe | note | Responsibility - Site Engineer
| checkpoint | 2.10 - Granatic Gravel Placement
c61f52fd-99c3-5ff3-a6ef-e7207287b0c0 | note | Frequency - During Excavation
fd009671-9aa5-5975-bdf3-940c36cab8b5 | note | Acceptance Criteria - Granatic gravel is placed as per drawings and spead to level at 50mm depth.
9ca45366-7d02-507e-8592-1b2500b6c099 | note | Reference Documents - Document Review
46d0456a-66f2-5ffe-be57-a31d0e222e76 | note | Inspection / Test Method - Site Inspection
629e1a35-5b3f-5bb9-b65a-73376e97f31c | note | Record of conformity - Signed ITP
93a304bc-a0be-5b37-974b-42ee250a1fa6 | note | IP
a5439492-e9e6-5e1b-9f37-c20569b42d88 | note | Responsibility - Site Engineer
| checkpoint | 2.10 - Final Inspection
7f27eda3-1112-5ae4-aed5-fc9955435b06 | note | Frequency - After Excavation
250444da-0b71-568f-be3d-102257c2e793 | note | Acceptance Criteria - client sign off to confirm river rock terrace meets design and quality.
d0c2cfdb-0a19-5551-b0fe-d7934489164d | note | Reference Documents - Document Review
910302d1-3b47-59a8-87cd-2a51049b18f4 | note | Inspection / Test Method - Site Inspection
d374b88b-f0fe-5f67-a2ee-f8e44c1ab81a | note | Record of conformity - Signed ITP
2bbc1f62-41cf-5b74-a500-734f88a1aeb5 | note | HP
0d009f60-b013-57b4-9fab-0773f7898848 | note | Responsibility - Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - Environmental Impact Assesment
3da93ccd-c75f-5f00-bee6-36dd1cdc59d1 | note | Frequency - After Excavation
6b6cc412-fe3d-5981-aaca-7168eb6ecf1d | note | Acceptance Criteria - The installation has not negatively impacted the surrounding environment.
9ca28cda-325e-54b4-85ed-5b978d410a27 | note | ○ No signs of instability or erosion post installation.
67a34abf-cc91-56ba-a493-a6d3940907a5 | note | Reference Documents - Document Review
faaa3caa-b35b-5f5b-99c1-9b25ffbdbafb | note | Inspection / Test Method - Site Inspection
041a2696-b64d-5c51-af26-965a9182a734 | note | Record of conformity - Signed ITP
4270138d-bbb3-5423-b4d8-0e157301abfa | note | IP
3cfc9805-f0f8-589a-8ac1-ed4993105b14 | note | Responsibility - Site Engineer
| checkpoint | Final Inspection
b910a4e1-2e55-544f-ae8f-70bbd151da99 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
2c677ab0-c6d8-510e-9b4c-45586877d45f | textbox | Print Name:
3aa6a6e2-aae6-5597-84b7-94ec923c9331 | textbox | Position:
cc5f7e54-be35-5994-9be4-6ae6382484fe | date | Date:
| signoff | Sign ITP
| checklist | ITP-002 - Earthworks | itp | ITP-002 - Earthworks | a1c13c96-9540-4df8-af90-a6a42142b510
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
63ef06e4-2920-5a35-b5b9-535fc9e300ba | note | FREQUENCY: Prior to commencing any activity
975a3e51-9557-5498-a0e6-f409be88ad10 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
613e7170-9728-5570-9c31-94beb88c7c44 | note | – using the correct and complete set of drawings
8feb9044-c864-5b37-9c61-519e64230102 | note | – all drawings are the latest revision
7ef1083c-e883-5714-9b92-dd73a27abd47 | note | REFERENCE DOCUMENTS: IFC Drawings
c62d4720-bd30-52d5-8674-bf431547ccff | note | METHOD: Visual Inspection
661abbd6-eca8-532e-a3ff-1a64e77beb1b | note | RECORD: Signed ITP
9a9af3b3-4708-566d-a616-369ced59562c | note | IHP
72fb4da4-635e-5a66-ab2f-552827b9e2ba | note | RESPONSIBILITY: SWA Project Manager
51e49a8c-5445-526e-984b-423795089fd5 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
07d8c898-2208-523a-80f7-1387c0f63df8 | note | FREQUENCY: Prior to commencing any activity
0751365c-1d20-5c53-b1bb-3b51d00d3665 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
a8f70dba-46e3-5a26-95d6-26e96fae383e | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
1352caef-d602-554b-a7da-1423cabffbbb | note | METHOD: Visual Inspection
a0b75b41-f0dd-5860-96b6-6da3307d8ce6 | note | RECORD: Signed ITP
b53b50a3-f195-5159-859f-bc717daeffdb | note | IHP
06ed450d-b079-5465-9db2-0846a76be876 | note | RESPONSIBILITY: SWA Project Manager
7c543fa3-0593-5ec2-863a-f310fc8ca8f9 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
046dd51c-0175-5459-a6c5-f55a289e5f9f | note | FREQUENCY: Prior to commencement of excavation.
59adf8ec-c302-58b0-9358-84cc178503e2 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
f4ef093d-e2c1-520a-bcb4-4f73075c4346 | note | REFERENCE DOCUMENTS: Work Procedure
6cb1adab-fa85-5394-b96a-55d7a6d14d84 | note | METHOD: Verify
f4f4540d-46e7-5141-aded-2d93b7455cf6 | note | RECORD: Signed ITP
8ef72872-7802-5f59-bf65-b457024a33ac | note | IP
4357050c-8bee-5b9c-851a-a546b7d3e05b | note | RESPONSIBILITY: SWA Project Manager
4f7fa3db-aedc-5e1b-aadc-9eee1d7a7f47 | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
b66700e3-f3fb-5637-82da-e55576bdf4b2 | note | FREQUENCY: Each Lot
19e84c8b-81ad-5fc9-9c1c-2cf7de12c162 | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
ce7a9b89-7a27-5c68-9149-9254a6ab0e3c | note | REFERENCE DOCUMENTS: Excavation Permit
1fcaa11d-5c25-529c-bc7a-fb66f002513e | note | METHOD: Verify
b940a2cc-622a-5268-b6d5-4174d5bfe926 | note | RECORD: Signed ITP
8d23f1bc-479e-5750-b0a8-4dc379f2e99d | note | IHP/IP
19cde785-dfd3-5089-a243-0103582f7314 | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
329413a2-cceb-5639-8216-500c4af30ad1 | date | Date Completed:
| checkpoint | 2.3 - Sub grade Material Properties
5fd83012-c466-593d-9c1a-748bded75184 | note | FREQUENCY: Each Lot
afe4b2e2-ed25-5b1b-9af5-d1e138adac8a | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut ﬂoor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
a1ffa119-4d34-5673-9c44-9dc6ea662460 | note | ○ If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
ad5e0754-0df5-5c5e-abad-2aae1ada4c77 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
8ae13c3c-13ac-50c2-8189-e50b75a74f02 | note | METHOD: Site Inspection/Test Report
6d2aaaa3-68de-5559-b12a-b31c9741aade | note | RECORD: Signed ITP & Test Report
07fd6496-84d5-54b1-b081-eab94ff926ce | note | TP/AP
10ab7e0c-4532-54d5-a31a-e33a6cd96b1d | note | RESPONSIBILITY: SWA Project Manager/External testing Company representative/RRV Superintendent
3e8552c4-a105-5534-846a-e1af640e3f76 | date | Date Completed:
| checkpoint | 2.4 - Inspection of Subgrade Material
fc2ff622-f8b0-5225-9a20-3b3fb6fdc287 | note | FREQUENCY: Each Lot
13024377-9a3c-5b23-84e9-ad46c0eb0d37 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to veriﬁcation by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
d2cc98f5-f540-50ae-8a5e-e3e548ef5835 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
0db4cef1-508a-5807-bef9-04f66542a0d3 | note | METHOD: Visual Inspection
76a001cd-1c60-595d-81ea-30fe6d7c513e | note | RECORD: Signed ITP
5b5cb03e-be09-5c3e-ae18-32be5d6e95ec | note | IHP/AP
c06704ae-32fe-5fa2-9cb1-3c0294866db3 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
d3926330-b65c-5374-aab5-5164629eeec9 | date | Date Completed:
| checkpoint | 2.5 - Material Classiﬁed as Silt
43018c9f-362c-57f1-a789-d614010c526d | note | FREQUENCY: Prior to commencing
762a0a86-0d34-5b1d-abfa-fa16440eb526 | note | ACCEPTANCE CRITERIA: Material classiﬁed as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
56b42410-7b7a-50f6-b7d5-89d80bb5a441 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (e)
68b0c69e-dc73-5f91-a426-5d5e86656bb2 | note | METHOD: Visual Inspection
5e98c672-e09a-5ac8-982a-016dbe24374d | note | RECORD: Signed ITP
cf5098b9-e705-5cac-a813-266e60de3dc5 | note | IHP/AP
b907f15a-9cc7-564b-8b66-da57e9316eb3 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
a0191669-b753-5b5a-a7a3-8c73f82bad58 | date | Date Completed:
| checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
cb481af3-2357-5cbf-ad97-bc04aed2500c | note | FREQUENCY: Prior construction of the regulating layer.
51f0b093-c186-5f27-a8c3-ccabdfbfd53c | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
8ad4bf0a-5290-51af-a3e5-ee684a223608 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
61cb11b6-7c28-56b9-8dc8-cf645c711174 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (f)
14a6497b-1d6f-5818-8481-9bf14cba7709 | note | METHOD: Site Inspection/ Document Review
d35e44fd-e587-5be6-a24f-718975f149ec | note | RECORD: Signed ITP
49338d4e-2a96-5325-800c-ad111c64dd75 | note | IHP/AP
12cb7c2b-36df-5553-ba6f-24e68e0207a8 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
2b1425cc-b454-5d77-98dd-96bd3b7aa072 | date | Date Completed:
| checkpoint | 2.7 - Unsuitable Material
db94795f-3834-5c1c-91f3-9fc4301600ab | note | FREQUENCY: Each lot as required
702af76c-3a00-56f1-9fd7-7ccc840360ca | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review
1b3e2ac5-48c1-5654-bd54-7761b3098b42 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (d)
36c5022f-b720-5452-8061-86025516a283 | note | METHOD: Visual Inspection
244ed7f3-e86b-5bac-9517-ea83524d8369 | note | RECORD: Signed ITP & Test Reports
f80bc235-fc80-596b-85fd-e33c182b9bd7 | note | IHP/AP/TP
f10559a8-06b7-5b31-8da5-5968ae7501a7 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
56094748-985f-5079-8f95-88fb28e47e3f | date | Date Completed:
| checkpoint | 2.8 - Groundwater
8e947778-8b84-5100-89f5-2f3fd0129bdf | note | FREQUENCY: Each lot as required
7673e185-bc79-53b7-bcb2-29c2e8a77f19 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
516134ef-d6bb-59c1-8b17-ab08d4c1f88c | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (h)
d1271fbf-7904-518b-b1e7-07dbd73a020f | note | METHOD: Visual Inspection
5ea962a4-e35d-5646-9f69-39256bf464cd | note | RECORD: Signed ITP & Test Reports
3692b2d5-c7e4-55f3-90a5-cbebc233d986 | note | IHP/AP
cc609a62-4df2-51a4-b6b1-bc840724da7e | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
9e689064-6953-575d-8309-6c093fb7d00c | date | Date Completed:
| checkpoint | 2.9 - Trimming and level conformity
61509124-0ebf-5b78-8745-f05a38c4eab4 | note | FREQUENCY: Each lot as required
a17b198b-f0c1-55dd-8a4a-d54afc2b9c1c | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
0d7a5745-75d9-57e4-9081-7b79048b2506 | note | ○ Level tolerances: Range x (Mean value of all measurements) (Scale A) x = +5, -25mm (Scale B )x = +5, -15mm
ad920ce8-f8b7-53b3-8743-60328344a9de | note | ○ Max S (Standard deviation of all readings) (Scale A) = 12 mm (Scale B) = 15 mm
5e252ff1-5950-54c6-bf76-db5a1f002010 | note | ○ No. measurements (Scale A) 80 per lot (Scale B) 40 per lot
87493cb0-d115-51c4-9d1f-759d71102d10 | note | REFERENCE DOCUMENTS: VcRoads Std 204.03 (f,g,h) Table 204.031
d04f4af3-fe8c-5e49-bcac-93f66a7ec19d | note | METHOD: Survey
311b327e-4037-5495-95d9-fdd693c1be25 | note | RECORD: Signed ITP & Survey Report
1018ec42-1b82-5abf-96e9-81d3440f82b4 | note | SCP
92e60c36-bee9-5e0c-8f85-d4a9bc691cf3 | note | RESPONSIBILITY: SWA Project Manager/External Surveyor
3b911a52-4913-54fd-8ba4-e6fcbb275574 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Test Rolling
d3a1bc80-faee-5112-bc75-bec68db18977 | note | FREQUENCY: Each lot as required
4e918e84-6387-53fd-91c4-0ca52044fde4 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03.
5aaa4854-fe7e-5cad-b4e1-74d41e8f3994 | note | ○ Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
4277ddd7-f14f-588f-b3b9-ea39086bd6ec | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Section173.03 173.03 (ii)
6ba8ef5c-35b4-5365-a45f-95d31a5cef58 | note | METHOD: Visual Inspection
1a0d1f68-b539-5451-b907-0976dddbb2e2 | note | RECORD: Signed ITP
9b6dc80f-3f74-52a8-8bd4-abfbdd979797 | note | IHP/WP
9ead8112-2025-5ed7-be9d-429f573ab070 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
b2ea547c-739f-5d7f-aa8f-212f732da151 | date | Date Completed:
| checkpoint | 3.2 - Compaction Testing
f6a27ea9-f413-5e1c-9775-326bd9c2ee19 | note | FREQUENCY: Each lot as required
cb715b59-c134-524b-89fc-b956d96a3462 | note | ACCEPTANCE CRITERIA: Ripped and re- compacted material below Cut Floor Level = minimum compaction 98%.
e62dc0ef-1dae-5206-971f-c837806fad71 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 98%.
5d92ffe2-2202-5931-b8a7-a03620b229c9 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where ﬁll is to be constructed = minimum compaction 95%.
ce30c178-8296-5470-93d3-337682e65b40 | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Table 204.131
8cc9c55b-be60-5c5c-a496-fe978d289bd0 | note | METHOD: Compaction Test
1e3b7c0a-b2a1-539a-bacd-7cfd0f0697dc | note | RECORD: Signed ITP & Test Reports
56699200-6334-5d20-84a4-70d33c6231aa | note | IHP/AP/TP
a0e93b15-f5af-5c9a-8e7c-cf39d73bfe28 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representative
bfd3e807-29e4-5f56-ae7a-2ce38924e07a | date | Date Completed:
| checkpoint | Final Inspection
dcd25591-fde7-5bcd-a09b-d3e6d47d71ec | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
16a05b1a-935d-5290-8681-c77a6eab76c0 | textbox | Print Name:
64743c84-a5c9-5c74-99f1-e395de6b42c8 | textbox | Position:
49bd4889-f620-5147-a465-3d6c08b91f49 | date | Date:
| signoff | Sign ITP
| checklist | ITP-004 - Underground Drainage | itp | ITP-004 - Underground Drainage | 555a15e2-c394-4195-b3b7-2def244e05c1
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
ff7f771d-f196-5e94-89c0-d98ee7bccdc5 | note | FREQUENCY: Prior to commencing works
f1e48edd-754f-5254-98e2-0d81f4bf1295 | note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
846dc3d1-3f0d-548b-88ce-ec81a4516cfc | note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
3b32932d-65ad-5802-8d9b-f12f832e80a9 | note | METHOD: Visual Inspection
9af47316-48b4-5e62-a789-d9cb5127c919 | note | RECORD: Signed ITP
09237390-a739-5faf-b772-8dade004f4a6 | note | IHP
7c013968-a164-5048-9bf4-0e39e513a1eb | note | RESPONSIBILITY: SWA Project Manager
30b0e11b-b6b1-5617-ae1d-0998085e5877 | date | Date Completed:
| checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
195669b0-1473-5494-a15a-ad3ec8a39b49 | note | FREQUENCY: Approval prior to placement of order
31a43218-3e13-5342-b183-b8ec49858bb2 | note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
5700c480-85eb-5218-93a3-706a1f664619 | note | REFERENCE DOCUMENTS: Vic roads Standard drawings
dd1103a1-592e-5fa2-a1df-403df97b4a5e | note | METHOD: Review and approval of documentation, Visual inspection
b1ea887b-e0bf-56d9-9b74-1e58a173bb73 | note | RECORD: Signed ITP
87e90362-6a1a-532a-b98e-3458a3a56f01 | note | IHP
ef83053c-2695-53b4-b1cd-2a6e14967af3 | note | RESPONSIBILITY: SWA Project Manager
4eee7202-5202-5afd-a007-1628a7ce0d0f | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
41bc5e39-ebc3-5862-ae41-6030e1febc70 | note | FREQUENCY: Each lot as required
8048936d-695b-5cdd-937b-b38056a05933 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
44adf031-0957-5d70-9ecf-c9728a776289 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
2af47ceb-97b3-5f1e-8621-68cb1577ea32 | note | METHOD: Construction Drawings
4eb6ebae-de34-501e-b1c7-690696fc4379 | note | RECORD: Signed ITP
c1e9b9c5-bfe7-56fc-8315-e88f4513fc5d | note | IHP
0314b7e7-da94-50cc-96a9-00fc9f06bed8 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
b225dc7d-df7d-533f-8ab6-615287710640 | date | Date Completed:
| checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
2253bb94-74fd-544f-b1be-00da20521073 | note | FREQUENCY: Each Lot
d326f21e-5a8e-5f77-b41b-fd03ece16966 | note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
91a11db4-0d59-5076-8514-b961491675e5 | note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
7af79b61-d7d4-592d-b239-f1ea814f9603 | note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
5ccb1813-f18a-572c-ad93-988c6e037d8b | note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
d89417c4-1dbd-54c6-a591-3542d3627404 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
6e29027b-260e-5746-8b1e-04e31e593e2a | note | METHOD: Construction Drawings
f646c043-e403-532e-bf52-ac5c9d1595e4 | note | RECORD: Signed ITP
5796186f-716a-5899-afe2-91ea32a06e83 | note | IHP
08433fe9-66f6-596e-b684-be188dd7aa3d | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
f4968ee5-7261-587f-a4c3-61303e64aad8 | date | Date Completed:
| checkpoint | 2.3 - EXCAVATION
eb6a81b1-106b-5f34-acc5-de0ef1dc8f6b | note | FREQUENCY: Each Lot
d37c6318-756c-531a-b22b-17daa23f131a | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
5f543bae-e0ac-5b82-80d5-ad5d368ef555 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
239f74ed-19b8-5b33-a3e6-4f71c526e866 | note | METHOD: On-site Measurement
c5554e91-31f3-535b-a926-8a87cca0db04 | note | RECORD: Signed ITP & Drainage Checklist
a828992a-5878-5fea-a175-7d8ac53ec858 | note | WP
33b10b9d-3efd-5adc-aff9-bbe3d9ff2872 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
d8375f6f-ff33-5a15-b156-fb2952ca0d6e | date | Date Completed:
| checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
25edea32-d970-5686-9c14-edca3b9efbfc | note | FREQUENCY: Each Lot
eb66c574-bb8f-5179-b2c3-6a00493b25af | note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
3388aab4-97b7-511f-94a8-f344513ebbc7 | note | ○ 100 mm where D < 1500 mm
7d4a4a5d-71ea-55d7-af83-c565b0b0ecd2 | note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
63c746b0-d9c2-53e3-82b2-3869e08c7f7f | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
1efcf702-d6c4-5fc2-b96a-28f08dfcd303 | note | METHOD: Site Inspection
18a937f2-a3e1-5bfd-80bd-dcaa997371f6 | note | RECORD: Signed ITP
cfb493f4-4784-5d48-844f-4e73bfc61023 | note | WP
bfa05788-6b45-5bad-ac25-11dc14849300 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
164537f7-8e27-51d7-84f9-89a18d28af18 | date | Date Completed:
| checkpoint | 2.5 - PLACEMENT OF FILLING
c1c0360c-17a2-5ff3-bc82-281da7c28cc7 | note | FREQUENCY: Each lot as required
bd9a776e-abe2-546a-b401-bb87129b5561 | note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
160d80d9-ff77-5f51-b798-2054f70cd708 | note | (I) Culvert Under Area not to be Paved
0520f71c-d372-5b7a-915f-3b14a6e7c495 | note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
288ada38-b0ab-508b-a609-231cf2a5eb01 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
c11628d9-8c2f-547c-a3d4-bd3c29584dbd | note | METHOD: Site Inspection
34d13068-7144-586d-9cb4-8dc1e9561164 | note | RECORD: Signed ITP
fa434381-2d8a-5b79-8a37-a56f27a08b6b | note | WP
95987a52-448a-5ad6-ad46-d0a13403a993 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
96f4d2af-c83c-5fea-88d4-62590757ddd1 | date | Date Completed:
| checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
138dc408-69fc-5f5a-8457-3469d3d95724 | note | FREQUENCY: Each lot as required
9a2feca4-3283-5092-bfd0-a4678f117675 | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
4e9109f9-343f-5fbc-9da1-718231d95947 | note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
87e7f08a-f96f-5d07-b90d-aa12b5d88b49 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
62e347ab-b426-508c-ae0c-1024c9cc5cfa | note | METHOD: Visual inspection
d7f8dc8d-3819-5d55-8f64-c2b409877f47 | note | RECORD: Signed ITP
8089c255-87cb-5470-a96e-b2c801bafb1d | note | HP/AP
c3e603f4-4c5b-53b7-8f4f-ee08d4470d78 | note | RESPONSIBILITY: Project Engineer/Clients Superinten dent
d5bd297f-9113-5a39-b980-f5e0b8f88b12 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
cd3f9388-74bb-5021-a6db-086733703b09 | note | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
bf175921-e803-564c-8f3d-1bf7d662556d | note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
a88ccc67-6170-5043-a577-bb75f2d995aa | note | REFERENCE DOCUMENTS: NIL
c4b9166f-c4a8-5869-8242-4ff325f26b11 | note | METHOD: Visual inspection
8d82beaf-77e0-5b9c-877d-eefb3b017b03 | note | RECORD: Signed ITP
bdadf9cc-a6a1-5f77-81ee-d96f0df941b1 | note | IHP
d4dafda0-0727-562c-994e-7c2f64c04999 | note | RESPONSIBILITY: Project Engineer/Si te Supervisor
aebf675d-db93-5925-94f6-6aaaedf55e39 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
38f7f3fd-186b-5a94-9d3c-d46cfddc8722 | note | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
39406688-46e7-5934-88dd-11172fada3d6 | note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
fc9b0346-7df2-5e7c-8e79-36472f115322 | note | (b) Backﬁll
84515d71-0f2e-55eb-9c0a-e16782ff187a | note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
73d39840-e6d7-5c0b-8fd4-8bafe562197f | note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
396e2c2c-1b7b-578c-bd19-8bc8eb1b9057 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
b4b94626-f9df-5024-bf29-1e39dbd6c81e | note | METHOD: Lab Test
74d128c5-1452-5f90-beee-94ceb44c230b | note | RECORD: Signed ITP
3782413a-7cf5-5707-89ed-a514e9b0186e | note | IHP
020dfa56-df5b-5eee-81e0-d26e3b402d1a | note | RESPONSIBILITY: SWA Project Manager
1492241a-2e16-51e4-bc88-241b9eba531f | date | Date Completed:
| checkpoint | Final Inspection
bd0e6189-8169-5e75-838d-b3124d3c7a13 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
0db37f49-dd06-5ab4-9403-1ca4a21edb57 | textbox | Print Name:
f9cbb62d-571f-5bfd-bb23-97eeb63cd4a6 | textbox | Position:
52ce646b-4fd7-5d88-bf27-a1d49b30da0a | date | Date:
| signoff | Sign ITP
| checklist | ITP-005 - Flexible Pavement Construction | itp | ITP-005 - Flexible Pavement Construction | 8e95ad02-824a-4de1-905c-ed068ecc0ebf
| section | 1 - Preliminary Works
| checkpoint | 1.1 - SET OUT OF WORKS
21a438d3-f799-5869-9ca0-65c3b2e95d5d | note | FREQUENCY: Each lot as required
1d06acbf-a00b-5e03-9db8-c71bc225cc9b | note | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
e7ec4598-5998-59f4-a6da-3f7c62b4d1c4 | note | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
472ba5b7-b2fb-5b14-afce-13d6e376b05d | note | ○ Refence checking to be conducted with string lines
56cd3848-d046-5659-9cff-3b5220170d1e | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
3c2d0e5c-ad3e-51fb-98da-f6b89fada6e6 | note | METHOD: Survey set-out
46d63712-60bf-5ace-98dd-1bb84e6dab98 | note | RECORD: Signed ITP
21f50034-22b9-5a3f-a7a2-09ceb5f4bd7e | note | SCP
703fbd8e-ae1f-50f0-8dd9-fd0f1075f13b | note | RESPONSIBILITY: SWA Project Manager
2c71cf9a-452c-5dba-96a4-f047f6c8fbae | date | Date Completed:
| checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
e0c1e4c3-01ae-5a28-a97c-457c30e6c254 | note | FREQUENCY: Prior to commencing any activity
83cee339-0a84-599d-96a0-5475fb179165 | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
77b93b7c-0603-5666-8f86-2d17e5e3bf3e | note | REFERENCE DOCUMENTS: Vicroads std sec 204.03
bb1ab119-fea3-5851-ae1a-f1ed4b3d8e0d | note | METHOD: Survey Report
f870a3d7-5a52-5e57-a3ad-fb8808c4ba5c | note | RECORD: Signed ITP
9a11a0fc-62d5-5c21-baed-7d41c3cfb678 | note | IHP
d54a04d6-e5f9-5007-a6a1-5f5743055cd1 | note | RESPONSIBILITY: SWA Project Manager
103858ec-6146-5004-8f4e-cc047cefe7fe | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
4f049f58-666a-5046-a5a3-8c374b9a2092 | note | FREQUENCY: Each lot as required
890cc7f0-2c5e-5912-a0df-e7880170454d | note | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
33ba4406-6891-5a3e-be9b-aeb2dd202059 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
45aafbde-c218-53c8-ba9f-ec8067913673 | note | METHOD: Visual & Laboratory Report
21091960-9352-507b-9d8e-8277980a5e20 | note | RECORD: Signed ITP
6b7d5eae-9cf2-575f-ad7d-b90f11fad58e | note | IHP/AP
80f3b5fd-1d3f-5c4a-af15-dbc902752ec9 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
5b1c301b-eca4-5af8-918b-90a5383de1df | date | Date Completed:
| checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
f0d761e5-1cf1-5154-9067-05b632345722 | note | FREQUENCY: Each Lot
73f4bc54-68aa-56d1-8e9f-b58949ad10f5 | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
58ca41af-e55f-53c8-ac78-0969bd212cab | note | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
7298ed6a-a8d2-5300-ad8c-a877189c71ff | note | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
673b97e8-f973-55cc-a012-7eff9d3dd982 | note | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
2d522158-75e2-5ada-b75c-c6d64e3633b6 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
5a2a1a0f-8eb3-5562-985f-a06d6a3bd2ca | note | METHOD: Laboratory Test Report
38b38ded-4382-55a9-8321-91cce0bafc89 | note | RECORD: Signed ITP
fc050c64-6bbd-5fcc-a1d3-60db57ebc55a | note | IHP/IP/AP
aa41352b-a014-580f-a92f-f3367cc11c4d | note | RESPONSIBILITY: SWA Project Manager/SWA Site supervisor/RRV Superintendent
091e976c-11b3-5010-bec3-26cdfc39bcbf | date | Date Completed:
| checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
cf26d6d1-0a57-51a5-8998-6140e6be89af | note | FREQUENCY: Each Lot
7021f6a6-d397-5d7a-891b-d587e34330a3 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
b77690bb-91cb-57fc-89d4-7c8858b0d4ec | note | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
ddebae22-3f6e-5344-8a8a-847524cc851a | note | METHOD: Proof roll
5502962f-5656-5b8c-b4cc-be0affcca612 | note | RECORD: Signed ITP & Test Report
1d60d458-0615-5369-8e39-1fa82e4810bb | note | HP/AP
fb4f3192-b1fb-5ea8-99b9-42ab1d8acccb | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
35502628-900b-5e3a-81f1-cd8fab79ff54 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
dd9451ef-7628-5777-b511-8406baf71479 | note | FREQUENCY: Each Lot
b5517203-2972-5415-a154-7513e172b6f0 | note | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
93744061-4d1c-5633-81ff-e0fcad3646da | note | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
7ca6e396-4048-5fbb-a817-d7b9b6aec8eb | note | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
8e8eaa68-3058-5d05-bab8-40a44dbc94ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
1bb3836a-8681-55de-961b-4ea84c3730ab | note | METHOD: Survey report
c9b54e4d-138a-5902-a65d-40167a8a0199 | note | RECORD: Signed ITP
17e955f5-a405-5b78-9b63-88db0449b409 | note | IHP/WP
0ee07f49-db61-5573-aa0e-f85d91236efa | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
0e76f698-81d7-554d-acc6-0a5da44178f2 | date | Date Completed:
| checkpoint | Final Inspection
7ac89bf9-222c-5771-bff6-eadc91bf12d7 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
726d8fff-32d0-5a53-897e-89e54955aa0a | textbox | Print Name:
9fd2b4b9-a3d2-5ac2-ae5f-5981ed4b8a07 | textbox | Position:
2b92b7c0-85c8-53f5-8ecf-7a7cc9248cd9 | date | Date:
| signoff | Sign ITP
| checklist | ITP-006 - Kerb & Channel | itp | ITP-006 - Kerb & Channel | a4d29837-c0f6-4b8e-8931-9cd929c359d9
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
406918ce-3cdc-5bf1-b99b-1cc0ce3670a6 | note | FREQUENCY: Prior to commencing any activity
e011307f-87f3-5b57-afc6-849b34cae3d6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
be8c534a-b509-5771-ac62-7b511d66b998 | note | – using the correct and complete set of drawings
c69f4138-b3f7-51db-b97d-ccc326af37c6 | note | – all drawings are the latest revision
822ffbea-10b5-5f82-8ab0-f8c159005040 | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
34936628-eb58-5204-b959-a44867dbf91e | note | METHOD: Drawing Register
79444e64-5635-591e-91f8-b477547447c6 | note | RECORD: Signed ITP
d9bd5ac5-3489-5b71-9430-2ce1611cfa4d | note | IHP
add5cad4-344d-5ff9-9b01-f3492d8fa430 | note | RESPONSIBILITY: Site Supervisor
f8ea5604-b840-516b-b9b6-3986295a792a | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
f1ed7616-4da5-594e-89ed-b752ad56207f | note | FREQUENCY: Prior to commencing any activity
897e971e-0b58-53da-ba2b-45c29e989652 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
a01e5185-92e6-5d8d-a6f3-c9eea4ec684c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c3a498a8-cfc9-5cf9-91bd-4bdad6bfba9d | note | METHOD: Visual Inspection
47148980-a363-51fc-aec0-5235296d4922 | note | RECORD: Signed ITP
bc3fe039-08d6-5b5e-a8c2-555746084963 | note | IP
e13d9d0a-b15d-5f8b-bd51-dc48258f1cb3 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
2a2f6067-9e00-575e-b431-248df43cc440 | date | Date Completed:
| checkpoint | 1.3 - Setting Out
f103293e-2257-5261-bc5c-72da2d09ed65 | note | FREQUENCY: Prior to commencing any activity
2fed43cc-312a-53e7-8a8e-f9ece4210455 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
31f53ffb-c188-501b-9f47-21af8c4b9fd6 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.13
1688d011-d595-5d40-bfd1-813a57c0c5d8 | note | METHOD: Survey Setout
f132a59f-8e2b-5db4-ac00-1a50c25e51f6 | note | RECORD: Signed ITP
abe4a46c-5cab-59fd-919b-5f5eb81e9ca2 | note | IP
cf7c601a-6eea-58c4-92bf-cbcbc7a6625c | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
941f7e22-16ae-5d20-ab1b-03abed20d5b2 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation
fc4b5e5e-7efc-5785-b195-266e3c5e4d0b | note | FREQUENCY: Check prior to placing material
391c45c5-f8e1-5129-a718-7cde5ad901d0 | note | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
cd4e7867-48ed-52ef-8f01-7af0c0fe7913 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.20
395c6ce3-2753-51a3-93ac-2c98f38853b7 | note | METHOD: Survey/Site Inspection
b6a9d6b7-6aa3-5b2d-9e12-f998914f0c63 | note | RECORD: Signed ITP
3851b852-2945-58a2-b5e1-49e85c93b11c | note | IP
2748247b-269e-5276-8976-c1df5a2cb9ee | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
275a27df-78e2-54bb-beba-bccd1405ef56 | date | Date Completed:
| checkpoint | 2.2 - Subgrade Inspection
7419fe17-5292-5f9b-af6e-6ab9f3ed0a53 | note | FREQUENCY: Check prior to placing material
b448cca9-b6ce-5da8-b0e3-7d05f86ef3be | note | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
0728161c-0c6a-5ff6-b941-64cfbc2b7da1 | note | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
f39ed3b9-079b-58c8-9755-6fb9aba9ef11 | note | METHOD: Visual Inspection
e468e85e-66dc-585b-991d-a6061a47cd52 | note | RECORD: Signed ITP
68dbdd3b-1e7b-591b-9528-31a809df4c41 | note | IP
ba0308c4-4a24-5f91-9915-59aa7615f963 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
86650319-7ccf-5b27-a073-c105b613572c | date | Date Completed:
| checkpoint | 2.3 - Bedding Preparation
e59e6c97-83db-5648-ac91-397818f406a7 | note | FREQUENCY: Each lot as required
7ba6e700-5771-54d0-8877-7f24e9b6b106 | note | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
3f13d882-6cd5-5b8c-977a-a1143ab675b9 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
41f35c2c-a05f-520f-a7ec-6ec733bf708f | note | METHOD: Site Inspection
fbe9548a-bbbd-542c-8d90-54fc5c63104e | note | RECORD: Signed ITP
ddd43e43-3217-5d2f-b08d-63fe96bf5a7a | note | IP
fdc53d79-8c28-5630-813c-dcc3012d51a1 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
55becea8-8fc6-5e8f-9292-936708566548 | date | Date Completed:
| checkpoint | 2.4 - Kerb Concrete Mixture/Strength
1a135d14-44b7-59ab-abdf-e5d70cf31fbd | note | FREQUENCY: Each lot as required
3f26fb6f-256e-598e-b9e6-32f4e8b8994e | note | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
7b5cdbee-30f5-5e93-891b-da9cfc6152a2 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
65ecbc29-e2f8-5f0c-9b01-3b2f4a5cf809 | note | METHOD: Delivery Dockets
257a7f1c-f457-59cb-8c77-b6d58c927c89 | note | RECORD: Signed ITP
87154659-50e1-5da3-a1fe-e622c69d60d0 | note | IP
3593b420-23e2-5fba-aa66-ea5339877f43 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
0655ebfd-b77c-57fd-9155-b251f8b36dbe | date | Date Completed:
| checkpoint | 2.5 - Tolerances on Line, Level & Shape
8e4afeb6-97d5-5635-ad08-b6d52ddb3959 | note | FREQUENCY: Each lot as required
d8372740-cf9d-51c8-aef2-29373cca4e95 | note | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
9a5ffbb5-5164-51dd-b467-84c02f5bad84 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
6158c054-13b7-53b6-8521-4c14420bbc7b | note | METHOD: Visual Inspection
ba02012e-f3de-5cee-947a-ccc94dab95a8 | note | RECORD: Signed ITP
8bc8d6a9-f2df-5f9f-9f39-9ee3ee69107b | note | IHP
7d102f00-ae1b-5335-bdd7-2293953dcd21 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
fbf4435c-3c54-5df9-91a3-a82a670999a0 | date | Date Completed:
| checkpoint | 2.6 - Kerb and Channel Finish
152a4c81-2200-58c7-8846-475a98e97122 | note | FREQUENCY: Each lot as required
710f7d21-3cbf-56cd-8d40-0e5b7b49ca9e | note | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
efff80fd-0242-5e39-80b8-c9f8160181d1 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
d850c6d3-a71c-5054-84ea-71aeafd4b346 | note | METHOD: Visual Inspection
76ab2fe7-1bdf-5321-b5f0-3284d7615a29 | note | RECORD: Signed ITP
53219070-0f0e-5f92-92bc-22136a46688c | note | IHP
57dd1aee-e3f5-572b-a8dc-2d732d48fef2 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
394a1dec-5c62-5a2c-8294-8922811baf6e | date | Date Completed:
| checkpoint | 2.7 - Kerb Backﬁll
c74426ba-4f22-5b05-9f10-30fcfc2e71d4 | note | FREQUENCY: Each lot as required
7ca14e0d-b321-5913-b323-51a9714edbf0 | note | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
53f8edff-f0ea-5e80-bed1-59c7560088b6 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
7bc19819-ca2e-5e79-894d-e29bd539afa5 | note | METHOD: Visual Inspection
080fb305-c66f-556d-a03a-33861058893c | note | RECORD: Signed ITP
2d9a91b8-51ff-5edb-b545-a8456e4f6752 | note | IHP
df133037-dd9a-5711-96ad-bf48ac9a8097 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
6bb7c0a6-e316-5ac0-94bc-a436be1504c3 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Compaction Testing
b307cbbb-e0f3-54c8-a277-335031719f5e | note | FREQUENCY: Each lot as required
2f6160d1-c830-5bc1-b0c3-4f14ddd3bb97 | note | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
b9b69829-6d11-5e75-9067-7720b2b6557b | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
6adc21e0-8da3-58ab-aefd-8685be89e42b | note | METHOD: Test Point
a92a55bc-a934-53b1-90dd-41b857704a5e | note | RECORD: Signed ITP
55bcf49e-48ab-5bbe-9874-4ef19631138f | note | TP/HP/AP
c3d35af1-f2f2-529e-bd5e-850d1d7fa0be | note | RESPONSIBILITY: External Geo tester/SWA Project Manager/RRV Superintendent
ccbb13b1-06f1-5589-940d-1c78307f3d56 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
3f41a8b5-9b84-545e-a8f7-47afadee5d0b | note | FREQUENCY: Each lot as required
64bce072-3844-521b-a3a0-5dd2b3a16ba7 | note | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
e6dbae4c-ba22-505f-9712-e8ae967f620b | note | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
c07a8be1-b11d-51db-9679-f6b7058ac38c | note | METHOD: Survey Report
a73228ac-bee6-5e95-a53a-30015f0e35a9 | note | RECORD: Signed ITP & Test Reports
e0effab5-22c2-5331-abf3-391f5ddfa888 | note | TP/HP/AP
fb96dc8c-7e23-5fe2-9ae0-dfdbcf9b46db | note | RESPONSIBILITY: External Surveyor/SWA Project Manager/RRV Superintendent
bc9f3d1f-b1b4-541c-8f87-805c1d330bcc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
8138864d-4a3b-5bda-986f-6aa83420317b | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
873f6803-4544-5ef3-a4f4-c6a4310767ef | textbox | Print Name:
db859f22-cc9e-5287-af0c-cf55b244179c | textbox | Position:
751dba85-2a55-5a4e-a2b7-ea4dee9eefbc | date | Date:
| signoff | Sign ITP
| checklist | ITP-007 - Hot Mix Asphalt | itp | ITP-007 - Hot Mix Asphalt | 8a26ec7b-47e9-40ba-bcf0-db20d12d50e2
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Site Inspection and Base Conditions
d688b9be-5b87-57c4-9401-8e4ee3044ced | note | FREQUENCY: Prior to commencing paving.
77fe2bc8-1442-5be1-96e4-22b2b5e30898 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
5db3395a-5a33-563d-af34-17c90380b207 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
9f664117-1f46-5641-8a55-271a2941339d | note | METHOD: Visual Inspection
f6b9ce53-7b0e-55f5-bf58-2190378470f2 | note | RECORD: Signed ITP
3149520a-eadf-5e65-84c7-25d8c44897df | note | WP
62204960-fdca-5390-8706-6d46b6c16a02 | note | RESPONSIBILITY: Site supervisor
7a542c34-35be-501d-bef9-f7c96b21f6bf | date | Date Completed:
| checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
0a2ecb52-16f0-520a-a241-548c9b5501b7 | note | FREQUENCY: Prior to commencing paving.
58b668e8-a984-5f99-847e-f7f7849aa2ec | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
21a4db70-16bd-5874-b125-c5d207382d63 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
e74390b4-ae7a-5952-85e9-f515b4722f5a | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
c975c47b-f504-5bc5-af6d-5fc2f3139d57 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
b5ace85e-d10c-5e83-8616-5240a88f8e00 | note | METHOD: Calibrated thermometer
05794ef6-1210-5f5e-988c-9e216f5d1c6e | note | RECORD: Signed ITP
1fa6e8b4-45b7-5c03-9bd0-ad631acac909 | note | IP
b320e086-223b-5c4d-a615-12e62920d7f4 | note | RESPONSIBILITY: Project Engineer/Site supervisor
cc06b2f3-d3c5-5b1b-8572-83b09a446a34 | date | Date Completed:
| checkpoint | 1.3 - Surface Preparation
4e54f265-bace-5007-9924-59ff70e7ba9d | note | FREQUENCY: Prior to commencing paving.
3ca451bd-60bc-5aa8-82ff-2fb8f95d4ae6 | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
d7bca43d-b98f-5a72-b645-801e4af922e9 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
b7150c70-7401-5f10-a71c-de2898c7e3a7 | note | METHOD: Sweep Clean and Inspect
6deba588-d573-5826-8f7d-5cf57d2a7308 | note | RECORD: Signed ITP
4f8547f4-8f39-585e-846f-eb93a72dee5f | note | WP
97ac1dbb-d171-51cc-b773-9def1a760570 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
05dbeb64-1a43-5b0f-ab97-a2a9299cfea7 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Application of Tack Coat
2bc89cc0-05fd-5d39-8173-cf3ac73aea87 | note | FREQUENCY: Prior to commencing paving
984a04d0-36e7-50cd-8190-d10f5be69ef0 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
b126fdc9-f32a-5128-a548-41a431071e21 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
a513f9de-8a20-5afb-8cdb-fe7b7bf868e4 | note | METHOD: Visual Inspection & photo evidence
819b6f4c-677c-5939-bf3e-385c4c9c3ddf | note | RECORD: Signed ITP/Spray Record
085a77d8-e12c-5d16-97d2-38661c7775e2 | note | WP
db648bc6-04a9-5f5c-ac17-0872310e84da | note | RESPONSIBILITY: Project Engineer/Site Supervisor
9524c87e-3988-520f-8b62-836e7879ac95 | date | Date Completed:
| checkpoint | 2.2 - Planned Joints
ba46facf-a072-5cc6-93b1-8ddeca9a627d | note | FREQUENCY: Prior to commencing paving
22cc8efb-d9e3-5cfa-9255-9ae523d70f8a | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
ab9a16a0-8110-5e82-9f33-bbb12b923d13 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
95996cce-9371-5937-9658-016a41201d7a | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
3d58eaf1-61e9-5cc6-b381-2f3448a26604 | note | RECORD: Signed ITP/Job Sheet
00d39b2f-424d-567f-bfa5-6a0decd08391 | note | WP
9ec50226-d017-515d-846c-a3e479e4b999 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
dbb35a21-e66d-5201-a4d2-1dff79c94fad | date | Date Completed:
| checkpoint | 2.3 - Commencement of Placing
cca105be-6bd6-5600-ac6f-65bcc11a3079 | note | FREQUENCY: Prior to commencing Paving
683db6f9-07e7-55cd-8bb3-bdaa06b97f49 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
068e27e3-051d-572c-8924-d5b1ea8f3f4a | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
b511a1d6-2391-58b3-a195-d66345ed525d | note | METHOD: Visual Inspection
53a5f474-6809-567f-bcda-a795f9214c82 | note | RECORD: Signed ITP
63aeb9c7-da48-5ccd-8879-363cd0e982d5 | note | HP
a51be06b-60e3-5c7c-91e1-0b8ed01b9320 | note | RESPONSIBILITY: SWA Project Engineer
2feae5b8-a61c-5937-9a35-e1a01f92a36d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Delivery of Mix
35c6435e-3596-510a-ab77-9fe4f8e7b182 | note | FREQUENCY: Each Load
8dac07ce-4df2-5efe-83be-bf1ba1081dc2 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
9ef15b20-6680-5bdb-9cfb-9fa375011ac0 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
ed145bdc-d3cd-59b4-a60d-32e90a0175ef | note | METHOD: Visual Inspection & Delivery Docket
31350090-570c-5cb2-8a93-d05f68c8ecf7 | note | RECORD: Signed ITP & Production Dockets
01d78e9e-b9b9-5b71-bbd4-212c346d7d27 | note | WP
bec095f5-a796-55ca-b444-42f5b4d59bea | note | RESPONSIBILITY: Project Engineer/Site Supervisor
19cc829a-5c9e-5a21-8524-84978ad9bf59 | date | Date Completed:
| checkpoint | 2.5 - Traceability
82c1addb-3683-5b4c-93c1-01ea48344802 | note | FREQUENCY: Each Load
e1f1bbfe-0d5f-5c7f-83bc-c2f11703b555 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
7b7f2e40-84a3-555e-8ae0-489a7049337d | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ee9c3476-6420-55a6-9993-a2d1de3442f4 | note | METHOD: Project Engineer/Site Supervisor
23c11b58-21bc-500e-a1c6-850486660080 | note | RECORD: Signed ITP & Traceability
e70ee5c4-d130-52b6-a5d5-7af94576eccc | note | IP
9adf5571-8d0c-5fdf-b3ae-6535c2707fa5 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
44a30b4e-f09a-5f2b-bfae-62dff848ba35 | date | Date Completed:
| checkpoint | 2.6 - Layer Thickness and Level Control
ff96ea57-e6b4-5e2f-b266-c33d5fc970c0 | note | FREQUENCY: Regularly during paving
b8b4c9e2-2100-5327-a3a9-c2ab0e694095 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
5a70b30b-e11f-5018-bb87-4345416cb836 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
08d03c8b-a82b-5ccf-8737-a66353e78fcb | note | METHOD: Dips, string line, measurements oﬀ kerb
ad93486a-b761-59b7-8a32-3da121a65202 | note | RECORD: Signed ITP & Traceability
73b78505-8b06-529d-b7e6-0c4856c4aca5 | note | WP
34ac231a-8cb8-5f66-a3c2-d0bf25788dad | note | RESPONSIBILITY: Project Engineer/Site Supervisor
33018af0-6960-5889-8c7c-7c828282672d | date | Date Completed:
| checkpoint | 2.7 - Paver Stoppages
002feb29-adaf-5658-ae69-f5df46cafaf1 | note | FREQUENCY: If paver stops
3e721a1b-0f43-56cf-805a-523cb54c3fba | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
942ba5fa-42f6-5275-9f04-0f4ea0d094da | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
a00ce693-9716-5d75-b53b-2000b9676a84 | note | ○ 40km/h – 20-1
d42553af-6974-50c2-90d8-9801971de2bf | note | ○ 60km/h – 30-1
cac18e2c-74bf-5902-8668-cfd79548b07f | note | ○ 80km/h – 40-1
b5595fd4-381d-5048-8c44-8b281365a04f | note | ○ >80km/h – 50-1
81117fe2-cc8b-5f28-91ac-5bc494815aca | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
b2bc6f2f-ff8b-514c-8300-32611bfa4ad0 | note | METHOD: Thermometer
e73f5314-0277-5e7e-b7d9-f0cf640711b4 | note | RECORD: Signed ITP & Traceability
8a42da44-1238-560a-ad9a-d42ac4ae2cb9 | note | WP
1e0101a2-201b-53fd-bb91-8a1a1ca37140 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8ccf48ab-72e6-5fba-bf7d-c5a8ec70a402 | date | Date Completed:
| checkpoint | 2.8 - Surface Finish of Wearing Course
4dfcca4d-6cd9-5059-96c5-7f49ee738a46 | note | FREQUENCY: During paving and after ﬁnal roll
69febd5b-5b7e-5aaa-8709-463fd2426c24 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
150e0736-0b04-54a4-8e7a-7931c1c79df7 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
df87ffeb-c1aa-56b5-83c7-41217ac9ccdf | note | METHOD: Visual Inspection
9fea420f-2c0a-5f15-ba5e-3302a9a34645 | note | RECORD: Signed ITP & Traceability
984f1f0d-073b-5547-9c56-1bad2e6177d0 | note | WP
29c20c6b-d274-509f-bafb-d926f20bdb16 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
ad523783-fc01-5bf0-a6ee-655ee901c821 | date | Date Completed:
| checkpoint | 2.9 - Kerb and Channel
07ca60f3-ee52-57e6-b0dd-5cb66e9cc014 | note | FREQUENCY: During paving and after ﬁnal roll
8645ebc8-f881-5f69-8a08-46d7a3097f08 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
8dd06cfd-fb12-53a9-8ad4-f0e267ff66ff | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
767fd6b1-2d01-5b59-84fe-65c38d519d41 | note | METHOD: Visual Inspection & Measurement
ccbd261d-642c-5fbb-887f-4c9d8bd42bbb | note | RECORD: Signed ITP & Traceability
d7fce216-ea7a-573d-b611-c9e33c6889d4 | note | WP
accfc560-ed8b-54d2-a681-96c53a9c120b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8429c875-5a5e-5cce-ae99-b0f6f2a50ad8 | date | Date Completed:
| checkpoint | 2.10 - Alignment of layers not placed against concrete edge
627dfba2-fac7-556e-9e93-8665eddfa9ab | note | FREQUENCY: During paving and at completion of work
9f42c967-3d8b-50e2-b03a-b701b4fbb12b | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
cb25d7fe-dae1-5e4a-946c-f9075c8adc68 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
93f531db-bdf6-5972-91cb-a8bcc1019e4c | note | METHOD: Alignment as marked by Surveyor and measured
263cd0dd-a3b4-55bc-b476-0f0d7811254b | note | RECORD: Survey Report
7ad599ca-07d1-5ee5-9751-8cf7ecdc9b38 | note | SCP
7db19754-8f98-5056-befa-eb8448c94030 | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
be21af9a-dbbb-5d73-923b-ce2e4ed1d78b | date | Date Completed:
| checkpoint | 2.11 - Width of layers not placed against concrete edge
4a9a14be-2086-57b2-9593-b9bf91e5b5b0 | note | FREQUENCY: During paving and at completion of work
b081645d-0eff-5ff6-94da-c8c81aba66a7 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
5682dcc8-6286-5be5-9903-fe928cd88306 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
e182e220-7601-562e-bf1d-b783541a2e5a | note | METHOD: Measurement
576e1c36-cb82-5e07-add9-c30db9da78dd | note | RECORD: Survey Report
7e12bf87-ce19-57c7-a3cd-c48f136371db | note | IP
701fd94e-b617-5779-a62e-9088f361468c | note | RESPONSIBILITY: Project Engineer/Site Supervisor
e05f32b5-a38f-5191-b348-2b4e005ae60a | date | Date Completed:
| checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
297135e5-ed13-5bf2-b6b3-60822e7847e5 | note | FREQUENCY: During paving and at completion of work
8d32ab87-f6d9-51a3-8e39-5ddb6e23cb82 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
d9f9b24e-9138-5594-8bf9-8d9afacda926 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
08f0e70b-8783-508a-a289-8e3212659fc3 | note | METHOD: Measurement or suﬃcient time has lapsed
68f2edb5-423d-58f6-880b-ffe22f7d8951 | note | RECORD: This ITP
1a9d1188-0fef-5f2d-b2ce-39a176b42ce6 | note | IP
7f4e2eb8-984e-5863-aa73-35bf680251cf | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c0ea7700-500e-5ee0-81ff-63d8cd2a82fc | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Compaction
3ea01a93-90b8-5aad-ab52-1f0ad5c4630d | note | FREQUENCY: Per Lot (6 shot test)
f36c22c2-771b-518e-9f9f-2e96e8204641 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
df530418-75cf-5498-a9e5-98a12f1077d2 | note | ○ 95.0% or greater Accept lot
a885aa2a-d150-5ded-be97-e54e3a8180ee | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
8722fdb1-40ee-5b6c-abb6-5c54ceeb6058 | note | ○ 92.9% or less Remove and replace asphalt
7b0a66d6-9185-5c93-ad10-be01dcf44c4b | note | For layers ≥50mm, if characteristic thickness is:
4c3f1e16-ed84-5603-936e-2256cef26004 | note | ○ 96.0% or greater Accept lot
960a15fd-97c4-5533-bd6b-de6cc1e8d086 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
1ba6fd39-3ae3-5145-8d5c-44343953e3dd | note | ○ 93.9% or less Remove and replace asphalt
e43ae737-0256-515e-8077-48ee79a67f65 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
85937a4b-7422-55a2-b459-567d8e37a27f | note | METHOD: Compaction Testing
48296b9b-c05b-522a-8bdf-b1b3e3e1d468 | note | RECORD: Asphalt Field Compaction Report
c9314ccd-99a3-56e3-99d9-ad7ee2ee0c09 | note | TP
2f032d04-b346-521b-a1d8-8762ffc48592 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
ed7eab13-91ea-5ca6-93e8-5c612059edcf | date | Date Completed:
| checkpoint | 3.2 - Surface Levels
a3b57793-0945-5ea8-9026-0401d2e010c9 | note | FREQUENCY: Each lot as required
c97caed1-4c69-5de5-813f-f2b9636177e1 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
56a92c5a-65bf-53fe-9336-974dfc6b8971 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
d96e15c5-222a-5ebb-9cfc-9599336885ad | note | METHOD: Survey
b93cd5ab-2182-52e5-9651-43d28c3e9ba9 | note | RECORD: Signed ITP & Survey Reports
14cf22b7-2397-5b6a-903e-3f50db452276 | note | SCP
fa364c43-4d29-58d2-9f4a-d9e17cc7dac5 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
d05db9ed-8783-5625-8556-9a307514c7ca | date | Date Completed:
| checkpoint | Final Inspection
17776558-95c5-52a4-b43c-e734ad34c2d6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
12075917-4f55-5e71-a2da-d7268412a15a | textbox | Print Name:
59b83e06-98fd-57f0-a0b3-0202a69fc95c | textbox | Position:
58008f9d-4619-5f03-a977-6d42d33a406f | date | Date:
| signoff | Sign ITP
| checklist | ITP-008 - Line Marking | itp | ITP-008 - Line Marking | 1de5882a-7dde-4618-bf1c-3daf1cf0a34e
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Line marking Conformance
6decc52f-f238-5406-ab45-b16481be0a0b | note | FREQUENCY: Prior to commencing any activity
7c288dfd-04f6-552e-b391-cad67fc8e389 | note | SPECIFICATION REFERENCE: 721.A05
0eed24db-71c4-56d9-8c7a-215ae2ec8619 | note | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
fa4c2060-243b-501c-8e2f-27a76b3071ef | note | METHOD: Record Review
6433e9d9-b4ff-5fb3-90fa-e39d594a5687 | note | RECORDS: Material sheet
abe5d130-c2eb-59cf-932e-10707b24b6f6 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
a6bb2cbf-0d23-52b0-b090-753f9c10c343 | date | Date Completed:
| checkpoint | 1.2 - Site preparation
d18fc51f-9df8-57ee-b89e-384f6558a56e | note | FREQUENCY: Prior to commencing any activity
d66cd9af-99fe-503e-b88f-bec56f029177 | note | SPECIFICATION REFERENCE: 721.A06
c4e4e470-6b2e-5cbb-b3a3-fb2a6752d2b4 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
94a82f71-9f08-575c-9f6c-bdbbbe4ed1bd | note | METHOD: Visual and photos
b39132fc-055b-52d3-8708-1e0fd0fa57a5 | note | RECORDS: Photos
c9307376-374c-5ff1-b4c2-6f24de01fc24 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
14672bcf-16ca-5aa0-a5d7-8cfe11bb7f1c | date | Date Completed:
| checkpoint | 1.3 - Set-out of Pavement Markings
7bde258e-74c2-5c81-bf6b-35ad7ddc6081 | note | FREQUENCY: Prior to commencing any activity
de495b17-2a23-56c0-ad33-f7afc9581f62 | note | SPECIFICATION REFERENCE: 721.A09
6e1c40b2-5fcd-51d6-b2b3-7fb4bff75f4c | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
29c9a0d7-fe06-53d9-a7d2-a1303ed045e4 | note | METHOD: Visual and photos
c558960a-0248-57f7-90b1-384e21ba49ad | note | RECORDS: Photos
f1b399a1-dea7-51e6-87f2-19eb06a93111 | note | RESPONSIBILITY: IP - Contractor Representative, HP - SWA Representative
08893043-6dba-527a-9b46-af7ef49a05f5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Installation
| checkpoint | 2.1 - Line marking Installation
c216f09e-e64f-5289-90ff-ea17db6088ce | note | FREQUENCY: During Construction
7b41ef96-e45e-5b58-8eba-c45bf7e440a0 | note | SPECIFICATION REFERENCE: 721.E01
1fbb8408-bf5f-5a16-a62c-f142b6eaf5bb | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
c7f74a36-d531-5906-8184-1de2656be786 | note | METHOD: Visual and photos
2de447ee-5a6f-56df-822b-09690da6d889 | note | RECORDS: Photos
83888801-2031-57f3-9d6e-cf2df5ddddfa | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
ecf7e8c7-cd15-594e-b258-61d9a4262581 | date | Date Completed:
| checkpoint | 2.2 - Glass bead Install
5455461d-d578-5fef-9098-a807025a435f | note | FREQUENCY: During line marking works
129c5718-be6b-5fc0-91c6-c9e6c29be098 | note | SPECIFICATION REFERENCE: 721.E01
ce56130a-5110-595a-aec7-42c6ca9abcef | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
351b2f21-f74a-5d7f-b7a2-9715036c0f93 | note | METHOD: Visual and photos
e9e028e9-191f-54b7-80e9-a5bf175842e5 | note | RECORDS: Photos
6d897b20-0225-53cb-9378-5dd5cfdc8b15 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
66e6e253-8acf-59ac-ae0d-5e39d27d0b8f | date | Date Completed:
| section | 3 - Compliance
| checkpoint | 3.1 - Completion Inspection
a78cba1d-391d-5576-b565-d7c818c9ae63 | note | FREQUENCY: Upon Construction
eca57be0-f036-5a9c-bdf8-e25656d8747b | note | SPECIFICATION REFERENCE: 721.E01
c016ebed-7ed6-50d5-901b-0940617d2880 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
d3cc0d09-3bbe-5fda-a526-1c56c0b925f3 | note | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
89a29f29-226a-5cf8-a981-41a43db99235 | note | METHOD: Visual and photos
e7353a58-a06a-51aa-8a5e-2b88791f02b0 | note | RECORDS: Photos
2139db14-7aa0-5b72-8de0-a3783d940be8 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
453e1ff4-6428-5952-a42b-9d525c515a66 | date | Date Completed:
| checkpoint | Final Inspection
5d9c743b-b1d0-566a-9dda-72569b99b130 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
2275156b-b27e-564c-83c7-e53642e4cd9e | textbox | Print Name:
6b1dd9bd-aca6-522f-9252-6caa596d6f13 | textbox | Position:
3320fbd0-ce9f-544f-b805-702c0f697824 | date | Date:
| signoff | Sign ITP
| checklist | ITP-009 - Road Signage Checklist | itp | ITP-009 - Road Signage Checklist | 4a03a7de-8397-44e8-8eb7-36796f59925e
| checkpoint | Inspection Checklist Items
dc9b7c6f-a3ed-5493-8998-dbc970ea3834 | textbox | Sign Code & Dimensions
a917188f-ab1a-5f77-b82e-144aef0167e9 | textbox | Chainage Location
c5198dd8-98c3-59ae-a1b4-113408481183 | textbox | Number & Post per Assembly
2477ad5e-17d6-5890-b4ad-005a3ffec528 | textbox | Mounting Height (H) (mm) & Spacing b/w post(S) (mm)
98565e99-e225-56ba-bf92-09385b9da396 | textbox | Post Hole Depth (D) (mm)
64db3e30-c50c-5fe8-8663-c497b25407f1 | textbox | Fitting Type and Number of Fitting
dd0678d8-3635-54eb-bb12-b59c577f0e13 | date | Footing and Sign Installation Date
9600558b-1bcf-560a-b940-10cd212b3d9d | note | Photos
| checkpoint | Final Inspection
4c619913-70b2-59b9-8e85-7aa07009facc | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
7c9377e4-e5f8-5220-be1f-c2b39c3c57de | textbox | Print Name:
f6476e10-3a1a-5684-898c-a073d3a3fdf6 | textbox | Position:
bd7fa19e-daa1-5a8b-9ef3-03c4d76e0e2f | date | Date:
| signoff | Sign ITP
| checklist | ITP-010 - Guardrail | itp | ITP-010 - Guardrail | 959d7f0d-ee74-46fa-a68d-ba7171b95fc3
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
0ec57c45-86f2-5bdc-b58b-a216f96427bf | note | FREQUENCY: Prior to commencing any activity
086cb6b8-35d8-503d-979c-02b0754ff62e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ab817a45-c92b-5e09-af6c-7c7e05ebd0bf | note | – using the correct and complete set of drawings
0e87b665-1836-5f00-8bd9-0aff94e5fb43 | note | – all drawings are the latest revision..
aa50f204-8caf-51f3-b943-d67d410f8d74 | note | REFERENCE DOCUMENTS: Design Drawings
4a0abe65-ea75-56fc-871d-5432bf3fb90c | note | METHOD: Visual Inspection
251f8e93-1153-5553-8544-9e01118b4ab8 | note | RECORD: Signed ITP
03256eb2-10f7-5eb2-acbc-768daed6ab0d | note | IP
82c51713-01e0-5753-b05a-f8bc425c1a90 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
6dcf91aa-ca4f-5cd5-bded-9751eee20558 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
5afcc918-dc4a-558f-aa76-735dfd2c28bb | note | FREQUENCY: Prior to commencing any activity
663cff31-6696-5aa8-af87-521b6453cf31 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
6a2336c7-2787-58be-84c1-3df28befa56c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c37a8318-8c2d-5a69-8c75-a83252fb4bc3 | note | METHOD: Visual Inspection
f341f913-15fa-54c4-97bd-e055ff085002 | note | RECORD: Signed ITP
5742e225-b980-5fa7-b89e-fd6a8e25bfc2 | note | IP
12c453ab-0f00-53a1-9a99-d7a762d45f9b | note | RESPONSIBILITY: Project Manager/ Site Supervisor
179b0df0-6817-59e8-83a9-f173c1ad472a | date | Date Completed:
| checkpoint | 1.3 - Setting Out
4c70ffe9-0fd7-59db-aade-198edbbb95fa | note | FREQUENCY: Prior to commencing any activity
8dd0c908-2af4-5773-b10c-1cdd07379690 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
caac9424-8219-5a49-be8c-0b27d7d96fdf | note | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
f0a37273-72f2-5e02-a92c-218a38f5abef | note | REFERENCE DOCUMENTS: Drawings 708.08
a0b2264e-1557-5811-a657-fa658781abaf | note | METHOD: Document Review
25ba3632-56f1-5b5b-b635-2d5d334c04af | note | RECORD: Signed ITP
f9e669d5-a8fc-5868-88b2-85fd11d2861b | note | IP
5f22be86-56b4-51c7-a4f6-77db6d3b4243 | note | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
540fad9a-8918-51a5-bfb3-689327283865 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Supply of materials
07311716-27c3-59bc-8c66-34ff2ec8f1e8 | note | FREQUENCY: Each Delivery
41fd03e0-71a3-5cf0-8d71-d65231baead1 | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
8e743b2d-c7ea-5d17-8f27-b941961e81bb | note | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
65b15744-9046-51d6-9b49-9c0cb11e31e5 | note | METHOD: Visual Inspection
70bdaa8e-43b7-5dea-8b64-f89f86506728 | note | RECORD: Signed ITP
1e7a1bf2-e8a9-5d1c-bb3b-ec9a92bfb1d2 | note | IP
d5b348f3-513f-539d-9466-d8c71722ef26 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
0c0c4c74-906d-528e-b904-8c78909e065c | date | Date Completed:
| checkpoint | 2.2 - Installation
85a5de76-58b8-5d60-aee8-b55099377790 | note | FREQUENCY: Each lot as required
8db5e8bf-9e53-5d1f-a2c4-2912b045a9c6 | note | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
88f58727-1259-5f70-9b1b-a724f725415a | note | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
c5f6a30b-5ebc-515c-b4c2-7a399533416b | note | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
5f83d83c-6406-5083-9409-db6c8a43b72d | note | METHOD: Visual Inspection
fe660ed2-bef8-5c2e-9d8f-c860f088952e | note | RECORD: Signed ITP
b2c24674-080a-5153-8c78-959dfae3b2bb | note | IP
01ba80f2-36ab-5720-b70e-1c3e7a2f224c | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
cd466e90-8a5b-5335-b067-d55ed355d4d9 | date | Date Completed:
| checkpoint | 2.3 - End Treatments
51b415f8-bb9e-5625-823b-01f660682781 | note | FREQUENCY: Each lot as required
57c5859d-5b20-5d54-8805-88afb2bad015 | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
0bbb2739-8a95-53a2-ace1-5e372d6aed4b | note | REFERENCE DOCUMENTS: Detailed design 708.08
6ea32cbc-291c-531d-b0a3-17bcdbd44c54 | note | METHOD: Visual Inspection
370fc108-8336-590c-b227-ef32a7bac163 | note | RECORD: Signed ITP
623b922e-10a0-5aee-bbb3-be120111e4dd | note | IP
edfa7fad-f9b0-59fe-badc-78506f6adf76 | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
c070f63d-cad9-520d-a077-313ac75e4be6 | date | Date Completed:
| checkpoint | 2.4 - Motorcycle rub rail
4d5697fd-9c4c-5f8f-a59d-ac37aa7b95a5 | note | FREQUENCY: Each lot as required
a748f548-eee9-5b61-873c-7ce62cbd9938 | note | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
237b6204-7728-5f89-802a-f6314a444077 | note | REFERENCE DOCUMENTS: Detailed design 708.09
7509c32b-e1e2-562b-b3f5-6ad6425f2f4d | note | METHOD: Visual Inspection
e6c525e7-02f8-56aa-83bc-8a3ea15886d5 | note | RECORD: Signed ITP
54c65d0e-d8a3-539d-a84c-45b0a1bc4744 | note | IP
6ac946d1-567f-5d9d-8b3d-0ce869d45aaf | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
29a00349-f5ee-5795-8f98-7a256ef90ccf | date | Date Completed:
| checkpoint | Final Inspection
6ca108b5-1937-510e-89f1-beae553f2df9 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
68028ba3-22e7-5c2e-bfd6-3aaf14cc3eb5 | textbox | Print Name:
d1dbdee0-8b8e-5e3e-80e4-a67262f3bc1a | textbox | Position:
59922202-9206-54e2-84fd-08300ad09ec6 | date | Date:
| signoff | Sign ITP
| checklist | ITP-015 - Drainage Checklist | itp | ITP-015 - Drainage Checklist | f6cd55d0-eaf3-43cc-a503-3c65808da246
| checkpoint | Pit Details
afd16bda-97e3-5754-8cbb-5ee0a29304bc | textbox | Pit No.
bb7ea087-37fb-5cd4-a859-16092d3bfe5f | textbox | Pit Type
3700b52b-7d10-594f-95f2-b8e9dab30909 | textbox | Dimension
41e518d5-d2c6-5512-b24c-a7bc2898354f | textbox | Inlet Level
2ab54a67-4535-5730-b9c8-a8be2f5c6bb4 | textbox | Outlet Level
c1384ddb-1ec4-550c-bd3c-4778cc89c5c9 | textbox | FSL
290caf0d-9fba-5a85-a0dd-73e9cb030aad | textbox | Pit Depth
| checkpoint | Checklist Items
ac624d40-08bc-5426-9b5b-c423dd5c0b32 | textbox | Drainage Line Number
daa29e46-8508-5a48-b08d-f361bd3ae10f | textbox | Pipe Size
e4639f21-6947-5345-a311-15e53939e1f9 | textbox | Trench Width (mm)
499ecc76-afc3-516c-88d2-3c7a49542bfe | textbox | Minimum Cover (mm)
d2056b63-946c-5f28-b703-ec88f0006d41 | textbox | Beading Depth (mm)
ffd080c2-bbf6-53a0-9d39-930b9730536f | date | Start Date
515a47c7-7afb-50ee-b28d-2539758af222 | date | Finish Date
| checkpoint | Pipe/Pits/End Walls
3cfaf860-9b55-5617-b805-a33a0edf6914 | note | Pipes/Pits/End Wall in sound condition?
d4d0a798-2bbd-5bd2-86b0-698bcc3f625c | date | Start Date
829e1b3b-f075-58d3-bfe4-8c32bdbba046 | date | Finish Date
| checkpoint | Laying Direction
870fdf83-eae7-550c-8b8f-51b95043010a | note | The direction of Laying Satisfactory i.e Collar on Upstream?
ff9b4f1b-9a73-5a34-be7c-4fbdaac7d65d | date | Start Date
a56660c3-2851-551b-b087-3dbea48313df | date | Finish Date
| checkpoint | Rubber Joint
f90311b1-ba4f-5fec-b632-b87d0bcff459 | note | Rubber Joints in Satisfactory condition?
c4ef5e28-032f-5e32-96aa-dea191a1df86 | date | Start Date
3399d266-167e-5a7e-960e-a90cefa99f68 | date | Finish Date
| checkpoint | Gap Filling
97d086c1-dac2-5af5-8835-2f81a6f7f8bc | note | All the holes have been mortared to satisfactory condition?
2d35c2c4-4f3d-540a-b840-2305de4e50f9 | date | Start Date
9d077d7d-e1de-5a54-b9ca-c5dc9f487873 | date | Finish Date
| checkpoint | Step Irons
6448d217-65bd-5977-b378-0e887266a884 | note | Step Irons Installed in the Pit greater than 1000mm?
1a6d2c1e-2d63-5ae4-aa0c-ccdb11fc4325 | date | Start Date
4334c58c-5249-5bd2-82b0-431bad66f96a | date | Finish Date
| checkpoint | Final Inspection
4e42773f-3821-5e50-a586-f0f5f566380c | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
6db91f04-ea88-5494-894e-9f5a266a884d | textbox | Print Name:
2d884928-1d04-5d03-b9a2-196391ae2f4d | textbox | Position:
85dc6342-20eb-5e07-af92-556a8c64f6fc | date | Date:
| signoff | Sign ITP
| checklist | ITP-045 - General Concrete Paving | itp | ITP-045 - General Concrete Paving | 31e44898-df83-4487-b1cc-5d63c9e2acd3
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
eee305db-0ad2-5699-b288-4788c2b43125 | note | FREQUENCY: Prior to commencing any activity
c8d7bea0-57cc-583c-9fd9-b621043824cf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6b9c67dd-4cb9-5f4b-9744-4e7527ee10ca | note | – using the correct and complete set of drawings
3efe8d84-93fb-583e-bc2b-451f4118c0b7 | note | – all drawings are the latest revision
31b372e6-c70b-5e8e-b17b-8f237045cce6 | note | REFERENCE DOCUMENTS: IFC Drawings
38ee64f2-e227-5668-bfab-9ec0daf653ba | note | METHOD: Visual Inspection
7f692d85-cf72-5493-8c74-aaef275660b4 | note | RECORD: Signed ITP
45436503-1205-5db6-96ee-9a9e0dfc19a0 | note | IHP
fdd44d80-f5cd-5032-bfb5-8f806677d98e | note | RESPONSIBILITY: SWA Project Manager
8f7436cd-24d0-54e5-af47-eaeee43eef71 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
9f91c3b5-48be-5d37-85a0-8256be9ca02d | note | FREQUENCY: Prior to commencing any activity
93c0e39a-a5f8-5024-8170-a9a032969438 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
0d4b03c9-0adb-53ab-befb-105153d6be76 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
03b7fbd0-c5c4-5500-a36e-404816c634db | note | METHOD: Visual Inspection
0e717617-a77c-522a-8569-c6d075d69eab | note | RECORD: Signed ITP
88dddc8f-70a7-5945-a81b-4cb883b91b85 | note | IHP
2dab62d2-2af2-541a-baa5-45ecddeaafad | note | RESPONSIBILITY: SWA Project Manager
0c45d27c-a007-5bf8-8f0c-28f42159517f | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
abae3e05-7160-545e-a830-bc34f458e2b8 | note | FREQUENCY: Prior to commencement of excavation.
b4301f2d-b7b3-5195-ad81-984de74540b5 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
02d60dce-893c-51bf-a329-de97b920bb44 | note | REFERENCE DOCUMENTS: Work Procedure
97460939-0a43-504b-87a3-7e7a2c0a03e2 | note | METHOD: Verify
f09ee51f-e536-52c2-9ac9-de3e2305bacb | note | RECORD: Signed ITP
12b8d6be-108e-5097-a66e-99ebd8a9eca4 | note | IP
d8157272-ebae-54db-a99c-80b3065efb5e | note | RESPONSIBILITY: SWA Project Manager
02b04572-69a8-53d1-818b-757e80e6a654 | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
03252232-fe2e-5a4d-b036-738dad4895a7 | note | FREQUENCY: Each Lot
8af09b81-6abb-5249-a7bb-ab137bc4f8cb | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
c07e38af-35e2-5e79-b28e-0fc068c3c13e | note | REFERENCE DOCUMENTS: Excavation Permit
4a361387-65a4-5272-b5ec-4388fde85aaf | note | METHOD: Verify
856122d7-7ff0-5172-91bd-85e294e46ccd | note | RECORD: Signed ITP
97cbc96f-7798-5c85-a32b-0160f8864d66 | note | IHP/IP
45a8e1bc-177e-530b-8779-e42edbb64f42 | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
ab6dfcee-9cc6-5b21-bec3-6a58e2b39ce4 | date | Date Completed:
| checkpoint | 2.3 - Formwork
b3b985c0-28db-545c-8d82-3d36a4cfa80e | note | FREQUENCY: Each Lot
9ee77081-b54e-5159-bcb7-ea45c4ac6a7d | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
b760cfe0-e69e-511f-8e5e-33a77b7c533f | note | REFERENCE DOCUMENTS: AS 3610
89f51154-a6d6-5e74-8575-0ab43c80eb8e | note | METHOD: Site Inspection
84f7f7fe-b106-520f-8f37-4718d9860513 | note | RECORD: Signed ITP
e7d3d7a3-84e2-57cf-8274-2b32d9c52d50 | note | IP
ba5a65f5-ec86-5068-a12f-628344a3522f | note | RESPONSIBILITY: SWA Project Manager
43b7d9d1-2223-565c-8c60-93cfb407a4c2 | date | Date Completed:
| checkpoint | 2.4 - Reinforcement
d977ed63-365a-5784-8115-9cb77129d6b8 | note | FREQUENCY: Each Lot
9fbdaaf1-a7a8-5a80-a574-d0f94a16fe47 | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
deed33a2-cf34-5341-b812-33d94defdda1 | note | REFERENCE DOCUMENTS: AS/NZS 4671
bb66d9c4-36e8-5292-a3fb-894b1e131ce7 | note | METHOD: Visual Inspection
ab682694-8311-5184-8de8-d53d35473aa8 | note | RECORD: Signed ITP
b7836cc6-a210-5599-aefc-3a2b6b85f24e | note | IP
50cb1299-6081-5559-93fd-20d8e6674e5a | note | RESPONSIBILITY: SWA Project Manager
923e47b5-5730-54a5-aef7-ac426c05fb6c | date | Date Completed:
| checkpoint | 2.5 - Temporary Drainage Provisions
24f4c914-4947-5a8f-8ec7-2ecca6acae77 | note | FREQUENCY: Prior to commencing
3169cfbd-1019-5fc7-a713-0752a938f562 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
a5994913-35dc-5e73-8d0d-3af76faf0e42 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
fa7ae607-c8e0-51db-8357-442afacae9ea | note | METHOD: Visual Inspection
3952a518-6b38-5987-9d53-9f2618de5399 | note | RECORD: Signed ITP
6a994837-f953-506c-b73a-23444f4627ea | note | IHP
b295128c-a848-5bda-828d-6927061ea0f0 | note | RESPONSIBILITY: SWA Project Manager
247db84d-0562-5b5f-b1c7-aadaf6b5769d | date | Date Completed:
| checkpoint | 2.6 - Bedding
b86142db-7ed2-506c-8022-12f89d4cfec4 | note | FREQUENCY: Each lot as required
19ccc43e-9e69-5614-8486-9250ae584e49 | note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
f9b52c92-bf19-5eca-a988-d11736b9bb1c | note | ○ Bedding trimmed, moistened, and compacted as necessary
4150a687-4a52-5cb5-9ddf-29e55bdcd3b6 | note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
58cfa338-2c0a-5856-9c01-9fa94cae0523 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
8a81b5ba-6e5e-562a-b6e7-285e246fd04d | note | METHOD: Site Inspection/ Document Review
fc1ed9dd-34c1-5b3c-abb1-78b58b4fe61c | note | RECORD: Signed ITP
dbd7fe59-b8af-5708-bbd9-5d0d59c7e813 | note | IHP/AP
9424fe40-9803-541f-a6a3-27aa14256388 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
874afa84-ec5a-54d4-8a36-ee27ac2b52a5 | date | Date Completed:
| checkpoint | 2.7 - Concrete Placement
4f7d565d-7f57-5453-b26a-93912bc3bd78 | note | FREQUENCY: Each lot as required
acc00d4e-8e07-599d-a0fd-1db87aff3296 | note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
a663f449-dcd3-5701-bddf-3ba323dabc69 | note | ○ Comply with requirements of AS1379
665753b3-3f85-5bc6-9053-cd7aab90e78f | note | ○ Aggregates to comply with Table 703.051
1d6965d9-4404-563d-822a-7be694dfb7ac | note | ○ Extrusion machines cement content ≥ 320kg/m3
fad3e71a-cc88-5f5f-acc7-f5b89e5181d0 | note | ○ Surface pitting < 5mm diameter
9858029a-694f-585c-9191-dd273623ecd9 | note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
2d590dc3-87de-56f6-98c5-7ae19cd651e3 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
f6bee428-7f17-5475-aa09-5cfc7aad58e6 | note | METHOD: Visual Inspection
c09aa0fe-5e05-5d2e-9d3d-d1463ffac490 | note | RECORD: Signed ITP & Test Reports
d6565033-d887-5731-ad83-91bb7cb2a0b9 | note | IHP/AP/TP
cd559b5b-f877-5455-b216-12021ee4b89e | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
de0c3ad5-15ba-5d22-acab-0dc1ea949d0e | date | Date Completed:
| checkpoint | 2.8 - Finish Surfaces
97d1d49e-0650-5d7a-a283-fe6beac811b7 | note | FREQUENCY: Each lot as required
2458e28b-0d1d-55df-bf30-2fd7e5864265 | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
01554e45-55e2-573e-8714-8a9355e842ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
e383673f-a8cf-5bbc-8153-de67e5b615ec | note | METHOD: Visual Inspection
a9b975bf-17ce-5878-b1d3-1130035dbc29 | note | RECORD: Signed ITP & Test Reports
d787be7c-1b20-5e06-b37a-a68c9f3e271a | note | IHP/AP
9b3c965a-a117-5631-95d7-940e51cba2e9 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
0d0ba586-677c-5291-8567-6edcec752a21 | date | Date Completed:
| checkpoint | 2.9 - Tolerances
7e1f213e-c927-5e3a-bb54-588ffee96534 | note | FREQUENCY: Each lot as required
0039b4cc-3463-5e3d-9747-203a1732f40b | note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
c6d108b4-31ec-58dd-a1c9-0fdaf1cdb20e | note | Section dimensions:
76921a82-71b7-50fa-87ca-eb95f7c7e047 | note | ○ Within 5mm and 15mm for width; and
2f686c82-3021-5e91-86dc-383081391768 | note | ○ Within ±3mm for dimensions less than 25mm.
823267a9-7e77-531f-b955-7c5996bd3df5 | note | Concrete footpath:
423372ed-8a34-59a6-bb01-bacb34bc7c0a | note | ○ 150mm thick
1ac7b9db-405b-5a4b-9c53-d41690d3f1d5 | note | ○ SL72 reinforcement
2a0eae66-1f89-55b8-89cd-aca1468ee7b6 | note | Concrete Surfacing:
bd278de7-ae77-531c-8e6a-f98576d30908 | note | ○ Type 1 100mm
6a9a005c-a671-5582-88bc-e979a7ad5656 | note | ○ Type 2 150mm
59281743-6354-57b8-9065-4eb789c31dd4 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
fce9109c-59a6-57b8-a526-a376140eb285 | note | METHOD: Visual Inspection
cfca9fed-4e1f-5b37-ac15-be65df065258 | note | RECORD: Signed ITP
62a919a0-fbce-5427-bb9b-b5a2305a2328 | note | IHP
4f5590ec-c453-5983-b09d-f0a68b59cc58 | note | RESPONSIBILITY: SWA Project Manager
8b537dfe-da43-5a13-906f-d5e10c4d52d7 | date | Date Completed:
| checkpoint | 2.10 - Joints
c0eda2c0-4fdb-5684-a781-2574ebefbc25 | note | FREQUENCY: Each lot as required
a1d0afd5-e008-5fe7-9428-81a406c1d340 | note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
00367f8a-f964-588f-ad0e-9aece009add2 | note | ○ Expansion joints at 12.5m regular intervals
c7bb1a40-deab-58bd-a61d-eaff096da0d4 | note | ○ Control joints at 2.5m regular intervals
3b81d342-8743-502f-8d9b-d1fef036eafe | note | ○ 20mm deep and 5mm wide
6890dbdb-92eb-5c26-9d1f-694580d3c34e | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
28b948a1-deba-5b69-86f0-ce86f3b2389d | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
9dc6f66e-636b-5095-8f59-286d7cd20127 | note | METHOD: Visual Inspection
2c38b942-8492-52a6-861e-c17e97ea07ab | note | RECORD: Signed ITP
242f470e-e1d3-5f64-9745-98a9bb169abc | note | IHP
a8a79afc-d754-595c-a364-ffc1cd16cfb3 | note | RESPONSIBILITY: SWA Project Manager
398720d9-0b29-530a-9002-bd63a7e02063 | date | Date Completed:
| checkpoint | 2.11 - Backﬁlling
f2fea800-ab53-551b-8af7-686702f2bbeb | note | FREQUENCY: Each lot as required
a9e9f3e1-8090-57d3-89ab-f537973b7684 | note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
7bff6008-e82e-5e36-923d-bb08df9da072 | note | ○ Width ≥ 300mm behind edging to top of edging
00c16956-63fb-5a9f-95b5-38084361c3e7 | note | ○ Topsoil placed after 3 days of concrete placement
c4bb5253-c4e9-57f6-9cb7-12ababf9993d | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
cb708d60-148c-5c77-b55b-8c03917beea2 | note | METHOD: Visual Inspection
a52af329-6691-5041-b433-630a748bddb0 | note | RECORD: Signed ITP
c6d14f8b-b636-5e39-bd6c-45c1d8bcbb50 | note | IHP
eb384a0c-84cf-5b91-acb2-e9ce86be90b0 | note | RESPONSIBILITY: SWA Project Manager
8d7ea636-fc0d-536a-8d62-d1c00989f915 | date | Date Completed:
| checkpoint | Final Inspection
b61cd3df-1245-58d3-98da-582d5d4fb73e | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
ca92968e-fd7d-596f-b881-5c495579f796 | textbox | Print Name:
7536c187-d446-55b3-a24c-2c06c642217f | textbox | Position:
b45b5b7b-c0f3-5fb7-92e9-46c8c6e8a06c | date | Date:
| signoff | Sign ITP
| checklist | SWA-013 - Pre - Construction | itp | SWA-013 - Pre - Construction | b8738fa3-7d57-47cf-b2b4-798567fc0026
| section | 1.0 - Pre-Construction Checklist
| checkpoint | 1.1 - Communication (1)
6ac75fb9-74e2-5fb2-85a3-84c4b8008c39 | note | ACTIVITY / DESCRIPTION: Community and emergency services
c678d74b-a672-592b-b979-1c99b7f696d5 | date | Date:
| checkpoint | 1.1 - Communication (2)
e55c5068-9fa4-5a1b-aa0a-6de36cbc5bf4 | note | ACTIVITY / DESCRIPTION: Emergency response plan
bda3f06a-3c3c-5018-af54-e0aff08de424 | date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (1)
9628d657-61bb-5a84-9ad5-12752bc1064a | note | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
0d71f2f0-26f9-5995-bc5f-ccfbf607e17b | date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (2)
f343ec02-718c-59db-ab3a-25e80837e2df | note | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
60cef747-332a-5e37-80d6-c09065e0a958 | date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (3)
6486ac0a-36f4-5647-8cc9-8c58b9fc2796 | note | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
0951336e-809c-5108-957b-34c50eb0e7de | date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (4)
a291999a-7702-54be-a784-596df5954215 | note | ACTIVITY / DESCRIPTION: Quantities / Specifications
aee31bd7-4cde-5a8f-a5ba-9514c271b1c7 | date | Date:
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
03636c61-da3d-5862-9ef7-a0e61d9ba316 | note | EXTERNAL REFERENCE: Hold Point (HP)
79639933-4198-5797-be20-6f279137add8 | note | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
76df2442-44de-52f2-a7ee-9e1b2db476fd | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
6e875f2f-1f6d-54b8-ad88-e8bac65328d1 | note | EXTERNAL REFERENCE: Hold Point (HP)
ad5b0201-e292-57e1-b0be-3814d7cd5e6f | note | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
8118ed5e-26cf-5d2f-a5e1-25503267f92e | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
1825af1f-9911-5784-b310-f67d99f16c75 | note | EXTERNAL REFERENCE: Hold Point (HP)
34872f6b-7c88-59d7-8915-8ea569094049 | note | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
b9ca6609-db0a-5eaa-9c75-18e375ab6eb3 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
67ed8b4e-48f9-57f8-a600-390c9bdd29c2 | note | EXTERNAL REFERENCE: Hold Point (HP)
fa5dd48c-18b6-528b-a52f-0ec372b0b2c3 | note | ACTIVITY / DESCRIPTION: "No Go Zone"
255ffa41-0fb6-50b0-be8a-005e04fba535 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
aa5e5762-73d7-5990-869a-eae524283d11 | note | EXTERNAL REFERENCE: Hold Point (HP)
c0716d5a-f08e-5685-94f9-d746f9de8103 | note | ACTIVITY / DESCRIPTION: Tourist attraction
fb3f411a-7165-5bd9-81c8-65d0947b8412 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (1)
c3537a7b-f353-5fa5-9655-321eb8f210b2 | note | EXTERNAL REFERENCE: Hold Point (HP)
d36c54d2-7b0e-55a0-96df-a1570770f991 | note | ACTIVITY / DESCRIPTION: Flora
63416b39-c036-5c4f-9cdd-9efbf878ddc8 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (2)
e374ec65-344d-5f55-9163-0363f1fc82c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
6874e82f-7eb2-55a8-a9e5-dca3b0fb7d8d | note | ACTIVITY / DESCRIPTION: Fauna
5628aec3-4ec4-5365-a8b6-d9c417458b93 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (3)
ab221c3f-e8c1-5fcc-9705-0d3c8e189157 | note | EXTERNAL REFERENCE: Hold Point (HP)
f016b3a2-6fac-5fc4-8857-7be2cfcc15e3 | note | ACTIVITY / DESCRIPTION: Water bodies
07f39192-f364-5554-8b65-d980b885953a | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
e0f4292e-52b6-5e42-a758-b0de3e089e54 | note | ACTIVITY / DESCRIPTION: Dial Before You Dig
1e1eb03f-76ab-5ba0-855e-bcb622315ec9 | date | Date:
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
2e00c3ff-cbe8-5c74-af86-841465f410a7 | note | ACTIVITY / DESCRIPTION: Excavation Permit
2aec04a3-0aad-5ac9-b793-83d1ef151c2b | date | Date:
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
7533acb9-6cc7-596c-a296-26e31d51c11a | note | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
13f705f3-bf35-53d8-8ca7-e84941343889 | date | Date:
| section | 2.0 - Pre-Commencement Checklist
| checkpoint | 2.1 - Traffic Items (1)
55c62a7f-b4ab-5f3c-8def-280e4c917421 | note | ACTIVITY / DESCRIPTION: VMS boards
6ac3d201-2c28-52a7-a8b2-90c414058ae2 | date | Date:
| checkpoint | 2.1 - Traffic Items (2)
5b9dd624-ae8f-581b-8874-6c737a56c425 | note | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
ec18bf29-de58-576d-aabb-a088bed6a4ad | date | Date:
| checkpoint | 2.2 - Site marks / references (1)
502435bf-bca4-55cb-b6da-3dd2a6dd1dcf | note | ACTIVITY / DESCRIPTION: Limit of Works
1705a55f-e283-55eb-a225-cf0b20ff39c8 | date | Date:
| checkpoint | 2.2 - Site marks / references (2)
ce62becc-d90c-520d-97b2-d9ebc15c1536 | note | ACTIVITY / DESCRIPTION: Survey control point
1477e2f0-75ce-520a-97a9-db697eb6aa70 | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (1)
1de60d9c-e7ab-5885-a3f6-0366865fff98 | note | ACTIVITY / DESCRIPTION: Sewer, Water
f335f453-2ac9-58b4-b6b4-18bc46f26df7 | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (2)
c6d0efd6-f8c1-556b-9d3d-ae7f2b631821 | note | ACTIVITY / DESCRIPTION: Gas, Electricity
102be5f6-8768-518c-93a3-a2c773473a8f | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (3)
75076475-3b85-5121-ac0c-03db0e1eef54 | note | ACTIVITY / DESCRIPTION: Telecommunication
14f8a3e3-f9ec-5544-b28d-605ec91d8327 | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (4)
5f3060bb-3bb1-5591-b921-d4f59a6a92a6 | note | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
de24c3b0-6b49-5f90-8428-2c576569d3e0 | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (5)
5cd070f3-4bc2-5d15-82ac-70e37c344a84 | textbox | ACTIVITY / DESCRIPTION: Other specify:
50d772c2-4165-5d56-8320-9c86a7d20b54 | date | Date:
| checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
74683223-37ac-5f0b-9dc8-c59bbbb49457 | textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
082b5cea-cbd9-5d32-b47a-12a91485a800 | date | Date:
| checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
2d9b5ac8-2932-551d-afe9-cce406feb1b8 | textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
6ddf181a-e8b1-5fc9-ab3d-1f6b4ab98b3e | date | Date:
| checkpoint | 2.5 - SWMSs reviewed: (1)
91edcc50-d584-52ff-9a80-5cf97676facd | textbox | ACTIVITY / DESCRIPTION: Site-specific
f484d58c-c0a0-5b74-9e0c-44d3b5f26fef | date | Date:
| checkpoint | 2.5 - SWMSs reviewed: (2)
b108d9a3-d755-5fe7-a3ce-9b4c144ed150 | textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
241f3d92-8abd-5760-a197-07485a7903e6 | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
000ad7b0-a0b3-5691-adc5-5fdb50559397 | textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
49c34f83-a82c-5d2d-99ae-76a827d686e7 | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
845fa20d-5809-53bd-a769-4e8cf144dca5 | textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
8d29808c-5f6e-5d17-ab5d-12701fcc7f8a | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
da8e0f5e-1206-53be-ae77-1b48e2a2c06f | textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
42516fb7-f459-51b6-a80b-3d181e45b9cf | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
5e983dd6-62b6-5c14-abdf-4a9d516d310a | textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
78bb6672-239a-5d14-9e90-b6fff32dfc28 | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
e5327478-ff3b-525b-9d22-e123465c38a6 | textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
73da7c40-9c91-5b8e-8574-8dfb3ce76381 | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
9b5ae601-5c84-5742-862a-02d344119001 | textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
de3f3c7e-21fa-52b6-8b20-c9dea9d405fa | date | Date:
| section | 3.0 - Construction
| checkpoint | 3.1 - Vegetation Removal (1)
c4f91f9b-460b-5bf7-9724-1d68269b5fd8 | note | EXTERNAL REFERENCE: Hold Point (HP)
9a06f88c-d3ba-509b-94eb-73443c6aa6a3 | note | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
24caba61-85bc-5159-b0ec-72a77a683fad | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Vegetation Removal (2)
2440ce69-0b95-549f-bf60-60b1909778d8 | note | EXTERNAL REFERENCE: Hold Point (HP)
87e8fdf3-58d0-5c59-bdc3-c912e2382397 | note | ACTIVITY / DESCRIPTION: Equipment, Access
9b81ac8f-b070-5323-9dca-acfbdb427325 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Vegetation Removal (3)
ccf59e41-4ab4-5852-a208-c13193b332ce | note | EXTERNAL REFERENCE: Hold Point (HP)
d042cc4b-aab0-544a-85f7-80f1ce6852a5 | note | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
c63da54d-4452-5d56-aa26-80f408262e25 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Contaminated Materials
f1271195-0f83-5568-b48c-aea50c41dd87 | note | ACTIVITY / DESCRIPTION: Contaminated Materials
ffafd4b5-54da-5bfe-801d-00e309038cf1 | date | Date:
| checkpoint | 3.3 - Traffic Items (1)
d3430d21-a698-50e9-8359-dc7188cd9a6e | note | EXTERNAL REFERENCE: Hold Point (HP)
52a94787-19b2-56c7-bb15-816a2990cbb0 | note | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
70f42a74-ee1e-5d54-b8b0-1cde5b68b86f | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Traffic Items (2)
ec7ce81c-2ad7-50f3-9cbc-9f01a126af9d | note | EXTERNAL REFERENCE: Hold Point (HP)
580d0e38-7fdd-5696-a5d5-495e0cc60140 | note | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
c346f444-f86f-59e7-8e38-9f9909100dbd | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Trenching works (1)
941db789-7b82-594b-bb6b-fcef0d6edb67 | note | ACTIVITY / DESCRIPTION: Review escape plan (routes)
6d62af35-d0f5-5ef6-b239-b452fd3decb6 | date | Date:
| checkpoint | 3.4 - Trenching works (2)
b4ecbe1d-c4f4-56b2-aeff-6efdc65fdd2b | note | ACTIVITY / DESCRIPTION: Review ground / water conditions
619cc4c2-86a0-5d57-897a-31c5d6c53318 | date | Date:
| checkpoint | 3.4 - Trenching works (3)
540cea3b-7a41-5fa6-9f28-8540567fd217 | note | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
12f019cc-0473-5500-a16e-4c48b4fd9135 | date | Date:
| checkpoint | 3.5 - Drainage Works (1)
206c1000-b617-500b-9644-e5b5617da94c | note | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
70024a33-18da-5be1-9e03-818c3b557391 | date | Date:
| checkpoint | 3.5 - Drainage Works (2)
d8430f2c-7145-59d6-b01b-4d49402c154c | note | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
1e06ce8b-b227-5e32-b27a-c39c24c7bb90 | date | Date:
| checkpoint | 3.5 - Drainage Works (3)
4cce8002-4d20-5487-8f39-429bf484f752 | note | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
33acb2dc-5580-585c-86fc-a0d62281f5ab | date | Date:
| checkpoint | 3.5 - Drainage Works (4)
ea0ce010-f16e-5655-b25a-79d53b30ded2 | note | ACTIVITY / DESCRIPTION: Review confined space entry
f6040a37-cd0a-5d2b-b12f-5777b19c46ac | date | Date:
| checkpoint | 3.5 - Drainage Works (5)
055373e2-fcd2-5867-bae6-c62a3c9a7c4e | note | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
f396fea9-8948-5986-a2e1-3320dc2bbc80 | date | Date:
| checkpoint | 3.5 - Drainage Works (6)
e5e82d46-11a8-5768-bb45-772759095f7e | note | ACTIVITY / DESCRIPTION: Levels
00326889-24e1-507e-9670-084aaf6e1b9c | date | Date:
| checkpoint | 3.5 - Drainage Works (7)
4398c1aa-7394-5b74-b0bf-a13b96671e33 | note | ACTIVITY / DESCRIPTION: Pit covers / Grates
e659082f-e4d6-5e1d-a61b-b6414277833e | date | Date:
| checkpoint | 3.6 - Structural Items (1)
3b525321-4f28-5639-add6-31ec82bc5df6 | note | EXTERNAL REFERENCE: Hold Point (HP)
be017c29-8f47-5668-bdae-a8405425460c | note | ACTIVITY / DESCRIPTION: Crown units / culvert
395b34ca-3ed7-5d85-be46-515ca8a56d07 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Structural Items (2)
caeee054-0a9f-552c-80b4-84f23d4ffd26 | note | EXTERNAL REFERENCE: Hold Point (HP)
43028459-d569-558f-948f-38217645075c | note | ACTIVITY / DESCRIPTION: Retaining structure works
807220dc-dd15-50c5-a8fc-c003c6fae476 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Structural Items (3)
0df10fa0-c833-55e1-9193-0d7a4569cbd7 | note | EXTERNAL REFERENCE: Hold Point (HP)
303a4d60-fb15-5276-81ad-fab2e818ecb3 | note | ACTIVITY / DESCRIPTION: Bridge works
a8c8c7d3-a0f9-557d-86f0-ec9e894e650e | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Concrete kerb works: (1)
85ba550e-6b28-5857-bc5e-ccbab8a99472 | note | ACTIVITY / DESCRIPTION: Alignment / level
ad6260d7-5ed9-59c9-acbc-d5ce0a530454 | date | Date:
| checkpoint | 3.7 - Concrete kerb works: (2)
196e60b1-5cf7-5548-a2a2-2f21dce71563 | note | ACTIVITY / DESCRIPTION: profile / finish
81cc87f6-e6c0-5e62-bc6d-46af70cb2f8e | date | Date:
| checkpoint | 3.8 - Concrete Works (1)
401cdf12-25f0-5fd8-9ee9-30975c3b2303 | note | EXTERNAL REFERENCE: Hold Point (HP)
12a4338e-180e-5542-ae61-a968ebe17b5a | note | ACTIVITY / DESCRIPTION:
30e9d4f6-b44a-5cd4-9e38-c9188dca2b01 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (1)
50a1f3c8-852d-5f7d-a90f-bbe760fbedbf | note | EXTERNAL REFERENCE: Hold Point (HP)
b8b5e787-b8a9-522f-bc42-7971fc89dbbd | note | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
c90c15f0-ebc6-556f-a851-79e244f671c9 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (2)
3d269fdf-cde3-5045-b197-b495c7bf1264 | note | EXTERNAL REFERENCE: Hold Point (HP)
1f8d3ea8-ab2f-5a5a-8252-be864ae88514 | note | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
8f5b6cbd-ad5a-5282-b1f1-8450ee22c61c | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (3)
f8c6660a-0b26-5d62-98ea-ddc73be56ed4 | note | EXTERNAL REFERENCE: Hold Point (HP)
e1f3c380-ce16-557f-9480-15d08544bce7 | note | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
f7e3ff3c-d599-5193-8553-3425282b40b2 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (4)
538b3710-fbf1-576a-9efb-9cda272d4314 | note | EXTERNAL REFERENCE: Hold Point (HP)
14e24089-3285-5a04-be40-c2f11bbf4886 | note | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
b1c808e3-525b-5745-880b-ed644c29343e | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (5)
4362a75c-8d17-58f2-a2b9-37e835138dc9 | note | EXTERNAL REFERENCE: Hold Point (HP)
517c09cb-52a7-55c1-af1d-c19b4061c574 | note | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
ba98caf0-cd34-5675-a817-86ab1e308f91 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (6)
bab3caaf-3e29-5150-9f97-102d3d7e3f11 | note | EXTERNAL REFERENCE: Hold Point (HP)
b0f820c0-a955-5788-bfbb-884b9b202c56 | note | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
2088c290-f00d-5619-969f-6f3235b7382d | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (7)
dfe49555-ae54-5b30-b62e-f56301f61a2c | note | EXTERNAL REFERENCE: Hold Point (HP)
d03928cd-fe9d-5ac9-b157-dcd34632c6ea | note | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
ed14191b-2a26-5984-b326-bb45015ed9c3 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (8)
8884b095-83d5-5ce6-8d8d-80eaf4306d63 | note | EXTERNAL REFERENCE: Hold Point (HP)
17cf4daa-0a6f-5fb4-9b7c-5f129acf634d | note | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
6e271065-4fde-52f2-8ee8-97b76b48f1f6 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
e73589a9-ec36-54cd-9029-5ee29ce1deec | note | EXTERNAL REFERENCE: Hold Point (HP)
1b3a26cc-7010-5158-ab72-bbdbee1bd096 | note | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
75b4e119-6301-5b94-b8ce-839b4666ce1f | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
8b2306d3-92b6-5476-83a2-281a1b1190f1 | note | EXTERNAL REFERENCE: Hold Point (HP)
e70bb6c6-d7ea-5908-a5dd-e5a62cd09130 | note | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
f937da68-feb6-5804-b46e-17e5c22c049a | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
90496a06-77d2-58e8-a89d-fb4b7d1f7ecf | note | EXTERNAL REFERENCE: Hold Point (HP)
6bce577a-706e-5a14-aafe-da3385ac4755 | note | ACTIVITY / DESCRIPTION: Density results
c1445df0-8e52-5f7f-96e1-74811d8d9e30 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
e51627c3-a02b-5a2c-867d-795095cde3c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
fd110d90-715a-5e18-9914-c7a94602cd50 | note | ACTIVITY / DESCRIPTION: Proof-roll
f3628880-a322-519a-a4fb-4d030a922d59 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (1)
b0e21f3b-781c-567f-9184-cedcd7dba172 | note | EXTERNAL REFERENCE: Hold Point (HP)
5b32bd42-1cfa-5ce5-b6d4-e6b7b8432557 | note | ACTIVITY / DESCRIPTION: Density results
981e0eb1-3b86-5839-a78d-f4ca87dddfb8 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (2)
de3488c1-cb69-51df-9b46-9083c7620eb3 | note | EXTERNAL REFERENCE: Hold Point (HP)
4460a507-b9c6-5ecf-94c7-151aeee07db0 | note | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
13da7516-ddc1-5ea8-864c-3925ea208098 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (3)
7f373744-f16a-59ab-8365-8d1b2626e0d1 | note | EXTERNAL REFERENCE: Hold Point (HP)
ebf648f9-2a90-524a-9a17-27d3e7fcc4ed | note | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
447c7ffb-ccd8-547d-8638-4bf69813c694 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (4)
3fef4dd5-2ef3-59f8-927a-73fce94b43d5 | note | EXTERNAL REFERENCE: Hold Point (HP)
cf83917c-4162-5eb0-8ed4-456ddbf42093 | note | ACTIVITY / DESCRIPTION: Ball Penetration Test
7f10fe4e-729a-547e-a479-92f014ea1436 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
d038a06b-3e2a-5e9c-bf71-de2b832e1b7f | note | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
43daad50-b548-5b48-a1ad-7365ecc21eef | date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
575b00ff-78d5-57f8-a161-2d17d6d112c3 | note | ACTIVITY / DESCRIPTION: Approved equipment for installation
765441c7-7694-5c75-a283-4c365041838c | date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
a46320d2-7f1e-5097-a48d-6447073a73da | note | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
561ad1d9-de3b-57fe-9f7f-e9a880990643 | date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
25963336-1eba-572e-b0e9-e5b299512e7c | note | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
3e25cae7-33e3-5629-9827-724e49802f46 | date | Date:
| checkpoint | 3.12 - Pavement Surface Works (1)
b6eaf2b8-9418-57ed-b6c3-2eacb3f58fb4 | note | EXTERNAL REFERENCE: Hold Point (HP)
0ab970b0-5923-5246-afca-a41d27053472 | note | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
b377244e-049f-565e-b5ab-9b6c17b108f6 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.12 - Pavement Surface Works (2)
b846e4a9-d9b0-5d0f-8d23-23db84ef0d0c | note | EXTERNAL REFERENCE: Hold Point (HP)
9bf5d3da-5e55-5f80-8075-102e2cd4bdbd | note | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
96810742-a4c1-5113-a84e-f2d7a6584165 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Landscape (1)
398e27fa-a911-566f-a856-c1ead55abbe6 | note | ACTIVITY / DESCRIPTION: Seed / Grass
2afa04d7-980a-5c03-b9a5-80f631a38a8f | date | Date:
| checkpoint | 3.13 - Landscape (2)
087d861a-ac33-5a99-9133-2da489077fdb | note | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
ced50251-08f1-5808-a1b4-ff6e82306766 | date | Date:
| checkpoint | 3.13 - Landscape (3)
851c9681-9923-5889-8551-1992519214c2 | note | ACTIVITY / DESCRIPTION: Street furniture
52496859-46bb-5845-886a-71886ad7d6ba | date | Date:
| checkpoint | 3.13 - Landscape (4)
307cf2ee-fa00-58a1-8d27-d9f5b40676fe | note | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
3d76ca1d-49f4-530b-ae11-4b845347c14c | date | Date:
| section | 4.0 - Practical Completion
| checkpoint | 4.1 - Road Fixtures (1)
a78b448f-3d6b-5115-bf91-68755dbd1d50 | note | EXTERNAL REFERENCE: Hold Point (HP)
491ff107-7508-5ded-bcd7-46dc66d1889c | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
c3234fb8-5a01-54b2-8c31-df4d3772bb61 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1 - Road Fixtures (2)
68e0deb5-ff03-5ad4-a55e-aa978e856497 | note | EXTERNAL REFERENCE: Hold Point (HP)
4c2e81e9-4907-5868-b8d1-d123752e8ef6 | note | ACTIVITY / DESCRIPTION: Signs
2b632d02-8e86-56ae-9497-1942b780189c | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1 - Road Fixtures (3)
8460d55e-5f83-5331-ab37-22230156ea0b | note | EXTERNAL REFERENCE: Hold Point (HP)
88345f33-bc9b-505b-98a5-80a9327974ed | note | ACTIVITY / DESCRIPTION: Guide posts
30bfad2f-388f-5f9b-92ba-6d644b77d9e8 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (1)
45a477e3-6218-5f97-9aec-324bc41f1015 | note | EXTERNAL REFERENCE: Hold Point (HP)
f7ea3589-d893-5f22-8fb1-b84637152666 | note | ACTIVITY / DESCRIPTION: Guardrail
f44c2698-72a0-5bb0-9da0-24d0e9af787d | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (2)
5816b8bc-7785-502f-93d7-b22dd3287534 | note | EXTERNAL REFERENCE: Hold Point (HP)
6d99b1d0-3c0e-52c2-b183-fbdcf96608c4 | note | ACTIVITY / DESCRIPTION: Wire-rope
d834a3c0-472e-5f71-a98c-db0213e7605a | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (3)
95c4c178-aad0-5b49-958e-e6d0d0d481b1 | note | EXTERNAL REFERENCE: Hold Point (HP)
2d487db0-bf78-5a7f-ad16-57cea40f5505 | note | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
c650ada4-30b7-578a-b8e5-f31b1ba00970 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Fences and Gates
8912adce-b3ab-5d7e-8c53-a6455556f9c2 | note | ACTIVITY / DESCRIPTION: Fences and Gates
da41faa5-b8d9-57fb-b5a4-91fce97a9ed7 | date | Date:
| checkpoint | 4.4 - Quality Ride Test
6930f8cd-1a69-5aeb-8223-009d731a03c5 | note | EXTERNAL REFERENCE: Hold Point (HP)
b7076034-b179-54d3-a933-b8d5ceb054f0 | note | ACTIVITY / DESCRIPTION: Quality Ride Test
1284124b-0fc7-5008-9461-e2d2bf5cf373 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| section | 5.0
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
dff99e57-221f-5d1e-8fb6-c9aafa0555bf | note | EXTERNAL REFERENCE: Hold Point (HP)
8eedd16b-1f11-57f6-9019-0bdbc003a50b | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
09948306-f65b-5d5a-a0b7-328132f80554 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
4bb23012-1b28-5815-847a-52fce7be4eac | note | EXTERNAL REFERENCE: Hold Point (HP)
de297435-d6a4-5eab-9aaa-3271b9fbf73a | note | ACTIVITY / DESCRIPTION: Signs, guide posts
503f7189-fc53-5a4d-86b7-2acb91f9cf01 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
39ec032c-277e-50b6-b1aa-1447b14abf8f | note | EXTERNAL REFERENCE: Hold Point (HP)
91679e6d-2a25-531d-9495-cb4792238201 | note | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
136e4b81-c14c-55b1-91b7-266d280b636a | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
fbce7819-e701-5581-a44f-36c502e9a0d9 | note | EXTERNAL REFERENCE: Hold Point (HP)
4d3ba9f5-d460-5173-b974-75d6edf1a06f | note | ACTIVITY / DESCRIPTION: Landscape (where applicable)
e560aa7e-540e-5ad9-9d8b-16f7d9db106c | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
30e35763-5253-53b3-a77e-c12431fd0cb6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
cb9f02e9-9908-55ca-8cd9-4341da118c0d | textbox | Print Name:
d84717bd-2a80-5c3a-b881-8158314def49 | textbox | Position:
0f7b88f2-0a7d-540b-889a-2ecfe760bed4 | date | Date:
| signoff | Sign ITP