## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
CTN-ITP-002 - Stormwater Drainage
Scope
Rows
|  | Separable Portion A - Stage 3 - Loop Road - Stormwater Drainage | dynamic | Separable Portion A | Stage 3 - Loop Road | Stormwater Drainage
|  | Separable Portion A - Commercial Road - Stormwater Drainage | dynamic | Separable Portion A | Commercial Road | Stormwater Drainage
|  | Separable Portion C - Main Car Park: Area 1 - Stormwater Drainage | dynamic | Separable Portion C | Main Car Park: Area 1 | Stormwater Drainage
|  | Separable Portion C - Main Car Park: Area 2 - 02 - Stormwater Drainage | dynamic | Separable Portion C | Main Car Park: Area 2 | 02 - Stormwater Drainage
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 2.1 - Precast Reinforced Concrete Pipe Supply |  | 2.1 - Precast Reinforced Concrete Pipe Supply | 2 - Procurement of Materials
|  | 2.2 - Precast Reinforced Concrete Inlet and Outlet Structures supply |  | 2.2 - Precast Reinforced Concrete Inlet and Outlet Structures supply | 2 - Procurement of Materials
|  | 2.3 - Bedding and Backfill Material Specification |  | 2.3 - Bedding and Backfill Material Specification | 2 - Procurement of Materials
|  | 2.4 - Setout of Works |  | 2.4 - Setout of Works | 2 - Procurement of Materials
|  | 3.1 - Excavation for pipe |  | 3.1 - Excavation for pipe | 3 - Installation of Underground Stormwater Drainage
|  | 3.2 - Trench Inspection |  | 3.2 - Trench Inspection | 3 - Installation of Underground Stormwater Drainage
|  | 3.3 - Trench Base Preparation / Bedding |  | 3.3 - Trench Base Preparation / Bedding | 3 - Installation of Underground Stormwater Drainage
|  | 3.4 - Haunching |  | 3.4 - Haunching | 3 - Installation of Underground Stormwater Drainage
|  | 3.5 - Laying of pipes |  | 3.5 - Laying of pipes | 3 - Installation of Underground Stormwater Drainage
|  | 3.6 - Jointing |  | 3.6 - Jointing | 3 - Installation of Underground Stormwater Drainage
|  | 3.7 - Drainage Pits |  | 3.7 - Drainage Pits | 3 - Installation of Underground Stormwater Drainage
|  | 3.8 - Tolerance |  | 3.8 - Tolerance | 3 - Installation of Underground Stormwater Drainage
|  | 4.1 - Inspection Prior to Backfilling |  | 4.1 - Inspection Prior to Backfilling | 4 - Backfilling of Stormwater
|  | 4.2 - Filling |  | 4.2 - Filling | 4 - Backfilling of Stormwater
|  | 4.3 - Testing and Acceptance of Fill Materials |  | 4.3 - Testing and Acceptance of Fill Materials | 4 - Backfilling of Stormwater
|  | 5.1 - Finishing and Rendering Pipes |  | 5.1 - Finishing and Rendering Pipes | 5 - Finishing and Commissioning
|  | 5.2 - As-Constructed survey and documentation |  | 5.2 - As-Constructed survey and documentation | 5 - Finishing and Commissioning
|  | Final Inspection |  | Final Inspection | 5 - Finishing and Commissioning
CTN-ITP-003 - Service Trenching & Install
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Electrical & Communications Trenching | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Electrical & Communications Trenching
|  | Separable Portion A - Stage 3 - Loop Road - Electrical & Communications Trenching | dynamic | Separable Portion A | Stage 3 - Loop Road | Electrical & Communications Trenching
|  | Separable Portion A - Commercial Road - Electrical & Communications Trenching | dynamic | Separable Portion A | Commercial Road | Electrical & Communications Trenching
|  | Separable Portion C - Main Car Park: Area 1 - Electrical & Communications Trenching | dynamic | Separable Portion C | Main Car Park: Area 1 | Electrical & Communications Trenching
|  | Separable Portion C - Main Car Park: Area 2 - Electrical & Communications Trenching | dynamic | Separable Portion C | Main Car Park: Area 2 | Electrical & Communications Trenching
|  | Separable Portion B - 03 - Service Trenching & Install | dynamic | Separable Portion B | 03 - Service Trenching & Install
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls
|  | 1.3 - Materials |  | 1.3 - Materials
|  | 2.1 - Survey set-out |  | 2.1 - Survey set-out
|  | 2.2 - Excavation/Boring & Trenching |  | 2.2 - Excavation/Boring & Trenching
|  | 2.3 - Installation of Conduits |  | 2.3 - Installation of Conduits
|  | 2.4 - Back Fill of Trenches |  | 2.4 - Back Fill of Trenches
|  | 2.6 - Compaction |  | 2.6 - Compaction
|  | 2.7 - Compaction |  | 2.7 - Compaction
|  | 2.8 - Installation of marker tape |  | 2.8 - Installation of marker tape
|  | 2.9 - Cable Pits & Pit Lids |  | 2.9 - Cable Pits & Pit Lids
|  | 3.1 - Cleaning of Site |  | 3.1 - Cleaning of Site
|  | 3.2 - Recording/As Built |  | 3.2 - Recording/As Built
|  | Final Inspection |  | Final Inspection
CTN-ITP-004 - Subsurface Drains
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Subsoil Drainage | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Subsoil Drainage
|  | Separable Portion A - Stage 3 - Loop Road - Subsurface Drainage | dynamic | Separable Portion A | Stage 3 - Loop Road | Subsurface Drainage
|  | Separable Portion A - Commercial Road - Subsurface Drainage | dynamic | Separable Portion A | Commercial Road | Subsurface Drainage
|  | Separable Portion C - Main Car Park: Area 2 - 04 - Subsurface Drains | dynamic | Separable Portion C | Main Car Park: Area 2 | 04 - Subsurface Drains
|  | Separable Portion B - 04 - Subsurface Drains | dynamic | Separable Portion B | 04 - Subsurface Drains
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls
|  | 1.3 - Material Classification |  | 1.3 - Material Classification
|  | 2.1 - Excavation Permit |  | 2.1 - Excavation Permit
|  | 2.2 - Outlets |  | 2.2 - Outlets
|  | 2.3 - Excavation of Trench |  | 2.3 - Excavation of Trench
|  | 2.4 - Bedding |  | 2.4 - Bedding
|  | 2.5 - Placing pipes |  | 2.5 - Placing pipes
|  | 2.6 - Backfilling |  | 2.6 - Backfilling
|  | 2.6 - Backfilling |  | 2.6 - Backfilling
|  | 2.8 - Access Points and Flushouts |  | 2.8 - Access Points and Flushouts
|  | 3.1 - As-Constructed survey and documentation |  | 3.1 - As-Constructed survey and documentation
|  | Final Inspection |  | Final Inspection
CTN-ITP-005 - Asphalt Placement
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Asphalt Placement | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Asphalt Placement
|  | Separable Portion A - Stage 3 - Loop Road - Asphalt Placement | dynamic | Separable Portion A | Stage 3 - Loop Road | Asphalt Placement
|  | Separable Portion A - Commercial Road - Asphalt | dynamic | Separable Portion A | Commercial Road | Asphalt
|  | Separable Portion C - Main Car Park: Area 1 - Asphalt Pavements | dynamic | Separable Portion C | Main Car Park: Area 1 | Asphalt Pavements
|  | Separable Portion C - Main Car Park: Area 2 - 05 - Asphalt Placement | dynamic | Separable Portion C | Main Car Park: Area 2 | 05 - Asphalt Placement
|  | Separable Portion B - 05 - Asphalt Placement | dynamic | Separable Portion B | 05 - Asphalt Placement
Columns
|  | 1.1 - Submission of Mix Design |  | 1.1 - Submission of Mix Design
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls
|  | 1.3 - Site Inspection and Base Condition |  | 1.3 - Site Inspection and Base Condition
|  | 1.4 - Ambient Conditions for Placing |  | 1.4 - Ambient Conditions for Placing
|  | 2.1 - Tack Coat |  | 2.1 - Tack Coat
|  | 2.2 - Prime Coat |  | 2.2 - Prime Coat
|  | 2.3 - Commencement of Placing |  | 2.3 - Commencement of Placing
|  | 2.4 - Delivery of Mix |  | 2.4 - Delivery of Mix
|  | 2.5 - Layer Thickness and Level Control |  | 2.5 - Layer Thickness and Level Control
|  | 2.6 - Asphalt Placement works |  | 2.6 - Asphalt Placement works
|  | 2.7 - Surface Finish of Wearing Course |  | 2.7 - Surface Finish of Wearing Course
|  | 2.8 - Kerb and Channel |  | 2.8 - Kerb and Channel
|  | 3.1 - Compaction |  | 3.1 - Compaction
|  | 3.2 - As-constructed survey and conformance documentation |  | 3.2 - As-constructed survey and conformance documentation
|  | Final Inspection |  | Final Inspection
CTN-ITP-006 - Concrete - Kerbs
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Concrete Kerbs | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Concrete Kerbs
|  | Separable Portion A - Stage 3 - Loop Road - Concrete Kerbs | dynamic | Separable Portion A | Stage 3 - Loop Road | Concrete Kerbs
|  | Separable Portion A - Commercial Road - Concrete Kerbs | dynamic | Separable Portion A | Commercial Road | Concrete Kerbs
|  | Separable Portion C - Main Car Park: Area 1 - Concrete Kerbs | dynamic | Separable Portion C | Main Car Park: Area 1 | Concrete Kerbs
|  | Separable Portion C - Main Car Park: Area 2 - 06 - Concrete Kerbs | dynamic | Separable Portion C | Main Car Park: Area 2 | 06 - Concrete Kerbs
|  | Separable Portion B - 06 - Concrete Kerbs | dynamic | Separable Portion B | 06 - Concrete Kerbs
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Submission & Approval of Concrete Mix Design |  | 1.3 - Submission & Approval of Concrete Mix Design | 1 - Preliminary Works
|  | 2.1 - Setting Out |  | 2.1 - Setting Out | 2 - Construction Works
|  | 2.2 - Excavation Permit |  | 2.2 - Excavation Permit | 2 - Construction Works
|  | 2.3 - Excavation |  | 2.3 - Excavation | 2 - Construction Works
|  | 2.4 - Concrete Placement |  | 2.4 - Concrete Placement | 2 - Construction Works
|  | 2.5 - Pram Crossings |  | 2.5 - Pram Crossings | 2 - Construction Works
|  | 2.6 - Joints |  | 2.6 - Joints | 2 - Construction Works
|  | 2.7 - Protection of concrete |  | 2.7 - Protection of concrete | 2 - Construction Works
|  | 2.8 - Curing - Kerb |  | 2.8 - Curing - Kerb | 2 - Construction Works
|  | 3.1 - Carry out sampling of concrete - strength and consistency |  | 3.1 - Carry out sampling of concrete - strength and consistency | 3 - Completion
|  | 3.2 - Tolerances |  | 3.2 - Tolerances | 3 - Completion
|  | 3.3 - Backfilling |  | 3.3 - Backfilling | 3 - Completion
|  | 3.4 - As-constructed survey and conformance documentation |  | 3.4 - As-constructed survey and conformance documentation | 3 - Completion
|  | Final Inspection |  | Final Inspection | 3 - Completion
CTN-ITP-007 - Concrete - Footpaths & Islands
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Concrete Footpaths & Islands | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Concrete Footpaths & Islands
|  | Separable Portion A - Stage 3 - Loop Road - Pavements | dynamic | Separable Portion A | Stage 3 - Loop Road | Pavements
|  | Separable Portion A - Stage 3 - Loop Road - Concrete Footpaths & Islands | dynamic | Separable Portion A | Stage 3 - Loop Road | Concrete Footpaths & Islands
|  | Separable Portion A - Commercial Road - Concrete Footpaths & Islands | dynamic | Separable Portion A | Commercial Road | Concrete Footpaths & Islands
|  | Separable Portion C - Main Car Park: Area 1 - Concrete Footpaths & Islands | dynamic | Separable Portion C | Main Car Park: Area 1 | Concrete Footpaths & Islands
|  | Separable Portion C - Main Car Park: Area 2 - 07 - Concrete Footpath & Island | dynamic | Separable Portion C | Main Car Park: Area 2 | 07 - Concrete Footpath & Island
|  | Separable Portion B - 07 - Concrete Footpath & Island | dynamic | Separable Portion B | 07 - Concrete Footpath & Island
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Concrete Mix Design |  | 1.3 - Concrete Mix Design | 1 - Preliminary Works
|  | 2.1 - Setting Out |  | 2.1 - Setting Out | 2 - Construction Works
|  | 2.2 - Excavation Permit |  | 2.2 - Excavation Permit | 2 - Construction Works
|  | 2.3 - Excavation |  | 2.3 - Excavation | 2 - Construction Works
|  | 2.4 - Formwork |  | 2.4 - Formwork | 2 - Construction Works
|  | 2.5 - Reinforcement |  | 2.5 - Reinforcement | 2 - Construction Works
|  | 2.6 - Concrete Placement |  | 2.6 - Concrete Placement | 2 - Construction Works
|  | 2.7 - Surface Finish |  | 2.7 - Surface Finish | 2 - Construction Works
|  | 2.8 - Joints |  | 2.8 - Joints | 2 - Construction Works
|  | 2.9 - Protection of concrete |  | 2.9 - Protection of concrete | 2 - Construction Works
|  | 2.10 - Curing - Pedestrian Footpaths |  | 2.10 - Curing - Pedestrian Footpaths | 2 - Construction Works
|  | 3.1 - Carry out sampling of concrete - strength and consistency |  | 3.1 - Carry out sampling of concrete - strength and consistency | 3 - Completion
|  | 3.2 - Backfilling |  | 3.2 - Backfilling | 3 - Completion
|  | 3.3 - As-constructed survey and conformance documentation |  | 3.3 - As-constructed survey and conformance documentation | 3 - Completion
|  | Final Inspection |  | Final Inspection | 3 - Completion
CTN-ITP-008 - Cast In-Situ Pits
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Insitu Concrete Pits | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Insitu Concrete Pits
|  | Separable Portion A - Stage 3 - Loop Road - In-situ concrete pits | dynamic | Separable Portion A | Stage 3 - Loop Road | In-situ concrete pits
|  | Separable Portion A - Stage 3 - Loop Road - Stormwater Drainage | dynamic | Separable Portion A | Stage 3 - Loop Road | Stormwater Drainage
|  | Separable Portion A - Commercial Road - In-site concrete pits | dynamic | Separable Portion A | Commercial Road | In-site concrete pits
|  | Separable Portion C - Main Car Park: Area 1 - Insitu Concrete Pits | dynamic | Separable Portion C | Main Car Park: Area 1 | Insitu Concrete Pits
|  | Separable Portion C - Main Car Park: Area 1 - Stormwater Drainage | dynamic | Separable Portion C | Main Car Park: Area 1 | Stormwater Drainage
|  | Separable Portion C - Main Car Park: Area 2 - Insitu Concrete Pits | dynamic | Separable Portion C | Main Car Park: Area 2 | Insitu Concrete Pits
|  | Separable Portion C - Main Car Park: Area 2 - 02 - Stormwater Drainage | dynamic | Separable Portion C | Main Car Park: Area 2 | 02 - Stormwater Drainage
|  | Separable Portion B - 08 - Concrete Cast Insitu Pits | dynamic | Separable Portion B | 08 - Concrete Cast Insitu Pits
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 2.1 - Materials & source Approval - In-Situ Pits |  | 2.1 - Materials & source Approval - In-Situ Pits | 2 - Material Conformance
|  | 2.2 - Materials & source Approval - Pit Covers |  | 2.2 - Materials & source Approval - Pit Covers | 2 - Material Conformance
|  | 2.3 - Materials & source Approval - Step Irons |  | 2.3 - Materials & source Approval - Step Irons | 2 - Material Conformance
|  | 2.4 - Source In-situ Pit Material |  | 2.4 - Source In-situ Pit Material | 2 - Material Conformance
|  | 3.1 - Pouring Concrete |  | 3.1 - Pouring Concrete | 3 - Construction \ Erection of Formwork
|  | 3.2 - Bedding |  | 3.2 - Bedding | 3 - Construction \ Erection of Formwork
|  | 3.3 - Formwork |  | 3.3 - Formwork | 3 - Construction \ Erection of Formwork
|  | 3.4 - Subsurface Drainage Accomodation |  | 3.4 - Subsurface Drainage Accomodation | 3 - Construction \ Erection of Formwork
|  | 4.1 - Steel Fixing |  | 4.1 - Steel Fixing | 4 - Reinforcement
|  | 4.2 - Reinforcement Installation |  | 4.2 - Reinforcement Installation | 4 - Reinforcement
|  | 5.1 - Pre-pour Inspection - Pit Base and Pit Walls |  | 5.1 - Pre-pour Inspection - Pit Base and Pit Walls | 5 - Inspections
|  | 6.1 - Pour in-situ Pits |  | 6.1 - Pour in-situ Pits | 6 - Placing and Finishing Concrete
|  | 6.2 - Finishing |  | 6.2 - Finishing | 6 - Placing and Finishing Concrete
|  | 6.3 - Installation of Pit Cover |  | 6.3 - Installation of Pit Cover | 6 - Placing and Finishing Concrete
|  | 6.4 - Concrete Testing |  | 6.4 - Concrete Testing | 6 - Placing and Finishing Concrete
|  | 7.1 - Concrete Curing |  | 7.1 - Concrete Curing | 7 - Post Pour Details and Inspections
|  | 7.1 - Removal of Formwork |  | 7.1 - Removal of Formwork | 7 - Post Pour Details and Inspections
|  | 7.2 - Allowable Tolerances Level & Alignment |  | 7.2 - Allowable Tolerances Level & Alignment | 7 - Post Pour Details and Inspections
|  | 7.3 - Post-pour Checklist |  | 7.3 - Post-pour Checklist | 7 - Post Pour Details and Inspections
|  | 7.4 - Backfilling Around Pits |  | 7.4 - Backfilling Around Pits | 7 - Post Pour Details and Inspections
|  | Final Inspection |  | Final Inspection | 7 - Post Pour Details and Inspections
GT4-ITP-009 - Unbound Flexible Pavement Construction
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Pavement | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Pavement
|  | Separable Portion A - Stage 3 - Loop Road - Pavements | dynamic | Separable Portion A | Stage 3 - Loop Road | Pavements
|  | Separable Portion C - Main Car Park: Area 1 - Pavements | dynamic | Separable Portion C | Main Car Park: Area 1 | Pavements
|  | Separable Portion C - Main Car Park: Area 2 - 09 - Unbound Flexible Pavement | dynamic | Separable Portion C | Main Car Park: Area 2 | 09 - Unbound Flexible Pavement
|  | Separable Portion B - 09 - Unbound Flexible Pavement | dynamic | Separable Portion B | 09 - Unbound Flexible Pavement
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Plant and Equipment |  | 1.3 - Plant and Equipment | 1 - Preliminary Works
|  | 2.1 - The commencement of construction of base and subbase |  | 2.1 - The commencement of construction of base and subbase | 2 - Placement
|  | 2.2 - Shape |  | 2.2 - Shape | 2 - Placement
|  | 2.3 - Delivery Dockets |  | 2.3 - Delivery Dockets | 2 - Placement
|  | 2.4 - Layer Thickness |  | 2.4 - Layer Thickness | 2 - Placement
|  | 2.5 - Conformity with Drawing |  | 2.5 - Conformity with Drawing | 2 - Placement
|  | 2.6 - Jointing |  | 2.6 - Jointing | 2 - Placement
|  | 3.1 - Test Rolling |  | 3.1 - Test Rolling | 3 - Testing and Conformance
|  | 3.2 - Compaction of road pavement |  | 3.2 - Compaction of road pavement | 3 - Testing and Conformance
|  | 3.3 - Completed Surface Level Compliance |  | 3.3 - Completed Surface Level Compliance | 3 - Testing and Conformance
|  | 3.4 - Shape |  | 3.4 - Shape | 3 - Testing and Conformance
|  | Final Inspection |  | Final Inspection | 3 - Testing and Conformance
GT4-ITP-011 - Earthworks - Cut, Fill and Subgrade Preparation
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Earthworks | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Earthworks
|  | Separable Portion A - Stage 3 - Loop Road - Earthworks | dynamic | Separable Portion A | Stage 3 - Loop Road | Earthworks
|  | Separable Portion A - Commercial Road - Earthworks | dynamic | Separable Portion A | Commercial Road | Earthworks
|  | Separable Portion C - Main Car Park: Area 1 - Earthworks | dynamic | Separable Portion C | Main Car Park: Area 1 | Earthworks
|  | Separable Portion C - Main Car Park: Area 2 - 11 - Earthworks | dynamic | Separable Portion C | Main Car Park: Area 2 | 11 - Earthworks
|  | Separable Portion B - 11 - Earthworks | dynamic | Separable Portion B | 11 - Earthworks
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Survey set-out |  | 1.3 - Survey set-out | 1 - Preliminary Works
|  | 1.4 - Ground Penetration Permit |  | 1.4 - Ground Penetration Permit | 1 - Preliminary Works
|  | 1.5 - Protection of Services |  | 1.5 - Protection of Services | 1 - Preliminary Works
|  | 2.1 - Material Categorisation |  | 2.1 - Material Categorisation | 2 - Earthworks
|  | 2.2 - Stripping of Topsoil |  | 2.2 - Stripping of Topsoil | 2 - Earthworks
|  | 2.3 - Protection of Works |  | 2.3 - Protection of Works | 2 - Earthworks
|  | 2.4 - Unsuitable Material |  | 2.4 - Unsuitable Material | 2 - Earthworks
|  | 2.5 - Subgrade Material |  | 2.5 - Subgrade Material | 2 - Earthworks
|  | 2.6 - Placing of Fill |  | 2.6 - Placing of Fill | 2 - Earthworks
|  | 3.1 - Test Rolling |  | 3.1 - Test Rolling | 3 - Testing and Surface Preparation
|  | 3.2 - Cut and Fill Tolerances |  | 3.2 - Cut and Fill Tolerances | 3 - Testing and Surface Preparation
|  | 3.3 - Subgrade level conformity |  | 3.3 - Subgrade level conformity | 3 - Testing and Surface Preparation
|  | 3.4 - Fill Material Compaction & Moisture Content Requirements |  | 3.4 - Fill Material Compaction & Moisture Content Requirements | 3 - Testing and Surface Preparation
|  | 3.5 - CBR Testing of Subgrade |  | 3.5 - CBR Testing of Subgrade | 3 - Testing and Surface Preparation
|  | Final Inspection |  | Final Inspection | 3 - Testing and Surface Preparation
GT4-ITP-012 - Concrete Structural Footings
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Structural Footings | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Structural Footings
|  | Separable Portion A - Stage 3 - Loop Road - Structural Footings | dynamic | Separable Portion A | Stage 3 - Loop Road | Structural Footings
|  | Separable Portion A - Commercial Road - Structural Footings | dynamic | Separable Portion A | Commercial Road | Structural Footings
|  | Separable Portion C - Main Car Park: Area 1 - Structural Footings | dynamic | Separable Portion C | Main Car Park: Area 1 | Structural Footings
|  | Separable Portion C - Main Car Park: Area 1 - Carpark Bollards | dynamic | Separable Portion C | Main Car Park: Area 1 | Carpark Bollards
|  | Separable Portion C - Main Car Park: Area 2 - Structural Footings | dynamic | Separable Portion C | Main Car Park: Area 2 | Structural Footings
|  | Separable Portion B - 12 - Concrete Structural Footings | dynamic | Separable Portion B | 12 - Concrete Structural Footings
|  | Separable Portion D - Southern Substation | dynamic | Separable Portion D | Southern Substation
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 2.1 - Materials & source Approval - Reinforcing |  | 2.1 - Materials & source Approval - Reinforcing | 2 - Material Conformance
|  | 2.2 - Materials & source Approval - Cast-in Items |  | 2.2 - Materials & source Approval - Cast-in Items | 2 - Material Conformance
|  | 2.3 - Source In-situ Concrete Material |  | 2.3 - Source In-situ Concrete Material | 2 - Material Conformance
|  | 3.1 - Set Out |  | 3.1 - Set Out | 3 - Construction \ Erection of Formwork
|  | 3.2 - Excavation |  | 3.2 - Excavation | 3 - Construction \ Erection of Formwork
|  | 3.3 - Blinding Concrete |  | 3.3 - Blinding Concrete | 3 - Construction \ Erection of Formwork
|  | 3.4 - Formwork |  | 3.4 - Formwork | 3 - Construction \ Erection of Formwork
|  | 4.1 - Steel Fixing |  | 4.1 - Steel Fixing | 4 - Reinforcement
|  | 4.2 - Reinforcement Installation |  | 4.2 - Reinforcement Installation | 4 - Reinforcement
|  | 4.3 - Cast-In Items |  | 4.3 - Cast-In Items | 4 - Reinforcement
|  | 5.1 - Pre-pour Inspection |  | 5.1 - Pre-pour Inspection | 5 - Inspections
|  | 6.1 - Pour Concrete Footings |  | 6.1 - Pour Concrete Footings | 6 - Placing and Finishing Concrete
|  | 6.2 - Finishing |  | 6.2 - Finishing | 6 - Placing and Finishing Concrete
|  | 6.3 - Concrete Testing |  | 6.3 - Concrete Testing | 6 - Placing and Finishing Concrete
|  | 7.1 - Concrete Curing |  | 7.1 - Concrete Curing | 7 - Post Pour Details and Inspections
|  | 7.2 - Removal of Formwork |  | 7.2 - Removal of Formwork | 7 - Post Pour Details and Inspections
|  | 7.3 - Allowable Tolerances Level & Alignment |  | 7.3 - Allowable Tolerances Level & Alignment | 7 - Post Pour Details and Inspections
|  | 7.4 - Post-pour Checklist |  | 7.4 - Post-pour Checklist | 7 - Post Pour Details and Inspections
|  | 7.5 - Backfilling |  | 7.5 - Backfilling | 7 - Post Pour Details and Inspections
|  | Final Inspection |  | Final Inspection | 7 - Post Pour Details and Inspections
GT4-ITP-013 - Precast Installation
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Precast Pits | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Precast Pits
|  | Separable Portion A - Stage 3 - Loop Road - Precast Pits | dynamic | Separable Portion A | Stage 3 - Loop Road | Precast Pits
|  | Separable Portion A - Commercial Road - Pre-cast concrete pits | dynamic | Separable Portion A | Commercial Road | Pre-cast concrete pits
|  | Separable Portion A - Commercial Road - Stormwater Drainage | dynamic | Separable Portion A | Commercial Road | Stormwater Drainage
|  | Separable Portion C - Main Car Park: Area 1 - Precast Pits | dynamic | Separable Portion C | Main Car Park: Area 1 | Precast Pits
|  | Separable Portion C - Main Car Park: Area 2 - Precast Pits | dynamic | Separable Portion C | Main Car Park: Area 2 | Precast Pits
|  | Separable Portion B - 13 - Polycrete Pit | dynamic | Separable Portion B | 13 - Polycrete Pit
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 2.1 - Materials & source Approval - In-Situ Pits |  | 2.1 - Materials & source Approval - In-Situ Pits | 2 - Material Conformance
|  | 2.2 - Materials & source Approval - Pit Covers |  | 2.2 - Materials & source Approval - Pit Covers | 2 - Material Conformance
|  | 2.3 - Source In-situ Pit Material |  | 2.3 - Source In-situ Pit Material | 2 - Material Conformance
|  | 3.1 - Bedding |  | 3.1 - Bedding | 3 - Installation
|  | 3.2 - Installation of Precast Element |  | 3.2 - Installation of Precast Element | 3 - Installation
|  | 4.1 - Formwork |  | 4.1 - Formwork | 4 - Cast Insitu Lids/Frames
|  | 4.2 - Reinforcing |  | 4.2 - Reinforcing | 4 - Cast Insitu Lids/Frames
|  | 4.3 - Concrete Pour |  | 4.3 - Concrete Pour | 4 - Cast Insitu Lids/Frames
|  | 5.1 - Allowable Tolerances Level & Alignment |  | 5.1 - Allowable Tolerances Level & Alignment | 5 - Post Pour Details and Inspections
|  | 5.2 - Backfilling Around Pits |  | 5.2 - Backfilling Around Pits | 5 - Post Pour Details and Inspections
|  | Final Inspection |  | Final Inspection | 5 - Post Pour Details and Inspections
GT4-ITP-014 - Electrical Works
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Electrical Works | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Electrical Works
|  | Separable Portion A - Stage 3 - Loop Road - Electrical Works | dynamic | Separable Portion A | Stage 3 - Loop Road | Electrical Works
|  | Separable Portion C - Main Car Park: Area 2 - 14 - Electrical Works | dynamic | Separable Portion C | Main Car Park: Area 2 | 14 - Electrical Works
|  | Separable Portion B - Electrical Works | dynamic | Separable Portion B | Electrical Works
|  | Separable Portion D - Northern Substation | dynamic | Separable Portion D | Northern Substation
|  | Separable Portion D - Southern Substation | dynamic | Separable Portion D | Southern Substation
Columns
|  | 1.1 - Define physical bounds of a lot |  | 1.1 - Define physical bounds of a lot | 1 - Preliminary Works
|  | 1.2 - Site Access available |  | 1.2 - Site Access available | 1 - Preliminary Works
|  | 1.3 - Underlying lot(s) conform |  | 1.3 - Underlying lot(s) conform | 1 - Preliminary Works
|  | 1.4 - Ensure current Termination drawing revisions and cable schedules are available |  | 1.4 - Ensure current Termination drawing revisions and cable schedules are available | 1 - Preliminary Works
|  | 2.1 - Receive completed FLE ITP SS107 - Fence and gate installation |  | 2.1 - Receive completed FLE ITP SS107 - Fence and gate installation | 2 - Subcontractor ITP
|  | 2.2 - Receive completed FLE ITP SS108 - Internal road |  | 2.2 - Receive completed FLE ITP SS108 - Internal road | 2 - Subcontractor ITP
|  | 2.3 - Receive completed FLE ITP SS109 - Switchyard Surfacing |  | 2.3 - Receive completed FLE ITP SS109 - Switchyard Surfacing | 2 - Subcontractor ITP
|  | 2.4 - Receive completed FLE ITP SS110 - Stormwater Pipe Installation |  | 2.4 - Receive completed FLE ITP SS110 - Stormwater Pipe Installation | 2 - Subcontractor ITP
|  | 2.5 - Receive completed FLE ITP SS200 - Structural Steel Installation |  | 2.5 - Receive completed FLE ITP SS200 - Structural Steel Installation | 2 - Subcontractor ITP
|  | 2.6 - Receive completed FLE ITP SS301- Substation Earth Grid Inspection Checklist |  | 2.6 - Receive completed FLE ITP SS301- Substation Earth Grid Inspection Checklist | 2 - Subcontractor ITP
|  | 2.7 - Receive completed FLE ITP SS302 - Current and Voltage Transformer Installation Checklist |  | 2.7 - Receive completed FLE ITP SS302 - Current and Voltage Transformer Installation Checklist | 2 - Subcontractor ITP
|  | 2.8 - Receive completed FLE ITP SS303 - Isolator and Earth Switch Installation Checklist |  | 2.8 - Receive completed FLE ITP SS303 - Isolator and Earth Switch Installation Checklist | 2 - Subcontractor ITP
|  | 2.9 - Receive completed FLE ITP SS304 - Circuit Breaker Installation Checklist |  | 2.9 - Receive completed FLE ITP SS304 - Circuit Breaker Installation Checklist | 2 - Subcontractor ITP
|  | 2.10 - Receive completed FLE ITP SS305 - Post Insulator Checklist |  | 2.10 - Receive completed FLE ITP SS305 - Post Insulator Checklist | 2 - Subcontractor ITP
|  | 2.11 - Receive completed FLE ITP SS306 - Bus Bar and Clamps Installation Checklist |  | 2.11 - Receive completed FLE ITP SS306 - Bus Bar and Clamps Installation Checklist | 2 - Subcontractor ITP
|  | 2.12 - Receive completed FLE ITP SS307 - Control Panel Installation Checklist |  | 2.12 - Receive completed FLE ITP SS307 - Control Panel Installation Checklist | 2 - Subcontractor ITP
|  | 2.13 - Receive completed FLE ITP SS308 - Lighting Mast Installation Checklist |  | 2.13 - Receive completed FLE ITP SS308 - Lighting Mast Installation Checklist | 2 - Subcontractor ITP
|  | 2.14 - Receive completed FLE ITP SS309 - Low Voltage Cable Termination Checklist |  | 2.14 - Receive completed FLE ITP SS309 - Low Voltage Cable Termination Checklist | 2 - Subcontractor ITP
|  | 2.15 - Receive completed FLE ITP SS310 - Ductor Test Results (Insulation resistance DLA/DDF) |  | 2.15 - Receive completed FLE ITP SS310 - Ductor Test Results (Insulation resistance DLA/DDF) | 2 - Subcontractor ITP
|  | 2.16 - Receive completed FLE ITP SS311 - Marshalling Box Installation Checklist |  | 2.16 - Receive completed FLE ITP SS311 - Marshalling Box Installation Checklist | 2 - Subcontractor ITP
|  | 2.17 - Receive completed FLE ITP SS312 - HV Cable termination |  | 2.17 - Receive completed FLE ITP SS312 - HV Cable termination | 2 - Subcontractor ITP
|  | 2.18 - Receive completed FLE ITP SS313 - Light and Power in Substation Building |  | 2.18 - Receive completed FLE ITP SS313 - Light and Power in Substation Building | 2 - Subcontractor ITP
|  | 2.19 - Receive completed FLE ITP SS314 - Field Cable Installation |  | 2.19 - Receive completed FLE ITP SS314 - Field Cable Installation | 2 - Subcontractor ITP
|  | Final Inspection |  | Final Inspection | 3 - Final Inspection
GT4-ITP-015 - Container Farm Construction
Scope
Rows
|  | Container farm | dynamic | Container farm
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls
|  | 1.3 - Plant and Equipment |  | 1.3 - Plant and Equipment
|  | 1.4 - Service Locating and Proving |  | 1.4 - Service Locating and Proving
|  | 1.5 - Protection and Remoal of Services |  | 1.5 - Protection and Remoal of Services
|  | 2.1 - Tree Removal |  | 2.1 - Tree Removal
|  | 2.2 - Mulching and Chipping |  | 2.2 - Mulching and Chipping
|  | 2.3 - Stripping of topsoil |  | 2.3 - Stripping of topsoil
|  | 3.1 - Earthworks |  | 3.1 - Earthworks
|  | 3.2 - Subgrade Preperation |  | 3.2 - Subgrade Preperation
|  | 3.3 - Survey Conformance |  | 3.3 - Survey Conformance
|  | 4.1 - Placement |  | 4.1 - Placement
|  | 4.2 - Material Quality |  | 4.2 - Material Quality
|  | 4.3 - Testing and Proof Roll |  | 4.3 - Testing and Proof Roll
|  | 4.4 - Shape |  | 4.4 - Shape
|  | 4.5 - Conformance |  | 4.5 - Conformance
|  | 5.1 - Asphalt Mix Specification |  | 5.1 - Asphalt Mix Specification
|  | 5.2 - Placement |  | 5.2 - Placement
|  | 5.3 - Jointing |  | 5.3 - Jointing
|  | 5.4 - Compaction |  | 5.4 - Compaction
|  | 5.5 - Layer Thickness |  | 5.5 - Layer Thickness
|  | 5.6 - Tolerances |  | 5.6 - Tolerances
|  | 6.1 - Concrete Mix Design |  | 6.1 - Concrete Mix Design
|  | 6.2 - Reinforment |  | 6.2 - Reinforment
|  | 6.3 - Placement |  | 6.3 - Placement
|  | 6.4 - Tolerances |  | 6.4 - Tolerances
|  | Final Inspection |  | Final Inspection
GT4-ITP-016 - Cement Treated Crushed Rock
Scope
Rows
|  | Separable Portion A - Commercial Road - Cementitious Treated Rigid Pavement | dynamic | Separable Portion A | Commercial Road | Cementitious Treated Rigid Pavement
|  | Separable Portion C - Main Car Park: Area 2 - 16 - Cement Treated Crushed Rock | dynamic | Separable Portion C | Main Car Park: Area 2 | 16 - Cement Treated Crushed Rock
|  | Separable Portion B - 16 - Cement Treated Crushed Rock | dynamic | Separable Portion B | 16 - Cement Treated Crushed Rock
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used | 1 - Preliminary Works
|  | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place |  | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place | 1 - Preliminary Works
|  | 1.3 - Traffic Management (When required) |  | 1.3 - Traffic Management (When required) | 1 - Preliminary Works
|  | 1.4 - Survey set out works |  | 1.4 - Survey set out works | 1 - Preliminary Works
|  | 2.1 - Delivery Dockets |  | 2.1 - Delivery Dockets | 2 - Placement
|  | 2.2 - Placing of Crushed Rock |  | 2.2 - Placing of Crushed Rock | 2 - Placement
|  | 2.3 - Moisture Content |  | 2.3 - Moisture Content | 2 - Placement
|  | 2.4 - Water |  | 2.4 - Water | 2 - Placement
|  | 2.5 - Conformity with drawing |  | 2.5 - Conformity with drawing | 2 - Placement
|  | 2.6 - Jointing |  | 2.6 - Jointing | 2 - Placement
|  | 2.7 - Compaction |  | 2.7 - Compaction | 2 - Placement
|  | 2.8 - Curing and Protection of Compacted Layers |  | 2.8 - Curing and Protection of Compacted Layers | 2 - Placement
|  | 3.1 - Test Rolling |  | 3.1 - Test Rolling | 3 - Conformance
|  | 3.2 - Testing and Acceptance of Compaction (Scale B) |  | 3.2 - Testing and Acceptance of Compaction (Scale B) | 3 - Conformance
|  | 3.3 - Survey Conformance |  | 3.3 - Survey Conformance | 3 - Conformance
|  | 3.4 - Shape |  | 3.4 - Shape | 3 - Conformance
|  | Final Inspection |  | Final Inspection | 3 - Conformance
GT4-ITP-017 - Concrete Rigid Pavement Construction
Scope
Rows
|  | Separable Portion A - Commercial Road - Concrete Rigid Pavement | dynamic | Separable Portion A | Commercial Road | Concrete Rigid Pavement
|  | Separable Portion C - Main Car Park: Area 2 - 17 - Concrete Rigid Pavement | dynamic | Separable Portion C | Main Car Park: Area 2 | 17 - Concrete Rigid Pavement
|  | Separable Portion B - 17 - Concrete Rigid Pavement | dynamic | Separable Portion B | 17 - Concrete Rigid Pavement
Columns
|  | 1.1 - Check for correct documentation |  | 1.1 - Check for correct documentation | 1 - Preliminary Works
|  | 1.2 - Implementation of all measures and controls |  | 1.2 - Implementation of all measures and controls | 1 - Preliminary Works
|  | 1.3 - Concrete Mix Design |  | 1.3 - Concrete Mix Design | 1 - Preliminary Works
|  | 2.1 - Setting Out |  | 2.1 - Setting Out | 2 - Initial Works
|  | 2.2 - Pre-Seal Inspection |  | 2.2 - Pre-Seal Inspection | 2 - Initial Works
|  | 2.3 - De-Bonding Treatment |  | 2.3 - De-Bonding Treatment | 2 - Initial Works
|  | 3.1 - Formwork |  | 3.1 - Formwork | 3 - Construction Works
|  | 3.2 - Reinforcement |  | 3.2 - Reinforcement | 3 - Construction Works
|  | 3.3 - Dowels |  | 3.3 - Dowels | 3 - Construction Works
|  | 3.4 - Tie Bars |  | 3.4 - Tie Bars | 3 - Construction Works
|  | 3.5 - Authority to Place Concrete |  | 3.5 - Authority to Place Concrete | 3 - Construction Works
|  | 3.6 - Concrete Placement |  | 3.6 - Concrete Placement | 3 - Construction Works
|  | 3.7 - Compaction |  | 3.7 - Compaction | 3 - Construction Works
|  | 3.8 - Surface Finish |  | 3.8 - Surface Finish | 3 - Construction Works
|  | 3.9 - Joints |  | 3.9 - Joints | 3 - Construction Works
|  | 3.10 - Protection of concrete |  | 3.10 - Protection of concrete | 3 - Construction Works
|  | 3.11 - Curing |  | 3.11 - Curing | 3 - Construction Works
|  | 4.1 - Carry out sampling of concrete - strength and consistency |  | 4.1 - Carry out sampling of concrete - strength and consistency | 4 - Completion
|  | 4.2 - As-constructed survey and conformance documentation |  | 4.2 - As-constructed survey and conformance documentation | 4 - Completion
|  | Final Inspection |  | Final Inspection | 4 - Completion
GT4-ITP-019 - Fire Services
Scope
Rows
|  | Separable Portion A - Stage 2 - Remnant Ready Bay - Fire Services | dynamic | Separable Portion A | Stage 2 - Remnant Ready Bay | Fire Services
|  | Separable Portion A - Stage 3 - Loop Road - Fire Services | dynamic | Separable Portion A | Stage 3 - Loop Road | Fire Services
|  | Separable Portion C - Main Car Park: Area 2 - 19 - Fire Services | dynamic | Separable Portion C | Main Car Park: Area 2 | 19 - Fire Services
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used | 1 - Preliminary Works
|  | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place |  | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place | 1 - Preliminary Works
|  | 1.3 - Traffic Management (When required) |  | 1.3 - Traffic Management (When required) | 1 - Preliminary Works
|  | 1.4 - Survey set out works |  | 1.4 - Survey set out works | 1 - Preliminary Works
|  | 2.1 - Water Pipes, Valves and fittings |  | 2.1 - Water Pipes, Valves and fittings | 2 - Material Conformance
|  | 2.2 - Correct embedment / backfill materials onsite |  | 2.2 - Correct embedment / backfill materials onsite | 2 - Material Conformance
|  | 3.1 - Trenching details |  | 3.1 - Trenching details | 3 - Excavation of trenches
|  | 3.2 - Benching & shielding (where required) |  | 3.2 - Benching & shielding (where required) | 3 - Excavation of trenches
|  | 4.01 - Bedding |  | 4.01 - Bedding | 4 - Watermain Installation
|  | 4.02 - Pipe Joints |  | 4.02 - Pipe Joints | 4 - Watermain Installation
|  | 4.03 - Pipe Embedment |  | 4.03 - Pipe Embedment | 4 - Watermain Installation
|  | 4.04 - Survey pickup of Services |  | 4.04 - Survey pickup of Services | 4 - Watermain Installation
|  | 4.05 - Pipe Backfill Material |  | 4.05 - Pipe Backfill Material | 4 - Watermain Installation
|  | 4.06 - Pipe Backfill Compaction |  | 4.06 - Pipe Backfill Compaction | 4 - Watermain Installation
|  | 4.07 - Marking Tape |  | 4.07 - Marking Tape | 4 - Watermain Installation
|  | 4.08 - Valves |  | 4.08 - Valves | 4 - Watermain Installation
|  | 4.9 - Hydrants and Valve Covers |  | 4.9 - Hydrants and Valve Covers | 4 - Watermain Installation
|  | 4.10 - Thrust blocks |  | 4.10 - Thrust blocks | 4 - Watermain Installation
|  | 5.1 - Compaction Testing (when applicable) |  | 5.1 - Compaction Testing (when applicable) | 5 - Testing
|  | 5.2 - Pipeline Pressure Testing |  | 5.2 - Pipeline Pressure Testing | 5 - Testing
|  | 6.1 - As constructed drawings |  | 6.1 - As constructed drawings | 6 - Completion
|  | Final Inspection |  | Final Inspection | 6 - Completion
GT4-ITP-020 - Sewer Rising Main
Scope
Rows
|  | Separable Portion C - Main Car Park: Area 2 - 20 - Sewer Rising Main | dynamic | Separable Portion C | Main Car Park: Area 2 | 20 - Sewer Rising Main
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used | 1 - Preliminary Works
|  | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place |  | 1.2 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place | 1 - Preliminary Works
|  | 1.3 - Traffic Management (When required) |  | 1.3 - Traffic Management (When required) | 1 - Preliminary Works
|  | 1.4 - Survey set out works |  | 1.4 - Survey set out works | 1 - Preliminary Works
|  | 2.1 - Water Pipes and fittings |  | 2.1 - Water Pipes and fittings | 2 - Material Conformance
|  | 2.2 - Correct embedment / backfill materials onsite |  | 2.2 - Correct embedment / backfill materials onsite | 2 - Material Conformance
|  | 3.1 - Trenching details |  | 3.1 - Trenching details | 3 - Excavation of trenches
|  | 3.2 - Benching & shielding (where required) |  | 3.2 - Benching & shielding (where required) | 3 - Excavation of trenches
|  | 3.3 - Capping and grouting of abandoned mains |  | 3.3 - Capping and grouting of abandoned mains | 3 - Excavation of trenches
|  | 4.1 - Bedding |  | 4.1 - Bedding | 4 - Watermain Installation
|  | 4.2 - Pipe Joints |  | 4.2 - Pipe Joints | 4 - Watermain Installation
|  | 4.3 - Pipe Embedment |  | 4.3 - Pipe Embedment | 4 - Watermain Installation
|  | 4.4 - Pipe Backfill Material |  | 4.4 - Pipe Backfill Material | 4 - Watermain Installation
|  | 4.5 - Pipe Backfill Compaction |  | 4.5 - Pipe Backfill Compaction | 4 - Watermain Installation
|  | 4.6 - Marking Tape |  | 4.6 - Marking Tape | 4 - Watermain Installation
|  | 4.7 - Valves |  | 4.7 - Valves | 4 - Watermain Installation
|  | 4.9 - Scour/Pump Out Points |  | 4.9 - Scour/Pump Out Points | 4 - Watermain Installation
|  | 4.10 - Thrust blocks |  | 4.10 - Thrust blocks | 4 - Watermain Installation
|  | 5.1 - Compaction Testing (when applicable) |  | 5.1 - Compaction Testing (when applicable) | 5 - Testing
|  | 5.2 - Pipeline Pressure Testing |  | 5.2 - Pipeline Pressure Testing | 5 - Testing
|  | 6.1 - As constructed drawings |  | 6.1 - As constructed drawings | 6 - Completion
|  | Final Inspection |  | Final Inspection | 6 - Completion