## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | CPB-NZ1006-ITP-4006_02 - Resilient Flooring - TP23000 | [5 empty] | CPB-NZ1006-ITP-4006_02 - Resilient Flooring - TP23000
section | Part 1.1 - Preliminaries
checkpoint | Samples
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Provide samples for approval of:
label | – Vinyl Surfacing
label | – Rubber Surfacing
label | – Linolium Surfacing
label | – Altro Safety Floors & Walls
label | – Carpet Tiles
label | – Entry Mats & Carpets
label | ○ Note: No samples required for freedom trimmaster transition flooring
label | Method - Review
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - WP
label | Record - Aconex Doc Register
checkpoint | Slip Resistance (Vinyl / Rubber / Linoleum)
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Provide certificates and any other evidence at the time of selection/supply that the vinyl complies with NZBC D1/VM1 and ANBC D1/AS1: Access Routes.
label | Slip resistance to comply with NZBC D1/AS1: 2.0 Level access routes and 3.0 Ramps.
label | – When in place on a level access routek, to have a mean coefficient of friction not less than 0.4 when tested in accordance with AS/NZS3661.1.
label | – When in place of a sloping access route, to have a coefficient of friction not less than 0.4 + 0.0125S (S=Slope of surface expressed as percentage).
label | Method - Certificate of Conformance
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - WP
label | Record - Aconex Doc Register
checkpoint | Surface Fire Performance (Vinyl / Rubber / Linoleum / Carpet)
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Flooring to meet fire performance requirements of NZBC C/AS1-AS7 4.17.3, by either:
label | – Flooring is tested and achieved the minimum critical radiant flux requirements of NZBC C/as2- as6.. Provide certificates or other evidence that the flooring will comply.
label | – Critical Radiant Flux not required if area of non- confirming products have an aggregate surface area of not greater than 5m2 within a firecell to NZBC C/AS2-AS7.
label | Method - Certificate of Conformance
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - WP
label | Record - Aconex Doc Register
checkpoint | Qualifications Altro Safety Floors & Walls
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Altro premier Whiterock installers approved by Altro APAC Pty Ltd.
label | Method - Review
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
checkpoint | Info for O&M
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Prior to Practical Completion, provision of Altro APAC Pty Ltd cleaning and maintenance instruction as electronic Pdf Format Document.
label | Method - Review
label | Frequency - Post Completion
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - WP
label | Record - Aconex Doc Register
checkpoint | Acoustic Requirements (Carpet)
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Floor finishes shall achieve a minimum >Lw16. Where floor finish specified do not achieve this, a resilient acoustic underlay is required.
label | ○ Vertical impact performance of >= IIC 70 and the measured one third octave sound pressure between 50 & 100 Hz from impacts on the floor shall be <=55 dB LAmax.
label | Method - Review
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
checkpoint | Fire Performance (Carpet, vinyl, tiles or finished/unfinished surfaces)
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Floor surfaces are required to either be non- combustible or have a critical radiant flux of no less than those given in table 3, tested to ISO9239 part 1:2010. This applies to flexible finishes such as carpets, vinyl sheets or tiles and to finished or unfinished floor surfaces.
label | Method - Review
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - WP
label | Record - N/A
checkpoint | Surface Fire performance (Entry Mats)
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Product tested to ISO9239.1 and achieve the minimum critical radiant flux requirements of NZBC C/AS2-AS6 table 4.2. Coral/Tread entry Mat 2.5kW/m2.
label | ○ Requirement no applicable if product is non- combustible or if area of product has been an aggregate surface area of not greather than 5m2
label | Method - Review
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - WP
label | Record - N/A
checkpoint | Acessible requirements (Trimmaster transition flooring trim)
label | Responsibility - Senior Project Engineer
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - To comply with NZS 4121.
label | Method - Review
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
section | Part 1.2 - Conditions Before Starting
checkpoint | Storage
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Take delivery of materials and store on site protecting it from damage. Accept it undamaged and dry. If in Rolls, store it upright with an other material on the level surfaces in- nontraffic area that is enclosed, clean and dry.
label | ○ Reject and replace goods that are damaged or will not provide the required finish.
label | ○ Avoid distortion, strecthing, marking and damage to edges while shifting.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
checkpoint | Building Conditions Carpet (1)
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Concrete slab Humidity not to exceed 75% or until the moisture content does not exceed 5.5%, in accordance with NZS2455.1.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
checkpoint | Building Conditions Carpet (2)
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Floor temperature minimum 16 degrees celcius. Concrete PH no more than 10.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
checkpoint | Execution Condition (Vinyl / Rubber / Linoleum / Altro)
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - To comply with NZS 1884.
label | Method - Review
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
checkpoint | Execution Condition (Carpet)
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - To comply with NZS 2455.1, NZS2455.2
label | Method - Review
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
checkpoint | Building Conditions Preparation
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Dot not start work before the building is enclosed, wet work is complete, doors are hung and lockable, finishes and trims complete and in good lighting is available.
label | ○ Check that each colour supplied is from the same batch. Follow the preparatory conditioning and working temperatures at all times. Protect work from solar heat gain and switch off under-floor heating during and for 48h either side of the work period.
label | ○ Inspect substrate to ensure it is a suitable finish. Do not start work if it will not allow work of the required standard.
label | ○ Clear substrate of debris, clean off surface contamination and carry out surface repairs using a proprietary levelling compound if required. Carefully feather out at perimeters of repaired areas. Grind level than vaccuum to remove dust.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - Photo
checkpoint | Layout
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Before beggining the installation, confirm the proposed layout of material, location fo seams and other visual considerations.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - N/A
section | Part 1.3 - Installation
checkpoint | Application Primer or Adhesive (Rubber / Vinyl / Linolium / Altro)
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Rubber / Vinyl / Linoleum / Altro: Apply approved adhesive by trowel and wetted roller as required. Follow requirements for open time, taking notes of the substrate porosity, ambient temperature and relative humidity. Remove excess if required.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - Photo
checkpoint | Application of Vinyl and Linoleum
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Vinyl & Linoleum: Roll out, cut, leave to condition and isntall sheets. Ensure there are no air bubbles or twisting, the seams are kept clear of adhesive and immediately she sheet is adhered, roll with a 68kg roller.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - Photo
checkpoint | Application of Carpet Tiles & Mat
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Set out from the cnetre of the area in two experimental runs and if required modify to suit. Lay tiles from the centre to the flooring manufacturer's requirements ensuring air is expelled. As each section is completed, immediately roll with a 68kg roller and sandbag corners. Complete sections before scribing perimeter tiles.
label | ○ Lay in a mono direction, execpt where specifically instructed otherwise. Cut tiles back using carpet tile manufacturer's required
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - Photo
checkpoint | Welding Vinyl / Linoleum / Altro
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - After machine grooving, thermo weld seams, heating the sheet and weld rod to a sufficient temperature to melt and fuse them together in a single mass. Trim and glaze the weld to leave a smooth, flush surface with the sheet. The width of the weld to be 1.33 times the sheet thickness.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - Photo
checkpoint | Cross Joins (Vinyl / Linoleum)
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Cross joins are not allowed in wet areas. Plan and allow cuts to avoid cross joins. Review position and before proceeding, if in a dry area and cross joins are unavoidable, seek approval by the Client.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - Photo
checkpoint | Fitting Accessories
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Scribe fit, adhere and otherwise fix true to line and face for each particular location.
label | ○ Install transition trims where necessary in accordance with specification and drawings.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - Photo
checkpoint | Cleaning
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - For Rubber floors only: Strip protective wax coating before cleaning and buffing according to the manufacturers requirements to achieve the slip resistant properties.
label | ○ All Floors: Clean flooring surfaces of adhesive, drit and debris. Vaccuum off.
label | ○ For Linoleum & Rubber floors only: Mop it, dry and apply rotary machine using pads at 300rpm.
label | ○ Protect the floor to avoid damages from follow on trades.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Sub-contractor - WP
label | Witness/Hold Point Requirements: CPB - WP
label | Witness/Hold Point Requirements: Client - No
label | Record - Photo
section | Part 2 - On Site Checklist
checkpoint | Storage
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Take delivery of materials and store on site protecting it from damage. Accept it undamaged and dry. If in Rolls, store it upright with an other material on the level surfaces in- nontraffic area that is enclosed, clean and dry.
label | ○ Reject and replace goods that are damaged or will not provide the required finish.
label | ○ Avoid distortion, strecthing, marking and damage to edges while shifting.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Client - N/A
label | Record - N/A
checkpoint | Building Conditions Carpet
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Concrete slab Humidity not to exceed 75% or until the moisture content does not exceed 5.5%, in accordance with NZS2455.1.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Client - N/A
label | Record - N/A
checkpoint | Building Conditions Carpet
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Floor temperature minimum 16 degrees celcius. Concrete PH no more than 10.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Client - N/A
label | Record - N/A
checkpoint | Building Conditions Preparation
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Dot not start work before the building is enclosed, wet work is complete, doors are hung and lockable, finishes and trims complete and in good lighting is available.
label | ○ Check that each colour supplied is from the same batch. Follow the preparatory conditioning and working temperatures at all times. Protect work from solar heat gain and switch off under-floor heating during and for 48h either side of the work period.
label | ○ Inspect substrate to ensure it is a suitable finish. Do not start work if it will not allow work of the required standard.
label | ○ Clear substrate of debris, clean off surface contamination and carry out surface repairs using a proprietary levelling compound if required. Carefully feather out at perimeters of repaired areas. Grind level than vaccuum to remove dust.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Client - N/A
label | Record - Photo
checkpoint | Layout
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Before beggining the installation, confirm the proposed layout of material, location fo seams and other visual considerations.
label | Method - Inspection
label | Frequency - Pre-Start
label | Witness/Hold Point Requirements: Client - N/A
label | Record - N/A
checkpoint | Application Primer or Adhesive (Rubber / Vinyl / Linolium / Altro)
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Rubber / Vinyl / Linoleum / Altro: Apply approved adhesive by trowel and wetted roller as required. Follow requirements for open time, taking notes of the substrate porosity, ambient temperature and relative humidity.
label | ○ Remove excess if required.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Client - N/A
label | Record - Photo
checkpoint | Application of Vinyl and Linoleum
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Vinyl & Linoleum: Roll out, cut, leave to condition and isntall sheets. Ensure there are no air bubbles or twisting, the seams are kept clear of adhesive and immediately the sheet is adhered, roll with a 68kg roller.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Client - N/A
label | Record - Photo
checkpoint | Application of Carpet Tiles & Mat
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Set out from the cnetre of the area in two experimental runs and if required modify to suit. Lay tiles from the centre to the flooring manufacturer's requirements ensuring air is expelled. As each section is completed, immediately roll with a 68kg roller and sandbag corners. Complete sections before scribing perimeter tiles.
label | ○ Lay in a mono direction, execpt where specifically instructed otherwise. Cut tiles back using carpet tile manufacturer's required cutting technique
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Client - N/A
label | Record - Photo
checkpoint | Welding Vinyl / Linoleum / Altro
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - After machine grooving, thermo weld seams, heating the sheet and weld rod to a sufficient temperature to melt and fuse them together in a single mass. Trim and glaze the weld to leave a smooth, flush surface with the sheet. The width of the weld to be 1.33 times the sheet thickness.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Client - N/A
label | Record - Photo
checkpoint | Cross Joins (Vinyl / Linoleum)
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Cross joins are not allowed in wet areas. Plan and allow cuts to avoid cross joins. Review position and before proceeding, if in a dry area and cross joins are unavoidable, seek approval by the Client.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Client - N/A
label | Record - Photo
checkpoint | Fitting Accessories
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - Scribe fit, adhere and otherwise fix true to line and face for each particular location.
label | ○ Install transition trims where necessary in accordance with specification and drawings.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Client - N/A
label | Record - Photo
checkpoint | Cleaning
label | Responsibility - Supervisor
label | Specification Reference - WAM-SPC-00001
label | Conformance Criteria Summary - For Rubber floors only: Strip protective wax coating before cleaning and buffing according to the manufacturers requirements to achieve the slip resistant properties.
label | ○ All Floors: Clean flooring surfaces of adhesive, drit and debris. Vaccuum off.
label | ○ For Linoleum & Rubber floors only: Mop it, dry and apply rotary machine using pads at 300rpm.
label | ○ Protect the floor to avoid damages from follow on trades.
label | Method - Inspection
label | Frequency - Work in Progress
label | Witness/Hold Point Requirements: Client - N/A
label | Record - Photo
section | Client Inspection Record
checkpoint | Client Inspection Record
label | Sub-Contractor
textbox | Sub-Contractor: Position
textbox | Sub-Contractor: Name
textbox | Sub-Contractor: Position
select | Sub-Contractor: Accepted or Rejected? | Accepted,Rejected
label | CPB
textbox | CPB: Position
textbox | CPB: Name
textbox | CPB: Position
select | CPB: Accepted or Rejected? | Accepted,Rejected
label | Client
textbox | Client: Position
textbox | Client: Name
textbox | Client: Position
select | Client: Accepted or Rejected? | Accepted,Rejected
holdpoint | Add Signature