## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
78515f02-4146-451c-bc35-188229f23a87 | checklist | All Subbie Fit off & Testing Progression Checklist |  | All Subbie Fit off & Testing Progression Checklist
ddf3d42b-9762-4ee6-978f-d3fe24e97e58 | section | All Subbie Fit off & Testing Progression
04b1a425-e77e-445f-adc6-366ccc17e43d | checkpoint | All work in zone completed and appear compliant
9f03c6fd-1180-5d4f-af1c-6e97a8d9a118 | note | Pass once all work complete
2203d31a-42b7-4ec3-bd03-d45521e95372 | checklist | All Subbie Rough-in Progression Checklist |  | All Subbie Rough-in Progression Checklist
db295db0-2698-41a8-a72a-c00c7585e9b2 | section | All Subbie Rough-in Progression
a284db79-7a79-420e-93c1-aae2482cc343 | checkpoint | All work in zone completed and appear compliant
4a906dab-f011-5f3c-82e6-32e28cd937bd | note | Pass once all work complete
a6c58bd1-bef6-4b5e-b3b9-c682115f717d | checklist | As Builts Checklist |  | As Builts Checklist
1c635b19-dcb4-43d9-8f05-a353edccd355 | section | As Builts
0d49cd2c-a3f9-4890-9fa3-5dd99f9579a8 | checkpoint | Update As-Built's of any known changes
0ee0342a-9dff-4be9-8748-a9b1f8724822 | checklist | Ductwork Checklist |  | Ductwork Checklist
0df016f2-9653-4594-b6dc-4fa3005b85d3 | section | Ductwork Checklist
29159e00-0299-44c7-abf4-a5254aa8733b | checkpoint | Rectangular duct installed as per latest drawing
b9c60166-565c-469a-8153-107aaa7127a5 | checkpoint | Duct flanges firmly bolted and sealed where required
652b62d3-d10d-46c5-bcf4-cfafb2bc673e | checkpoint | Cleats installed as required
8f4dbd31-8947-4d53-998b-dbe7be1c3334 | checkpoint | Correct hanger spacing / supports installed
ba9fc408-6307-4867-8906-610d84d66f83 | checkpoint | Pops & flex installed as per latest drawing
69b2931a-3cc6-4b16-a932-655520717447 | checkpoint | Correct hanger spacing / supports installed for flex
8e198130-4870-411f-a26b-7c9388cb3ada | checkpoint | Free from support off other services
c6a5f48f-34cc-4bbd-a497-1109bf5239b9 | checkpoint | Flexible duct connections completed correctly
fc2ac43c-8a55-4280-9a52-fde559fdce16 | checkpoint | Blade dampers installed as documented and left in the open position
00494ae8-d7ee-4d12-b70d-117dc3c517d4 | checkpoint | BD pop access panel coordinated and marked
6ce88749-bab6-467d-ad58-cd95bafd5467 | checkpoint | Cushion boxes installed as per latest drawing
8b35a199-3b0c-4f49-81c5-22cc08750e69 | checkpoint | Balancing dampers installed as documented and left in the open position
6f737f6a-f36a-4bd7-be80-4e6ecfd07d71 | checkpoint | Location of register coordinted with other services and marked on plan or floor
4f5d08d0-e59a-4786-97b6-48efc8487e97 | checkpoint | Volume Control Dampers installed as per latest drawing
fbf328b2-ddb9-4afc-8a9f-04bac272c541 | checkpoint | Motorised dampers installed as per latest drawing / actuator fit off
e9d41abb-cd25-4c14-af88-379fdc7cec66 | checkpoint | Fire dampers installed as per latest drawing / access panel in DW where required
b4d1911b-00c5-4678-927e-8dfa74d9db72 | checkpoint | Damper access panels coordinated and marked
51771006-d16d-4a7d-b840-b3c56a8752ae | checklist | Grille Fit-Off Checklist |  | Grille Fit-Off Checklist
2cd3f8cd-5bc1-4c44-81a3-501c3802a66a | section | Grille Fit-Off
8587f9e9-063a-49ee-b523-5331f7f8aa34 | checkpoint | Grilles installed in correct location as per latest duct layout / RCP
c643d7b3-c25a-4ea3-af22-c6a607e96795 | checkpoint | Correct grille type installed
1d939301-4754-438f-a4e0-2ff07d335f7a | checkpoint | Grille installed flush and square
75a72946-eb98-44ed-922e-131d26fb558a | checkpoint | Are all grilles installed correctly? Air leaks, vibration or failure
4fbeff69-e1c3-4832-aa32-a5ece44e22a3 | checkpoint | Grille color as per schedule
55f63306-beb8-448c-b187-0c354c771d42 | checkpoint | Grille left clean of fingerprints and caps installed where required
f6ddf4cb-818b-4a03-a390-8355f9563815 | checkpoint | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
afb84d35-56e8-43ff-bb28-91c2a93e3176 | checklist | Indoor Equipment Checklist |  | Indoor Equipment Checklist
5f4bb578-884c-466b-9b9c-3497c10636e0 | section | Indoor Equipment
6fe3312d-af44-404e-98d1-f00f385bda8a | checkpoint | Indoor Unit (IDU) correctly supported as per project engineering requirements
3956db53-1a8d-4c3a-a1a4-e8e09665fceb | checkpoint | Correct IDU installed as per latest drawing
ccca03d9-3b20-4420-995b-3b78f7456119 | checkpoint | Flexible connections installed and sealed
1c773d8e-085a-4d12-83a1-358f924acda2 | checkpoint | Access to filter bank / filters installed
ab84952b-3f08-442d-ac68-3916a1d5df53 | checkpoint | Access to all relevant controls and isolators
e330cd97-9c3c-4d17-b77d-59d9270a30f4 | checkpoint | IDU access panel coordinated and marked
8baefa9e-0f4b-44ae-8a40-0bd6b1fb2728 | checkpoint | Ventilation fan correctly supported as per project engineering requirements
13d290a0-9c5e-49e2-85b0-0eaae0124a05 | checkpoint | Correct fan installed as per latest drawing
cb095fbf-ebed-4285-8bc9-6f801746ffc7 | checkpoint | Fan connections secured and sealed
c1ef3a1e-77fa-4f7e-9106-feb60e26b51a | checkpoint | Access to fan and isolator
2ee62058-f177-4dd9-8532-144c56e95397 | checkpoint | Ventilation fan access panel coordinated and marked
1f281c6c-a5a7-4224-8527-670c67edf374 | checklist | Outdoor Equipment Checklist |  | Outdoor Equipment Checklist
0a9e0acf-2cb6-4b6d-bfe1-d7cbd0c778e5 | section | Outdoor Equipment
3e169152-2670-41de-a872-0a4658b902c5 | checkpoint | Floor or Platform Mounted Thermal Plant correctly supported as per project engineering requirements
d635b5ff-1480-428b-98e7-2e6dfdd7d168 | checkpoint | Maintenance and ventilation clearance maintained as per manufacturer's specs
3452b83f-d968-479f-b9d8-6ec2b5e056c1 | checkpoint | All manufacturer specific requirements have been provided in addition to project requirements
dd81ffcd-45e3-4c6d-83e0-f485374e2724 | checklist | Pipework Checklist |  | Pipework Checklist
e0e2c0f6-473a-492e-a3d5-8ccb3d3306df | section | Pipework
967a3d38-a4a0-4433-9e47-c9095c909937 | checkpoint | Drain trapped where required
477822fc-ac48-4ff7-9a83-108fe338b800 | checkpoint | Correct hanger spacing / fall
b27187de-ea87-428b-885e-4d8729123aba | checkpoint | Drain tested
85692212-8967-4103-baa6-62e6a58c36c7 | checkpoint | Drain pump installed level and tested
f8309681-5d9f-4b47-b7f0-5600df128031 | checkpoint | Drain terminates at a tundish
33443eed-56af-43a1-8ca8-27c533d981dc | checkpoint | Drains, pump and tundish access for maintenance.
8da13401-9788-4c51-9f11-26db99914882 | checklist | Refrigeration Pipe Checklist |  | Refrigeration Pipe Checklist
c1575bcf-0305-4252-8f53-707d083f5a77 | section | Refrigeration Pipe
802a7104-67bb-457c-90b9-7b5ae418d3d6 | checkpoint | Correct IDU & ODU installed as per latest drawing & schedule
b1de4c60-635e-493b-9edb-78d25e706d95 | checkpoint | Installed as per latest drawings
5bb4cb04-3670-44fe-bf45-72ea11e2a6a2 | checkpoint | No other services suspended from pipe work (Attach Photos below)
f888105b-c802-45e6-af3d-c36dc2b7e92b | checkpoint | Installation damage free (Any Issues comment/attach Photos below)
a8b6fa1d-04c2-43fc-9f5b-404f687ce15b | checkpoint | Correct supports used and support spacing
09bb9687-e664-4c5b-b7e3-c38ce74aeca3 | checkpoint | Pipe labelled after insulation - provide photo evidence
15044363-a4ea-4f1a-938e-0e20480f3ae4 | checkpoint | Pipe mains installation completed to drawings/specification
3c46a33c-5d7e-4af6-a642-563f797cf960 | checkpoint | Pipework system pressure tested
35cc8bee-7640-476b-95d8-b4fae2aea503 | checkpoint | Area left clean and tidy - photos of cleanliness or issues
70184f96-b65d-427f-aa20-5197104ed7f9 | checklist | Site Establishment and Safety Checklist |  | Site Establishment and Safety Checklist
46f6d451-3319-45a7-89d4-380d253e7078 | section | Details
c5ecfe45-a39a-43f4-bdb9-009d3ea8898c | checkpoint | Delivery and goods lift location
4e9ed839-7589-4e81-8f47-910638338e16 | checkpoint | Delivery requirements i.e. booking process
c7ae18ca-c30a-42dc-b3c9-573d2da5e485 | checkpoint | On site storage / office location
27e9f8ae-6380-47cb-9dcd-031525676d52 | checkpoint | Site specific restrictions i.e. noise / starting times