## Sheet1
Samples | Senior Project Engineer | WAM-SPC-00001 | Provide samples for approval of: - Vinyl Surfacing - Rubber Surfacing - Linolium Surfacing - Altro Safety Floors CHAR(AMP) Walls - Carpet Tiles - Entry Mats CHAR(AMP) Carpets Note: No samples required for freedom trimmaster transition flooring | Review | Pre-Start | WP | WP | WP | Aconex Doc Register | Samples | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Provide samples for approval of: - Vinyl Surfacing - Rubber Surfacing - Linolium Surfacing - Altro Safety Floors CHAR(AMP) Walls - Carpet Tiles - Entry Mats CHAR(AMP) Carpets Note: No samples required for freedom trimmaster transition flooring | Method - Review | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - WP | Record - Aconex Doc Register | Samples
Slip Resistance (Vinyl / Rubber / Linoleum) | Senior Project Engineer | WAM-SPC-00001 | Provide certificates and any other evidence at the time of selection/supply that the vinyl complies with NZBC D1/VM1 and ANBC D1/AS1: Access Routes. Slip resistance to comply with NZBC D1/AS1: 2.0 Level access routes and 3.0 Ramps. - When in place on a level access routek, to have a mean coefficient of friction not less than 0.4 when tested in accordance with AS/NZS3661.1. - When in place of a sloping access route, to have a coefficient of friction not less than 0.4 + 0.0125S (S=Slope of surface expressed as percentage). | Certificate of Conformance | Pre-Start | WP | WP | WP | Aconex Doc Register | Slip Resistance (Vinyl / Rubber / Linoleum) | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Provide certificates and any other evidence at the time of selection/supply that the vinyl complies with NZBC D1/VM1 and ANBC D1/AS1: Access Routes. Slip resistance to comply with NZBC D1/AS1: 2.0 Level access routes and 3.0 Ramps. - When in place on a level access routek, to have a mean coefficient of friction not less than 0.4 when tested in accordance with AS/NZS3661.1. - When in place of a sloping access route, to have a coefficient of friction not less than 0.4 + 0.0125S (S=Slope of surface expressed as percentage). | Method - Certificate of Conformance | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - WP | Record - Aconex Doc Register | Responsibility - Senior Project Engineer
Surface Fire Performance (Vinyl / Rubber / Linoleum / Carpet) | Senior Project Engineer | WAM-SPC-00001 | Flooring to meet fire performance requirements of NZBC C/AS1-AS7 4.17.3, by either: - Flooring is tested and achieved the minimum critical radiant flux requirements of NZBC C/as2- as6.. Provide certificates or other evidence that the flooring will comply. - Critical Radiant Flux not required if area of non- confirming products have an aggregate surface area of not greater than 5m2 within a firecell to NZBC C/AS2-AS7. | Certificate of Conformance | Pre-Start | WP | WP | WP | Aconex Doc Register | Surface Fire Performance (Vinyl / Rubber / Linoleum / Carpet) | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Flooring to meet fire performance requirements of NZBC C/AS1-AS7 4.17.3, by either: - Flooring is tested and achieved the minimum critical radiant flux requirements of NZBC C/as2- as6.. Provide certificates or other evidence that the flooring will comply. - Critical Radiant Flux not required if area of non- confirming products have an aggregate surface area of not greater than 5m2 within a firecell to NZBC C/AS2-AS7. | Method - Certificate of Conformance | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - WP | Record - Aconex Doc Register | Specification Reference - WAM-SPC-00001
Qualifications Altro Safety Floors CHAR(AMP) Walls | Senior Project Engineer | WAM-SPC-00001 | Altro premier Whiterock installers approved by Altro APAC Pty Ltd. | Review | Pre-Start | WP | WP | No | N/A | Qualifications Altro Safety Floors CHAR(AMP) Walls | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Altro premier Whiterock installers approved by Altro APAC Pty Ltd. | Method - Review | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Conformance Criteria Summary - Provide samples for approval of: - Vinyl Surfacing - Rubber Surfacing - Linolium Surfacing - Altro Safety Floors CHAR(AMP) Walls - Carpet Tiles - Entry Mats CHAR(AMP) Carpets Note: No samples required for freedom trimmaster transition flooring
Info for OCHAR(AMP)M | Senior Project Engineer | WAM-SPC-00001 | Prior to Practical Completion, provision of Altro APAC Pty Ltd cleaning and maintenance instruction as electronic Pdf Format Document. | Review | Post Completion | WP | WP | WP | Aconex Doc Register | Info for OCHAR(AMP)M | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Prior to Practical Completion, provision of Altro APAC Pty Ltd cleaning and maintenance instruction as electronic Pdf Format Document. | Method - Review | Frequency - Post Completion | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - WP | Record - Aconex Doc Register | Method - Review
Acoustic Requirements (Carpet) | Senior Project Engineer | WAM-SPC-00001 | Floor finishes shall achieve a minimum >Lw16. Where floor finish specified do not achieve this, a resilient acoustic underlay is required. Vertical impact performance of >= IIC 70 and the measured one third octave sound pressure between 50 CHAR(AMP) 100 Hz from impacts on the floor shall be CHAR(LESS)=55 dB LAmax. | Review | Pre-Start | WP | WP | No | N/A | Acoustic Requirements (Carpet) | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Floor finishes shall achieve a minimum >Lw16. Where floor finish specified do not achieve this, a resilient acoustic underlay is required. Vertical impact performance of >= IIC 70 and the measured one third octave sound pressure between 50 CHAR(AMP) 100 Hz from impacts on the floor shall be CHAR(LESS)=55 dB LAmax. | Method - Review | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Frequency - Pre-Start
Fire Performance (Carpet, vinyl, tiles or finished/unfinished surfaces) | Senior Project Engineer | WAM-SPC-00001 | Floor surfaces are required to either be non- combustible or have a critical radiant flux of no less than those given in table 3, tested to ISO9239 part 1:2010. This applies to flexible finishes such as carpets, vinyl sheets or tiles and to finished or unfinished floor surfaces. | Review | Pre-Start | WP | WP | WP | N/A | Fire Performance (Carpet, vinyl, tiles or finished/unfinished surfaces) | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Floor surfaces are required to either be non- combustible or have a critical radiant flux of no less than those given in table 3, tested to ISO9239 part 1:2010. This applies to flexible finishes such as carpets, vinyl sheets or tiles and to finished or unfinished floor surfaces. | Method - Review | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - WP | Record - N/A | Witness/Hold Point Requirements: Sub-contractor - WP
Surface Fire performance (Entry Mats) | Senior Project Engineer | WAM-SPC-00001 | Product tested to ISO9239.1 and achieve the minimum critical radiant flux requirements of NZBC C/AS2-AS6 table 4.2. Coral/Tread entry Mat 2.5kW/m2. Requirement no applicable if product is non- combustible or if area of product has been an aggregate surface area of not greather than 5m2 | Review | Pre-Start | WP | WP | WP | N/A | Surface Fire performance (Entry Mats) | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Product tested to ISO9239.1 and achieve the minimum critical radiant flux requirements of NZBC C/AS2-AS6 table 4.2. Coral/Tread entry Mat 2.5kW/m2. Requirement no applicable if product is non- combustible or if area of product has been an aggregate surface area of not greather than 5m2 | Method - Review | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - WP | Record - N/A | Witness/Hold Point Requirements: CPB - WP
Acessible requirements (Trimmaster transition flooring trim) | Senior Project Engineer | WAM-SPC-00001 | To comply with NZS 4121. | Review | Pre-Start | WP | WP | No | N/A | Acessible requirements (Trimmaster transition flooring trim) | Responsibility - Senior Project Engineer | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - To comply with NZS 4121. | Method - Review | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Witness/Hold Point Requirements: Client - WP
Storage | Supervisor | WAM-SPC-00001 | Take delivery of materials and store on site protecting it from damage. Accept it undamaged and dry. If in Rolls, store it upright with an other material on the level surfaces in- nontraffic area that is enclosed, clean and dry. Reject and replace goods that are damaged or will not provide the required finish. Avoid distortion, strecthing, marking and damage to edges while shifting. | Inspection | Pre-Start | WP | WP | No | N/A | Storage | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Take delivery of materials and store on site protecting it from damage. Accept it undamaged and dry. If in Rolls, store it upright with an other material on the level surfaces in- nontraffic area that is enclosed, clean and dry. Reject and replace goods that are damaged or will not provide the required finish. Avoid distortion, strecthing, marking and damage to edges while shifting. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Record - Aconex Doc Register
Building Conditions Carpet | Supervisor | WAM-SPC-00001 | Concrete slab Humidity not to exceed 75% or until the moisture content does not exceed 5.5%, in accordance with NZS2455.1. | Inspection | Pre-Start | WP | WP | No | N/A | Building Conditions Carpet | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Concrete slab Humidity not to exceed 75% or until the moisture content does not exceed 5.5%, in accordance with NZS2455.1. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Slip Resistance (Vinyl / Rubber / Linoleum)
Building Conditions Carpet | Supervisor | WAM-SPC-00001 | Floor temperature minimum 16 degress celcius. Concrete PH no more than 10. | Inspection | Pre-Start | WP | WP | No | N/A | Building Conditions Carpet | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Floor temperature minimum 16 degress celcius. Concrete PH no more than 10. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Responsibility - Senior Project Engineer
Execution Condition (Vinyl / Rubber / Linoleum / Altro) | Supervisor | WAM-SPC-00001 | To comply with NZS 1884. | Review | Pre-Start | WP | WP | No | N/A | Execution Condition (Vinyl / Rubber / Linoleum / Altro) | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - To comply with NZS 1884. | Method - Review | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Specification Reference - WAM-SPC-00001
Execution Condition ( Carpet ) | Supervisor | WAM-SPC-00001 | To comply with NZS 2455.1, NZS2455.2 | Review | Pre-Start | WP | WP | No | N/A | Execution Condition ( Carpet ) | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - To comply with NZS 2455.1, NZS2455.2 | Method - Review | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Conformance Criteria Summary - Provide certificates and any other evidence at the time of selection/supply that the vinyl complies with NZBC D1/VM1 and ANBC D1/AS1: Access Routes. Slip resistance to comply with NZBC D1/AS1: 2.0 Level access routes and 3.0 Ramps. - When in place on a level access routek, to have a mean coefficient of friction not less than 0.4 when tested in accordance with AS/NZS3661.1. - When in place of a sloping access route, to have a coefficient of friction not less than 0.4 + 0.0125S (S=Slope of surface expressed as percentage).
Building Conditions Preparation | Supervisor | WAM-SPC-00001 | Dot not start work before the building is enclosed, wet work is complete, doors are hung and lockable, finishes and trims complete and in good lighting is available. Check that each colour supplied is from the same batch. Follow the preparatory conditioning and working temperatures at all times. Protect work from solar heat gain and switch off under-floor heating during and for 48h either side of the work period. Inspect substrate to ensure it is a suitable finish. Do not start work if it will not allow work of the required standard. Clear substrate of debris, clean off surface contamination and carry out surface repairs using a proprietary levelling compound if required. Carefully feather out at perimeters of repaired areas. Grind level than vaccuum to remove dust. | Inspection | Pre-Start | WP | WP | No | Photo | Building Conditions Preparation | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Dot not start work before the building is enclosed, wet work is complete, doors are hung and lockable, finishes and trims complete and in good lighting is available. Check that each colour supplied is from the same batch. Follow the preparatory conditioning and working temperatures at all times. Protect work from solar heat gain and switch off under-floor heating during and for 48h either side of the work period. Inspect substrate to ensure it is a suitable finish. Do not start work if it will not allow work of the required standard. Clear substrate of debris, clean off surface contamination and carry out surface repairs using a proprietary levelling compound if required. Carefully feather out at perimeters of repaired areas. Grind level than vaccuum to remove dust. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - Photo | Method - Certificate of Conformance
Layout | Supervisor | WAM-SPC-00001 | Before beggining the installation, confirm the proposed layout of material, location fo seams and other visual considerations. | Inspection | Pre-Start | WP | WP | No | N/A | Layout | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Before beggining the installation, confirm the proposed layout of material, location fo seams and other visual considerations. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - N/A | Frequency - Pre-Start
Application Primer or Adhesive (Rubber / Vinyl / Linolium / Altro) | Supervisor | WAM-SPC-00001 | Rubber / Vinyl / Linoleum / Altro: Apply approved adhesive by trowel and wetted roller as required. Follow requirements for open time, taking notes of the substrate porosity, ambient temperature and relative humidity. Remove excess if required. | Inspection | Work in Progress | WP | WP | No | Photo | Application Primer or Adhesive (Rubber / Vinyl / Linolium / Altro) | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Rubber / Vinyl / Linoleum / Altro: Apply approved adhesive by trowel and wetted roller as required. Follow requirements for open time, taking notes of the substrate porosity, ambient temperature and relative humidity. Remove excess if required. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - Photo | Witness/Hold Point Requirements: Sub-contractor - WP
Application of Vinyl and Linoleum | Supervisor | WAM-SPC-00001 | Vinyl CHAR(AMP) Linoleum: Roll out, cut, leave to condition and isntall sheets. Ensure there are no air bubbles or twisting, the seams are kept clear of adhesive and immediately she sheet is adhered, roll with a 68kg roller. | Inspection | Work in Progress | WP | WP | No | Photo | Application of Vinyl and Linoleum | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Vinyl CHAR(AMP) Linoleum: Roll out, cut, leave to condition and isntall sheets. Ensure there are no air bubbles or twisting, the seams are kept clear of adhesive and immediately she sheet is adhered, roll with a 68kg roller. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - Photo | Witness/Hold Point Requirements: CPB - WP
Application of Carpet Tiles CHAR(AMP) Mat | Supervisor | WAM-SPC-00001 | Set out from the cnetre of the area in two esxperiemental runs and if required modify to suit. Lay tiles from the centre to the flooring manufacturer`s requirements ensuring air is expelled. As each section is completed, immediatel roll with a 68kg roller and sandbag corners. Complete sections before scribing perimeter tiles. Lay in a mono direction, execpt where specifically instructed otherwise. Cut tiles back using carpet tile manufacturer`s required | Inspection | Work in Progress | WP | WP | No | Photo | Application of Carpet Tiles CHAR(AMP) Mat | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Set out from the cnetre of the area in two esxperiemental runs and if required modify to suit. Lay tiles from the centre to the flooring manufacturer`s requirements ensuring air is expelled. As each section is completed, immediatel roll with a 68kg roller and sandbag corners. Complete sections before scribing perimeter tiles. Lay in a mono direction, execpt where specifically instructed otherwise. Cut tiles back using carpet tile manufacturer`s required | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - Photo | Witness/Hold Point Requirements: Client - WP
Welding Vinyl / Linoleum / Altro | Supervisor | WAM-SPC-00001 | After machine grooving, thermo weld seams, heating the sheet and weld rod to a sufficient temperature to melt and fuse them together in a single mass. Trim and glaze the weld to leave a smooth, flush surface with the sheet. The width of the weld to be 1.33 times the sheet thickness. | Inspection | Work in Progress | WP | WP | No | Photo | Welding Vinyl / Linoleum / Altro | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - After machine grooving, thermo weld seams, heating the sheet and weld rod to a sufficient temperature to melt and fuse them together in a single mass. Trim and glaze the weld to leave a smooth, flush surface with the sheet. The width of the weld to be 1.33 times the sheet thickness. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - Photo | Record - Aconex Doc Register
Cross Joins (Vinyl / Linoleum) | Supervisor | WAM-SPC-00001 | Cross joins are not allowed in wet areas. Plan and allow cuts to avoid cross joins. Review position and before proceeding, if in a dry area and cross joins are unavoidable, seek approval by the Client. | Inspection | Work in Progress | WP | WP | No | Photo | Cross Joins (Vinyl / Linoleum) | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Cross joins are not allowed in wet areas. Plan and allow cuts to avoid cross joins. Review position and before proceeding, if in a dry area and cross joins are unavoidable, seek approval by the Client. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - Photo | Surface Fire Performance (Vinyl / Rubber / Linoleum / Carpet)
Fitting Accessories | Supervisor | WAM-SPC-00001 | Scribe fit, adhere and otherwise fix true to line and face for each particular location. Install transition trims where necessary in accordance with specification and drawings. | Inspection | Work in Progress | WP | WP | No | Photo | Fitting Accessories | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Scribe fit, adhere and otherwise fix true to line and face for each particular location. Install transition trims where necessary in accordance with specification and drawings. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - Photo | Responsibility - Senior Project Engineer
Cleaning | Supervisor | WAM-SPC-00001 | For Rubber floors only: Strip protective wax coating before cleaning and buffing according to the manufacturers requirements to achieve the slip resistant properties. All Floors: Clean flooring surfaces of adhesive, drit and debris. Vaccuum off. For Linoleum CHAR(AMP) Rubber floors only: Mop it, dry and apply rotary machine using pads at 300rpm. Protect the floor to avoid damages from follow on trades. | Inspection | Work in Progress | WP | WP | No | Photo | Cleaning | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - For Rubber floors only: Strip protective wax coating before cleaning and buffing according to the manufacturers requirements to achieve the slip resistant properties. All Floors: Clean flooring surfaces of adhesive, drit and debris. Vaccuum off. For Linoleum CHAR(AMP) Rubber floors only: Mop it, dry and apply rotary machine using pads at 300rpm. Protect the floor to avoid damages from follow on trades. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - WP | Witness/Hold Point Requirements: CPB - WP | Witness/Hold Point Requirements: Client - No | Record - Photo | Specification Reference - WAM-SPC-00001
Storage | Supervisor | WAM-SPC-00001 | Take delivery of materials and store on site protecting it from damage. Accept it undamaged and dry. If in Rolls, store it upright with an other material on the level surfaces in- nontraffic area that is enclosed, clean and dry. Reject and replace goods that are damaged or will not provide the required finish. Avoid distortion, strecthing, marking and damage to edges while shifting. | Inspection | Pre-Start |  |  | N/A | N/A | Storage | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Take delivery of materials and store on site protecting it from damage. Accept it undamaged and dry. If in Rolls, store it upright with an other material on the level surfaces in- nontraffic area that is enclosed, clean and dry. Reject and replace goods that are damaged or will not provide the required finish. Avoid distortion, strecthing, marking and damage to edges while shifting. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - N/A | Conformance Criteria Summary - Flooring to meet fire performance requirements of NZBC C/AS1-AS7 4.17.3, by either: - Flooring is tested and achieved the minimum critical radiant flux requirements of NZBC C/as2- as6.. Provide certificates or other evidence that the flooring will comply. - Critical Radiant Flux not required if area of non- confirming products have an aggregate surface area of not greater than 5m2 within a firecell to NZBC C/AS2-AS7.
Building Conditions Carpet | Supervisor | WAM-SPC-00001 | Concrete slab Humidity not to exceed 75% or until the moisture content does not exceed 5.5%, in accordance with NZS2455.1. | Inspection | Pre-Start |  |  | N/A | N/A | Building Conditions Carpet | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Concrete slab Humidity not to exceed 75% or until the moisture content does not exceed 5.5%, in accordance with NZS2455.1. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - N/A | Method - Certificate of Conformance
Building Conditions Carpet | Supervisor | WAM-SPC-00001 | Floor temperature minimum 16 degress celcius. Concrete PH no more than 10. | Inspection | Pre-Start |  |  | N/A | N/A | Building Conditions Carpet | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Floor temperature minimum 16 degress celcius. Concrete PH no more than 10. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - N/A | Frequency - Pre-Start
Building Conditions Preparation | Supervisor | WAM-SPC-00001 | Dot not start work before the building is enclosed, wet work is complete, doors are hung and lockable, finishes and trims complete and in good lighting is available. Check that each colour supplied is from the same batch. Follow the preparatory conditioning and working temperatures at all times. Protect work from solar heat gain and switch off under-floor heating during and for 48h either side of the work period. Inspect substrate to ensure it is a suitable finish. Do not start work if it will not allow work of the required standard. Clear substrate of debris, clean off surface contamination and carry out surface repairs using a proprietary levelling compound if required. Carefully feather out at perimeters of repaired areas. Grind level than vaccuum to remove dust. | Inspection | Pre-Start |  |  | N/A | Photo | Building Conditions Preparation | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Dot not start work before the building is enclosed, wet work is complete, doors are hung and lockable, finishes and trims complete and in good lighting is available. Check that each colour supplied is from the same batch. Follow the preparatory conditioning and working temperatures at all times. Protect work from solar heat gain and switch off under-floor heating during and for 48h either side of the work period. Inspect substrate to ensure it is a suitable finish. Do not start work if it will not allow work of the required standard. Clear substrate of debris, clean off surface contamination and carry out surface repairs using a proprietary levelling compound if required. Carefully feather out at perimeters of repaired areas. Grind level than vaccuum to remove dust. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - Photo | Witness/Hold Point Requirements: Sub-contractor - WP
Layout | Supervisor | WAM-SPC-00001 | Before beggining the installation, confirm the proposed layout of material, location fo seams and other visual considerations. | Inspection | Pre-Start |  |  | N/A | N/A | Layout | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Before beggining the installation, confirm the proposed layout of material, location fo seams and other visual considerations. | Method - Inspection | Frequency - Pre-Start | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - N/A | Witness/Hold Point Requirements: CPB - WP
Application Primer or Adhesive (Rubber / Vinyl / Linolium / Altro) | Supervisor | WAM-SPC-00001 | Rubber / Vinyl / Linoleum / Altro: Apply approved adhesive by trowel and wetted roller as required. Follow requirements for open time, taking notes of the substrate porosity, ambient temperature and relative humidity. Remove excess if required. | Inspection | Work in Progress |  |  | N/A | Photo | Application Primer or Adhesive (Rubber / Vinyl / Linolium / Altro) | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Rubber / Vinyl / Linoleum / Altro: Apply approved adhesive by trowel and wetted roller as required. Follow requirements for open time, taking notes of the substrate porosity, ambient temperature and relative humidity. Remove excess if required. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - Photo | Witness/Hold Point Requirements: Client - WP
Application of Vinyl and Linoleum | Supervisor | WAM-SPC-00001 | Vinyl CHAR(AMP) Linoleum: Roll out, cut, leave to condition and isntall sheets. Ensure there are no air bubbles or twisting, the seams are kept clear of adhesive and immediately she sheet is adhered, roll with a 68kg roller. | Inspection | Work in Progress |  |  | N/A | Photo | Application of Vinyl and Linoleum | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Vinyl CHAR(AMP) Linoleum: Roll out, cut, leave to condition and isntall sheets. Ensure there are no air bubbles or twisting, the seams are kept clear of adhesive and immediately she sheet is adhered, roll with a 68kg roller. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - Photo | Record - Aconex Doc Register
Application of Carpet Tiles CHAR(AMP) Mat | Supervisor | WAM-SPC-00001 | Set out from the cnetre of the area in two esxperiemental runs and if required modify to suit. Lay tiles from the centre to the flooring manufacturer`s requirements ensuring air is expelled. As each section is completed, immediatel roll with a 68kg roller and sandbag corners. Complete sections before scribing perimeter tiles. Lay in a mono direction, execpt where specifically instructed otherwise. Cut tiles back using carpet tile manufacturer`s required cutting technique | Inspection | Work in Progress |  |  | N/A | Photo | Application of Carpet Tiles CHAR(AMP) Mat | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Set out from the cnetre of the area in two esxperiemental runs and if required modify to suit. Lay tiles from the centre to the flooring manufacturer`s requirements ensuring air is expelled. As each section is completed, immediatel roll with a 68kg roller and sandbag corners. Complete sections before scribing perimeter tiles. Lay in a mono direction, execpt where specifically instructed otherwise. Cut tiles back using carpet tile manufacturer`s required cutting technique | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - Photo | Qualifications Altro Safety Floors CHAR(AMP) Walls
Welding Vinyl / Linoleum / Altro | Supervisor | WAM-SPC-00001 | After machine grooving, thermo weld seams, heating the sheet and weld rod to a sufficient temperature to melt and fuse them together in a single mass. Trim and glaze the weld to leave a smooth, flush surface with the sheet. The width of the weld to be 1.33 times the sheet thickness. | Inspection | Work in Progress |  |  | N/A | Photo | Welding Vinyl / Linoleum / Altro | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - After machine grooving, thermo weld seams, heating the sheet and weld rod to a sufficient temperature to melt and fuse them together in a single mass. Trim and glaze the weld to leave a smooth, flush surface with the sheet. The width of the weld to be 1.33 times the sheet thickness. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - Photo | Responsibility - Senior Project Engineer
Cross Joins (Vinyl / Linoleum) | Supervisor | WAM-SPC-00001 | Cross joins are not allowed in wet areas. Plan and allow cuts to avoid cross joins. Review position and before proceeding, if in a dry area and cross joins are unavoidable, seek approval by the Client. | Inspection | Work in Progress |  |  | N/A | Photo | Cross Joins (Vinyl / Linoleum) | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Cross joins are not allowed in wet areas. Plan and allow cuts to avoid cross joins. Review position and before proceeding, if in a dry area and cross joins are unavoidable, seek approval by the Client. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - Photo | Specification Reference - WAM-SPC-00001
Fitting Accessories | Supervisor | WAM-SPC-00001 | Scribe fit, adhere and otherwise fix true to line and face for each particular location. Install transition trims where necessary in accordance with specification and drawings. | Inspection | Work in Progress |  |  | N/A | Photo | Fitting Accessories | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - Scribe fit, adhere and otherwise fix true to line and face for each particular location. Install transition trims where necessary in accordance with specification and drawings. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - Photo | Conformance Criteria Summary - Altro premier Whiterock installers approved by Altro APAC Pty Ltd.
Cleaning | Supervisor | WAM-SPC-00001 | For Rubber floors only: Strip protective wax coating before cleaning and buffing according to the manufacturers requirements to achieve the slip resistant properties. All Floors: Clean flooring surfaces of adhesive, drit and debris. Vaccuum off. For Linoleum CHAR(AMP) Rubber floors only: Mop it, dry and apply rotary machine using pads at 300rpm. Protect the floor to avoid damages from follow on trades. | Inspection | Work in Progress |  |  | N/A | Photo | Cleaning | Responsibility - Supervisor | Specification Reference - WAM-SPC-00001 | Conformance Criteria Summary - For Rubber floors only: Strip protective wax coating before cleaning and buffing according to the manufacturers requirements to achieve the slip resistant properties. All Floors: Clean flooring surfaces of adhesive, drit and debris. Vaccuum off. For Linoleum CHAR(AMP) Rubber floors only: Mop it, dry and apply rotary machine using pads at 300rpm. Protect the floor to avoid damages from follow on trades. | Method - Inspection | Frequency - Work in Progress | Witness/Hold Point Requirements: Sub-contractor - | Witness/Hold Point Requirements: CPB - | Witness/Hold Point Requirements: Client - N/A | Record - Photo | Method - Review
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Info for OCHAR(AMP)M
Responsibility - Senior Project Engineer
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Prior to Practical Completion, provision of Altro APAC Pty Ltd cleaning and maintenance instruction as electronic Pdf Format Document.
Method - Review
Frequency - Post Completion
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - WP
Record - Aconex Doc Register
Acoustic Requirements (Carpet)
Responsibility - Senior Project Engineer
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Floor finishes shall achieve a minimum >Lw16. Where floor finish specified do not achieve this, a resilient acoustic underlay is required. Vertical impact performance of >= IIC 70 and the measured one third octave sound pressure between 50 CHAR(AMP) 100 Hz from impacts on the floor shall be CHAR(LESS)=55 dB LAmax.
Method - Review
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Fire Performance (Carpet, vinyl, tiles or finished/unfinished surfaces)
Responsibility - Senior Project Engineer
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Floor surfaces are required to either be non- combustible or have a critical radiant flux of no less than those given in table 3, tested to ISO9239 part 1:2010. This applies to flexible finishes such as carpets, vinyl sheets or tiles and to finished or unfinished floor surfaces.
Method - Review
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - WP
Record - N/A
Surface Fire performance (Entry Mats)
Responsibility - Senior Project Engineer
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Product tested to ISO9239.1 and achieve the minimum critical radiant flux requirements of NZBC C/AS2-AS6 table 4.2. Coral/Tread entry Mat 2.5kW/m2. Requirement no applicable if product is non- combustible or if area of product has been an aggregate surface area of not greather than 5m2
Method - Review
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - WP
Record - N/A
Acessible requirements (Trimmaster transition flooring trim)
Responsibility - Senior Project Engineer
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - To comply with NZS 4121.
Method - Review
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Storage
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Take delivery of materials and store on site protecting it from damage. Accept it undamaged and dry. If in Rolls, store it upright with an other material on the level surfaces in- nontraffic area that is enclosed, clean and dry. Reject and replace goods that are damaged or will not provide the required finish. Avoid distortion, strecthing, marking and damage to edges while shifting.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Building Conditions Carpet
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Concrete slab Humidity not to exceed 75% or until the moisture content does not exceed 5.5%, in accordance with NZS2455.1.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Building Conditions Carpet
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Floor temperature minimum 16 degress celcius. Concrete PH no more than 10.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Execution Condition (Vinyl / Rubber / Linoleum / Altro)
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - To comply with NZS 1884.
Method - Review
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Execution Condition ( Carpet )
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - To comply with NZS 2455.1, NZS2455.2
Method - Review
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Building Conditions Preparation
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Dot not start work before the building is enclosed, wet work is complete, doors are hung and lockable, finishes and trims complete and in good lighting is available. Check that each colour supplied is from the same batch. Follow the preparatory conditioning and working temperatures at all times. Protect work from solar heat gain and switch off under-floor heating during and for 48h either side of the work period. Inspect substrate to ensure it is a suitable finish. Do not start work if it will not allow work of the required standard. Clear substrate of debris, clean off surface contamination and carry out surface repairs using a proprietary levelling compound if required. Carefully feather out at perimeters of repaired areas. Grind level than vaccuum to remove dust.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - Photo
Layout
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Before beggining the installation, confirm the proposed layout of material, location fo seams and other visual considerations.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - N/A
Application Primer or Adhesive (Rubber / Vinyl / Linolium / Altro)
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Rubber / Vinyl / Linoleum / Altro: Apply approved adhesive by trowel and wetted roller as required. Follow requirements for open time, taking notes of the substrate porosity, ambient temperature and relative humidity. Remove excess if required.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - Photo
Application of Vinyl and Linoleum
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Vinyl CHAR(AMP) Linoleum: Roll out, cut, leave to condition and isntall sheets. Ensure there are no air bubbles or twisting, the seams are kept clear of adhesive and immediately she sheet is adhered, roll with a 68kg roller.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - Photo
Application of Carpet Tiles CHAR(AMP) Mat
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Set out from the cnetre of the area in two esxperiemental runs and if required modify to suit. Lay tiles from the centre to the flooring manufacturer`s requirements ensuring air is expelled. As each section is completed, immediatel roll with a 68kg roller and sandbag corners. Complete sections before scribing perimeter tiles. Lay in a mono direction, execpt where specifically instructed otherwise. Cut tiles back using carpet tile manufacturer`s required
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - Photo
Welding Vinyl / Linoleum / Altro
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - After machine grooving, thermo weld seams, heating the sheet and weld rod to a sufficient temperature to melt and fuse them together in a single mass. Trim and glaze the weld to leave a smooth, flush surface with the sheet. The width of the weld to be 1.33 times the sheet thickness.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - Photo
Cross Joins (Vinyl / Linoleum)
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Cross joins are not allowed in wet areas. Plan and allow cuts to avoid cross joins. Review position and before proceeding, if in a dry area and cross joins are unavoidable, seek approval by the Client.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - Photo
Fitting Accessories
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Scribe fit, adhere and otherwise fix true to line and face for each particular location. Install transition trims where necessary in accordance with specification and drawings.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - Photo
Cleaning
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - For Rubber floors only: Strip protective wax coating before cleaning and buffing according to the manufacturers requirements to achieve the slip resistant properties. All Floors: Clean flooring surfaces of adhesive, drit and debris. Vaccuum off. For Linoleum CHAR(AMP) Rubber floors only: Mop it, dry and apply rotary machine using pads at 300rpm. Protect the floor to avoid damages from follow on trades.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor - WP
Witness/Hold Point Requirements: CPB - WP
Witness/Hold Point Requirements: Client - No
Record - Photo
Storage
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Take delivery of materials and store on site protecting it from damage. Accept it undamaged and dry. If in Rolls, store it upright with an other material on the level surfaces in- nontraffic area that is enclosed, clean and dry. Reject and replace goods that are damaged or will not provide the required finish. Avoid distortion, strecthing, marking and damage to edges while shifting.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - N/A
Building Conditions Carpet
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Concrete slab Humidity not to exceed 75% or until the moisture content does not exceed 5.5%, in accordance with NZS2455.1.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - N/A
Building Conditions Carpet
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Floor temperature minimum 16 degress celcius. Concrete PH no more than 10.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - N/A
Building Conditions Preparation
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Dot not start work before the building is enclosed, wet work is complete, doors are hung and lockable, finishes and trims complete and in good lighting is available. Check that each colour supplied is from the same batch. Follow the preparatory conditioning and working temperatures at all times. Protect work from solar heat gain and switch off under-floor heating during and for 48h either side of the work period. Inspect substrate to ensure it is a suitable finish. Do not start work if it will not allow work of the required standard. Clear substrate of debris, clean off surface contamination and carry out surface repairs using a proprietary levelling compound if required. Carefully feather out at perimeters of repaired areas. Grind level than vaccuum to remove dust.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - Photo
Layout
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Before beggining the installation, confirm the proposed layout of material, location fo seams and other visual considerations.
Method - Inspection
Frequency - Pre-Start
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - N/A
Application Primer or Adhesive (Rubber / Vinyl / Linolium / Altro)
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Rubber / Vinyl / Linoleum / Altro: Apply approved adhesive by trowel and wetted roller as required. Follow requirements for open time, taking notes of the substrate porosity, ambient temperature and relative humidity. Remove excess if required.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - Photo
Application of Vinyl and Linoleum
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Vinyl CHAR(AMP) Linoleum: Roll out, cut, leave to condition and isntall sheets. Ensure there are no air bubbles or twisting, the seams are kept clear of adhesive and immediately she sheet is adhered, roll with a 68kg roller.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - Photo
Application of Carpet Tiles CHAR(AMP) Mat
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Set out from the cnetre of the area in two esxperiemental runs and if required modify to suit. Lay tiles from the centre to the flooring manufacturer`s requirements ensuring air is expelled. As each section is completed, immediatel roll with a 68kg roller and sandbag corners. Complete sections before scribing perimeter tiles. Lay in a mono direction, execpt where specifically instructed otherwise. Cut tiles back using carpet tile manufacturer`s required cutting technique
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - Photo
Welding Vinyl / Linoleum / Altro
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - After machine grooving, thermo weld seams, heating the sheet and weld rod to a sufficient temperature to melt and fuse them together in a single mass. Trim and glaze the weld to leave a smooth, flush surface with the sheet. The width of the weld to be 1.33 times the sheet thickness.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - Photo
Cross Joins (Vinyl / Linoleum)
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Cross joins are not allowed in wet areas. Plan and allow cuts to avoid cross joins. Review position and before proceeding, if in a dry area and cross joins are unavoidable, seek approval by the Client.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - Photo
Fitting Accessories
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - Scribe fit, adhere and otherwise fix true to line and face for each particular location. Install transition trims where necessary in accordance with specification and drawings.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - Photo
Cleaning
Responsibility - Supervisor
Specification Reference - WAM-SPC-00001
Conformance Criteria Summary - For Rubber floors only: Strip protective wax coating before cleaning and buffing according to the manufacturers requirements to achieve the slip resistant properties. All Floors: Clean flooring surfaces of adhesive, drit and debris. Vaccuum off. For Linoleum CHAR(AMP) Rubber floors only: Mop it, dry and apply rotary machine using pads at 300rpm. Protect the floor to avoid damages from follow on trades.
Method - Inspection
Frequency - Work in Progress
Witness/Hold Point Requirements: Sub-contractor -
Witness/Hold Point Requirements: CPB -
Witness/Hold Point Requirements: Client - N/A
Record - Photo