## Sheet1
Enviro B-LV+700X V1.1
SECTION | BATCH DETAIL NUMBER OF PRODUCTS
Checkpoint | Enviro Flex FC/ Sika Flex Pro
label | Record Batch Number
Checkpoint | Enviro B-LV
Record Batch Number
Checkpoint | Enviro 700X
Record Batch Number
SECTION | PRE COMMENCEMENT
Checkpoint | Material Management & Storage
Label | Store materials in a dry, clean place away from direct sunlight. -Provide timestamped photograph.
Checkpoint | Acceptance of Substrate
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane. - Provide timestamped photograph.
Checkpoint | Acceptance of Puddle Flanges
Label | All puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
Checkpoint | Falls in Substrate
Label | Builder to confirm compliant falls; minimum 1-100 falls.
Checkpoint | Cracks in Substrate
Label | Ensure no substrate cracks greater than 1.6mm. Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
SECTION | SUBSTRATE PREPERATION: AS 4654.2-2012
Label | Ensure Surface is prepared to receive primer application. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
SECTION | EPOXY B-LV - PRIME COAT
Checkpoint | Moisture Content
Label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
Checkpoint | Weather/RH
Label | Apply within 5-35°C RH must be 0-85%
Checkpoint | Product Mixing
Label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | Primer Application
Label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
SECTION | BOND BREAKER
Label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Bond breaker to be tack free prior to coating.
SECTION | ENVIRO 700X - FIRST COAT
Checkpoint | Weather/RH
Label | Apply within 5-35°C RH must be 0-85%
Checkpoint | Product Mixing
Label | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | 700X Application
Label | • Enviro 700X to be applied by roller vertically on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
SECTION | ENVIRO 700X - SECOND COAT
Checkpoint | Weather/RH
Label | Apply within 5-35°C RH must be 0-85%
Checkpoint | Product Mixing
Label | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Checkpoint | 700X Application
Label | • Enviro 700X to be applied by roller horizontally on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
SECTION | QA TESTING - EACH LOCATION
Checkpoint | Inspection
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
Label | Records - time stamped photograph
Checkpoint | Thickness Testing - Delfasco Positector
Label | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
Label | Records - time stamped photograph
Checkpoint | ELT Testing - Delfasco Holiday Tester
Label | Conduct Electronic Leak Testing ( ELT) on area membraned
Label | Records - time stamped photograph
SECTION | DETAILING
CHECKPOINT | Vertical Termination Detailing
Label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
SECTION | FINAL BUILDERS SIGN OFF
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman Detailing inspection review
SIGNOFF | Site Engineer/foreman inspection sign off