## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Auckland - BTS Install |  | Auckland - BTS Install | 18736d17-b2d7-4e68-9db6-44362e846ef2
| checkpoint | Location as per plan / discussion
| checkpoint | Installed level
| checkpoint | Earth electrode installed
| checkpoint | Earth tag installed
| checkpoint | Earth clamp installed
| checkpoint | Zinc spray applied
| checkpoint | Earth toby installed and secured in place
| checkpoint | Danger sign installed
| checkpoint | Terminations checked for tightness
| checkpoint | Cable installed at minimum depth of 600mm
| checkpoint | Cable bought up next to gyro / pole
| checkpoint | Test results recorded
| checkpoint | COC complete
| checkpoint | Photos
| checklist | Auckland - First Fix - Bathrooms/Ensuite |  | Auckland - First Fix - Bathrooms/Ensuite | e6a997f4-ebb8-4dc1-bc62-a5fab6c05b76
| section | Flush Boxes
| checkpoint | Height as per plan
| checkpoint | Location as per plan
| checkpoint | Nogging installed for towel rail
| checkpoint | Marked on floor
| section | Cabling
| checkpoint | Circuits clearly labelled
| checkpoint | Cables secured
| checkpoint | Separation between data and power
| section | Lights
| checkpoint | Cabling in correct location
| checkpoint | Measurements recorded
| checkpoint | Nogging installed
| checkpoint | Marked on floor
| section | Fans
| checkpoint | Installed in accessible location
| checkpoint | Surface socket fit-off and lead taped on (inline fan)
| checkpoint | Ducts run flat and straight
| checkpoint | Measurements recorded
| checkpoint | Marked on floor
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - First Fix - Exterior |  | Auckland - First Fix - Exterior | eb206cf9-4b63-4dfc-8e0b-75f2e8cb0bd7
| section | Cabling
| checkpoint | Circuits clearly labelled
| checkpoint | Cables secured
| checkpoint | Separation between data and power
| checkpoint | Dektite waterproofing seals installed
| section | Lights
| checkpoint | Cabling in correct location
| checkpoint | Measurements recorded
| checkpoint | Nogging installed
| checkpoint | Photos
| section | Fans
| checkpoint | Measurements recorded
| checkpoint | Grills installed
| section | Earthing
| checkpoint | Earth electrode installed
| checkpoint | Earth tag installed
| checkpoint | Earth clamp installed
| checkpoint | Zinc spray applied
| checkpoint | Earth toby installed and secured in place
| section | Fibre
| checkpoint | Interior fibre cable installed through trade seal
| checkpoint | Exterior fibre cable installed through trade seal
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - First Fix - Kitchen/Living/Photos/Bedrooms/Garage/Hallway |  | Auckland - First Fix - Kitchen/Living/Photos/Bedrooms/Garage/Hallway | 45769fc3-cc43-4b20-a10d-05215e77619c
| section | Flush Boxes
| checkpoint | Height as per plan
| checkpoint | Location as per plan
| checkpoint | Marked on floor
| section | Cabling
| checkpoint | Circuits clearly labelled
| checkpoint | Cables secured
| checkpoint | Separation between data and power
| section | Lights
| checkpoint | Cabling in correct location
| checkpoint | Measurements recorded
| checkpoint | Nogging installed
| checkpoint | Marked on floor
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - First Fix - Laundry/Scullery |  | Auckland - First Fix - Laundry/Scullery | 2ec78743-d2bd-4a3e-abc2-d14336f2c394
| section | Flush Boxes
| checkpoint | Height as per plan
| checkpoint | Location as per plan
| checkpoint | Marked on floor
| section | Cabling
| checkpoint | Circuits clearly labelled
| checkpoint | Cables secured
| checkpoint | Separation between data and power
| section | Lights
| checkpoint | Cabling in correct location
| checkpoint | Measurements recorded
| checkpoint | Nogging installed
| checkpoint | Marked on floor
| section | Fans
| checkpoint | Installed in accessible location
| checkpoint | Power plug fit-off
| checkpoint | Ducts run flat and straight
| checkpoint | Measurements recorded
| checkpoint | Marked on floor
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - First Fix - Switchboards |  | Auckland - First Fix - Switchboards | ea62455d-3a3b-4877-80b1-0510ef24ceea
| section | Electrical
| checkpoint | Installed as per plan
| checkpoint | Height as per plan
| checkpoint | Cables clearly labelled
| checkpoint | Check all cables have been bought into switchboard
| checkpoint | Mains cable installed
| checkpoint | Photos
| section | Data
| checkpoint | Installed as per plan
| checkpoint | Height as per plan
| checkpoint | Cables clearly labelled
| checkpoint | Check all cables have been bought into board
| checkpoint | Interior fibre cable installed
| checkpoint | Photos
| checklist | Auckland - First Fix - Under Floor Heating |  | First Fix - Under Floor Heating | 45f20f35-dde3-4b0e-8183-936080dd0c1b
| section | Pre-wire
| checkpoint | Flush box installed for controller
| checkpoint | Draw wire installed
| checkpoint | Supply cable installed to flush box
| section | Element Install
| checkpoint | Floor prepped and clean
| checkpoint | Element laid as per plan
| checkpoint | Element ohm tested
| checkpoint | Floor sensor probe installed
| checkpoint | Element alarm installed
| checkpoint | Silicone installed for edges (5mm)
| checkpoint | Screed laid
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Mains Install |  | Auckland - Mains Install | 19f785a0-d78a-4f13-951c-33bfeb191b91
| section | Electrical
| checkpoint | Duct installed at minimum depth of 600mm
| checkpoint | Protection mag slab installed
| checkpoint | Warning signal tape installed
| checkpoint | Duct bought up next to gyro / pole
| checkpoint | Duct upstands installed
| checkpoint | Draw wire installed through duct
| checkpoint | Duct ends taped up
| checkpoint | Cable installed through duct
| checkpoint | Cable installed through concrete slab
| checkpoint | Cable clearly labelled
| checkpoint | Cable size and Measurements recorded
| checkpoint | Plan marked with as-built
| checkpoint | Photos
| section | Telecom / Fibre
| checkpoint | Duct installed at minimum depth of 400mm
| checkpoint | Approved chorus duct used
| checkpoint | Approved exterior fibre cable used
| checkpoint | Duct upstands installed
| checkpoint | Duct ends taped up
| checkpoint | Cable installed through concrete slab
| checkpoint | Cable / duct bought up next to gyro / pole
| checkpoint | Cable / duct Measurements recorded
| checkpoint | Plan marked with as-built
| checkpoint | Photos
| checklist | Auckland - Roof Cowl |  | Roof Cowl | 506907e8-24d9-4372-a33a-08b7b0216ff0
| section | Details
| checkpoint | Installed roof cowls vertically straight and levelled - Adequate supports - Photos
| checkpoint | Installed using correct materials - Photos
| checkpoint | Installed silicone around peneration hole - photos
| checkpoint | Installed silicone over top of screws and edging of dek seal - photos
| checkpoint | Duct attached to roof cowl - photos
| checkpoint | Photos
| checklist | Auckland - Second Fix - Bathroom/Ensuite |  | Auckland - Second Fix - Bathroom/Ensuite | 4f636345-3354-4782-b377-df6f42e28649
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan
| checkpoint | Tested for operation
| section | Fans
| checkpoint | Interior grill installed
| checkpoint | Exterior grill installed
| checkpoint | Tested for operation
| section | Towel rail
| checkpoint | Location as per plan
| checkpoint | Height as per plan
| checkpoint | Installed level
| checkpoint | Tested for operation
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Exterior |  | Auckland - Second Fix - Exterior | adf6a27c-e312-4f21-8bd0-53e5ba625888
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| checkpoint | Danger sign installed
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan
| checkpoint | Settings adjusted (sensores + timers)
| checkpoint | Tested for operation
| checkpoint | Landscape lighting (cable disconnected)
| section | Fans
| checkpoint | Exterior grill installed
| checkpoint | Installed square
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Hallway |  | Auckland - Second Fix - Hallway | 0c6618a3-166b-4bf1-bc9c-55f3ccb9af6f
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan / client preference
| checkpoint | Tested for operation
| section | Hot Water Cylinder
| checkpoint | Connection kit installed
| checkpoint | Earth bond tested
| checkpoint | Load test completed
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Kitchen |  | Auckland - Second Fix - Kitchen | 184e7ab2-a06f-4ddf-b76e-431d5427a2e5
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| checkpoint | Sink earth bond connected
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan / client preference
| checkpoint | Tested for operation
| section | Appliances
| checkpoint | HOB installed and secured
| checkpoint | Oven installed and secured
| checkpoint | Tested for operation
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Laundry/Scullery |  | Auckland - Second Fix - Laundry/Scullery | 78f0700d-1ff2-448f-af33-a171e96a9ef3
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan
| checkpoint | Tested for operation
| section | Fans
| checkpoint | Interior grill installed
| checkpoint | Exterior grill installed
| checkpoint | Tested for operation
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Living/Bedroom/Garage |  | Auckland - Second Fix - Living/Bedroom/Garage | e9fed97e-35a2-4d7e-8781-e42c4e97e09e
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan / client preference
| checkpoint | Tested for operation
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Switchboards |  | Auckland - Second Fix - Switchboards | 3b2a1913-b894-4e11-af79-b537151f3d93
| section | Electrical
| checkpoint | Cables clearly labelled
| checkpoint | Cables neatly dressed
| checkpoint | Switchboard bonded
| checkpoint | Neutrals and earths labelled
| checkpoint | Terminations checked for tightness
| checkpoint | Board is clean inside and outside
| checkpoint | Masking blanks installed
| checkpoint | Masking panel labelled with circuits
| checkpoint | Photos
| section | Data
| checkpoint | Cables clearly labelled
| checkpoint | Cables neatly dressed
| checkpoint | Board bonded
| checkpoint | Terminations checked for tightness
| checkpoint | Board is clean inside and outside
| checkpoint | Photos
| checklist | Auckland - Second Fix - Under Floor Heating |  | Second Fix - Under Floor Heating | ea6e2bc6-56d6-4e3d-880c-577fbe1609d8
| section | Fit-out
| checkpoint | Element ohm tested
| checkpoint | Thermostat connections correct
| checkpoint | Wall controller operational
| checkpoint | Element load tested (A)
| checkpoint | Wall controller installed level
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Solar installation |  | Auckland - Solar installation | faa2f08f-4f66-4f76-b793-27298d5a011b
| section | Switchboard
| checkpoint | Cables clearly labelled
| checkpoint | Cables neatly dressed
| checkpoint | Correctly rated MCB installed
| checkpoint | Neutrals and earths connected
| checkpoint | Module rail earth bonding connected
| checkpoint | Terminations checked for tightness
| checkpoint | Board is clean inside and outside
| checkpoint | Masking blanks installed
| checkpoint | Masking panel labelled with circuits
| checkpoint | PV Label kit installed
| checkpoint | Photos
| section | Inverter
| checkpoint | Inverter location as per plan
| checkpoint | Inverter installed level
| checkpoint | Inverter installed as per manufacturer's instructions
| checkpoint | AC circuit installed
| checkpoint | AC circuit clearly labelled
| checkpoint | AC isolator installed level
| checkpoint | AC isolator correctly rated
| checkpoint | AC cable terminated and checked for tightness
| checkpoint | DC circuit installed
| checkpoint | DC circuit clearly labelled
| checkpoint | DC isolator installed level
| checkpoint | DC isolator correctly rated
| checkpoint | DC inverter plug-ends connected
| checkpoint | DC cable terminated and checked for tightness
| checkpoint | Cat6 network cable connected
| checkpoint | Separation between data and power
| checkpoint | PV Label kit installed
| checkpoint | Photos
| section | Cable / conduit
| checkpoint | Cable adequately supported
| checkpoint | Cable adequately protected
| checkpoint | Conduit installed in accessible areas
| checkpoint | DC Conduit labelled every 600mm
| checkpoint | Conduit is solar type
| checkpoint | Earth bond installed per array
| checkpoint | Earth bond installed between rails
| checkpoint | Photos
| section | Rails / modules
| checkpoint | Correct support feet installed
| checkpoint | Support feet installed into purlin
| checkpoint | Rails installed straight
| checkpoint | Rails adequately supported
| checkpoint | Rail components checked for tightness
| checkpoint | Module layout as per plan
| checkpoint | Modules installed straight
| checkpoint | Module cabling kept off roof
| checkpoint | Module earth plates installed
| checkpoint | Module components checked for tightness
| checkpoint | Photos
| section | Compliance
| checkpoint | COC complete eForms
| checkpoint | ESC complete eForms
| checkpoint | Test results complete eForms
| checkpoint | Commissioning sheet complete eForms
| checkpoint | Documents uploaded eForms
| checklist | Auckland - Strip Out |  | Auckland - Strip Out | 3d9f85d1-6240-499b-b784-4e963b0b3b91
| checkpoint | Flush boxes cut as per plan
| checkpoint | Fans cut as per plan
| checkpoint | Lights cut as per plan
| checkpoint | Exterior lights have been bought out centre / as per pre-wire
| checkpoint | Cables stripped
| checkpoint | Switching as per plan
| checkpoint | Cables clearly labelled
| checkpoint | Complete final walkthrough check
| checkpoint | Damages and remedials documented
| checkpoint | Photos
| checklist | Compliance |  | Compliance | 173bfff6-1bc1-4700-b756-7349f36c1f54
| checkpoint | COC complete eForms
| checkpoint | ESC complete eForms
| checkpoint | Test results complete eForms
| checkpoint | Documents uploaded eForms
| checklist | Walkthrough Checklist |  | Walkthrough | c0cc3dc2-60b2-44fb-9513-220d1ab5bdff
| checkpoint | Power outlet locations confirmed and marked
| checkpoint | Light switch locations confirmed and marked
| checkpoint | Switchboard locations confirmed and marked
| checkpoint | Bathroom outlet locations confirmed and marked
| checkpoint | Bathroom outlets vertical or horizontal
| checkpoint | Towel rail locations confirmed and marked
| checkpoint | Interior light locations confirmed
| checkpoint | Exterior light locations confirmed and marked
| checkpoint | Exterior fan grills soffit mount or wall mount
| checkpoint | CCTV locations confirmed
| checkpoint | CCTV soffit mount or wall mount
| checkpoint | Aerial locations confirmed
| checkpoint | Aerial cabling location confirmed and marked
| checkpoint | Plans updated with changes