## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Auckland - BTS Install |  | BTS Install | 62d2a9ae-19d6-43cd-8421-6087e03ebf9e
| checkpoint | Location as per plan / discussion
| checkpoint | Installed level
| checkpoint | Earth electrode installed
| checkpoint | Earth tag installed
| checkpoint | Earth clamp installed
| checkpoint | Zinc spray applied
| checkpoint | Earth toby installed and secured in place
| checkpoint | Danger sign installed
| checkpoint | Terminations checked for tightness
| checkpoint | Cable installed at minimum depth of 600mm
| checkpoint | Cable bought up next to gyro / pole
| checkpoint | Test results recorded
| checkpoint | COC complete
| checkpoint | Photos
| checklist | Auckland - BTS Install - Remedials + Sign-off |  | BTS Install - Remedials + Sign-off | 2d75739c-05dc-46bf-b205-c5fe1b121c8a
| checkpoint | Damages and remedials documented
| checkpoint | All remedial work sent to CM and PM
| checkpoint | Remedial photos
| checkpoint | You are signing off that this job is fully complete
| checklist | Auckland - Compliance |  | Compliance | 9deda10d-eab5-4ac1-a230-1690b067e18a
| checkpoint | COC complete eForms
| checkpoint | ESC complete eForms
| checkpoint | Test results complete eForms
| checkpoint | Documents uploaded eForms
| checklist | Auckland - First Fix - Bathrooms/Ensuite |  | First Fix - Bathrooms/Ensuite | 96a4f4d8-463e-4ae0-8466-71dc9eb1d43b
| section | Flush Boxes
| checkpoint | Height as per plan
| checkpoint | Location as per plan
| checkpoint | Nogging installed for towel rail
| checkpoint | Marked on floor
| section | Cabling
| checkpoint | Circuits clearly labelled
| checkpoint | Cables secured
| checkpoint | Separation between data and power
| section | Lights
| checkpoint | Cabling in correct location
| checkpoint | measurements recorded
| checkpoint | Nogging installed
| checkpoint | Marked on floor
| section | Fans
| checkpoint | Installed in accessible location
| checkpoint | Surface socket fit-off and lead taped on (inline fan)
| checkpoint | Ducts run flat and straight
| checkpoint | measurements recorded
| checkpoint | Marked on floor
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - First Fix - Exterior |  | First Fix - Exterior | 04e0551e-adc1-4b78-8b01-07efbdae3f80
| section | Cabling
| checkpoint | Circuits clearly labelled
| checkpoint | Cables secured
| checkpoint | Separation between data and power
| checkpoint | Dektite waterproofing seals installed
| section | Lights
| checkpoint | Cabling in correct location
| checkpoint | measurements recorded
| checkpoint | Nogging installed
| checkpoint | Photos
| section | Fans
| checkpoint | measurements recorded
| checkpoint | Grills installed
| section | Earthing
| checkpoint | Earth electrode installed
| checkpoint | Earth tag installed
| checkpoint | Earth clamp installed
| checkpoint | Zinc spray applied
| checkpoint | Earth toby installed and secured in place
| section | Fibre
| checkpoint | Interior fibre cable installed through trade seal
| checkpoint | Exterior fibre cable installed through trade seal
| section | Photos
| checkpoint | Uploaded
| section | Aerial
| checkpoint | Pre-install photo
| checkpoint | Coax cables clearly labelled
| checkpoint | Aerial installed to roof
| checkpoint | Aerial installed with correct orientation
| checkpoint | Aerial installed level
| checkpoint | Check tightness of fixings and fittings
| checkpoint | Test signal levels
| checkpoint | Clean roof area
| checkpoint | Installed Splitter in cabinet if required
| checkpoint | Photos
| checklist | Auckland - First Fix - Kitchen/Living/Photos/Bedrooms/Garage/Hallway |  | First Fix - Kitchen/Living/Photos/Bedrooms/Garage/Hallway | 36c7674c-3785-41d2-a15f-dd979ad542b4
| section | Flush Boxes
| checkpoint | Height as per plan
| checkpoint | Location as per plan
| checkpoint | Marked on floor
| section | Cabling
| checkpoint | Circuits clearly labelled
| checkpoint | Cables secured
| checkpoint | Separation between data and power
| section | Lights
| checkpoint | Cabling in correct location
| checkpoint | measurements recorded
| checkpoint | Nogging installed
| checkpoint | Marked on floor
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - First Fix - Laundry/Scullery |  | First Fix - Laundry/Scullery | ab96726b-e79d-424d-a431-28df3235c64b
| section | Flush Boxes
| checkpoint | Height as per plan
| checkpoint | Location as per plan
| checkpoint | Marked on floor
| section | Cabling
| checkpoint | Circuits clearly labelled
| checkpoint | Cables secured
| checkpoint | Separation between data and power
| section | Lights
| checkpoint | Cabling in correct location
| checkpoint | Measurements recorded
| checkpoint | Nogging installed
| checkpoint | Marked on floor
| section | Fans
| checkpoint | Installed in accessible location
| checkpoint | Power plug fit-off
| checkpoint | Ducts run flat and straight
| checkpoint | Measurements recorded
| checkpoint | Marked on floor
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - First Fix - Remedials + Sign-off |  | First Fix - Remedials + Sign-off | d5d4712a-7379-4d20-986d-90397109b0e4
| checkpoint | Damages and remedials documented
| checkpoint | All remedial work sent to CM and PM
| checkpoint | Remedial photos
| checkpoint | You are signing off that this job is fully complete
| checklist | Auckland - First Fix - Security / CCTV |  | First Fix - Security / CCTV | e4ef1ccd-97cb-4aed-ad0f-b61659d9bc13
| checkpoint | Location as per plan
| checkpoint | Cables clearly labelled
| checkpoint | Photos
| checklist | Auckland - First Fix - Switchboards |  | First Fix - Switchboards | 1c3e7d8a-1be1-469d-b268-5395277e0f94
| section | Electrical
| checkpoint | Installed as per plan
| checkpoint | Height as per plan
| checkpoint | Cables clearly labelled
| checkpoint | Check all cables have been bought into switchboard
| checkpoint | Mains cable installed
| checkpoint | Photos
| section | Data
| checkpoint | Installed as per plan
| checkpoint | Height as per plan
| checkpoint | Cables clearly labelled
| checkpoint | Check all cables have been bought into board
| checkpoint | Interior fibre cable installed
| checkpoint | Photos
| checklist | Auckland - First Fix - Under Floor Heating |  | First Fix - Under Floor Heating | 59a5fc7d-f591-431e-8073-c42e183d5cfa
| section | Pre-wire
| checkpoint | Flush box installed for controller
| checkpoint | Draw wire installed
| checkpoint | Supply cable installed to flush box
| section | Element Install
| checkpoint | Floor prepped and clean
| checkpoint | Element laid as per plan
| checkpoint | Element ohm tested
| checkpoint | Floor sensor probe installed
| checkpoint | Element alarm installed
| checkpoint | Silicone installed for edges (5mm)
| checkpoint | Screed laid
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Mains Install |  | Mains Install | 37d98bcd-9979-4966-b282-f52256ba609a
| section | Electrical
| checkpoint | Cable installed at minimum depth of 600mm
| checkpoint | Protection mag slab installed
| checkpoint | Warning signal tape installed
| checkpoint | Cable installed through concrete slab
| checkpoint | Cable bought up next to gyro / pole
| checkpoint | Cable clearly labelled
| checkpoint | Cable size and measurements recorded
| checkpoint | Plan marked with as-built
| checkpoint | Photos
| section | Telecom / Fibre
| checkpoint | Cable installed at minimum depth of 400mm
| checkpoint | Approved exterior fibre cable used
| checkpoint | Cable installed through concrete slab
| checkpoint | Cable bought up next to gyro / pole
| checkpoint | Cable measurements recorded
| checkpoint | Plan marked with as-built
| checkpoint | Photos
| checklist | Auckland - Mains Install - Remedials + Sign-off |  | Mains Install - Remedials + Sign-off | 9b5301ad-0ae6-4fd0-8209-66f8b44523a0
| checkpoint | Damages and remedials documented
| checkpoint | All remedial work sent to CM and PM
| checkpoint | Remedial photos
| checkpoint | You are signing off that this job is fully complete
| checklist | Auckland - Roof Cowl |  | Roof Cowl | 506907e8-24d9-4372-a33a-08b7b0216ff0
| section | Details
| checkpoint | Installed roof cowls vertically straight and levelled - Adequate supports - Photos
| checkpoint | Installed using correct materials - Photos
| checkpoint | Installed silicone around peneration hole - photos
| checkpoint | Installed silicone over top of screws and edging of dek seal - photos
| checkpoint | Duct attached to roof cowl - photos
| checkpoint | Photos
| checklist | Auckland - Second Fix - Bathroom/Ensuite |  | Second Fix - Bathroom/Ensuite | 4f739036-af06-4562-b17a-fa4172b5b61a
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan
| checkpoint | Tested for operation
| section | Fans
| checkpoint | Interior grill installed
| checkpoint | Exterior grill installed
| checkpoint | Tested for operation
| section | Towel rail
| checkpoint | Location as per plan
| checkpoint | Height as per plan
| checkpoint | Installed level
| checkpoint | Tested for operation
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Exterior |  | Second Fix - Exterior | cd7347b1-fefa-4140-8897-af1049b5130c
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| checkpoint | Danger sign installed
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan
| checkpoint | Settings adjusted (sensores + timers)
| checkpoint | Tested for operation
| checkpoint | Landscape lighting (cable disconnected)
| section | Fans
| checkpoint | Exterior grill installed
| checkpoint | Installed square
| section | Photos
| checkpoint | Uploaded
| section | Aerial
| checkpoint | Pre-install photo
| checkpoint | Coax cables clearly labelled
| checkpoint | Aerial installed to roof
| checkpoint | Aerial installed with correct orientation
| checkpoint | Aerial installed level
| checkpoint | Check tightness of fixings and fittings
| checkpoint | Test signal levels
| checkpoint | Clean roof area
| checkpoint | Installed Splitter in cabinet if required
| checkpoint | Photos
| checklist | Auckland - Second Fix - Hallway |  | Second Fix - Hallway | 5c909481-c8ea-4a0f-9b04-1b2cd3825472
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan / client preference
| checkpoint | Tested for operation
| section | Hot Water Cylinder
| checkpoint | Connection kit installed
| checkpoint | Earth bond tested
| checkpoint | Load test completed
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Kitchen |  | Second Fix - Kitchen | 5014f2bb-88a1-4562-984b-7717b61639d3
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| checkpoint | Sink earth bond connected
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan / client preference
| checkpoint | Tested for operation
| section | Appliances
| checkpoint | HOB installed and secured
| checkpoint | Oven installed and secured
| checkpoint | Tested for operation
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Laundry/Scullery |  | Second Fix - Laundry/Scullery | 1f288c70-6fa9-46ac-948c-44022e864570
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan
| checkpoint | Tested for operation
| section | Fans
| checkpoint | Interior grill installed
| checkpoint | Exterior grill installed
| checkpoint | Tested for operation
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Living/Bedroom/Garage |  | Second Fix - Living/Bedroom/Garage | 633015d4-5d2c-430b-8d1f-8fee50fab26e
| section | Power outlets
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Installed level
| section | Light Switches
| checkpoint | Correct switchgear installed as per plan
| checkpoint | Location as per plan
| checkpoint | Switching as per plan
| checkpoint | Installed level
| section | Light Fixtures
| checkpoint | Correct fixtures installed as per plan
| checkpoint | Location as per plan
| checkpoint | Height as per plan / client preference
| checkpoint | Tested for operation
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Second Fix - Remedials |  | Second Fix - Remedials | 12eb772b-1e98-47a7-bcad-bb24927f1828
| checkpoint | Damages and remedials documented
| checkpoint | All remedial work sent to CM and PM
| checkpoint | Remedial photos
| checklist | Auckland - Second Fix - Remedials + Sign-off |  | Second Fix - Remedials + Sign-off | 1b54ebd0-b511-4716-b6de-a4195566945f
| checkpoint | Damages and remedials documented
| checkpoint | All remedial work sent to CM and PM
| checkpoint | Remedial photos
| checkpoint | You are signing off that this job is fully complete
| checklist | Auckland - Second Fix - Security / CCTV |  | Second Fix - Security / CCTV | a8f67b2e-d7cd-473f-826b-a0762ce5939e
| checkpoint | Installed as per plan
| checkpoint | Photos
| checklist | Auckland - Second Fix - Smoke Alarms |  | Second Fix - Smoke Alarms | 243793ae-136d-4127-a1c0-f951b6d8eda2
| checkpoint | Installed as per plan
| checkpoint | Photos
| checklist | Auckland - Second Fix - Switchboards |  | Second Fix - Switchboards | 3e3398cf-1509-47f8-80d7-79cccde18481
| section | Electrical
| checkpoint | Cables clearly labelled
| checkpoint | Cables neatly dressed
| checkpoint | Switchboard bonded
| checkpoint | Neutrals and earths labelled
| checkpoint | Terminations checked for tightness
| checkpoint | Board is clean inside and outside
| checkpoint | Masking blanks installed
| checkpoint | Masking panel labelled with circuits
| checkpoint | Photos
| section | Data
| checkpoint | Cables clearly labelled
| checkpoint | Cables neatly dressed
| checkpoint | Board bonded
| checkpoint | Terminations checked for tightness
| checkpoint | Board is clean inside and outside
| checkpoint | Photos
| checklist | Auckland - Second Fix - Under Floor Heating |  | Second Fix - Under Floor Heating | 255095cc-4194-4c00-a694-ff5583ff42fb
| section | Fit-out
| checkpoint | Element ohm tested
| checkpoint | Thermostat connections correct
| checkpoint | Wall controller operational
| checkpoint | Element load tested (A)
| checkpoint | Wall controller installed level
| section | Photos
| checkpoint | Uploaded
| checklist | Auckland - Solar installation |  | Solar installation | b833b75a-219c-4510-bc05-fc9f51d142c9
| section | Switchboard
| checkpoint | Cables clearly labelled
| checkpoint | Cables neatly dressed
| checkpoint | Correctly rated MCB installed
| checkpoint | Neutrals and earths connected
| checkpoint | Module rail earth bonding connected
| checkpoint | Terminations checked for tightness
| checkpoint | Board is clean inside and outside
| checkpoint | Masking blanks installed
| checkpoint | Masking panel labelled with circuits
| checkpoint | PV Label kit installed
| checkpoint | Photos
| section | Inverter
| checkpoint | Inverter location as per plan
| checkpoint | Inverter installed level
| checkpoint | Inverter installed as per manufacturer's instructions
| checkpoint | AC circuit installed
| checkpoint | AC circuit clearly labelled
| checkpoint | AC isolator installed level
| checkpoint | AC isolator correctly rated
| checkpoint | AC cable terminated and checked for tightness
| checkpoint | DC circuit installed
| checkpoint | DC circuit clearly labelled
| checkpoint | DC isolator installed level
| checkpoint | DC isolator correctly rated
| checkpoint | DC inverter plug-ends connected
| checkpoint | DC cable terminated and checked for tightness
| checkpoint | Cat6 network cable connected
| checkpoint | Separation between data and power
| checkpoint | PV Label kit installed
| checkpoint | Photos
| section | Cable / conduit
| checkpoint | Cable adequately supported
| checkpoint | Cable adequately protected
| checkpoint | Conduit installed in accessible areas
| checkpoint | DC Conduit labelled every 600mm
| checkpoint | Conduit is solar type
| checkpoint | Earth bond installed per array
| checkpoint | Earth bond installed between rails
| checkpoint | Photos
| section | Rails / modules
| checkpoint | Correct support feet installed
| checkpoint | Support feet installed into purlin
| checkpoint | Rails installed straight
| checkpoint | Rails adequately supported
| checkpoint | Rail components checked for tightness
| checkpoint | Module layout as per plan
| checkpoint | Modules installed straight
| checkpoint | Module cabling kept off roof
| checkpoint | Module earth plates installed
| checkpoint | Module components checked for tightness
| checkpoint | Photos
| section | Compliance
| checkpoint | COC complete eForms
| checkpoint | ESC complete eForms
| checkpoint | Test results complete eForms
| checkpoint | Commissioning sheet complete eForms
| checkpoint | Documents uploaded eForms
| checklist | Auckland - Strip Out |  | Strip Out | a27a934a-8786-44fe-849e-ee603419d343
| checkpoint | Flush boxes cut as per plan
| checkpoint | Fans cut as per plan
| checkpoint | Lights cut as per plan
| checkpoint | Exterior lights have been bought out centre / as per pre-wire
| checkpoint | Cables stripped
| checkpoint | Switching as per plan
| checkpoint | Cables clearly labelled
| checkpoint | Complete final walkthrough check
| checkpoint | Damages and remedials documented
| checkpoint | All remedial work sent to CM and PM
| checkpoint | Remedial photos
| checkpoint | Strip-out Photos
| checkpoint | You are signing off that this job is fully complete
| checklist | Auckland - Walkthrough Checklist |  | Walkthrough | 6fdf7be5-8e2f-4c5d-9206-38295f4041ae
| checkpoint | Power outlet locations confirmed and marked
| checkpoint | Light switch locations confirmed and marked
| checkpoint | Switchboard locations confirmed and marked
| checkpoint | Bathroom outlet locations confirmed and marked
| checkpoint | Bathroom outlets vertical or horizontal
| checkpoint | Towel rail locations confirmed and marked
| checkpoint | Interior light locations confirmed
| checkpoint | Exterior light locations confirmed and marked
| checkpoint | Exterior fan grills soffit mount or wall mount
| checkpoint | CCTV locations confirmed
| checkpoint | CCTV soffit mount or wall mount
| checkpoint | Aerial locations confirmed
| checkpoint | Aerial cabling location confirmed and marked
| checkpoint | Plans updated with changes