## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Subsoil Drainage | itp |  |  |  |  | ITP - Subsoil Drainage
section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
checkpoint | 1.01 - Drainage aggregate
label | Detail of Activity / Test - Crushing Resistance
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - NZS4407:3.10
label | Acceptance Criteria - > 100KN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Drainage aggregate
label | Detail of Activity / Test - Particle size distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - As per TNZ F/2
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Pipe
label | Detail of Activity / Test - Subsoil Pipe Material
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - each delivery
label | Inspection / Test method - Dockets for each delivery
label | Acceptance Criteria - Compliance with TNZ F/2
label | Record documents (QCP - Quality Control Portal) - Delivery Docket
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTUCTION
checkpoint | 3.12 - Alignment
label | Detail of Activity / Test - Subsoils to be placed behind the Kerb line or as instructed by Engineer
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Acceptance Criteria - Engineers Approval
label | Responsibility - Engineers Representative
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.13 - Excavation
label | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.14 - Trench Lining
label | Detail of Activity / Test - A29 or other approved Bidim to be placed and wrapped around Trench.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Minimum Width 300mm.
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.15 - Pipe laying
label | Detail of Activity / Test - Pipe must have 100mm of Cushion. Drainage 60:40 Material to be used.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Minimum 100mm
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.16 - Pipe laying
label | Detail of Activity / Test - 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - As Per Drawings
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.17 - Backfill
label | Detail of Activity / Test - Drainage 60:40 Material to be used.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - As Per Drawings
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
holdpoint | Add Signature
checklist | Shoulder Clearing Checklist | itp |  |  |  |  | Shoulder Clearing Checklist
section | Pre-site checks for the following
checkpoint | Photos taken @ Pre start of works
label | Responsibility - FP/Su
label | Comment - Field evidence for ITP
checkpoint | Check culverts in vicinty of work inlet/outlets
label | Responsibility - FP/Su
label | Comment - Field evidence for ITP
checkpoint | Edge Delineators - offset position to re-instate if required
label | Responsibility - FP/Su
label | Comment - Field evidence for ITP
checkpoint | Permanent Roadside Signage - Offset position to re-instate if required
label | Responsibility - FP/Su
label | Comment - Field evidence for ITP
checkpoint | Photos - Post completion of works
label | Responsibility - FP/Su
label | Comment - Field evidence for ITP