## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release
7f694258-afd9-4882-9923-f3d688de732a | checklist | ITP-000 - Client Pre-Construction Checklist Rev1 | itp | ITP-000 - Client Pre-Construction Checklist
18c558c8-c92f-4d3c-9cfd-51f942e9ce95 | section | 1 - Pre - Construction Works
c7f6031a-3745-4e38-959b-d053a3b8e4d5 | checkpoint | 1.1 Asphalt - submission of asphalt mix design
c2594028-97cf-5fa2-acab-acd92cc39fdb | note | FREQUENCY: Prior to commencing asphalt
bd24936f-bf8e-5b32-b288-0a638fc4b9d6 | note | ACCEPTANCE CRITERIA: Ensure the mix design/s have been registered and are approved by Superintendent prior to laying mix.
e8aa614f-89c0-5d87-8482-389f69f08164 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09. RAP DoT letter from production plant
7765a7af-0fd0-507e-a078-998e68d34ba1 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from the RAP DoT Letter.
c436bb80-b790-5812-b274-56df02ed9787 | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
d889d90c-00e5-53a7-90bb-935b4faea868 | note | HP
a9aa9830-2293-5edc-9131-cb694914c38e | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
1da9b33d-651c-5b62-80e0-14832bac8d98 | textbox | DATE:
44a5d687-1032-488b-8058-b12cb5e5b812 | signoff | HOLD POINT AUTHORITY
8b70a8b9-b974-47ae-a65a-88db30658f62 | checkpoint | 1.2 Concrete - submission & approval of concrete mix design prior to commencement of project
b92324ec-58d2-54e5-b7d8-eefd0b988c1a | note | FREQUENCY: Prior to first concrete pour
47dac52e-3d8c-50ce-9fd3-4a1f9b61493a | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix shall contain minimum 460 kg/m3 cement content. Special 50 mPa mix is to be VS502B25MET1 with a suitably flowable design slump agreed prior to construction.
3f0d0394-a7e2-547e-8f9d-e0d9109033c4 | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 VicRoads Spec. Cl. 503.04
249206f0-88b9-54f6-ad50-b08a2179584a | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from supplier
196bde20-a4fb-5c4b-8a54-109c8d28c48e | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
ee0d4f79-3664-500c-bc6c-ca2fa9361154 | note | HP
ab13a186-472a-52f9-b6c3-661587f83c4d | note | RESPONSIBILITY: FH Engineer / Superintendent
315e6ab5-664b-54d0-b097-f4d1d972d6fe | textbox | DATE:
f92f8325-bc73-4e4a-8a2e-ac849b2a2f8f | signoff | HOLD POINT AUTHORITY
2f20c85d-4394-40fa-ba3c-1107a5fb9276 | checkpoint | 1.3 Welders qualifications, competencies & work methodology
a6151f76-188f-5695-a576-d22bbed71d1a | note | FREQUENCY: Prior to commencing works
6c84e434-94d0-5a21-ad15-2679e2e6e643 | note | ACCEPTANCE CRITERIA: Weld methodology to be submitted prior to commencement of works. Welders shall be trained and compliant in Australian aluminothermic welding competencies as outlined below;
afee8c04-5835-5f88-a122-7cde90ddf15b | note | – TLIW2012 Grind Rails
f1b75cde-cf05-5e3a-bf7e-acaf3d792278 | note | – TLIW3015 Weld Rails using Aluminothermic welding process
d9607035-89dc-5b81-aa39-c1838384a8c2 | note | – TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
0ae696c2-b9c5-523b-a1ab-1ac373fb3f04 | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 Appendix C
c7d62929-6548-5df0-bfc7-925f9ba1b7ee | note | INSPECTION/TEST METHOD: Welding methodology
5519079a-9e9d-582d-871f-0bc5d0a54fc2 | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
6ec838d8-5398-55d5-ad99-7ac0945707ca | note | HP
c01aa2a1-0954-536c-8686-12878dc639e1 | note | RESPONSIBILITY: FH Engineer / Superintendent
88a2ca52-b5ce-5dcf-b778-1503863c3268 | textbox | DATE:
37ed168d-9a63-44ac-946d-88b7878e4657 | signoff | HOLD POINT AUTHORITY
c4512c79-40ec-4c01-ac1c-8d8ee79958ba | checkpoint | Final Inspection
cb680214-aa47-5ba5-bbde-67e7e449fedc | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7d5ea351-9ebc-5536-ac1a-11af7d34f8de | textbox | Print Name:
6e498d8c-a293-5c9e-8c4b-d8488af39bcd | textbox | Position:
b7a2db9a-6256-5f12-ad8f-9d843cc0b978 | textbox | Date:
f929064e-568a-44b8-9265-f24f2a8a1d28 | checklist | ITP-001 - Subgrade Preparation Rev2 | itp | ITP-001 - Subgrade Preparation
001dd911-d937-48b2-98d3-800d71131449 | section | 1 - Preliminary Works
08e0024d-231b-4647-9a6e-d43302fb49fd | checkpoint | 1.1 Prior to commencing any activity
62f9d2a2-eb0f-5668-a613-e424ef6d3bfc | note | FREQUENCY:
1f782522-4a00-5645-b973-e53782913847 | note | – – – – – – – – –
d1deab9c-1c5f-588a-bb14-8b70511a5ce7 | note | ACCEPTANCE CRITERIA:
1579c397-9798-5825-be1e-814e75f24c77 | note | • Ensure that all employees and subcontractors are:
106e3cdb-ff1c-54fb-9698-e73a571a32a1 | note | – using the correct and complete set of drawings
0734c511-b115-5d62-b9ac-44a90f4937f4 | note | – all drawings are the latest revision
fc584765-e697-59d8-b8ed-8de7cbc6525b | note | – – – – – – – – –
0ddf6bb1-41dd-5e60-a227-f2fcb0938263 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
70406ba7-3c2d-5414-a236-1ea587c13a29 | note | – – – – – – – – –
73a3f299-75e2-5df7-8a02-8f600426869a | note | INSPECTION/TEST METHOD: Visual inspection
ed75cbda-f83b-538a-a167-2da1a478f8a5 | note | – – – – – – – – –
da8a8733-2ce8-5f1f-86ee-e504c77e76f8 | note | RECORD OF CONFORMITY: This ITP signed off
5f83cb23-8cfa-59e8-b787-053cfd076a84 | note | – – – – – – – – –
4e76c56b-50ee-5eaa-89cd-a866be104203 | note | WP
90e18748-fb3a-588d-8874-3ea2e378704e | note | – – – – – – – – –
e4bc8fea-7824-5a24-a472-3acf23feaf9d | note | RESPONSIBILITY: Fulton Hogan
a872a435-c580-517f-96db-4df5bd96d24e | note | – – – – – – – – –
77e8f216-8afd-5162-9926-208f3cdabaca | textbox | DATE:
e14f2d41-5934-4e94-b41a-356c38a4340d | checkpoint | 1.2 Implementation of all measures and controls
f122a68a-35cb-5b64-835c-26e7638f23d9 | note | FREQUENCY: Prior to commencing any activity
4e170b53-ba54-55ae-9b68-a67caf75f7aa | note | – – – – – – – – –
b59eee26-c887-5111-abe8-cc1f482e5c2e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
ad0bd468-324b-5d2a-9c43-390d5828f4bd | note | – – – – – – – – –
696a264e-24dc-5277-b46c-5dc95b4190fd | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
91d9bdbf-a178-5eef-8453-0a89a0708c96 | note | – – – – – – – – –
e3c12262-f245-5553-b3c6-a36159b175f8 | note | INSPECTION/TEST METHOD: Visual Inspection
bf11d8f2-3c8f-5681-8835-022840c0f61f | note | – – – – – – – – –
04fe345a-688b-56aa-ab33-7f70914e6bc5 | note | RECORD OF CONFORMITY: This ITP signed off
66139be7-fe13-5fff-950d-00e745b50805 | note | – – – – – – – – –
b5b255c7-1f7f-56ce-a8c9-3bffe07da55e | note | WP
10b5adb8-31b1-5a54-a750-1d1f785bf167 | note | – – – – – – – – –
e4fa5ec5-eb0d-58e6-8d7e-30f8176caa7b | note | RESPONSIBILITY: Fulton Hogan
29b46ab1-c4b8-5132-b73d-bd6cdc51e87d | note | – – – – – – – – –
8ea1ef1d-bca5-51a3-85fb-e223293bb64c | textbox | DATE:
89b1c2e3-80b1-415f-b4b7-f68a08c4ceb3 | checkpoint | 1.3 Selection and approval of Disposal Site
7892b0ae-154a-5f04-be8b-da8253677e7c | note | FREQUENCY: Prior to commencing any activity
6ff0e8d7-8f32-5a8c-b53f-fb5d325d2aef | note | – – – – – – – – –
e8301558-c3f3-5870-85ba-07ee8f58e5ca | note | ACCEPTANCE CRITERIA:
883c2214-a136-5332-820b-a871f747e7f8 | note | • Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
4294df9a-93f3-5892-a985-666f23a3d0ba | note | • It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
425b148a-8db1-50fa-850b-c10ce6b467d4 | note | – – – – – – – – –
fa799b54-8fd5-5e73-a1cd-44bdb5a8768e | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019ST-0033 CL. 4.2.1.5.
5a31fb25-3862-59ff-9dbd-3fd054189b14 | note | – – – – – – – – –
c58f5fe8-4d8b-57aa-9c7c-68f2f7415a23 | note | INSPECTION/TEST METHOD: Verify
cf7671e7-df1e-55f8-80ad-b89d55d90e1d | note | – – – – – – – – –
78b91ef3-1683-5bab-a89f-5f19cda169d5 | note | RECORD OF CONFORMITY: This ITP signed off
34c485e5-742b-5e53-a60c-8a4d5d04e110 | note | – – – – – – – – –
782a07ef-35f7-563c-98a6-13a22cc9a8be | note | WP
1e55eeba-825f-5478-8eff-11c28a77fe35 | note | – – – – – – – – –
96f78f6a-d6d1-5547-9ea1-f0b7cd36ddb1 | note | RESPONSIBILITY: Fulton Hogan
2475ea40-478f-5620-9e54-9b96611ba0ca | note | – – – – – – – – –
ee8f6c8a-c918-5fd9-8091-a94761fe2b6a | textbox | DATE:
165cd49f-4c12-478d-8bd3-99ed859ad1aa | section | 2 - Construction Works
6ead4c3d-1f76-4041-98b9-735797e5e66a | checkpoint | 2.1 Excavation
04a24fd2-5b00-51d7-a9ca-c9aa717f319a | note | FREQUENCY: Each lot
492253a7-b3d8-5570-b020-c5ce763af084 | note | – – – – – – – – –
efb94f2e-cd37-5320-8a6e-d0de104247e9 | note | ACCEPTANCE CRITERIA:
baa863f2-d1c9-5a5c-b146-8343f22e29d3 | note | • Plant and equipment shall be appropriate for the task.
9c40d5dd-dc67-5291-82d7-3ee417c0d39d | note | • Excavation operations shall not disturb areas outside the limit of works
ea06e8ca-25bb-5a0f-a596-267ecb8a2b44 | note | – – – – – – – – –
c2d626ef-e9a1-518f-a3de-79624e2d314e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3., 4.2.4. Subgrade Preparation Work Procedure
4fd3b54d-df40-5f78-a962-06fec7cdf259 | note | – – – – – – – – –
0f3001c4-d5be-5e9c-9fd3-8d6ee43abf80 | note | INSPECTION/TEST METHOD: Verify
8d9c9c98-e561-53f7-9c6f-31ffdae504db | note | – – – – – – – – –
06a955ff-b6d8-5e17-96cf-92e5f236b8ac | note | RECORD OF CONFORMITY: This ITP Signed Off
bc68a1d0-e8c2-51a9-bb91-93888edb40c7 | note | – – – – – – – – –
f026da7f-121b-5bdc-8149-f050f061d70a | note | IP
aa3fcbdb-8d1e-5771-b64e-410e5cc50979 | note | – – – – – – – – –
2635c1b0-40d0-53fe-bb25-835a7dc906e3 | note | RESPONSIBILITY: Fulton Hogan
921c4796-8256-5ffc-a8e8-5eff4017aeb1 | note | – – – – – – – – –
2fc52efc-3c8d-503c-8f9c-dbaaafb5fa9e | textbox | DATE:
802ca758-3ed1-49cc-b623-d176b80ca889 | checkpoint | 2.2 Reinstatement of bonds
b2f18abf-29ff-5c3c-8b2b-617b0b15d20d | note | FREQUENCY: –
3276cb1c-ba9c-5ef6-a718-86a376bca5b0 | note | – – – – – – – – –
1611c3e7-3fd9-5250-835c-4f5d3dabcb40 | note | ACCEPTANCE CRITERIA:
c56f39e4-6f45-57e0-82a0-4e725de86474 | note | • Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
ba86160b-c645-526a-818d-babb46b3cb50 | note | • All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
47d730f5-6ba2-5b49-8557-c596c04ac689 | note | – – – – – – – – –
2db21435-71e8-55f6-94ff-0ae774c83bed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
3ae8cc64-79a4-5789-9cae-4e9dada33188 | note | – – – – – – – – –
b05afce8-1d41-5aef-9b80-4cb06cea6376 | note | INSPECTION/TEST METHOD: Verify
fdcb428e-4618-5bfc-ac95-0060c463692c | note | – – – – – – – – –
47abd4dc-af42-5443-a15b-f395a277951a | note | RECORD OF CONFORMITY: This ITP Signed Off
af44f208-4a33-5758-abb0-ac0bcfe7210f | note | – – – – – – – – –
7b78c6ce-2524-5562-b24a-7198fd2e4651 | note | IP
73057817-2852-54b7-bc46-667849451a1c | note | – – – – – – – – –
1b1bf03c-2c0a-5a77-ac2b-045cbe47602a | note | RESPONSIBILITY: Fulton Hogan
a1913f69-ef5d-598f-8b51-f144bbe646e8 | note | – – – – – – – – –
21166443-ea74-569e-900e-144e71da9eae | textbox | DATE:
aa819b0f-1537-40ff-8ff0-f28640a7253e | checkpoint | 2.3 Inspection of Subgrade Material
9e19d421-f547-5b12-b685-5339217907b1 | note | FREQUENCY: Each lot
6c6a27ae-c44f-5fe2-9c26-672f40a5d000 | note | – – – – – – – – –
6db22b10-27f3-59ce-acd5-9ca5c8f8ba01 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
b99ab6b4-533b-5ba4-8b6a-c689c82cf172 | note | – – – – – – – – –
5da3edb5-abe4-565e-bd14-4f32ee34d3e7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
301bccdd-8c01-50d8-b343-e992b0e50edf | note | – – – – – – – – –
cfa6d697-5076-5877-9dfb-4d1e1f694f91 | note | INSPECTION/TEST METHOD: Verify
dc1794fe-daa3-569a-8110-833774d69c10 | note | – – – – – – – – –
fe75f356-711b-5278-84ba-856975c88e52 | note | RECORD OF CONFORMITY: This ITP Signed Off
2f20abdc-13d0-572c-a6d4-9c4081e2c9c3 | note | – – – – – – – – –
2f4cbba4-8165-5e31-89fd-9360b2b07247 | note | HP
9e445c29-fa09-56fb-837c-e6f40466060f | note | – – – – – – – – –
5514190b-9b13-5929-a8da-70c531b745c0 | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
53e8baa5-5df3-5ea3-b758-5f788f1d0898 | note | – – – – – – – – –
d6d7c255-3e25-5623-841c-ba0fdb9c2169 | textbox | DATE:
8d227978-c3fd-4821-9092-b79b3a2a723d | signoff | HOLD POINT AUTHORITY
de70ef90-206d-417a-bbae-d4a027f4aa30 | checkpoint | 2.4 Width and Level conformity
a94a2e99-32c1-5406-8109-bec445d72519 | note | FREQUENCY: Each Lot
33326ec3-2087-5816-be92-bc4437a84a5f | note | – – – – – – – – –
5b68f9bf-3a2e-5301-8d68-fa6d3f28eaaa | note | ACCEPTANCE CRITERIA:
37e97c70-0483-572a-8ed3-d3d8f2f8a989 | note | • The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings.
bb29ddde-bd63-5bba-bac4-9e4b46f82e37 | note | • No point in the general surface shall vary more than 12mm from a 3m straight edge.
1525af19-3354-5a0b-aa93-4625836b8e10 | note | • Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
a0e61e5e-25bb-5f5e-b4a8-0800ccee6e33 | note | – – – – – – – – –
78c26b8d-8d93-5c84-a9b7-4d659afd965f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
d13bad2a-3743-5e07-b5ef-f13141427e1c | note | – – – – – – – – –
05b5309a-e090-5069-8281-6f28f3100869 | note | INSPECTION/TEST METHOD: Survey Report
885ee8b3-efe1-5921-8b20-d9bcb4e30304 | note | – – – – – – – – –
2b4df271-387b-5333-9d89-792db466b974 | note | RECORD OF CONFORMITY: Survey Record
22c79b27-1ff0-515e-b2cf-b4735d228444 | note | – – – – – – – – –
d69316af-172f-51cd-9f5d-29ae147e860e | note | IP
9357f8e2-a4d7-5b90-b99e-0012aaaf125f | note | – – – – – – – – –
e31c514f-1589-5939-a702-b18e3976e687 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
41250458-cd3b-5b43-a827-08fa756f36ae | note | – – – – – – – – –
91b5070b-f523-5c2f-86b4-837a5523bdf6 | textbox | DATE:
9354554c-477f-46cc-80f3-fd6152b7dbb3 | checkpoint | Final Inspection
982e8627-7db0-5628-bc49-d17e69663b91 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e0019a79-27e0-597e-a9f1-a27028318fe2 | textbox | Print Name:
9af4c584-2dc1-5ed8-900b-5cacb3c76a9e | textbox | Position:
240943ab-196e-5849-a9b3-471e09479da2 | textbox | Date:
4bd53acd-6405-4e3e-a599-dc5d4aa54a1a | checklist | ITP-002 - Feeder Conduits and Pits Rev2 | itp | ITP-002 - Feeder Conduits and Pits
c0fdca6c-9fb3-4ae7-913f-6a4b051a60ac | section | 1 - Preliminary Works
a46884c7-852b-4bc8-8107-83cbce107959 | checkpoint | 1.1 Check for correct documentation
1dd02b6f-cb20-50b0-af91-29c941336207 | note | FREQUENCY: Prior to commencing any activity
53936eae-1376-58f2-835b-37a4076cf038 | note | – – – – – – – – –
74d3e9ed-67fe-5385-abae-33733cce56ae | note | ACCEPTANCE CRITERIA:
cb06cb9c-ec2f-56c7-ac67-68dc8af70f95 | note | • Ensure that all employees and subcontractors are:
7edbdd30-85f5-5bb3-a6ff-93580d65be30 | note | – using the correct and complete set of drawings
ef193c2a-8d93-5c32-8590-d75b06db3c49 | note | – all drawings are the latest revision
c3ac8eb7-a7f1-594d-97f9-9ed95f4a60c8 | note | – – – – – – – – –
930331f8-238c-59e6-b164-afd483b350d6 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
074302b5-0dc5-51b6-a30d-cf25b8eb99a4 | note | – – – – – – – – –
62de1c25-2d66-5785-ab8b-edb723f6c9b6 | note | INSPECTION/TEST METHOD: Visual inspection
b96db47e-7769-52f1-9fa0-f7e5cfab558a | note | – – – – – – – – –
3796e4e2-e520-5904-8cbe-3c6218e6ca9a | note | RECORD OF CONFORMITY: This ITP signed off
f5ad2e9e-fce7-5471-b1d3-f2a9197a9be1 | note | – – – – – – – – –
c9939422-5637-5878-93db-86a8bc3de6e3 | note | HP*
e268fd35-30e2-5aba-840d-7905597002f7 | note | – – – – – – – – –
bb638971-8de7-5b83-a139-01a79b71c691 | note | RESPONSIBILITY: Fulton Hogan Engineer
572a8e78-e16d-5f09-b0cd-6d49a0e935cf | note | – – – – – – – – –
5abb1941-da2c-5861-bb51-10776769e729 | textbox | DATE:
9b0cad6e-a5d1-45a0-b1c4-0af4c94088a4 | checkpoint | 1.2 Implementation of all measures and controls
0c73006f-2171-5f13-8e75-af39e9451324 | note | FREQUENCY: Prior to commencing any activity
48c6f006-f7d4-57ae-9169-64036584104c | note | – – – – – – – – –
db30c66d-9b03-55e2-8fd0-49c81aa634fa | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
0e5b7d26-0456-59d5-aa1d-d350b7909ded | note | – – – – – – – – –
ea979269-855e-5d61-8c31-93defbcadb3c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
2bb76f68-b5a5-53dc-a019-6f0c325dc257 | note | – – – – – – – – –
ff0a736e-cf31-5f75-84c3-90ef359b193d | note | INSPECTION/TEST METHOD: Visual Inspection
036e5182-ae23-5ada-92c4-b812842c0a72 | note | – – – – – – – – –
6d4bc889-2df9-52f1-b3df-66d87db0aa9b | note | RECORD OF CONFORMITY: This ITP signed off
bad3a163-9635-5774-99f7-a3a2fb545707 | note | – – – – – – – – –
50a3cc96-050f-5cd9-bd0d-ada92a712982 | note | HP*
ef61a32d-a231-512e-b491-dedcd0c227cd | note | – – – – – – – – –
03e3e14d-2f87-5273-91ed-600a1dc081d5 | note | RESPONSIBILITY: Fulton Hogan Engineer
41ec1505-2c42-5a27-bb89-32604800520f | note | – – – – – – – – –
3510f2fe-8b18-5c80-8b30-7f212bd7ed29 | textbox | DATE:
51127dad-de18-408a-b4b8-8c4bd7cead89 | checkpoint | 1.3 Materials
cd71f4d7-f62a-5521-909e-683d75311c6f | note | FREQUENCY: Per Batch
0153130f-8cfc-5fd4-8fe2-c26e3d0f667f | note | – – – – – – – – –
89cbbdc6-5627-5fa3-abb7-de1601ef85a0 | note | ACCEPTANCE CRITERIA:
477fe3bc-18c4-5c50-8a8e-77ecbab99503 | note | • Electrical supply conduit to be Orange
0187fab5-714c-5479-9541-206fb528cfdf | note | • Heavy Duty 100mm diameter UPVC
31a6bd62-579b-5e79-b740-9ef6d5e62d9b | note | • Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw
e17d7cc9-f5ca-55bb-9df5-8e91e376ff4b | note | • All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
64f2cdd2-bdae-557f-aad7-8c8429459ae3 | note | – – – – – – – – –
695bf958-fdf2-568a-a789-be08fcfd8844 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4AS 2053
24a7b7e4-fcad-5cca-9900-97f1548d53d1 | note | – – – – – – – – –
f76b0ca7-4bf5-5269-b265-69d34d90254a | note | INSPECTION/TEST METHOD: Verify
7c1d99d0-5b12-5841-9d20-78cee620a623 | note | – – – – – – – – –
6c41a7b2-6e51-5498-ba67-cad5a1b5f70c | note | RECORD OF CONFORMITY: This ITP signed
cb1bd67e-e666-5b47-aec4-388458575134 | note | – – – – – – – – –
a4ec63bf-b7cf-5bf3-a7ae-33cca2f6165f | note | HP*
30155774-56bb-5ba4-9698-b59146ab0e88 | note | – – – – – – – – –
dc835441-3994-5f4b-9d73-a8281cf2e1c4 | note | RESPONSIBILITY: Fulton Hogan Engineer
7ba94bd3-ec08-5458-a7ba-3f42940ab2f0 | note | – – – – – – – – –
d567f42e-33df-5466-af48-b2c30a899760 | textbox | DATE:
1033c23c-c402-49ae-b26d-ec1c7717fbb5 | section | 2 - Construction Works
5ba0b3f0-ba25-4425-9842-d89ba5ecff7b | checkpoint | 2.1 Survey set-out
f4301acb-d642-58c3-9c91-54e6dda108bf | note | FREQUENCY: As required
f0ffa06c-a853-5bcf-9351-5a848de66a1a | note | – – – – – – – – –
c9e86ae9-3028-5f15-91c5-41e83d3d343c | note | ACCEPTANCE CRITERIA:
3a1642b3-eb16-54a4-8bef-8a45a510c6c1 | note | • Work is set out in accordance with drawings.
34f1a8d2-dc7e-58c9-87a8-3f5712644582 | note | • Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
e2f42362-d75e-549d-bd4a-184d106d27d0 | note | – – – – – – – – –
c501af14-d912-57c5-9578-d28bcac86dc4 | note | REFERENCE DOCUMENTS: Work procedure
38dfebf4-110b-5c12-a920-fb0530ae2b78 | note | – – – – – – – – –
37426b98-c29d-5140-aaf8-33c6a9350155 | note | INSPECTION/TEST METHOD: Verify
96ec9810-c3b2-5591-91e0-2409749f761c | note | – – – – – – – – –
0444e3f3-2ca7-5856-bdfd-0454c0f20988 | note | RECORD OF CONFORMITY: This ITP signed
82d75cdb-0b7a-5361-b6e5-402a52c5ee78 | note | – – – – – – – – –
a8e1d7fc-d755-5fc0-b698-932d2cb53031 | note | HP*
418b9a39-9e60-545e-ab09-9acd4fb463d4 | note | – – – – – – – – –
60e27b74-8d7f-50a1-9694-994558cbde7b | note | RESPONSIBILITY: Fulton Hogan Engineer
3aa11815-3366-512b-bb38-d1af10c7144f | note | – – – – – – – – –
4a9e3882-895f-517a-b27f-0902b2a0e8bc | textbox | DATE:
e149b514-72a0-41c2-bc41-44211afed155 | checkpoint | 2.2 Excavation and Trenching
d257f2e6-1587-54ce-b5a0-e39009ff8322 | note | FREQUENCY: Prior to Installation
62c2ba10-d8e4-5bcf-938c-7ece00f8b3f3 | note | – – – – – – – – –
4ca53c3d-c27e-5042-9cb5-a1d5afcdb073 | note | ACCEPTANCE CRITERIA:
65eb0d15-fb8e-518a-a50c-9181451805e3 | note | • Minimum cover for underground conduits shall be 600mm
617eee52-1727-5330-a011-7de41c7b7a95 | note | • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
7c9fcdfe-8631-5290-9ac2-4cdf29b46ba0 | note | • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
ccb7df12-7540-5e66-8287-e312926a46ce | note | – – – – – – – – –
137dc1b8-5945-5b7f-85a8-c2bfcf127aaf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
955c4e8e-7cf2-53df-ba1c-75e68f52b5ed | note | – – – – – – – – –
551c3555-25ba-52c0-a31b-a904f3b38f4e | note | INSPECTION/TEST METHOD: Verify
f77b2d65-e5c3-597b-b05d-09b186d3a3ea | note | – – – – – – – – –
3d12bbcf-bf4e-5aee-8b23-40657afa4424 | note | RECORD OF CONFORMITY: This ITP signed
711eb98e-376d-5e94-9f0d-bc3876053353 | note | – – – – – – – – –
6df89054-41bc-5053-b592-6943742e5374 | note | WP
57613063-26a3-5a63-94b6-dd349014299a | note | – – – – – – – – –
9628fea1-0b93-57d6-9347-e9177e8555da | note | RESPONSIBILITY: Fulton Hogan Engineer
192b8f5f-1dbb-510b-8208-af071770e567 | note | – – – – – – – – –
9b6da768-b289-544b-9893-e07ad0d1c3bb | textbox | DATE:
7225e839-da4a-45a2-948a-60d6e7fb480b | checkpoint | 2.3 Installation of Conduits and pits
c832c8ba-8e13-5576-b77e-7d707229268e | note | FREQUENCY: Each Lot
f54ed3d5-08e1-5c68-8b27-bdcc2e1e83f2 | note | – – – – – – – – –
c099495d-eafe-56ac-8c2f-54a3d87f2750 | note | ACCEPTANCE CRITERIA:
8bbddfbc-3ff5-5233-93c7-ddab287bdaab | note | • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
1dda2e31-5566-53b8-b178-5c4c90ba0066 | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
b77f9ef5-236e-5f41-b82a-107c9789d2df | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
25cb1706-cb3c-5884-826d-79b4c50b6512 | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
63a37aaf-930b-52fd-9b3f-71e527be293f | note | • Conduits shall not be subject to construction loadings
44ac61d9-f53d-58e7-bfcc-cf22ed64914e | note | • Pits shall be constructed as to allow for class D rated covers
d7ca8d42-7294-50a1-bec9-a00e641e6864 | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
86a38c3b-55b5-5563-a9b5-85eb1a3ca008 | note | • Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mmbeyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
1693d599-26a2-5db9-bcea-e91a55976d89 | note | • Conduits shal be placed a minimum of 100mm above pit floor
4a76aea0-ab91-5d46-97d4-b73b3d27525d | note | • Conduits installed for future connections shall be installed to the track Margin
6de82dee-719c-50e1-adff-3adc0e3a5481 | note | • 100mm of concrete around and under pit lid
01f30a28-80ae-5e15-bccb-a29f07bcb157 | note | – – – – – – – – –
f6c9a846-0382-5487-84d3-383deda05fa8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
36d6a885-397e-5fb9-a339-f7035b281552 | note | – – – – – – – – –
73ca6c71-6ee6-5294-9efa-9ecd1ef6bd36 | note | INSPECTION/TEST METHOD: Visual inspection
9bc8e6d0-7c6a-5f70-a780-feeb7dd8096f | note | – – – – – – – – –
b15e974f-0393-5c44-a5a9-c666a7888569 | note | RECORD OF CONFORMITY: This ITP signed
2ca4db01-7b40-535c-9aa9-043c783907e2 | note | – – – – – – – – –
aacf2caa-b99c-581d-8649-036b5c2f9696 | note | WP
44fd1db8-7c67-5fc3-961e-38e3c24eeb55 | note | – – – – – – – – –
342950e6-b2ad-50ad-81a3-93406401b868 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
298cc5bb-75e9-5a63-92a4-0a5677306da1 | note | – – – – – – – – –
50280934-0bb4-5a28-bae4-e322d738a3ee | textbox | DATE:
037ee90b-47cd-42e5-b832-d64d6cf4d41b | checkpoint | 2.4 Inspection of conduit installation
680d57be-c1a2-5bee-bc0d-b26d7dea7497 | note | FREQUENCY: Each Lot
f25ccc85-43fe-5018-b88b-42c321c569c0 | note | – – – – – – – – –
4ab9713a-916a-5125-b601-5df2b9f9db40 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
69585fbd-0c76-5877-bb5c-a8e6ee38682e | note | – – – – – – – – –
50502878-4ef2-51e2-86aa-35a7391036bc | note | REFERENCE DOCUMENTS: Work procedure
82cb2f1c-a474-5514-8373-28d9b6f57f26 | note | – – – – – – – – –
77266c6f-dbf5-53db-8d4f-02ade1712c3e | note | INSPECTION/TEST METHOD: Visual Inspection
1174c2c3-b503-5bd2-9eaa-e678d5667da2 | note | – – – – – – – – –
6a65f469-134c-52c1-9015-f83457acf783 | note | RECORD OF CONFORMITY: This ITP Signed
84f9b3f3-e841-5b30-bb35-8ab67b885431 | note | – – – – – – – – –
f9e33d29-3934-5a49-8280-75a3730388fc | note | HP*
f8e3e43f-4574-54c0-8c25-d94fbd7f8d11 | note | – – – – – – – – –
44ea229e-2696-590a-8891-6c3ec09cf3e1 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
04d6b968-583e-559c-b11f-603f181312eb | note | – – – – – – – – –
e58453ef-ea0a-56a5-82e5-d0d577fd9df4 | textbox | DATE:
0460ee88-5f82-4f99-8d42-74966ffdabe9 | checkpoint | 2.5 Back Fill of Trenches
38e9b78a-16b7-5fde-af32-b7769317baad | note | FREQUENCY: Each Lot
7356c77b-5521-5252-8d0c-d4f7ac90a21a | note | – – – – – – – – –
884f29c0-fcad-5d0b-9059-07402f3ad160 | note | ACCEPTANCE CRITERIA:
6ff2836d-94f8-52fb-8f48-92a0277edb60 | note | • Backfilling (Only to be used for road crossing trenches)
05b9fd81-93a7-5f3b-9473-b7510d25335c | note | – conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
c4e3e82a-858d-5339-bec9-0b66c61615f6 | note | – – – – – – – – –
cb73b548-e6f7-5136-9398-1cd7b2baa95f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
aeb1bf70-77ef-53b8-ab54-2a2610196f36 | note | – – – – – – – – –
b2852812-e46c-58d7-bc73-e4fb38df8f1f | note | INSPECTION/TEST METHOD: Verify
10385264-54e4-598b-8bd1-7471522ac429 | note | – – – – – – – – –
16e3ab25-2e01-53a0-ac5c-89c16803e07c | note | RECORD OF CONFORMITY: This ITP signed
d1890ee5-ab4f-5b1a-8e9e-37fef6e32e0d | note | – – – – – – – – –
9e89c5b6-a8fc-5ba9-a9d7-ba483bb284ea | note | WP
db02d89c-fb1e-5257-8345-2535f909c134 | note | – – – – – – – – –
c3c2a196-db26-574b-9c63-29c835e28373 | note | RESPONSIBILITY: Fulton Hogan Engineer
ad81dc4e-f732-5d75-95b6-4c95aa6df20d | note | – – – – – – – – –
fa22bae2-4241-5ca1-aad0-5315d4ef74da | textbox | DATE:
7c08edda-a5ad-4374-8060-88d932440622 | checkpoint | 2.6 Installation of Draw Cords
c267afaa-f569-5831-b99c-9af873e02a53 | note | FREQUENCY: Each Lot
9ebcfb0e-2255-5099-8e5c-6e1246cb6b1b | note | – – – – – – – – –
14ae882d-8c13-517a-abf4-9d30b6d45ae9 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
42cdfe92-14a8-54ac-90cc-172c8124bcb2 | note | – – – – – – – – –
207eecf7-9b02-50bc-82f9-f09b75523e68 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
80927d31-120c-58c2-8f5f-a05bf2fe37ee | note | – – – – – – – – –
44b04b8f-37b1-5cf7-9709-4e339847763b | note | INSPECTION/TEST METHOD: Verify
f076534e-7551-53c4-9495-e764b10cbf85 | note | – – – – – – – – –
01a3ef3d-2436-5787-ac79-7c0574dcdc79 | note | RECORD OF CONFORMITY: This ITP signed
3a372057-41c5-533e-b3bc-4b3c034010b2 | note | – – – – – – – – –
4ca78694-0202-5ed5-a302-b5be118da294 | note | WP
048d396d-06eb-5834-ade5-ec9075f5c9b6 | note | – – – – – – – – –
0259af1f-8864-555e-b3a6-f5844ebef30e | note | RESPONSIBILITY: Fulton Hogan Engineer
b2a7eeeb-024b-5a72-8393-63e6ef041c21 | note | – – – – – – – – –
4d65725d-06e0-5a21-9c13-792fcc4ff712 | textbox | DATE:
5d7709fb-6c38-465e-848f-7c16d40450d5 | checkpoint | 2.7 Compaction
d7d9a326-831e-5775-b3da-348c1bffcae0 | note | FREQUENCY: Each Lot
8c043268-8800-5c34-8984-be133e90aeb7 | note | – – – – – – – – –
9807efd3-112e-593f-b589-1dff7bb37bb2 | note | ACCEPTANCE CRITERIA: Bedding and backfill material to be compacted using mechanical plant During compaction optimum moisture content of bedding and select fill is within 85% to 115%
bb1ee45b-6225-509e-8a67-aee3cdd30de3 | note | – – – – – – – – –
c34562e0-142d-5685-a626-26cc94b2c679 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
c48225ca-f862-5356-b502-2377bc493276 | note | – – – – – – – – –
aee163b4-25cc-5e10-b899-03b7c19b3c93 | note | INSPECTION/TEST METHOD: Verify
ae3b21b5-7dc4-5579-98e7-335ee7cb0a7a | note | – – – – – – – – –
0d3c485b-a2a1-54f3-84df-3308a9f41e1e | note | RECORD OF CONFORMITY: This ITP signed
11ad3cf0-f0a2-583e-b07e-b19b067548c5 | note | – – – – – – – – –
2162a43f-01ce-5819-861f-91f4860501a9 | note | IP
c13a94b2-e854-53b0-a7c6-a9f4cc701ad2 | note | – – – – – – – – –
898fb964-89ac-50e9-abb3-f20b564b9095 | note | RESPONSIBILITY: Fulton Hogan Engineer
07793e92-757e-5cbd-ab0b-8a9b054dd34c | note | – – – – – – – – –
3eaea696-d67b-5800-82ff-271f3f19d4a6 | textbox | DATE:
81757977-3546-4c59-9538-3d82d7ecce0b | checkpoint | 2.8 Feeder Pits & Pit Lids
c50215c1-1617-561d-bb94-f0fd734cde58 | note | FREQUENCY: Each Lot
5b88014e-7690-59ba-8ff6-426787d19099 | note | – – – – – – – – –
43ef3cfd-e862-5fbe-b64d-e4e707668cac | note | ACCEPTANCE CRITERIA:
71c052cd-dd63-5c3a-80cb-1054046c039f | note | • Feeder Pits constructed and installed as per drawings
7b82e055-38aa-5ef6-be3a-fb7831423ff8 | note | • All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
222acd19-d724-5a6d-aa9e-6d288a7e831b | note | • Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
ca0a7b13-836d-5154-ab69-03806ad53bbb | note | • Gatic pit lids shall be filled with structural grade concrete
923e726b-4bff-5e28-a5a7-4e892b7ee2dc | note | – – – – – – – – –
f82b7bf3-9e96-5151-b848-2e2cce6ad230 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
11a77176-2d82-5102-ab4e-7ccf1eb820e7 | note | – – – – – – – – –
0cd1206e-f5b9-5de5-a0fa-7f4eb70a1b28 | note | INSPECTION/TEST METHOD: Verify
77e5ffd8-ab26-5b3e-b311-64ad1bcaeb87 | note | – – – – – – – – –
0c6f21e3-2390-5f81-9378-5a8f9999ae3f | note | RECORD OF CONFORMITY: This ITP signed
d5e81153-3b23-5dc8-ba0d-5a3319996dca | note | – – – – – – – – –
b0fdb187-67b6-59c7-9072-db596abf1337 | note | WP
0ab9efc3-848f-533b-82e5-3c01cd4ee1c1 | note | – – – – – – – – –
89ae9fbd-0fc5-5489-b2a4-1c3553c6b966 | note | RESPONSIBILITY: Fulton Hogan Engineer
78941e4d-fea4-5c60-96b5-757a808a300a | note | – – – – – – – – –
79ade2eb-391a-5102-8175-d1d419475791 | textbox | DATE:
78da752a-3eb2-409b-ad7c-09e0da86c9fe | checkpoint | Final Inspection
4889b1e6-cdf7-5283-836b-dff8808bd0b4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4adbe82e-a0db-58fb-8417-21fd7ca999a6 | textbox | Print Name:
a6714e63-3953-5b7b-9188-a6f235fc564a | textbox | Position:
81671e29-e7a6-5830-b391-36e62c60ca03 | textbox | Date:
5c9dd9ae-5d73-40a9-950e-78a5209e1f91 | checklist | ITP-004a - Class 2 Base Course Placement Rev2 | itp | ITP-004a - Class 2 Base Course Placement
a58d392b-8507-40de-9d14-3b67c45a49a7 | section | 1 - Preliminary Works
a0bc2d42-8bdf-4ec6-9419-cfdd9492eb6b | checkpoint | 1.1 Check for correct documentation
cfc7655d-31c0-5ef5-9b85-4c1b13e35450 | note | FREQUENCY: Prior to commencing any activity
3ae55c86-6f33-59a9-8641-bd4b1c677306 | note | – – – – – – – – –
877f7fa9-4440-5784-a2c8-ff7bac9f47b6 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
684638b6-6603-50fa-8f79-e44a2a68e036 | note | – – – – – – – – –
f8b78a94-e4ac-588c-ad41-0a17b533ea6b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2085bd3d-b21d-52a7-b2ee-988f01c7490d | note | – – – – – – – – –
8fbb0231-0f9f-5ada-97dd-09062d57d0cc | note | INSPECTION/TEST METHOD: Visual inspection
06a67814-4295-5435-b429-d6bde7ff16aa | note | – – – – – – – – –
3c2e8f40-9c97-5315-9a51-b2f35bc9a093 | note | RECORD OF CONFORMITY: This ITP signed
fe58df24-a6b9-58f5-a1c3-afe8e634c5f1 | note | – – – – – – – – –
b244c56e-594d-5115-9d53-662078c07aff | note | HP*
43724fc3-8592-56cf-992e-64eb814f76e2 | note | – – – – – – – – –
69edf44d-eea9-5f41-927a-da07444e7b58 | note | RESPONSIBILITY: FH Engineer
35f11678-3f4b-5c27-969a-545ba095713b | note | – – – – – – – – –
fd19d9fc-3881-54d1-b8a9-b70957a4ef5e | textbox | DATE:
8ba63960-72ad-4383-bedc-6a5e1372d6dc | checkpoint | 1.2 Implementation of all measures and controls
81499de5-c2ea-54ff-99a6-394c122a494c | note | FREQUENCY: Prior to commencing any activity
b545ba73-edb6-5e5c-91fc-f6d5f4c29efb | note | – – – – – – – – –
f033dcb3-ab7a-5857-9b95-9f5491bff488 | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
685605bb-d8bd-5cdb-9d11-21cbd0e992ef | note | – – – – – – – – –
99004b8b-70de-5e30-b481-efc1041a83f0 | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
d0641372-2309-590b-b73b-b01d78330f62 | note | – – – – – – – – –
29e229c9-c2c9-544b-8d0c-b05f2a97423e | note | INSPECTION/TEST METHOD: Verify
f9fa70d2-b7db-589a-92c6-13c5a904e057 | note | – – – – – – – – –
f0511825-d3d7-5f4f-b8fe-9ad6cfbfe248 | note | RECORD OF CONFORMITY: This ITP signed
d2aaba3b-cc22-5446-92d6-d178dcace77e | note | – – – – – – – – –
41f03478-21c6-5aef-be12-bc84ae2bafd3 | note | HP*
89b6c30f-fcaa-57a7-b706-5283ada39b72 | note | – – – – – – – – –
03436fbc-38f6-558e-9495-f3e9bd2c4017 | note | RESPONSIBILITY: FH Engineer
3be20bcb-7b36-5173-a732-edd37d1cd01f | note | – – – – – – – – –
1b6845b7-a41d-5132-951b-8b9701356648 | textbox | DATE:
87d949dc-2830-48c0-b747-8a917df29c15 | checkpoint | 1.3 Material Compliance
ebc0ad7e-0456-551e-9108-304475bfac37 | note | FREQUENCY: Prior to commencing any activity
e888974f-a8df-52be-a4c2-88362e9fce39 | note | – – – – – – – – –
1a030818-daf6-5f04-848e-55bf6e19538e | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
739e1e36-776d-5247-a3af-85ce2c78172e | note | – – – – – – – – –
28a65559-40f7-5ad3-aafa-c956e08804c7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
e9e40033-37b2-59aa-9769-0a91127eda62 | note | – – – – – – – – –
bf9ca5f6-e30c-535b-ba40-7ce54b6e4a11 | note | INSPECTION/TEST METHOD: Document Review
bf7d58c9-e186-5fd6-885b-b9ae98bc48f8 | note | – – – – – – – – –
6641289e-a7c0-5286-8c12-94256845e0a2 | note | RECORD OF CONFORMITY: Test Reports from supplier
343d35b6-603a-557e-ad94-bf3b0656356e | note | – – – – – – – – –
33e4dd9c-9921-59e2-9e88-06b30e17a1e6 | note | HP*
99dc89da-6be9-57e1-9e39-383a7d21ce59 | note | – – – – – – – – –
ebcda4f4-0f98-51b0-9118-753cf1627287 | note | RESPONSIBILITY: FH Engineer
74a7b333-b168-51c2-b844-81ad3d8ded13 | note | – – – – – – – – –
b30d4ba7-737b-5463-81db-08d011866f06 | textbox | DATE:
c172d805-d207-43d4-aed3-7c9670e3552f | section | 2 - Construction Works
c42f5f2d-b785-411e-8046-58394baa62b5 | checkpoint | 2.1 Sub Base
1931267d-5f09-547f-b16c-5da4aba88d9b | note | FREQUENCY: Each Lot
810c323a-0d74-5a4d-8a9c-06996ff2ca1b | note | – – – – – – – – –
12dc0943-5075-5493-98ec-9a0913072a6d | note | ACCEPTANCE CRITERIA:
48c7c843-5094-5515-b8cc-3eb2160e7b27 | note | • Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
256db458-d0da-582d-8e25-aaed8a6e205f | note | • ITP-001 HP for subgrade inspection signed off
fb24cde3-94a9-5c78-9bdf-fd2099b16e18 | note | – – – – – – – – –
b03c7a17-7d05-569d-99c2-6439ed0c4630 | note | REFERENCE DOCUMENTS: VicRoads 173.03
7f1b2265-b3f2-55be-be40-546d18ef6fbd | note | – – – – – – – – –
6da3be09-e99e-52cf-a3b3-c5e6a1efaf31 | note | INSPECTION/TEST METHOD: Inspection / Test Method
9cef3515-523e-56fd-9389-f29a0a525d72 | note | – – – – – – – – –
03092c90-505a-5fa3-9c1b-dab4a78237a0 | note | RECORD OF CONFORMITY: This ITP signed
8d3264ea-e79b-578e-91f0-9899a1f973f4 | note | – – – – – – – – –
983dc9a8-2f1a-55ed-99f7-ca07a0918aea | note | HP*
c5f73368-7e19-5998-87a2-189d61bcb2b4 | note | – – – – – – – – –
94dedd20-06df-5e6b-a341-25b18c15719e | note | RESPONSIBILITY: Fulton Hogan Engineer
bb70e2c3-abf5-5ab3-a534-081a49bee1a1 | note | – – – – – – – – –
41ad4f56-063a-58ac-acc0-296ceaf1b53e | textbox | DATE:
a1a5d84c-f77d-4e4e-ae09-f4a9321a5261 | checkpoint | 2.2 Spreading material
84ac2692-cdef-5671-9456-e16195efb4bd | note | FREQUENCY: Each lot
4af64b69-cd44-5054-86e3-a616dc6b34a4 | note | – – – – – – – – –
ceff4e8b-e578-54d7-b1c8-3b6f36615167 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
104a328e-9407-50bf-9794-1aea8867db89 | note | – – – – – – – – –
3eae7764-84fd-5b6c-b1d2-126190303569 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
62aa53d4-6614-5541-9fb8-ec55bd6485d9 | note | – – – – – – – – –
c34e6c29-1c2b-519c-9410-96334de72c6c | note | INSPECTION/TEST METHOD: Visual Inspection
a9025305-d923-55ed-89d1-0a892ebc8a34 | note | – – – – – – – – –
ac44c65a-3739-5c7c-bc54-763cdfc87946 | note | RECORD OF CONFORMITY: This ITP signed off
08d6b27e-d4b3-52bb-9c79-aa5615d5301b | note | – – – – – – – – –
c7644079-7a2e-5d70-9010-a355eb42c336 | note | IP
ffff7f56-cddf-5c28-a347-165c6d898ace | note | – – – – – – – – –
516c3949-346f-595e-9d89-48ba7a4c3687 | note | RESPONSIBILITY: FH Engineer
29991042-242f-5ecf-a1f1-e1f562b099ac | note | – – – – – – – – –
5156023a-c1c9-5204-bdf4-53c2d98ad483 | textbox | DATE:
572e7028-e482-4943-ad91-e52782625161 | checkpoint | 2.3 Compaction
673e7657-0522-55cd-a622-dc41073ef5dd | note | FREQUENCY: Each lot
4ac4688e-6c99-5b67-80bb-df80f04a664a | note | – – – – – – – – –
c8f0e426-c1dc-5ec0-9fc3-e492f4cb10c9 | note | ACCEPTANCE CRITERIA:
a509639f-6459-5ddb-b58e-5c9952d38def | note | • Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
bb9dbfae-479a-520a-8638-eaac678a6126 | note | • Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
5960acb8-3e6c-505b-a1ac-336eaf54b8ef | note | • Compaction testing shall be carried out once per days production and shall comprise of three samples
21c01599-7301-5bbd-8b19-64c7d2a69402 | note | – – – – – – – – –
86fce273-ce6e-52b3-aaa2-0d6835f03983 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
b7146ba0-719b-5e78-8836-a5d44e6729d3 | note | – – – – – – – – –
dfd3fdd1-1332-55f5-8912-2467ce47fdd5 | note | INSPECTION/TEST METHOD: Visual Inspection
95ce237b-fd77-5fc6-ada3-85b21d9d7c97 | note | – – – – – – – – –
9ebae320-ea6d-5604-a88e-aadcff2b330e | note | RECORD OF CONFORMITY: Test Results
dc73d67b-51fb-5a71-8449-4e82106758ca | note | – – – – – – – – –
4b82f3d3-37bd-57f5-90f0-c99c7edbed38 | note | TP
a3ed372e-44b8-5906-8cff-2f0d536f6254 | note | – – – – – – – – –
944594dd-90fe-5726-b182-d9c206975c1f | note | RESPONSIBILITY: FH Engineer
083225b5-dab3-59d7-b4af-e13de4dd0d34 | note | – – – – – – – – –
21f839e9-dbe8-50d9-905e-787b53f5424e | textbox | DATE:
e6117e45-8595-44e6-ae79-c6b1c18d4864 | checkpoint | 2.4 Level Checking and Conformance
d56a8dd0-cbc5-5337-b8d8-43e4f2d86673 | note | FREQUENCY: –
003f33f1-742f-5a67-9c65-4e17423df627 | note | – – – – – – – – –
5575175d-22d6-5214-a176-e98f03bdc4cd | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
d22639ec-0cf9-5532-9694-b4d4c96b01b3 | note | – – – – – – – – –
e611c6f5-4751-5c2d-b9ad-a8cdd69b68b0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
727a48e4-5907-5659-b7d2-ac06cf30de15 | note | – – – – – – – – –
985d9c8a-91ca-5086-a6a3-09396f04505a | note | INSPECTION/TEST METHOD: Verify
1f3732f9-6dad-5e5a-860d-fedeea1b0261 | note | – – – – – – – – –
cd98ffe2-3de9-57d7-aaf0-52996d1b5ea5 | note | RECORD OF CONFORMITY: This ITP signed off
1e8c2e7d-28ef-532e-89c8-c3a77e0164d9 | note | – – – – – – – – –
7a325358-5e60-5ce0-8540-8ae1c855f6ff | note | IP
efbdd9e2-3e22-53ab-b576-df1066b105d0 | note | – – – – – – – – –
aa6504a8-6c3d-55cd-beab-9345ff21957b | note | RESPONSIBILITY: FH Engineer
f60c53a1-28e6-5186-810b-b1c9e9c2844f | note | – – – – – – – – –
f6cc034f-6986-54d4-8344-9de2cb47192e | textbox | DATE:
f182fe4e-a413-4ec4-82d3-d06dc37b9fbb | checkpoint | 2.5 Finished surface
4693e9a1-a7ce-5bfc-8da9-072d7c390a86 | note | FREQUENCY: Each lot
9f0c56e9-0d68-5d38-8a7d-b941fb85a1db | note | – – – – – – – – –
4d20fba5-5d41-5dcd-9a95-4ac8e377977d | note | ACCEPTANCE CRITERIA:
925c6e80-b4c8-5971-a3fd-20af26a5da0e | note | • Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
a199d8d7-19d3-5b31-a4fc-e1592c050bee | note | • Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
8dcf7954-23ec-5ee7-87af-2c65145c780c | note | – – – – – – – – –
6b76877c-f125-582a-9763-1d9b46a8f714 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.2.8, Contract drawings
7527fc89-ceeb-56ad-bbb8-3ddbf84199da | note | – – – – – – – – –
a6146de9-63ab-5fd8-b760-dcb3f722a84b | note | INSPECTION/TEST METHOD: Visual inspection
6336d428-d9f7-562f-9268-e64cba7f7f2c | note | – – – – – – – – –
c00f6a9f-01d2-5e18-ab68-4473fb53beb9 | note | RECORD OF CONFORMITY: This ITP signed off
6b637412-7433-582f-8209-4844621b5c08 | note | – – – – – – – – –
ec355f4a-79fe-55d0-bcd5-fcceb0d0e493 | note | SCP
92409896-f78a-596d-857d-306591373de7 | note | – – – – – – – – –
aed36dce-5bc9-5fe9-9e63-ed0dca903c81 | note | RESPONSIBILITY: Surveyor / FH Engineer
ad5b7c39-d977-5b09-958b-323117971338 | note | – – – – – – – – –
dfe46485-20a0-5e51-b688-aec1711188c8 | textbox | DATE:
93e27ce4-99e1-4d66-9166-5e0ee7344ec8 | checkpoint | Final Inspection
5bc85d36-b360-5cf7-b83b-e172be71d23c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e6de64b2-703b-5106-b870-c404047499c8 | textbox | Print Name:
a0b9fbd1-9a45-56f2-87d0-e2fb12b7ffee | textbox | Position:
ccf506c9-7755-5475-bbb8-b581f86b8f59 | textbox | Date:
a563a155-1a21-45f9-8d21-358c5ace7ef7 | checklist | ITP-005 -Track Drains | itp | ITP-005 -Track Drains
28dc7dd8-264a-4baf-94a8-6c3cca55f804 | section | 1 - Preliminary Works
2ed9b094-7e3d-4e4b-a438-ffa3fd5fd2f5 | checkpoint | 1.1 Check for correct documentation
2a0a260e-6f85-54a1-b1f1-969b5fd32fd0 | note | FREQUENCY: Prior to commencing any activity
7cab29b2-6e3a-5912-af61-2f05d722132c | note | – – – – – – – – –
33e51d44-8297-5ae9-a818-bbafe2bf426d | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent
0f6716f9-e10e-5e93-91ad-2164f657c895 | note | – – – – – – – – –
56fb834a-49d5-59c4-8002-fc1f95cb00d1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
82999cc1-45bf-59c9-87c2-2717e555485c | note | – – – – – – – – –
304930ed-bcea-539e-b8e6-55b6ff33ff22 | note | INSPECTION/TEST METHOD: Visual inspection
b58ebf91-dd54-5d06-b2df-25fe097809ab | note | – – – – – – – – –
6ec65096-2e14-549b-aa84-2b724d3b3705 | note | RECORD OF CONFORMITY: This ITP signed off
dd9e6f38-807c-5547-81a6-42af48c7db26 | note | – – – – – – – – –
1a3b062d-70da-52df-bcd7-7497a61f0ac9 | note | HP*
09f6d359-10c2-508b-a041-da5e54e17cea | note | – – – – – – – – –
b954a024-da7a-5989-90a0-3e1fa0ede1d4 | note | RESPONSIBILITY: Fulton Hogan Engineer
d8841d47-e342-5685-ba41-9149d855f722 | note | – – – – – – – – –
4b8c11da-f012-5919-8e0b-f24482093151 | textbox | DATE:
7e8efe72-068d-49e9-8653-35d95f5b1d04 | checkpoint | 1.3 Materials Check
906c90ea-da5c-593f-bf60-408cfccb9e67 | note | FREQUENCY: Prior to commencing any activity
a7007cc2-5ab1-52e9-952a-e9903b09c8a5 | note | – – – – – – – – –
20eafd1e-d5c3-56db-97b3-0a87e06016a1 | note | ACCEPTANCE CRITERIA:
f8bb0c34-0b1b-5a29-83ec-3d0dbcb7082c | note | • Ensure drainage pipes are of correct classification and are without damage
f33c625d-53e8-5b08-80a2-75b15f8f9e3b | note | • Check triangle drains are of adequate quality, and are design according Ri57A rail profile
56667528-cb83-53f7-ac1b-7c2536921ffc | note | • Ensure lid and j-bolts being used are in accordance with STD T9022
86a468b4-3c91-5234-af26-efac2a857b5f | note | – – – – – – – – –
5061905d-9d55-53a3-b634-c9ebbe7a3f63 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
c4a7c1b0-798a-5294-8d80-05ed0ea34ffa | note | – – – – – – – – –
542479bf-95f8-5fa1-b429-16c4b3a77099 | note | INSPECTION/TEST METHOD: Visual inspection, Inspection Checklist
c7905531-d490-5d24-bbf4-ed62664c5d41 | note | – – – – – – – – –
cb7a08f9-ab79-5a60-b022-4be9e12f4aa9 | note | RECORD OF CONFORMITY: This ITP signed off, Recievable Inspection Checklist
b8834d8a-1846-5840-9403-757ffd03fc68 | note | – – – – – – – – –
bcde4652-4b49-56fe-8e0a-3a1692f04803 | note | HP*
1e147c17-5224-58f4-b8ba-bf1b3ed9fc51 | note | – – – – – – – – –
c84eb8e7-1a88-50f0-a790-3cfd616c7124 | note | RESPONSIBILITY: Fulton Hogan Engineer
eeb488aa-3d12-5d03-a2ea-c71e1f8b065a | note | – – – – – – – – –
415d66c1-303a-5c31-80ef-c7faf3554bd5 | textbox | DATE:
ef9ed69c-d7b7-45f5-88dd-6e7debe8c2c9 | checkpoint | 1.4 Bedding Sand
84dab116-e1ff-5ad1-aa75-9f915b5d9032 | note | FREQUENCY: Prior to commencing any activity
d4f4884e-497c-589e-96cc-7bdf83802834 | note | – – – – – – – – –
2bd41323-99ad-538c-b021-3fe39762ba9c | note | ACCEPTANCE CRITERIA:
48cdd688-0a69-5eb7-82ec-a606456d5a0f | note | • The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following:
d9a59f6e-51c3-512c-ab59-bd97e8974560 | note | • Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities,Consisting of hard durable particles, and well graded.
fe1f32ed-d495-5404-bf76-0d0c5b661544 | note | – – – – – – – – –
aba81991-e612-57e1-86c5-635c65519828 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
4213f298-6033-5e2b-a636-71dba85ded1b | note | – – – – – – – – –
6befffa5-90e7-5588-a927-eba9460a63c8 | note | INSPECTION/TEST METHOD: Visual inspection
900883c6-bce7-5c81-9827-31ee5c606769 | note | – – – – – – – – –
e6f64653-3e60-5ffa-be8a-67f4222e33ee | note | RECORD OF CONFORMITY: This ITP signed off
dcacdd0e-3c4f-5234-b919-fa70907ac1ba | note | – – – – – – – – –
1f5d64e5-5d39-5ef4-a94d-349fde006fd2 | note | HP*
b82a0eec-60cc-54f4-abe4-3a4f875111df | note | – – – – – – – – –
577ea088-0746-5502-8e15-027ca5ce09bb | note | RESPONSIBILITY: Fulton Hogan Engineer
35cdc7c4-cfd5-5bbc-83ec-78985e45bb3e | note | – – – – – – – – –
ee763750-562b-5de5-a5cc-fdedd8845aba | textbox | DATE:
910fd00a-c512-4cf8-ab84-4e9e9220d618 | section | 2 - Construction Works
fa4c2b33-3d57-442b-a957-fa512a32278b | checkpoint | 2.1 Set out drainage
853356a7-92b8-5218-87f7-e87b8bfee7de | note | FREQUENCY: Prior to commencing any activity
cf0bb28e-7e13-51e8-b9ec-f6aa94d7c5fa | note | – – – – – – – – –
c41b2925-f8d2-5312-8d5b-20515c2f21c9 | note | ACCEPTANCE CRITERIA:
83a4a16c-f976-5002-b3ac-a5171040a192 | note | • The position of all drainage lines are to be confirmed with the superintendent
6eb2a5f5-9bb0-586a-9f44-f44326f7347a | note | • Track drain locations are to be identified and based off IFC drawings and sections.
50241dd6-642e-5002-ac1e-1dba21ce8032 | note | – – – – – – – – –
75ed57c2-6252-571a-b0e7-af5f895204ab | note | REFERENCE DOCUMENTS: Design Drawings and Register
b97e27c3-081c-5217-a2d0-266fd65b8d0a | note | – – – – – – – – –
69f4ce93-ea1e-52af-a99d-0a9eda1bf4e8 | note | INSPECTION/TEST METHOD: Visual inspection
e3178044-b2a3-5ad1-8cd6-6de0a293004e | note | – – – – – – – – –
f531681e-e2a3-5f9c-bb53-162909c23ebe | note | RECORD OF CONFORMITY: This ITP signed off
1db8a2d4-e3cc-52f4-81f7-644a93fe14b7 | note | – – – – – – – – –
d772f973-5a24-5b53-a101-454d05f2a4bf | note | HP*
eb2aed3e-3632-54f6-be58-ab514823a04e | note | – – – – – – – – –
51399e3d-3c46-5807-ba7e-de163b685560 | note | RESPONSIBILITY: Fulton Hogan Engineer
28043a20-9626-5494-84de-789e6891d6ad | note | – – – – – – – – –
8112d44c-c88b-5c3d-a177-6f8059e339eb | textbox | DATE:
8299c231-888a-4272-a7c9-81bb40e4d403 | checkpoint | 2.2 Excavation (pipes)
8950d38c-76b7-5c14-9d88-ddc030b68b58 | note | FREQUENCY: Each Trench
852aa655-37f8-5798-a51b-45176e7c7ad8 | note | – – – – – – – – –
1429795c-1eeb-5be8-91a5-8d9fdadc059f | note | ACCEPTANCE CRITERIA:
3fb56a77-318c-532f-b85b-e8ee46e2447c | note | • Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe
4ebbaa4c-c42c-54c7-b109-ebc80719164a | note | • Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
cd2b754f-9623-500e-8cf6-1ca43025b7d5 | note | – – – – – – – – –
b062b583-0b18-5d09-a042-28cf4b43ef64 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
74bdaf62-3c95-57df-ab27-8a455d3c2920 | note | – – – – – – – – –
cd0a65d9-dce0-52d8-870b-7a4aa5dd78cd | note | INSPECTION/TEST METHOD: Visual Inspection
4b5b1ed5-8bc5-5c4e-a3dd-fce582d82b4e | note | – – – – – – – – –
398beb1e-f81e-54dc-949e-a28635ea31a4 | note | RECORD OF CONFORMITY: This ITP signed off
5ae2c492-a716-5429-9f16-1bc9b157c649 | note | – – – – – – – – –
c6185d67-229c-58cb-9145-db87c36af4ee | note | IP
08a02833-d001-5834-8b27-c8658097261c | note | – – – – – – – – –
d1821562-2541-5373-aee7-1f4dd13c4a89 | note | RESPONSIBILITY: Fulton Hogan Engineer
83441b39-3120-5c28-bb09-3e3c48699d2b | note | – – – – – – – – –
64ba9bfa-190a-5b8f-88f5-a570a075c2d2 | textbox | DATE:
255e607e-f341-462b-b452-021c3b2da001 | checkpoint | 2.3 Bedding
88c3073d-04ce-502a-9197-b1132fa421cb | note | FREQUENCY: Each lot
ce99aa1d-5997-53a3-912f-c2c523eb968a | note | – – – – – – – – –
2589139a-7c1d-5317-94b0-9cdc03fdc1b5 | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
a04d773a-b945-5b1d-b4e4-ec674ff28dd3 | note | – – – – – – – – –
204cf9dd-513b-52a4-a1c7-640a2a1d00d8 | note | REFERENCE DOCUMENTS: STD T9021A
2cbd3898-ee50-54ae-9ca4-e442c48000dc | note | – – – – – – – – –
5467c70d-e4a6-5390-80b9-f82d2fd9611a | note | INSPECTION/TEST METHOD: Visual inspection
5e96d665-b4ca-54ef-aea8-b511c3980f98 | note | – – – – – – – – –
1e527b60-b87c-527c-97bf-d857784e4fbc | note | RECORD OF CONFORMITY: This ITP signed off
75aa6469-10b6-59ab-a95c-01bfb7e55dc8 | note | – – – – – – – – –
3fc05fe8-7c31-59ba-9e56-afef071590f3 | note | IP
359fa016-cd53-582d-9168-7362ce8f848c | note | – – – – – – – – –
31027811-b127-5672-b6e8-ac3c565b29b4 | note | RESPONSIBILITY: Fulton Hogan Engineer
d11812df-cef7-5dd6-8152-0fa3e17315ce | note | – – – – – – – – –
e314e674-2629-5c33-bd21-8d5e2deb4e88 | textbox | DATE:
72ce173f-77a8-4d30-b261-c7a426d4d5ff | checkpoint | 2.4 Joining
5c138dab-ca1d-5ac9-a0b1-9bc218860f2b | note | FREQUENCY: Each lot
60937e15-15d1-577f-8ba7-00fd37504052 | note | – – – – – – – – –
624876a9-09a6-5e44-9e9c-ccb7082d79f8 | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
73c1c963-02e0-5c9e-8171-c54d97ef912e | note | – – – – – – – – –
b0fafc96-de50-519f-a749-44b6cb444b97 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
443c8a47-5e92-51e0-98f1-0e19f360dde9 | note | – – – – – – – – –
3a1fc85b-fd08-5174-97d1-b4f00aa6db5c | note | INSPECTION/TEST METHOD: Verify
3e2aa1c5-18c3-55e3-b129-e777124bba4c | note | – – – – – – – – –
04777b75-4fa9-5fc6-a5f4-69dbe409e97a | note | RECORD OF CONFORMITY: This ITP signed off
d32e4060-69f4-53fb-ac53-e5a008612976 | note | – – – – – – – – –
47f35d09-7ff7-5eaa-a30c-ae2f9f586f99 | note | IP
00ad6485-1ae3-5671-a6bf-0567488d8316 | note | – – – – – – – – –
85c9fc51-5e91-5431-a7ba-d7dfeefc7c83 | note | RESPONSIBILITY: Fulton Hogan Engineer
c0d99f2c-1d42-5aff-81e7-6e8cc0fa143a | note | – – – – – – – – –
9c3f1e18-dc23-5a99-b6e8-2d523d3c187c | textbox | DATE:
0ad4a57d-4d96-4fc3-811e-0db2c72500c5 | checkpoint | 2.5 Track Drain Installation
fa567ec2-c404-5998-8677-ef7dca4f8a4e | note | FREQUENCY: Each Lot
23d97caa-06f4-5c95-8225-2fbc7522fdce | note | – – – – – – – – –
585b8830-c34c-5b46-9102-c7c9b3e6a091 | note | ACCEPTANCE CRITERIA:
0fa3b107-ba7d-538f-bd68-430095306a49 | note | • Track drains shall be welded to designated positions, and cleaned of all weld splatter.
44b8d623-5c93-5b15-bd95-b9f2f672cf85 | note | • Weld shall be sealed after installation
25f6c6c9-aa36-5c2e-abb0-3a3d44b900e7 | note | • Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
edb819fb-40e1-5aeb-9d06-02e5f2b1dbd5 | note | – – – – – – – – –
e8e30589-8a5f-530c-a402-cc09989ef5b1 | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
0955441d-da40-54a8-83e9-ab4c16b3314c | note | – – – – – – – – –
7b43a569-19a4-51eb-ab58-507d7a9c7a3f | note | INSPECTION/TEST METHOD: Visual inspection
c45e6438-cb27-50ea-9000-d42e0e2a1823 | note | – – – – – – – – –
9fc9f5b5-4e0c-5ba7-b012-b3f4856f1f8c | note | RECORD OF CONFORMITY: This ITP signed off
7a9f5c6c-250d-5a6f-a956-28ad23fd1fa1 | note | – – – – – – – – –
b19e20c6-21ed-5542-9cb9-27d5282540ff | note | IP
3af31a00-5fdf-5255-9b00-b402f362e47d | note | – – – – – – – – –
f13e9ec9-0eb7-5f19-92ea-61291c57ec08 | note | RESPONSIBILITY: Fulton Hogan Engineer
4059fc62-2a95-5ccf-bbae-f75077052787 | note | – – – – – – – – –
a6bd4a4a-74e5-539e-ad39-903f17514487 | textbox | DATE:
46272b0d-a0d3-4eee-b599-58644dacbb70 | checkpoint | 2.6 Points Drainage
0e03d372-e268-53aa-8d19-1aa9e6327cf6 | note | FREQUENCY: Where required
65baa327-1774-56b9-870a-81ed9e751a3c | note | – – – – – – – – –
f7d685ed-19d0-5722-bca6-3f23169618b6 | note | ACCEPTANCE CRITERIA:
4af86203-361a-5c80-a9bf-6c8cee24b3fa | note | • The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit.
2378823b-00c0-5549-af0b-7350a03c7cad | note | • Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
54d26bba-9fb7-5b37-9bb5-3c71185fb873 | note | – – – – – – – – –
800785e3-b21d-5606-84b5-91514bca3080 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
69749a83-4c42-5338-99f9-a865e476895b | note | – – – – – – – – –
3888db01-39d5-5ce8-8293-48ea687e193c | note | INSPECTION/TEST METHOD: Visual inspection
cb6dc5c1-dc50-555b-b1a1-779c1767e75e | note | – – – – – – – – –
efc5dd61-cd5c-57d2-a0c5-79e1f2a55bab | note | RECORD OF CONFORMITY: This ITP signed off
7c467bf0-8c06-5380-98ba-c5bf89e0a655 | note | – – – – – – – – –
1c09bc8f-dded-5684-a09f-164ed984eb7f | note | IP
781aef2a-d080-5c59-a4cc-b0494e75743c | note | – – – – – – – – –
3858509a-cddb-520c-9ec8-a9ffd2cb7e53 | note | RESPONSIBILITY: Fulton Hogan Engineer
cee8f367-e217-55f1-9bbc-5dcc772a337c | note | – – – – – – – – –
d37fff4d-dc20-58e6-9e7a-06e0c0c04619 | textbox | DATE:
715fd835-37e2-4788-a02d-c536cdfa267d | checkpoint | 2.7 Concrete Pour
bc65749f-5d22-5acf-b46e-78bd14e77465 | note | FREQUENCY: Each Lot
420e28e8-9931-51b6-88e3-d236cc05737f | note | – – – – – – – – –
6159f91a-e058-5999-bd7e-81333448e0f6 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
0daddc1b-091c-53be-ac9c-f2728c07675f | note | – – – – – – – – –
6646ae7a-f64b-55ba-b79d-71bea1993102 | note | REFERENCE DOCUMENTS: STD T9021A
26eb50b4-d0d6-5648-8c50-93a3fa595145 | note | – – – – – – – – –
a6921e60-ce42-5711-9889-89274e2fc93a | note | INSPECTION/TEST METHOD: Visual inspection
79a73bbd-5c2e-5db3-8a33-4a8a940923e1 | note | – – – – – – – – –
26b79637-5ad5-5e52-99c6-061997fdeb83 | note | RECORD OF CONFORMITY: This ITP Signed off
7387b46b-d1dd-57d4-9e04-7829b811c745 | note | – – – – – – – – –
05eada67-20d0-5171-a708-bc0da3b7e2e6 | note | IP
d913d1ec-52b2-5d35-978a-774cda8e7ea4 | note | – – – – – – – – –
bd5cf79e-5cdb-5839-805b-b1545aefa149 | note | RESPONSIBILITY: Fulton Hogan Engineer
dffd6a5a-a302-5b3c-8822-6ab8a557a4de | note | – – – – – – – – –
343c186d-13ae-5f08-a25d-aeaa9673c0df | textbox | DATE:
568099d6-d37d-4100-a6fc-5ce443174c2c | checkpoint | 2.8 Connection to local drainage
0030c7e6-62da-5f04-adbd-d0e3221ee40e | note | FREQUENCY: Each Lot
2e204e38-3f4f-5795-85bf-9a97aa978e16 | note | – – – – – – – – –
e538a49e-be64-51da-9781-6c34d22606c1 | note | ACCEPTANCE CRITERIA:
3ce4c5b2-64c8-5fdb-b24e-53eb6a2dc4bb | note | • Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority.
7f4ea20f-b504-5bac-b679-ce2a283306ff | note | • The minimum pipe size shall be 150 mm.
a3286186-df97-5401-a341-e26e7cf29445 | note | – – – – – – – – –
fcf19655-ceec-5163-aec1-7a0db975991a | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
3145aefa-cd42-5cb5-acfe-62a7b75f9db1 | note | – – – – – – – – –
a0974d67-6578-5657-a2b0-74252a9189b6 | note | INSPECTION/TEST METHOD: Visual inspection
fe3c5939-23a4-5b32-a262-243cb0348b77 | note | – – – – – – – – –
93c019b4-134c-53f3-b6ca-850c377fbf46 | note | RECORD OF CONFORMITY: This ITP Signed off
2694d046-0f85-577a-b8cc-d2b6908bb302 | note | – – – – – – – – –
a8d3c658-952e-5b5d-b4c4-6c996ea2b627 | note | IP
c2fb0093-99cb-5703-936b-e9fae2439e50 | note | – – – – – – – – –
2c0d0166-dd87-57e1-a419-519f73b4db5f | note | RESPONSIBILITY: Fulton Hogan Engineer
49d38fcd-2603-5e1d-a997-7ccdc0a2441b | note | – – – – – – – – –
78f0b8b2-aff0-581b-8ed4-2883b6164769 | textbox | DATE:
f2d50830-b040-477d-b00c-23ff20d32a6f | checkpoint | Final Inspection
de7e82da-bde4-5df6-a0b5-10ae36eab927 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb65f8cc-1c7b-5d1d-8040-42a0d013f749 | textbox | Print Name:
1ce0ef8b-9490-5619-a354-392eff6531f7 | textbox | Position:
cc45c789-89ae-5dd4-9119-ec911347a826 | textbox | Date:
1ab0257c-0850-40e9-9843-d5785dd440b2 | checklist | ITP-006 - Track Placement Rev3 | itp | ITP-006 - Track Placement
24667aaa-d1b7-4d25-9b62-4e0bc150964b | section | 1 - Preliminary Works
9c400344-52c6-40bf-ae01-913f3a4e1f54 | checkpoint | 1.1 Check for Correct Documentation
db8224fe-760d-56e8-be3f-c35ea8bd6134 | note | FREQUENCY: Prior to Commencing Works
acd185c6-f14a-5ace-8f5a-9f149fdbaf4b | note | – – – – – – – – –
9423663b-e936-5294-a2f3-3ac475e8c971 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
0adea5d6-3654-59b8-a393-ab12a5a939f1 | note | – – – – – – – – –
8cfe857e-68ea-5096-8ff8-45a81ebb2f9a | note | REFERENCE DOCUMENTS: Design Drawings and Register
2e3d8538-5f0e-5db0-ad82-afa1fda82c92 | note | – – – – – – – – –
055f4d45-66c5-54ef-9cda-6836c07f498d | note | INSPECTION/TEST METHOD: Visual Inspection
60df6cd4-fc2f-52b7-b50b-118b7b1fd7e2 | note | – – – – – – – – –
b2372165-6cba-5731-abf8-af5f1c863197 | note | RECORD OF CONFORMITY: This ITP Signed Off
4103c3ec-6d38-5e00-a7c4-6d2f68e2cfe2 | note | – – – – – – – – –
02123363-0acd-59ee-9137-113d159cee59 | note | HP*
101209c5-1a44-5824-889e-94bff4688bd6 | note | – – – – – – – – –
6f060038-265e-56a0-861f-b91ac57541bb | note | RESPONSIBILITY: Fulton Hogan Engineer
f7c403b0-eabd-578c-a690-16f33f8377b4 | note | – – – – – – – – –
43adeb5b-d86e-5ad3-b13b-aeda88a4b9db | textbox | DATE:
193e432a-536f-44c3-884a-3963203868d2 | checkpoint | 1.2 Check Materials
a33d4c53-1966-59d5-a266-07e334632c55 | note | FREQUENCY: Prior to Commencing Works
49970f97-418f-50fd-89ba-43a30335feff | note | – – – – – – – – –
bb2e6fb8-a026-5d7b-95ad-76854b956eb4 | note | ACCEPTANCE CRITERIA:
fff18da3-e323-55ba-9ef0-23aa9e6a5374 | note | • Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
b55ad6b1-6a87-5cce-8f85-daa58cf74914 | note | • Check condition of rail sleepers
db4294a7-e1fb-5645-be23-ea9e9add3a6d | note | • Ensure rail jewellery is of sound condition
8f7b080c-e7f1-5e43-8932-3a911dd09af4 | note | – – – – – – – – –
5ababb39-93a8-571e-898b-90b94814edc8 | note | REFERENCE DOCUMENTS: AS 1085
c52bce5e-3415-5e5d-bbc4-6b4129e2c67c | note | – – – – – – – – –
f51ffe29-45a2-51b8-8c6f-4da578e5a6b3 | note | INSPECTION/TEST METHOD: Visual Inspection
8354f33c-afad-54ce-88a7-ecf95503debf | note | – – – – – – – – –
de76202f-68bd-5bca-bebc-00212cfb8d02 | note | RECORD OF CONFORMITY: This ITP Signed Off
bbb1d01f-e052-51da-8595-b2fa046915ac | note | – – – – – – – – –
3d7eb362-050d-5c19-ae55-0950b30216bd | note | HP*
e2515b2e-90e4-5eeb-a774-bdb76e0b60c1 | note | – – – – – – – – –
ff3d44c7-42d6-5789-b2c4-e9b7d7a96aca | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
e903b17d-1f97-52c6-a74f-e574e9d446d8 | note | – – – – – – – – –
73e8a78e-d3b9-58cf-8c05-dcd8acff29c8 | textbox | DATE:
aecea445-dfed-42c3-a1b4-de7166e36fb1 | checkpoint | 1.3 Check Special Works Components
94067da2-367d-503a-af89-dea921692605 | note | FREQUENCY: Prior to Commencing Works
6dd237fe-f8fb-57b6-9733-1abc813b0ed8 | note | – – – – – – – – –
83941dd3-dc82-5358-b210-d34b19cc1275 | note | ACCEPTANCE CRITERIA:
2e8d3510-6927-5946-bf6d-93bff793a30e | note | • Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
75e97d9d-2e85-59f5-b507-a5df256ba356 | note | • Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails.
414b2b05-36d2-592a-b5bc-ea5becacc100 | note | • Superintendent to visit yard from intial inspection of the rail and fabrication plans.
1a9d4c19-7d36-5b9f-8ba0-1a8352227da8 | note | – – – – – – – – –
35c1abb2-75ce-581d-85f5-db5dfca4bc0e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
3a61cc93-744a-5f15-9515-206590dab640 | note | – – – – – – – – –
f094d12f-8c56-5208-b838-f7d38e67b6c2 | note | INSPECTION/TEST METHOD: Verify
72766437-968b-5670-acd9-fb5977db86cc | note | – – – – – – – – –
ff91bfc6-c048-5881-9d18-575874c85f37 | note | RECORD OF CONFORMITY: This ITP Signed Off
cfc09f19-e2c5-5044-90eb-a3b31fecc275 | note | – – – – – – – – –
4f25c9bc-71eb-53bb-84a7-58ae68e6dee6 | note | IP
86dc71f6-d3e8-5030-9848-b7bdb29ca559 | note | – – – – – – – – –
70c0613f-e26f-5594-9625-86e5d3f2581c | note | RESPONSIBILITY: Fulton Hogan Engineer
fd9b31d8-a3f5-5d03-a9cf-43a6186ec4b5 | note | – – – – – – – – –
32a88e8f-4fce-5e8b-8cfb-d245d70b9bf7 | textbox | DATE:
a5606e24-0038-4bd0-b861-5a7366e7015e | checkpoint | 1.4 Check Curved rail
c058526c-5c98-5411-8a56-a2d740193281 | note | FREQUENCY: Prior to Commencing Works
0e730b19-6e60-513b-991e-64a36bb9ad18 | note | – – – – – – – – –
bbd5e121-bab7-5248-91f5-8e022c3f67a1 | note | ACCEPTANCE CRITERIA:
2ebbd81c-f77e-57bb-bc95-6b9af228feb0 | note | • Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
8891fbd4-0b67-569d-b5fc-d09ffa63e667 | note | • Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
b47ae67e-2712-5776-a258-38851824e1a0 | note | – – – – – – – – –
e911eb58-f044-5937-985a-f49f2ce005ed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
ce6c3bf2-ced0-51f2-979b-0a042d47df24 | note | – – – – – – – – –
592300eb-d6bf-5453-baec-33a454cea07f | note | INSPECTION/TEST METHOD: Verify
fe1b774b-77ba-56ba-99ad-d9ebde85adb4 | note | – – – – – – – – –
d6ee1093-f56f-5c36-a439-a41af172a325 | note | RECORD OF CONFORMITY: This ITP Signed Off
f281b0db-d8c4-578b-9f9f-98cc7020f357 | note | – – – – – – – – –
a13a2365-5f7d-5244-a8bd-df7434f4e280 | note | HP*
c9e7a831-a12c-58a4-93b4-612387b82184 | note | – – – – – – – – –
32fefc3e-5e15-5c45-a40d-5dc8b811498e | note | RESPONSIBILITY: Fulton Hogan Engineer
4c218297-b38d-50bf-aab0-85191fa73a59 | note | – – – – – – – – –
ccacca26-b530-5b18-b3e0-ea05bf8a00eb | textbox | DATE:
d8c01044-dd90-44be-bb29-42ba8278bf1a | checkpoint | 1.5 Welders Qualifications
edfec91f-1ea0-5aec-97bd-79fcbf128874 | note | FREQUENCY: Prior to Commencing Works
a29feb93-4b00-57e8-b6db-f577d74809af | note | – – – – – – – – –
ba6d92c1-b3b2-5b5b-83ff-53a4a05687d0 | note | ACCEPTANCE CRITERIA:
a94592f9-da4c-5165-a2f2-292bcde76179 | note | • Welders shall be trained and compliant in Aluminothermic Welding Requirements;
2f9cad02-1224-596e-b9d9-e49e601914d1 | note | ○ TLIW2012 Grind Rails
60d0ad60-d686-5926-bfe4-41e005636176 | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
591a803b-d2a2-5748-9aaa-eefa8371ad0b | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
7c8a2f9d-6101-5049-a08e-669da2f6abd2 | note | – – – – – – – – –
b1a92464-e928-5305-b51d-a98f6f8870a6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
3f882e5e-4e47-5800-abc2-a1d5748ab210 | note | – – – – – – – – –
03542f16-2868-5594-b7d4-9dcabcacfe4d | note | INSPECTION/TEST METHOD: Verify
52e9aa42-9b43-5a15-846d-26cd54e7d33f | note | – – – – – – – – –
f3ffbbd6-1937-5756-a196-921cf681142f | note | RECORD OF CONFORMITY: This ITP Signed Off
f9baa77f-723a-597a-9ec5-ae406f4e7500 | note | – – – – – – – – –
b365a5df-a9ea-5518-82a6-9bb3241cded2 | note | HP*
14371439-703e-56c6-8d9c-de7dd752f014 | note | – – – – – – – – –
7e914d8f-b698-5186-90bf-a9ce64f0772c | note | RESPONSIBILITY: Fulton Hogan Engineer
d5701434-7770-5043-89de-733ca4c7490f | note | – – – – – – – – –
4286c1d7-57a7-548c-88c5-70991556e4a8 | textbox | DATE:
54af46ea-156e-45de-9eb3-a499855d7f10 | checkpoint | 1.6 Ultrasonic Testers Qualifications
3363028e-acec-5dee-88e8-fe30f11a9d9b | note | FREQUENCY: Prior to Commencing Works
8cb88b23-f931-5610-a793-4dcf7bf71432 | note | – – – – – – – – –
932e5319-d770-56a6-8f35-cab15629edb7 | note | ACCEPTANCE CRITERIA:
a6c8458f-b0ca-541c-82ec-56aa38922076 | note | • Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing.
a6bda1e3-a65f-5c6f-b83d-559f1f018293 | note | • Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
a29a99ee-b4c8-5236-91d2-cf7b731f2f17 | note | – – – – – – – – –
90448311-3bc3-5945-9cbc-d51a111df8d1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
cd6f1119-a7bb-5a57-9fd7-009a038559f4 | note | – – – – – – – – –
8777db36-6b6e-5665-923c-d05ab2d1058f | note | INSPECTION/TEST METHOD: Verify
27c9f0a1-12f8-5b26-9ec5-67844ebacf98 | note | – – – – – – – – –
559a73ce-948e-5a92-83d6-534682e95d79 | note | RECORD OF CONFORMITY: This ITP Signed Off
5e51707a-f03d-56e5-a865-d31dfd412d45 | note | – – – – – – – – –
6c095786-6c4a-549c-880c-2cfca1d3be29 | note | HP*
ae701413-4264-5180-80bd-29d27ef17355 | note | – – – – – – – – –
b0e7b29d-8377-5c49-9b81-ce4955221abc | note | RESPONSIBILITY: Fulton Hogan Engineer
8a19b932-3b99-5dd2-951c-3c9ee5e57e71 | note | – – – – – – – – –
7c86e8bb-232b-56fd-a3ff-bfaf2b0b7ce3 | textbox | DATE:
10de851d-eb4d-4d46-8f9e-0fc4f0a1cf20 | section | 2 - Construction Works
e10da0a0-f38f-4d02-a895-424b5d96c307 | checkpoint | 2.1 Installation of Sleeper
1ce74de5-67fc-5aa4-a6e9-f5c4adf264c0 | note | FREQUENCY: Each Lot
a47dfb44-e8ea-5669-86b5-5f3e230f3c55 | note | – – – – – – – – –
db80831e-5ee3-510d-9134-97411297b1b0 | note | ACCEPTANCE CRITERIA:
612e7b95-78a2-50f9-975d-faf46fa6051d | note | • Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
cf3aeee1-b20a-5f3c-be94-c7d8af589f02 | note | • Dual block sleepers shall also comply with the design offsets at each chainage
27441a03-dde2-5417-bbb9-34866704e822 | note | – – – – – – – – –
aa4387e1-01ff-59aa-801f-bcd7b396dad3 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
ef438131-10c7-5d9b-80ee-19beb2bbe224 | note | – – – – – – – – –
421af280-dace-5577-a813-afdbdb145ff6 | note | INSPECTION/TEST METHOD: Visual Inspection
a2de9345-72ee-5e93-a65e-ba7cdad186ac | note | – – – – – – – – –
b56d6101-d15c-5be6-8059-49678a55f52c | note | RECORD OF CONFORMITY: This ITP Signed Off
72304b2d-96a7-5985-b90c-1663727e6a4f | note | – – – – – – – – –
ed9a27b0-9a1d-5888-9bf4-c6a5bf5cac2e | note | IP
f21a0dc6-6c81-5329-9f1f-fcae6edc1002 | note | – – – – – – – – –
a1f91dad-7952-50b0-9bf6-439f2efe63a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
ebeb1000-25d4-57e3-b333-908225ed75e9 | note | – – – – – – – – –
1a419f03-c656-5ff1-a660-5023ddf22fc5 | textbox | DATE:
1c631e1e-578a-43ef-9bb8-9f44fd09889f | checkpoint | 2.2 Placement of Rail
db1d57cf-0e11-5374-80c7-a7ba90d2a275 | note | FREQUENCY: Each Lot
c77f35e3-0e00-58e6-8eea-220354a921a5 | note | – – – – – – – – –
d3f8a0aa-8c67-55e7-929a-5cf2b700bae1 | note | ACCEPTANCE CRITERIA:
4894d7a2-86b0-564b-81a1-86ffa9434541 | note | Ensure rail strings conform to rail plan
f712775d-8d7f-50a1-96c5-b78b606e0aaa | note | • All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
d55813af-cae5-501c-bc0a-6ab2190e63d3 | note | • Bottom of rail and bearing surface shall be clean of foreign materials before laying
670ba4e6-6238-59a1-b025-e19c343112b9 | note | • Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
36079b7d-6d25-545f-832d-6b78d4761da8 | note | • Geometry tolerances as follows:
782b0f96-c951-59d7-9594-bf8026a11248 | note | – Centreline location: +/- 3mm
ee655657-83dd-59fa-917e-fb7c9ec9db5a | note | – Level: +/- 3mm - Line measured (>10m chord): +/- 3mm
541946f4-b7fb-5e46-b071-6072e7bb9314 | note | – Twist (3.5m chord): +/- 2mm
2260fa2e-dd2f-5acc-89ac-e7c7d194f052 | note | – Cant: +/- 3mm
38b7db40-024b-56bf-887a-a6deab3b235e | note | – Gauge (open track): +3mm, -0mm
efddf516-1a37-5eca-82f4-5b7597159fef | note | – Gauge,Turnouts (opposite crossings): +2, -0mm
e52b8cef-b120-5919-adba-e0e37d89bff3 | note | – Gauge, Diamonds and ‘H’ Crossings: +2, -0mm
ea42293a-bed3-5118-b5e9-11f7b95603a6 | note | • Note: Cant shall be applied uniformly over transitions
222ebc9c-937f-5956-aecf-78155f2ec641 | note | – – – – – – – – –
4c6f2b9f-c165-5600-acff-5327e064e8b7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
b438ee1c-6dfb-5349-8410-3fe55ef5c944 | note | – – – – – – – – –
4476a817-b081-5068-a678-14898f87b369 | note | INSPECTION/TEST METHOD: Visual Inspection
98385482-e515-58d1-8545-6aa661d75629 | note | – – – – – – – – –
8a20974e-bd51-5d75-a9db-6eb184b665b4 | note | RECORD OF CONFORMITY: Completion of track charts
4642264d-d3b3-5376-a32f-13636f5db4ac | note | – – – – – – – – –
36f89d78-cc91-5acb-ada4-5f2a70f2ad13 | note | HP*
c17c8ec0-9061-5fec-83b2-1ab8a9b783c0 | note | – – – – – – – – –
a7003db7-c302-538e-9180-23998c856924 | note | RESPONSIBILITY: Fulton Hogan Engineer
694d2dda-c266-5db1-9d6b-9dba7bea64e6 | note | – – – – – – – – –
c66b666f-32f4-5e2b-9510-3d367f0f5136 | textbox | DATE:
21e36e42-f22a-40eb-a09e-e8d1e04982aa | checkpoint | 2.3 Placement of Jewellery
fd7a3ea0-aeeb-5a28-9518-3738346b0f19 | note | FREQUENCY: Each Lot
934abb86-ba4c-578a-b48c-176438cfd8f8 | note | – – – – – – – – –
592104b9-8cc9-5648-b134-6f54d88bc7df | note | ACCEPTANCE CRITERIA:
75e5d90e-452d-5d22-a131-cfad40516ad5 | note | • Each sleeper shall be fastened to track with approved jewellery and rail clips
81949c41-e487-5f95-9517-8ccf6e4b21ff | note | • Clips shall be installed with panpuller or equivalent
7c9790e7-c26a-512e-bc3f-366cffcedf28 | note | • All fasteners shall be sealed as per agreed method with Yarra Trams
8b1a9675-7ed2-5652-8b9b-4ae756739879 | note | – – – – – – – – –
0cd89289-0778-527f-8e99-9e2d27d9941d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
863b22a0-c8d9-5c9a-804f-7852cca9e327 | note | – – – – – – – – –
39fc205c-9506-5761-b65e-8c4518e5f66c | note | INSPECTION/TEST METHOD: Visual Inspection
cdede682-d968-501c-a302-f930a14f3398 | note | – – – – – – – – –
c100f020-fb1e-52c4-a391-692b959cb1ad | note | RECORD OF CONFORMITY: This ITP Signed Off
1064fbf6-5cbd-51f9-beb6-ed8b4a1a6f9c | note | – – – – – – – – –
7a67c57d-5ce5-5d60-a351-99fd18695342 | note | WP
1afff3fc-b727-5230-9dae-fe8770c797df | note | – – – – – – – – –
9ffb41b1-a7c0-5a84-afa0-5514cd5d4d2b | note | RESPONSIBILITY: Fulton Hogan Engineer
d5fa2cb2-446b-5a00-9680-68f3443c6db2 | note | – – – – – – – – –
d64984af-80d8-53ec-b33e-4e58039aee4d | textbox | DATE:
fa5d72bf-fb56-4eb7-9442-6c2338c7854a | checkpoint | 2.4 Rail End Preparation
6520c8ed-7ab8-563b-8f2c-ac945f8dc478 | note | FREQUENCY: Each Lot
67b19d98-32b8-5ba7-b103-462c2f12c8c6 | note | – – – – – – – – –
eb701765-5fe5-5491-9b9e-1bd08af6956e | note | ACCEPTANCE CRITERIA:
ef3331be-a510-5387-b4f9-6415b2cf9844 | note | • Rails shall be saw cut or flame cut
66bd05d9-f613-5830-a604-21a78692ddfa | note | • Minimum closure length from proximity of welds shall be 2m
934b1414-12e8-5e09-a0c0-ce37eb444450 | note | • Rail end conditions shall match (i.e flame cut - flame cut)
71199edd-d189-53a5-887d-73263f88eec7 | note | – – – – – – – – –
c04748f7-8cce-54a7-8775-f32c80b92977 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
f9c1cb46-567b-53bb-b656-61f7ad4fdde0 | note | – – – – – – – – –
6a48df45-8a34-5166-a989-2042be7b853e | note | INSPECTION/TEST METHOD: Visual Inspection
6f9a7920-472a-5b2a-b78c-1d988372750e | note | – – – – – – – – –
6031e11b-0735-5134-b4f5-cb8ab933f613 | note | RECORD OF CONFORMITY: This ITP Signed Off
b67bcdf1-b804-56c1-94a9-64526856ac88 | note | – – – – – – – – –
ee50323e-f388-57f6-8c90-a0de7c663324 | note | WP
3b476977-d4d4-511f-9441-fe97585069d1 | note | – – – – – – – – –
70fe89bd-c591-5b4e-92f3-23293c731f10 | note | RESPONSIBILITY: Fulton Hogan Engineer
2a4153e1-43d1-5d80-8e53-44346e75a889 | note | – – – – – – – – –
ba1d898b-2636-51ef-9bb1-f65fb15dda48 | textbox | DATE:
9ebcb9ac-c985-4ab6-9049-366d01d1884c | checkpoint | 2.5 Welding of Rail
24bf2b42-4070-5626-838d-78d45fcd2128 | note | FREQUENCY: Each Weld
845a13ed-fd77-5da6-ad99-77bf1e9b44dc | note | – – – – – – – – –
541bd01d-1feb-5613-8c5f-43ce15772ae8 | note | ACCEPTANCE CRITERIA:
b12593f0-3af1-5833-8141-c9d7ca9d51ab | note | • Joints shall be square across the track
84aea222-77e5-5d86-9af9-e710a3b38a1e | note | • Maximum skew at square joints shall be 65mm
9cf9638c-dab5-529b-9a49-73bba91bb8c4 | note | • Portions shall match rail type (i.e HHR, Ordinary)
5a89bb8d-7e8a-51b1-991d-b75313913907 | note | • Welds shall not be within:
fd4cd6ed-779d-5d6d-a063-b257535e0c67 | note | – 3m of another weld
32626221-d20e-5c1b-89e9-a5cfe89c6743 | note | – 3m of a rail end
aa20ba8f-dff0-5f1a-bfbc-b3b7bcd854ac | note | – 1.5m of a glued insulation joint assembly
8c5c9ff3-1401-5c5a-98f8-02a2749c102b | note | • Field welds shall be +/- 50mm from centre of bay between sleepers
30ce5beb-d597-5e3e-9f00-522f8bcf4a34 | note | • Weld Return forms shall be completed by qualified welder
bf67bd38-06c4-5d00-9c25-aafcce3f6581 | note | • Welds shall be grinded after 1 hour
7b331555-43a0-5379-bf48-0aeebb0a4c26 | note | • Welds shall be free of water
986ee10a-179f-56fe-a3ec-1455c1126e2b | note | • Post grinding, welds shall be cleaned for visual inspection
747a4bbc-9c45-5adb-9537-8b352d849615 | note | – – – – – – – – –
2cc9d23d-e78e-530a-8a4f-5aa8140adc78 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
147f3e51-4bf0-5af4-906d-cf1d674c5350 | note | – – – – – – – – –
e872a7d9-795e-5aab-b7ea-63a064dd4686 | note | INSPECTION/TEST METHOD: Visual Inspection
36884a2f-e196-5b65-8316-080c19052aff | note | – – – – – – – – –
4d49d749-afd8-537e-a737-d968f5a8375c | note | RECORD OF CONFORMITY: This ITP Signed Off
069c88d2-a689-5211-b010-8a8a042de198 | note | – – – – – – – – –
09b1bd1a-5f80-51b0-8ca2-ebaf820f6469 | note | TP
48219e5f-f30b-5850-868e-582b49eb9a22 | note | – – – – – – – – –
f6187a2e-41fb-54ab-a7be-8f41f09c70df | note | RESPONSIBILITY: Fulton Hogan Engineer
cb91f03d-c017-50dd-80e4-c352d8621f53 | note | – – – – – – – – –
bac10196-6c3a-5187-a312-5ef1b01f00a9 | textbox | DATE:
08e68919-3478-4a68-91d6-cac2113a1dc3 | checkpoint | 2.6 Grinding & Cleaning Welds
8c376fa6-863a-5156-a7ef-d4eae4f599ad | note | FREQUENCY: Each Weld
6473977d-7a60-59b6-b71e-2b83b1f5f485 | note | – – – – – – – – –
184cc1b9-2c97-5049-940b-9f8747228089 | note | ACCEPTANCE CRITERIA:
93b122d2-3a90-524f-bf44-af176b1f6692 | note | • The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring).
1058848f-292a-5c08-9fb1-6b8d3c9274de | note | • The grinding stroke should not exceed 500 mm to each side of the weld.Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
deee0f02-5705-53be-818d-0c1718e980ac | note | • The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
36f56d1c-7077-535d-aaef-06839bbebdfb | note | – – – – – – – – –
155f370c-c196-5a7a-8feb-ad6ab362e309 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
904b6c8f-75df-5bb6-9e98-5f21acca4283 | note | – – – – – – – – –
f3f12c43-2a88-58f0-ad8d-7d8584177fef | note | INSPECTION/TEST METHOD: Visual Inspection
5c16f0a4-7c7c-552d-9f80-e65d6554ed45 | note | – – – – – – – – –
d8930176-742e-5622-9fdf-36bde22fe704 | note | RECORD OF CONFORMITY: This ITP Signed Off
416eb874-42ef-5b25-a515-cea5d87b7933 | note | – – – – – – – – –
8fd45468-447d-5a93-9c76-ff56f557ad09 | note | IP
8e436ddd-4f77-5a1f-a98d-1538e4a5cd7b | note | – – – – – – – – –
768a09bc-3c5e-5936-96af-464b698aabb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
c53e7297-4c2e-508f-8ab8-c8a61867c8f3 | note | – – – – – – – – –
f44b95d1-7ecf-510c-af69-4ad1dfe9c4d4 | textbox | DATE:
c26bfe7a-6a22-407b-8870-72b1570bb1ba | checkpoint | 2.7 Track Adjustment
d4b177aa-0861-555f-9b41-cec52507672e | note | FREQUENCY: When required
2cd28e1d-a354-5d9e-b994-2cef952a7e3f | note | – – – – – – – – –
98921c26-2e06-5cea-87f8-c5edfe2f680d | note | ACCEPTANCE CRITERIA:
4a1be384-751e-5f25-824c-88d89503b7ea | note | Allowance must be made for expansion and contraction of rail to control stress.
aae339f6-bace-52f9-b449-e58058d5ef62 | note | The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with anapproved type of thermometer.
74961083-62c0-514e-817a-adef213000ff | note | In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
5655633e-6686-5b15-8c2c-0a116bb43efe | note | Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
2d5c3d67-6d05-54a3-b4d1-e178e94f9e0a | note | – – – – – – – – –
d5e6d340-1153-5291-8bec-b77ef0eca6e5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
7d657b12-4837-51bd-aed7-e68dd28b668c | note | – – – – – – – – –
f60878cd-6883-5b28-9074-a571cbb383bd | note | INSPECTION/TEST METHOD: Visual Inspection
f10e7b7f-5e6c-5b8c-801e-d57b9802657b | note | – – – – – – – – –
9447dec2-76d3-5b5f-bdfe-e1e22d04dd95 | note | RECORD OF CONFORMITY: This ITP Signed Off
d193f7f5-92dc-511c-b688-f6e77cbc8034 | note | – – – – – – – – –
9eef05a8-f497-500a-9143-87594b3c6309 | note | IP
c71c67ec-0797-5ce1-956d-0e65a51c80d0 | note | – – – – – – – – –
b6f508e8-321b-52c5-ae3e-9a839c255180 | note | RESPONSIBILITY: Fulton Hogan Engineer
9e71a644-529e-5ea8-aece-77f28c2da035 | note | – – – – – – – – –
b96bb69d-444a-5a8d-9f56-5a555cc464c5 | textbox | DATE:
fe33f82d-7e03-4fb2-b2d6-c80e19557ab3 | checkpoint | 2.8 Track Bonds
00a27bb3-586f-5449-b5b5-6dc6cf6c73aa | note | FREQUENCY: Each Lot
b440b0fd-f4d1-50d7-b70f-4443a8bb61a7 | note | – – – – – – – – –
ae55cb6b-b78b-547e-9107-08d7fc5c9078 | note | ACCEPTANCE CRITERIA:
0410b825-7510-56ab-92e9-c77a0329a1c4 | note | • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
0044ca8c-04cb-561c-96c7-752ff464134d | note | • Ensure bonds are sealed as per agreed method with Yarra Trams
3c0eedd7-c44f-50f3-9cfc-6b32020a5b6e | note | – – – – – – – – –
f2d93732-9a9e-580a-8496-0919974899e5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
1867e505-b770-5f5d-836f-9bd1e54f073f | note | – – – – – – – – –
bb18a3a4-8b0e-5222-b868-00e08979b99e | note | INSPECTION/TEST METHOD: Inspection / Test Method
43c73e99-8578-509a-ab3c-7119f8086073 | note | – – – – – – – – –
891b6129-4acc-550c-bbbb-42dafc22d734 | note | RECORD OF CONFORMITY: This ITP Signed Off
9b874547-1838-528d-8a7f-e7055a2bbdb3 | note | – – – – – – – – –
b2a76721-f678-5889-bcca-fbdc3548a495 | note | IP
02c1b0b2-dc54-5a5c-b1cd-b80f910c3b3a | note | – – – – – – – – –
6017e730-13e3-5926-99f2-eacd803b9fb0 | note | RESPONSIBILITY: Fulton Hogan Engineer
9954d0f0-0bf5-5300-badf-440817aeb1c8 | note | – – – – – – – – –
09b73312-724f-5a13-bf0d-b2d1a2faf039 | textbox | DATE:
1fc1df1f-deda-4b40-a8e7-a7bb49c2d9ee | section | 3 - Testing
d97e47ed-12b8-4f7d-be16-5072be6d98a7 | checkpoint | 3.1 Track Testing
380b4d38-59cf-53fb-a49c-2b9491893d69 | note | FREQUENCY: Each Weld
e70f997e-3490-514a-ad88-e089086190f5 | note | – – – – – – – – –
fd992515-0e55-5955-842c-71eae10e2a10 | note | ACCEPTANCE CRITERIA:
faee323b-e8b6-5acd-939a-11aac6280f34 | note | • All welds shall be tested by qualified NDT operator
a0bd9fb3-9aff-585d-8400-b816ebd21228 | note | • Failed welds shall be cut out and replaced
c029a1ec-cd28-5bbe-9168-8ae818e25ac4 | note | • Testing documentation shall be recorded and supplied to the superintendent
5164def7-a92a-51d2-9fa5-9f471c78d03c | note | – – – – – – – – –
de2ce446-c03e-56f0-872c-20407c42cbcd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
b5b814f1-3568-50ab-a0b5-6f77872f3f5d | note | – – – – – – – – –
e4a23fa8-2d96-528f-ba2e-0b0c6f115e81 | note | INSPECTION/TEST METHOD: Inspection / Test Method
2c218955-9d88-5f53-8f9a-d97a8880cb77 | note | – – – – – – – – –
2d757200-529f-5817-aa52-42d5309e51f8 | note | RECORD OF CONFORMITY: This ITP Signed Off
53f8e052-7516-59fa-adbc-400430fcde37 | note | – – – – – – – – –
591f49e3-969c-5b62-b10f-77ba34675571 | note | TP
53d928fc-19df-5e72-92cc-92d99f393aff | note | – – – – – – – – –
ed141fcf-1eb5-5874-9ac7-2c6bb18214fc | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
61397b5e-ae5c-595e-af2b-2c76698034ec | note | – – – – – – – – –
0c07b41e-cff9-5fe6-9173-31b457431926 | textbox | DATE:
0bd4e755-898a-4fc4-bff9-7a97cfa4176f | checkpoint | Final Inspection
bb6075ab-180b-52c5-902d-6756af51a345 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
74e77242-1f9f-5fc4-9208-4edecd1f318f | textbox | Print Name:
88b50e03-f51f-52fe-9531-42434547c4af | textbox | Position:
e0d81f1e-7814-59f6-a4c0-7160da1ee96a | textbox | Date:
392e700a-0e07-457f-9d5c-6df20c50074a | checklist | ITP-007 - Concrete Track Slab Pour Rev2 | itp | ITP-007 - Concrete Track Slab Pour
d816c0f7-b1df-4e84-a8b0-135f87e77d72 | section | 1 - Preliminary Works
8b7e3a7a-1c26-4ff2-9e3d-b88692e4e2f6 | checkpoint | 1.1 Check for correct documentation
da623a02-195d-5cc8-bb9d-848331945cc4 | note | FREQUENCY: Prior to commencing any activity
546998b2-77ec-52e3-abde-3a06040daf1c | note | – – – – – – – – –
f882b465-7c94-5aec-b8ee-33997dc9c117 | note | ACCEPTANCE CRITERIA:
f408d9bf-dcee-5c86-b16a-c77f6d24a881 | note | • Ensure that all employees and subcontractors are:
07da9231-eee4-5b47-a1f1-920f74869379 | note | – using the correct and complete set of drawings
76ee42f3-06f4-5018-9769-b91c289112dd | note | – all drawings are the latest revision
a71909fb-cce2-5bad-83b4-4cddf09601ed | note | – – – – – – – – –
cfd01961-9ffe-56d1-9452-ef808917cc2c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
570e01e5-0fd1-5e66-a6c5-a37e4d36d6cd | note | – – – – – – – – –
946e2740-ba09-5632-ba3c-bf96e55b36c9 | note | INSPECTION/TEST METHOD: Visual inspection
09d1e82b-0a69-5173-ad9d-b7e4dc325599 | note | – – – – – – – – –
6f1f4114-0319-5626-99fd-bf5db0bc2eb2 | note | RECORD OF CONFORMITY: This ITP signed off
e2f6e0c2-c5a3-5ddd-ba09-737e919ec63c | note | – – – – – – – – –
967f66c5-e4bb-591f-a1fd-2e73f009434d | note | HP*
aa12c645-51ce-529e-9340-7aeab53197d6 | note | – – – – – – – – –
b2295147-3511-5691-bfc4-c858941ca5b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
fead5c5a-aed3-5442-91c9-ea6600064ceb | note | – – – – – – – – –
22b1cb72-cace-58ce-a249-9da547c11856 | textbox | DATE:
5e2a8c67-ec8b-4d54-a1c6-56724d1f16e6 | checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
9e7cbbc3-deb9-5d2c-b288-476c67ad6887 | note | FREQUENCY: Prior to first concrete pour
baec1c46-90b3-54ff-956f-4c1f1ddaf449 | note | – – – – – – – – –
876d56d7-f0e8-502e-bfbf-d0708b8cd6f3 | note | ACCEPTANCE CRITERIA:
763ac6cb-11fd-56bb-8510-da1da35c21a7 | note | • Concrete mix design submitted and approved at least 2 weeks prior to first pour.
b278e546-eac7-56c2-a0ed-ccde8d41f7ec | note | • Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
c08540de-a400-5764-81bb-ac6dedfac803 | note | • Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
813cd03f-2d5c-57c8-8f8a-b11045c32ec9 | note | – – – – – – – – –
4645dd56-daf8-50df-892e-85711f4f113b | note | REFERENCE DOCUMENTS: CE-019-ST-0033
3701bf9f-edd0-5ed2-9ba4-9c7aa1ffe988 | note | – – – – – – – – –
4631ee45-28af-5cd8-beb5-cbbdf5a256b1 | note | INSPECTION/TEST METHOD: Verify
436e9b19-7f91-5ad2-b552-bfdee8435921 | note | – – – – – – – – –
7d087f2a-2a5e-5a5c-bbbc-0815514632c3 | note | RECORD OF CONFORMITY: Mix Design ITP
1e907ca0-93e1-506e-9115-9be2cb405009 | note | – – – – – – – – –
7b246dee-1224-5866-95c8-51c40c6aed60 | note | HP*
fa3e6453-d643-546a-89f5-81e699ce4f4d | note | – – – – – – – – –
3c5e65be-e60a-53a8-8a2e-433dc9c19324 | note | RESPONSIBILITY: FH Engineer / Superintendent
6ad60acd-83b7-5417-8245-eaa2c57c11df | note | – – – – – – – – –
ebe9b3f8-4a6d-523d-b547-996c1ded0cc4 | textbox | DATE:
92c47959-556f-4807-addc-9a82406769ec | section | 2 - Construction Works
006a8104-c40f-46e1-acb8-3d6a85b22956 | checkpoint | 2.1 Weather Monitoring
fddb9bfd-4543-52a3-8e6f-191e7be8abfd | note | FREQUENCY: Prior to start
b0b34ba6-20c1-5edd-b45f-80637f2f63c7 | note | – – – – – – – – –
55b8c580-ab2b-564c-ab22-bfe758771e0f | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
1817cda0-4ef1-5441-aa60-da0887cc1b3b | note | – – – – – – – – –
ed39fe34-09a6-5d64-b875-ab3dd0356dcb | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
a2292102-346d-5886-9f4d-4cfbe0f9ed1b | note | – – – – – – – – –
c49a9b1d-00c1-5a8c-8517-9c1fd5f2aec4 | note | INSPECTION/TEST METHOD: Verify
744f4197-f9bf-5c61-962a-27b32ff26028 | note | – – – – – – – – –
5106412f-fbd9-5e03-a469-66135b61bf61 | note | RECORD OF CONFORMITY: This ITP signed off
8d319e84-228d-5b5f-aa78-43d0b46127fd | note | – – – – – – – – –
83c43ccf-7ee7-50df-b8ad-602ccc848cf7 | note | HP
27dfe6ec-b813-53dc-8f39-8f6bb18d68c0 | note | – – – – – – – – –
11a32ef4-f50e-5d14-9c82-f9c84224ed48 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
32b49df5-2484-5d1a-96d9-89e5d44b682a | note | – – – – – – – – –
539404fe-b6bc-54d4-9d00-e759eeab1aa8 | textbox | DATE:
d606af13-4759-4ec2-8eb5-6aa035b281d6 | signoff | HOLD POINT AUTHORITY
c56e2f7c-82ff-4a0e-aa6b-3d3f1391d877 | checkpoint | 2.2 Surface Preparation
37688fb9-01cb-5f20-bdb0-02d4c6798c4d | note | FREQUENCY: Prior to start
c50af1f8-2123-507f-9403-6372dd95f703 | note | – – – – – – – – –
bb317480-2244-5caa-b798-48a1fafe88f9 | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
029418e9-a35a-545a-9155-03054547b501 | note | – – – – – – – – –
22fa3543-3552-56b7-bb25-efe05579f137 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
b774bae9-4784-55e3-92e4-5cec3a09becb | note | – – – – – – – – –
a46a1075-61a5-51c5-b1c8-313be48630fe | note | INSPECTION/TEST METHOD: Verify
831edf8a-b708-5b4f-a18e-84f4d61890ce | note | – – – – – – – – –
f08cd20b-844d-50c4-8aac-694308b9449d | note | RECORD OF CONFORMITY: This ITP signed off
adf3813f-83bc-5c6d-8a49-edf8592e172a | note | – – – – – – – – –
a75415ee-dfa4-5092-a748-406277451f6f | note | IP
909aedab-8416-5330-86c5-821de7da638d | note | – – – – – – – – –
4f2d9fdc-980b-5036-9d80-b9478fad958d | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
f67e6742-785b-5cbd-9539-b5778158595f | note | – – – – – – – – –
b19bc243-4421-554c-9514-bf1668d505e6 | textbox | DATE:
47762765-f5e6-4c3e-9ac9-e096cea3f90f | checkpoint | 2.3 Setting Out
4e5e43e8-7781-599f-b838-b8277d13b927 | note | FREQUENCY: Prior to start
3ebb195f-133a-5f16-af45-0d3d759fcb11 | note | – – – – – – – – –
f1b64c0d-9356-5b29-926d-42c39cc2fdfe | note | ACCEPTANCE CRITERIA:
e0cd6f89-a9d2-53f6-8213-7b062a19d3ea | note | • Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications.
9a1e3697-6d44-5451-8a22-658ef3467b4e | note | • No survey/level pegs to be removed by any persons until completion of works.
4fedf475-9254-5a15-b380-aaf49045ba73 | note | • Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
16bb259c-f100-5528-9c29-bd933ecbf9b5 | note | – – – – – – – – –
6230c80e-ea0f-596a-ba5c-fbf5b24ce1e2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
577be325-b9bf-5111-9e2c-6470f9a6e9f7 | note | – – – – – – – – –
abd73cbd-5e19-5981-9fee-5d93fff9a9c2 | note | INSPECTION/TEST METHOD: Verify
cabce855-126c-5b87-a546-aa07389265cf | note | – – – – – – – – –
2fa26f37-f158-545c-8763-be1eab7b873d | note | RECORD OF CONFORMITY: This ITP signed off
5af8b15b-5db6-5e7c-b4d8-24ea5bd6fc29 | note | – – – – – – – – –
bdb64609-9cda-53a1-bb8b-30172e514263 | note | IP
dee6112c-a3cd-5382-9a56-22f2d9ad940c | note | – – – – – – – – –
87f8c103-7267-51df-8188-75e3985aa519 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
79e831ce-912f-56ee-9411-9fe87481965e | note | – – – – – – – – –
296e2bdc-daf3-554f-94df-3e039c1451ff | textbox | DATE:
434802ee-7f89-48ff-94e8-17d63f3e9a34 | checkpoint | 2.4 Preliminary Works Formwork
153d5e8c-d557-5ef7-9880-83b89f44b6cc | note | FREQUENCY: Prior to start
c2b03420-825c-5947-a7a0-9fe59fb67dc9 | note | – – – – – – – – –
713d571c-6c9e-5d13-bf51-8cf7221ab080 | note | ACCEPTANCE CRITERIA:
bb00d26f-429a-554a-9c9a-9ce7316a5e50 | note | • Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
f9a94a03-c76e-50cf-b0df-36bcf6931dd9 | note | • The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
6ddbf664-6c32-5a3c-9cda-bc0990cc3147 | note | • Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent
f942ec7e-9423-59c9-b04f-80962c9954ed | note | – – – – – – – – –
d42e7ba5-4bea-59b9-b39b-621a6f4f5ba8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
7e8c5702-61a8-5a62-808c-915a4d62593d | note | – – – – – – – – –
c552fec3-4493-5072-bca4-2f18a730d038 | note | INSPECTION/TEST METHOD: Verify
1c2b17a7-72b7-5c17-b93f-a2e0f2d3a4e8 | note | – – – – – – – – –
d750bf38-c787-561f-ad2d-1a5edf5a3f8c | note | RECORD OF CONFORMITY: This ITP signed off
494d1831-7e1c-5e8d-9bde-c578f6eb8dea | note | – – – – – – – – –
19062975-285c-5996-9688-b417bbe8f845 | note | WP
86fdc368-371e-5b84-a92c-b45d88c151d0 | note | – – – – – – – – –
2a0157b1-c14e-5a11-9f11-2cca112767fd | note | RESPONSIBILITY: Fulton Hogan Engineer
1cfdca1f-1d1a-528b-832e-f340de579be5 | note | – – – – – – – – –
4e9a9be5-1145-53a4-9b33-b00c24a1015f | textbox | DATE:
30bc8d5e-205e-4995-bc52-5f5d5144c140 | checkpoint | 2.5 Reinforcement
856bd8c7-e33c-52d6-bddd-85689f08d4d0 | note | FREQUENCY: Where Required
86766425-1ed3-5d5d-847f-b29406342fa6 | note | – – – – – – – – –
df6f01ee-0fcf-5253-aea0-54c3ac6de1eb | note | ACCEPTANCE CRITERIA:
d91bf87d-479c-592c-84a1-9ac20857af4c | note | • Ensure that all reinforcement is placed as specified by construction drawings.
66d6de07-1770-5556-bd4a-b03dd698cd66 | note | • All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
caa48137-23de-53ff-8fc3-21e8d23cd09c | note | • Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
82956558-82f3-5a1a-a994-21c63912c62d | note | • Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
abb464fe-4f91-5d27-9262-78eb8aa2c18c | note | • Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
93ea4b05-0aba-590e-bd12-e569e3c78e62 | note | – – – – – – – – –
cc829126-1fcc-57fe-a87e-baf1ab2aeb43 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
a85ac5fb-1dbe-5a3e-9d6a-f375742c57da | note | – – – – – – – – –
f0b61a55-2605-5326-b034-601edeb7a63a | note | INSPECTION/TEST METHOD: Verify
0d02bba2-ca1e-5174-909d-c339e93d754d | note | – – – – – – – – –
4737760f-13f7-51b9-87d0-5b744eb58534 | note | RECORD OF CONFORMITY: This ITP signed off
e7527fc3-617a-532e-8197-f0b952ef848c | note | – – – – – – – – –
2e2de00e-ab16-5e60-af2f-575a811abac4 | note | IP
3dbeb20e-b24e-548d-835f-419acafe885d | note | – – – – – – – – –
a4b7e142-4e05-5a91-aa57-eab8b47b1ebc | note | RESPONSIBILITY: Fulton Hogan Engineer
b468abf3-6eb2-5e53-94d9-f1cecc6d63c1 | note | – – – – – – – – –
9d83033c-eb95-571c-98a2-84893f92c4d0 | textbox | DATE:
63f86f0c-1482-4685-9c0a-140565c7ae05 | checkpoint | 2.6 Dowels
349486b6-e4e7-50c8-a1cb-31c41dbe5253 | note | FREQUENCY: Where Required
fe124443-f531-50fa-9def-47242e68a66d | note | – – – – – – – – –
7867be7c-34b4-50a4-9eaa-0d6c423c5f15 | note | ACCEPTANCE CRITERIA:
dc056be6-9217-5328-aa5a-1ed33f172472 | note | • Ensure that all dowels are placed as specified in the construction drawings
ce22260d-04d1-56f5-a4c2-1926042e548e | note | • All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
78fcc105-07c2-5aff-a3f6-c929d2d1f693 | note | • Dowels shall be clean and free from mill scale, loose rust or oil.
74ec8d08-789c-53ca-8b42-b7e7facdefba | note | • Ensure that all dowels are securely held in their correct position until the concrete has set.
4fea84d4-fa93-5c73-8fda-a39894a1ef52 | note | – – – – – – – – –
2503dc0f-4aaa-5412-ad7e-5b015de3d0c9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
c599e605-de47-539d-b00f-f5c7edafcc64 | note | – – – – – – – – –
0b05ab62-1d5f-544b-8fd8-85bc940b83de | note | INSPECTION/TEST METHOD: Verify
a79cb7d2-cd61-55cb-85ec-2d271ccafb84 | note | – – – – – – – – –
fd78a592-ab0d-5f0a-a76d-5c5a93dd3a20 | note | RECORD OF CONFORMITY: This ITP signed off
17f716aa-f475-5ddf-83ff-c62c10578cc8 | note | – – – – – – – – –
dd0907e0-c0a2-55fd-89de-2d2c3c75bcde | note | IP
3db62df3-6733-5f2c-9ca0-13342ae6afc0 | note | – – – – – – – – –
b8ec194e-1712-5993-81b5-6993cd7207e2 | note | RESPONSIBILITY: Fulton Hogan Engineer
34e44235-27ee-58b0-8672-a579b4f7daf4 | note | – – – – – – – – –
b1de681e-10f0-55c8-9f0b-e62fe852c84c | textbox | DATE:
5d934988-df15-4410-a1ca-034f4ea45192 | checkpoint | 2.7 Pre Pour Inspection
7595135b-396d-505f-ae92-6320721c15df | note | FREQUENCY: Prior to start
3c5d13b6-fb63-5ca0-8fb7-b94d2207adbb | note | – – – – – – – – –
659aba80-27e9-5dd0-8d62-d20285dec797 | note | ACCEPTANCE CRITERIA:
e9504930-7c77-51e3-a4a2-693ec9532f34 | note | • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
725c6e83-7006-5a8e-b9a5-0b038837d244 | note | • Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
65e348ec-dec3-5a90-a011-e0b1a3c5afa5 | note | • Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
87ef2715-d493-5270-bbe9-53a25de30811 | note | – – – – – – – – –
94f17f36-ed9d-5ff2-9a79-3bfdbe3531ab | note | REFERENCE DOCUMENTS: CE-019-ST-0033
7c43c698-2c0f-5acf-85e6-869b6d0e7927 | note | – – – – – – – – –
ada6659c-594f-5d81-be3a-7ed7a3f07654 | note | INSPECTION/TEST METHOD: Inspection / Test Method
18e3b77d-abc5-56d9-ad2a-d3390c6ca263 | note | – – – – – – – – –
79e187bd-7595-585a-8e16-b197ed6e52d4 | note | RECORD OF CONFORMITY: FH Track Inspection
723d328c-8e73-55ff-bc93-02496aa2e272 | note | – – – – – – – – –
54eb841d-2db9-5602-9a04-752a0ee465de | note | HP
b160ef65-f3c5-514a-a088-a81ff84801f8 | note | – – – – – – – – –
8de0f025-2f32-5053-97a8-d3cf035f4c21 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
5a1ad8c7-04bd-5b94-ad49-4d3857ba7c70 | note | – – – – – – – – –
dc1a95ec-479e-5c23-ac5e-97f08fd9ea05 | textbox | DATE:
c4382ff7-3a48-4c7e-8bd2-7f2021aa803c | signoff | HOLD POINT AUTHORITY
fa63ce95-3aed-4d3a-a055-8d4bcac337e8 | checkpoint | 2.8 Preliminary Works Carry out sampling of concrete
d159a2bc-5aac-5449-bb8a-8d4d3343f10e | note | FREQUENCY: Each concrete pour
1f48594b-a258-5ce4-a841-b640d3561425 | note | – – – – – – – – –
1f30f459-5a24-5518-b00a-a088134d6393 | note | ACCEPTANCE CRITERIA:
9ffa275e-8d3a-5aa8-8a71-a14e795dbcfb | note | Slump:
f409e95f-c07d-5c4e-8e1a-9a3263569342 | note | ○ Concrete Slump shall be 100mm +/-20 Compressive Strength:
4e44b77c-5857-5309-b38a-e898230b572e | note | • Shall be measured in accordance with CE-019-ST-0033
c5f4928e-5b27-5d83-b47b-310285ca6264 | note | ○ Testing frquency =
44ea80fb-8dc9-5cfe-9333-98e0372b6abe | note | • 0-50m3, 1 sample
8ca6b213-a325-5985-b91d-9615e8b97ddc | note | • 50-100m3, 2 samples
cde820e1-2a0c-5648-a32b-bfd0888c232a | note | • 100m3+, 3 samples
986eb4ea-7c00-5ecd-a258-e1c233bd318a | note | ○ Each sample shall consist of 4 cylinders
3241dcda-10a7-5934-be2e-c1e8b37e6dd0 | note | ○ Test Results will be provided to the Superintendent
4e45649d-3009-5196-af4f-e4b6070a03d2 | note | – – – – – – – – –
13b94abf-7fd3-52a3-80d7-5e0a69e98b83 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
ae945276-bf04-5c0e-9b3a-108cacd95412 | note | – – – – – – – – –
de9850df-9041-5612-b276-ef41528c4ea5 | note | INSPECTION/TEST METHOD: Verify
fab388c2-4c26-519f-a22c-d93733812e09 | note | – – – – – – – – –
62581a55-6557-5ee4-95fd-64ebcc6e3691 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
6d26034f-9946-5e03-a9fb-eefed60bcfa8 | note | – – – – – – – – –
f0d43b75-2edd-5cc1-b4bb-0e2e47692fbc | note | TP
c9b70c0b-8736-5603-8750-07d5ade237f3 | note | – – – – – – – – –
38d1d668-55ac-5d8e-8505-031ff829f4b1 | note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
33d2ba22-a0e0-5fa4-b2d5-ab626e2d1483 | note | – – – – – – – – –
5f647234-cacc-5b1e-aaff-ed348591ca7c | textbox | DATE:
7eafd0ec-1291-4ee4-bfb7-512d7c759ce6 | checkpoint | 2.9 Concrete Placement
3c08400f-9400-5e1e-ab2d-9dc240edb6fd | note | FREQUENCY: Each Lot
cbf03e54-c00e-58b6-93b2-1a5a62eacc70 | note | – – – – – – – – –
5cbecd56-7670-5f98-b726-065385798e07 | note | ACCEPTANCE CRITERIA:
8845c671-f94c-5580-b9ec-34c8213704d5 | note | • Ensure formwork is clean
206657ef-5c13-5523-9e73-7126dc3b2ddd | note | • Concrete shall be entirely discharged 60 minutes after batching,
208ad92a-1d76-56f2-bf2b-6f0649e187d3 | note | • Ensure that pouring does not occur from a height greater than 1200mm
f2e86bb6-d059-56c9-95b3-d7046a15efbf | note | • Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
be961c01-332b-543e-acee-630f893d4b56 | note | • The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
bd35c7f8-d0be-5867-8233-61127d9d3662 | note | • There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
f6d16012-0f0f-5d57-9798-cc66d1c10f7c | note | – – – – – – – – –
16ab02f2-09a6-5e20-8a5a-f3f5d1df8165 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
dfad79ee-daed-5a57-aff1-d0d65ee71810 | note | – – – – – – – – –
62800ce3-632d-5dce-8a23-32ecacfc30d2 | note | INSPECTION/TEST METHOD: Visual Inspection
1b4535d5-3904-590a-a3ae-267f3abb5d6d | note | – – – – – – – – –
47563973-c16d-5f5f-b7de-651d33c24491 | note | RECORD OF CONFORMITY: This ITP signed off
0a2ef532-9b4f-5169-a120-0b40a9025fb6 | note | – – – – – – – – –
db5f3109-d899-5a59-be9a-78e29f029edd | note | WP
35ad53bd-305f-5af5-94ad-47d3186d5bc3 | note | – – – – – – – – –
cbc36dd6-0a73-5e50-b2f3-64fcd23a302f | note | RESPONSIBILITY: Fulton Hogan Engineer
5e7b02ef-e1fa-5b17-be92-e7f9f91ced36 | note | – – – – – – – – –
35835311-a566-58aa-913b-4e552bab9069 | textbox | DATE:
26d17f9e-6baa-4b63-b6d9-68a597b576c0 | checkpoint | 2.10 Compaction
8b13d60d-c330-5f73-b3c3-3e14310ed98b | note | FREQUENCY: Each Lot
b8f7fa8f-a09d-573d-9668-1932661deea0 | note | – – – – – – – – –
5885daa7-199c-510c-a5bb-fe063e0481a8 | note | ACCEPTANCE CRITERIA:
c20c1eba-c2fa-553c-aafe-91693f4ebd52 | note | • Immediately after concrete placement, compaction shall take place with an approved vibrator
ecc22a7a-8dbe-57e0-b0b0-895c39d2b690 | note | • Vibration shall take place until exposed concrete surface is free from air voids
a80cc4ba-07c9-596b-ac8d-217238fdc1d1 | note | – – – – – – – – –
4b494ffa-a72e-56db-b40d-069a24251e4e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
2fc80b0c-e2fc-554c-a712-af80e7f104a6 | note | – – – – – – – – –
e5858f3f-236f-5c08-b0c0-1f2ce70f4188 | note | INSPECTION/TEST METHOD: Visual inspection
ca8be4e2-8de1-5fec-8019-b1d5b78cb911 | note | – – – – – – – – –
d1605d42-c5d4-5102-ae1a-1967989600ab | note | RECORD OF CONFORMITY: This ITP signed off
079fa2e9-6655-5438-8db8-dd5cfb0e4753 | note | – – – – – – – – –
88ad8298-5a10-5bee-a40d-3fb341c8d9e8 | note | IP
9d2dec9f-5a7a-52a7-81db-815730f5dd84 | note | – – – – – – – – –
9beffd52-9583-5ddf-965b-c458a4c3cad0 | note | RESPONSIBILITY: Fulton Hogan Engineer
69c33a50-d3da-577b-ae07-7f6d8462108d | note | – – – – – – – – –
501786d5-ca93-5ee2-9765-d90e7142d879 | textbox | DATE:
6f92c0b7-735c-4982-a5a2-f440acea19c8 | checkpoint | 2.11 Record location of each batch
70d70acd-8207-5329-8e68-7600e1b29aa1 | note | FREQUENCY: Each concrete pour
eea43cc4-32d1-515b-ac22-3da142a4cf16 | note | – – – – – – – – –
112f16cc-ddbd-5eaa-a154-4d810a190998 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
1412cd04-7579-58ff-97c9-2f683926b62d | note | – – – – – – – – –
feb02ac8-b29e-5163-86eb-09acaccd4dfa | note | REFERENCE DOCUMENTS: CE-019-ST-0033
ebd3050c-1db1-5481-8ec1-074d6bca2c47 | note | – – – – – – – – –
7232cf55-53ba-5eba-b3fc-20626c5f919a | note | INSPECTION/TEST METHOD: Checklist
5a986b85-bf60-5324-a29d-1609a49dbbc8 | note | – – – – – – – – –
4753f193-32bd-50a1-bb37-b2257fb1d81d | note | RECORD OF CONFORMITY: This ITP signed off
f9c42fb1-90d5-55c0-bc71-492cd6b1c250 | note | – – – – – – – – –
c5ee5368-2364-5820-a653-e4fc3ade8046 | note | IP
3aa84d81-755f-5d4c-b21c-98c5fbb16e55 | note | – – – – – – – – –
6a86f560-a93c-5db8-9f2c-d650218e3a8e | note | RESPONSIBILITY: Fulton Hogan Engineer
993a74b8-35c5-5fbb-ad86-9ce92a15a2da | note | – – – – – – – – –
4cc23669-ac84-5129-b07d-daef6535af47 | textbox | DATE:
2d9cd346-e83e-4142-aab9-a19329541ebe | checkpoint | 2.12 Curing
6bfaa850-068b-5dcd-9833-02d2d73bcbf0 | note | FREQUENCY: Each concrete pour
bebd2282-6b53-522c-880a-233a4337c56b | note | – – – – – – – – –
17512eee-e017-5452-95d0-bd62f6c4484c | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
d842a6ba-a344-54e9-82e9-d66747f564c5 | note | – – – – – – – – –
6adbe97b-53ef-5d46-a35a-f1259a524738 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
7d1240ae-e53c-5c90-98e1-69c8e34f7a5c | note | – – – – – – – – –
67e712b0-628e-5c34-98db-6d2000a9dd93 | note | INSPECTION/TEST METHOD: Checklist
ced358d3-3384-56a6-8aff-0c2c81d33a7d | note | – – – – – – – – –
8180e0f6-b57a-551a-8db4-d1a8541565c5 | note | RECORD OF CONFORMITY: This ITP signed off
8acec229-6ae3-5c73-a653-94203d47182d | note | – – – – – – – – –
22cb404f-29b7-5015-891d-4ee040fa6292 | note | IP
60a72a08-26fe-509e-9d01-14126e6dacee | note | – – – – – – – – –
f96b1205-7cb3-55e1-8a5b-4da3684320ba | note | RESPONSIBILITY: Fulton Hogan Engineer
5f57fba5-69fb-5a4d-9cf6-790184a7e407 | note | – – – – – – – – –
a9b60ca8-df1a-5567-8615-1635e7f2c441 | textbox | DATE:
10920819-ce05-4179-b156-c6a446b7299b | checkpoint | 2.13 Tolerances
0fa08a55-052c-510e-9105-0dbb57771722 | note | FREQUENCY: Each concrete pour
ec88ee9d-c313-5e7e-a430-686e9715bffd | note | – – – – – – – – –
eb004f46-277e-595a-afd2-ae47b4338426 | note | ACCEPTANCE CRITERIA:
b2ec4ce1-33d3-59a4-b407-3fb971642faa | note | All concrete shall finish true to the dimensions, the following tolerances apply:
ab1c3bc0-00c4-5c78-8368-0914bbf79c16 | note | • Plan dimension of slab +10,-10mm
fa48bcd0-cdd8-5079-b9cb-323f9c3265e1 | note | • Thickness of slab +10,-10mm
57f1a84b-f3d7-55a1-aeae-590d49927334 | note | • Cover to reinforcement +5,-3mm
146eab0c-742e-57fa-a966-20aec350999a | note | • Finished level of slab +3,-3mm
6de3f730-a467-5833-849d-a29e4fc0f138 | note | • Foundation level of slab +0,-20mm
1cb6a2c6-397f-5ab7-a111-5249ee0eabb7 | note | – – – – – – – – –
6066ab88-55f0-50c7-bdfc-d1c575695eaf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
38048913-ad64-5005-abdd-a59d128038d1 | note | – – – – – – – – –
299389a4-7b61-580c-9302-b9356e1e7011 | note | INSPECTION/TEST METHOD: Checklist
80a88f7a-7d7a-5c95-8947-57a82441a200 | note | – – – – – – – – –
ce112561-7635-59d0-b861-a044885f2a6e | note | RECORD OF CONFORMITY: This ITP signed off
e69ff171-6f5b-5069-bf3a-625df49eb09a | note | – – – – – – – – –
5bc2968a-49dd-5986-baad-d5c1f1690ce1 | note | IP
7f579b66-5241-54ef-9e1f-2f1a796b6942 | note | – – – – – – – – –
b09a8220-c6f1-5395-a29e-8e6bd286f632 | note | RESPONSIBILITY: Fulton Hogan Engineer
250e4fa7-6d66-5dfe-bf3a-d5135f73c9c5 | note | – – – – – – – – –
feb85f66-767c-597d-9611-44ae8534457b | textbox | DATE:
4d8cdc57-0afb-46d5-8450-bdcac4062ed5 | checkpoint | 2.14 Preliminary Works Slab finish
a49027b5-2cbc-5251-b501-ffd78a4a67cd | note | FREQUENCY: Where appilcable - if track is Type 1 structure
7e0461f5-9de8-5049-925d-f31a26b32b03 | note | – – – – – – – – –
55ad13b4-cb53-5ab2-8946-5123810cb490 | note | ACCEPTANCE CRITERIA:
95c70e0b-c629-5cd7-a4ee-a5d271149273 | note | • Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities.
3ff4d398-f8db-5993-97f8-b92ff262f903 | note | • All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
7afe6cd7-fdd5-588d-91cf-dc0309b30b12 | note | • A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
301f4cb5-0010-5914-8fe5-02ee74d084b4 | note | • The slab surfaces shall be broomed to provide a non-slip finish.
aec07e1c-f8dc-5169-a6ca-ce599a078153 | note | – – – – – – – – –
f2e00634-77b8-5c6f-9f33-2c33e833d074 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
f68da003-37bf-53f9-b823-0150e2c95bee | note | – – – – – – – – –
7d309d11-93c6-5d8a-8ff4-bba0213368b8 | note | INSPECTION/TEST METHOD: Checklist
63dffc97-91b1-5fce-9a48-8d43699d9a96 | note | – – – – – – – – –
93e50471-263a-56a7-9cfe-5279bb19f529 | note | RECORD OF CONFORMITY: This ITP signed off
2a57c6d0-5d62-5543-b0ac-0bdef6dacbf8 | note | – – – – – – – – –
afcfcec0-5ab6-5bf9-9283-5e0193f267a1 | note | IP
e54af82c-6eaf-5add-bf86-d08bae7d8c00 | note | – – – – – – – – –
8a2b2c2e-3e65-52e3-ac7e-b6194afa542b | note | RESPONSIBILITY: Fulton Hogan Engineer
caf3bf09-00ba-5e70-b54c-7664bfd851bd | note | – – – – – – – – –
6162f3e6-c690-55a7-8c6a-f935fc047dbc | textbox | DATE:
68aecfe1-314d-4d5d-a9a6-6a2290bf9b3f | checkpoint | 2.15 Post Pour Inspection
4a428604-1531-5fcd-99c6-d38e8df125f9 | note | FREQUENCY: Each Lot
17fc177c-77a1-5f10-849a-f16a3efc5569 | note | – – – – – – – – –
b3e8e416-092c-592a-a4e5-f61216c94943 | note | ACCEPTANCE CRITERIA:
329bfe77-5570-54bf-8313-35cff188c792 | note | • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
23355c68-cf73-5ce2-8b43-137d038aee28 | note | • Ensure no defects are present in slab
a131b245-0bd3-536f-92eb-bc703727ae65 | note | • Complete Fulton Hogan Post Pour Checklist
04b48e3b-b4cb-5d46-8100-ab18e0cc5bbc | note | – – – – – – – – –
38c2d995-2db9-5b12-8ea4-8ae1d95726da | note | REFERENCE DOCUMENTS: CE-019-ST-0033
fa00848c-a5f5-57ff-a831-598986663814 | note | – – – – – – – – –
214e0585-5d53-5ff8-a22f-d5729219a9e2 | note | INSPECTION/TEST METHOD: Visual Inspection
22a3ffe0-fe49-547d-89a4-e9fb2f081614 | note | – – – – – – – – –
7fe7b8fb-b935-5d26-bb04-5250966bba34 | note | RECORD OF CONFORMITY: Post pour checklist
7679e00d-717b-553f-8474-41fbcacfa78e | note | – – – – – – – – –
194f6ab8-1f58-5aba-a251-51a0aa209822 | note | IP
cf0efe87-8a41-5e0d-af92-14d0ec45497c | note | – – – – – – – – –
3a0f0283-bf4d-5f48-81bf-2f6ca4ff36d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
7cfc46f0-76d0-59a6-8d97-7248525c3a6f | note | – – – – – – – – –
c4b69e3b-9706-5051-9d93-c80795b2096e | textbox | DATE:
4acfc0c9-64a1-4788-8713-f05d45a50594 | checkpoint | Final Inspection
358805e0-7c71-5807-8bc9-7011d48e1b06 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications
627f3738-85c9-53b3-b153-c6eefd37139a | textbox | Print Name:
eaeba2eb-ec3a-5cfc-b9b9-b6d1a5219dea | textbox | Position:
fc212994-23a9-5008-9855-74fad5260c98 | textbox | Date:
f3edb058-0f89-482e-ad4a-ea66af7d1fdd | checklist | ITP-008 - Hot Mix Asphalt Rev2 | itp | ITP-008 - Hot Mix Asphalt
52c1fe73-6c81-4067-8a95-47f415a0d055 | section | 1 - Construction Works
9ce87d74-9207-444e-8bcf-478ea75136e1 | checkpoint | 1.1 Submission of Mix Design
3c7d5a74-4fa9-59cc-b9de-2a80b0f383f6 | note | FREQUENCY: Prior to commencing paving
41babb68-0e8c-5770-816b-3b8bd5834ff9 | note | – – – – – – – – –
1e8ccf90-9d35-5559-bf28-bb356cfe1d92 | note | ACCEPTANCE CRITERIA: Ensure the correct mix design has been registered and is approved by Superintendent prior to laying mix according to standard track structure drawings
4d8592de-7d63-54ae-a3de-89f04dbce9e3 | note | – – – – – – – – –
5c7aa9f0-26d2-5590-bd78-09776ebea4ac | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
150b27c1-e611-5cbf-b0b1-ff74e2c2c73a | note | – – – – – – – – –
db931383-e7a0-5379-86b3-051bd78e569c | note | INSPECTION/TEST METHOD: Correspondance of receival of mix design
4c0d2a98-3e6e-5d20-a868-4b99b6a6d522 | note | – – – – – – – – –
5b75cd4b-2bd0-5209-8903-09c18f817fba | note | RECORD OF CONFORMITY: Superintendent approval Completed ITP
6d784ef9-029f-5f82-a27a-de4a0632ad28 | note | – – – – – – – – –
b9c2944f-c129-56bc-9747-6cfaca3e3017 | note | HP
33bed93e-c9b6-5e1d-b28b-c98950296aa8 | note | – – – – – – – – –
681e9169-fb4d-59a2-ac70-e855b1d7230b | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor / Superintendent
dd17e25f-6f7a-52e0-aa8a-419628d59eac | note | – – – – – – – – –
4097e28c-0cb4-5d37-9db1-07704948aa00 | textbox | DATE:
ead1f852-1d69-4ebd-8233-6587e73d8bce | signoff | HOLD POINT AUTHORITY
5aafd120-be26-4304-9984-ace39ef74d78 | checkpoint | 1.2 Site Inspection and Base Condition
9d5137ff-87ac-5abc-9ef2-96264a988ee8 | note | FREQUENCY: Prior to commencing paving
e7e95e9c-6eb8-5a28-afa6-99f8d7e968c2 | note | – – – – – – – – –
c29d74a8-2484-5201-80a0-2016aa74496e | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
7580d616-b410-552f-b3d9-545327795e55 | note | – – – – – – – – –
adc4ec6d-9cc2-54dc-a95a-5f1369633022 | note | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
7797984d-48a9-5cb8-8eb6-3e6b4054f8ba | note | – – – – – – – – –
0c8acdf1-c13f-574d-a43a-e1d086153683 | note | INSPECTION/TEST METHOD: Visual Inspection
a712b2c0-f128-5e33-a06f-db6a9e6bc49f | note | – – – – – – – – –
d04b131a-8a80-57ff-b388-0485a90d9eba | note | RECORD OF CONFORMITY: ITP Signed
a204d70d-b5e1-593e-9292-8cdda7ef87cd | note | – – – – – – – – –
baf0933a-54a9-5603-be57-6d2d55cdd5ae | note | WP
25532200-c1a6-584a-a1be-cd319dd70574 | note | – – – – – – – – –
4729ad8d-cdfc-5a9a-88d3-f9677ea78522 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
bb34fbae-99a4-5189-b89c-557e55c1bc34 | note | – – – – – – – – –
993126bd-393c-5ad3-9c75-77dea26b88bb | textbox | DATE:
e2163b8e-eb5f-4e4b-bf0c-8b5399ec4e18 | checkpoint | 1.3 Ambient Conditions for Placing
4a59601e-8715-54be-b076-e5b72c37a001 | note | FREQUENCY: Prior to commencing paving
d30e52b4-b71b-5f18-ad16-0b24fa3bdb70 | note | – – – – – – – – –
9aac1bae-69c4-5a58-a82a-31693a7cb3d5 | note | ACCEPTANCE CRITERIA:
44bbd0ab-b0b0-5a36-99d2-3bf816fbca3a | note | • The majority of the surface area to be paved has a temperature greater than or equal to the following:
32f1c26b-c835-552a-9719-e286532ae680 | note | – Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
2456e870-6136-5671-a9fd-c9f4ab091e32 | note | – Wearing Courses: 10°C for conventional binders or 15°C for PMBs
09fba3d3-3dd1-572d-b593-18fe229aef47 | note | – – – – – – – – –
6f9dcb72-d89a-5990-9869-b9508e45b70b | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
05ca80b5-b09e-5bce-9280-6cce32677e93 | note | – – – – – – – – –
099f250d-9dda-59ff-aa00-ae70547bf988 | note | INSPECTION/TEST METHOD: Verify
c7edb61b-179b-5ba2-8f68-21b16cd8dfbb | note | – – – – – – – – –
3b11cf6f-fdbf-5482-bb46-3eddb72f122a | note | RECORD OF CONFORMITY: Thermometer
edff2a0d-bf67-541d-8e4f-3fe548c6cb85 | note | – – – – – – – – –
6db2748c-3c28-5f14-ab62-d3e5b12ac71c | note | IP
9d2a37f0-36a2-5c55-9bcc-f624642068db | note | – – – – – – – – –
1828ad3f-627d-55e3-a51a-b08e30f8393f | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
c30f1638-9ce5-50e7-ad42-317f8f3044ea | note | – – – – – – – – –
37ee4f90-ed9e-54e7-aea5-4ed3f04c92b3 | textbox | DATE:
747e67b6-7683-453d-8e95-d5b520d49c15 | checkpoint | 1.4 Planning of Joints
28c924f4-7be5-582b-9f7e-5287d4dcbe61 | note | FREQUENCY: Prior to commencing paving
6f94422a-771b-5692-9496-7694ae92dbbf | note | – – – – – – – – –
5a728779-ca49-54c9-9108-993b6806df4d | note | ACCEPTANCE CRITERIA:
ce1e8a2d-1704-582c-9469-cfb8163e6122 | note | ○ Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
d84b83d1-0a6d-557d-86be-e543fa2a4383 | note | • Transverse Joints Offset from layer to layer by at least 2m
4aadf958-2d35-576d-a8e3-4aa677ffabe3 | note | • Longitudinal Joints Offset from layer to layer by at least
02e4d722-fd84-55b0-889b-168020443efe | note | • 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
8518ac5b-6cd1-5e27-b6a8-ace248ea3a7b | note | – – – – – – – – –
ec22bb5a-716a-5d81-b536-0d5493e0da13 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c) Pavement Drawings
2ad2f498-6ea1-5048-9492-a4eb485e4c81 | note | – – – – – – – – –
b21775d5-9d48-5864-8249-6493685ba5e5 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
15c2745b-3038-53da-ba16-2a26bfaa61b0 | note | – – – – – – – – –
c1116d1c-18fa-540c-9567-9f0400f2a953 | note | RECORD OF CONFORMITY: Paving Plan
88a37cac-1a07-5151-8052-918f1253a247 | note | – – – – – – – – –
db96e033-dd2b-5026-bdda-4bda1d7d7065 | note | WP
55bf165a-b1d4-5388-9acb-fd8f8d84492c | note | – – – – – – – – –
0316f915-0495-537a-badf-8ea1775b97af | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
8ad2b351-ee11-56e0-8616-67b3a8489a4e | note | – – – – – – – – –
ec8187e5-22ec-56bf-8638-bfb24e68289e | textbox | DATE:
eb90047d-9f8b-4dc9-bf88-d2504d15494f | checkpoint | 1.5 Longitudinal Joints with existing Pavement
4f6a5bb9-c6c6-517f-9c58-48b8783ec6c2 | note | FREQUENCY: Prior to commencing paving
6b41f588-9bed-5eb5-9faa-037cba4e0337 | note | – – – – – – – – –
e9925f27-870c-5163-9293-0bdd69332a5e | note | ACCEPTANCE CRITERIA:
dfb7fbd5-cf01-5b23-a0bb-2abfe6299a9d | note | • Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
30bf793a-98b5-5869-b6bb-7de148cb49e5 | note | • Depth of step to be cut to the full depth of each indiviual layer.
f29df447-42bd-5f36-99f4-e7100875cf1f | note | – – – – – – – – –
7e763025-4b35-5c62-b08e-5f0c67cc404c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c) Project Specs. Section 3040.06 (d)(vii)
b3323b5d-027d-5905-a9d4-600195047e35 | note | – – – – – – – – –
5cea51ad-2677-5c38-87d9-f5d96987afcf | note | INSPECTION/TEST METHOD: Visual Inspection
12c3610a-b2d5-5bcd-a438-7890ce3acd4f | note | – – – – – – – – –
c96f4c6b-f27d-56d9-9a35-da52c0ae432e | note | RECORD OF CONFORMITY: ITP Signed
662c8eaa-3a4f-52bf-a50b-78f1a650e9c5 | note | – – – – – – – – –
00b37b54-eb4a-5e61-8c1f-3a4d4077aad8 | note | WP
90297288-3075-50ca-9283-0ff377cf8e5c | note | – – – – – – – – –
3c358c4d-c12e-5ac5-a4fb-e9ce7ce8e1c5 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
08cd158e-c6f4-55a8-a5ad-c8c67e2ce3b1 | note | – – – – – – – – –
9718ba3f-737d-5022-9a2d-d42b8779c5d1 | textbox | DATE:
4831288f-8945-46e7-8d57-6587f1a4b64c | section | 2 - Asphalt Placement works
09e92ab4-48e4-493d-bb70-5a03f96bb317 | checkpoint | 2.1 Commencement of Placing
ef707d7e-1250-5ca3-aa31-f9ccb1db8783 | note | FREQUENCY: Prior to commencing Paving
78288ac4-1134-57cc-931f-a845a05149e9 | note | – – – – – – – – –
78aca2a6-d74b-546f-a119-21a0bc0954e0 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
156044d8-b4e9-5526-99b1-58ba60dcd3c2 | note | – – – – – – – – –
1a015b04-4c4d-5ac8-941a-c7617191de0e | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
c449c265-95b9-5b11-8f98-95bfbdcecdc5 | note | – – – – – – – – –
19af8369-53b9-5a6e-92f5-76fe112922fb | note | INSPECTION/TEST METHOD: Visual Inspection
3959bdbe-a373-5e9c-9eab-052035279470 | note | – – – – – – – – –
90236489-3370-5a72-82a7-57c529964cf6 | note | RECORD OF CONFORMITY: ITP Signed
b8043043-cefa-5fa7-b626-5425540b1f43 | note | – – – – – – – – –
f6e42286-5ddb-5091-b2e9-ea68365f703e | note | HP
b579a6b5-882e-5472-bd7c-3ed72c3a9964 | note | – – – – – – – – –
b083fd84-1907-560e-a93e-685aff53ac02 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor / Superintendent
3a72a999-24a6-5c30-8f1b-5f92a456389d | note | – – – – – – – – –
af4060a4-596d-5372-a85e-20691fa00488 | textbox | DATE:
5a76f65d-30a8-4373-a427-a1546a24cf18 | signoff | HOLD POINT AUTHORITY
066a912c-a82a-42bb-8f7c-ddf7a099727e | checkpoint | 2.2 Mix Design Confirmation
715e22b3-4876-5ced-860b-a76c1a9da9b8 | note | FREQUENCY: Each lot
2a12e0ce-d6f4-562a-a87e-00104531ebfd | note | – – – – – – – – –
aa987ecc-fc8f-5fc9-ad80-8f470f679eab | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt wearing and base layer mixes must abide to IFC drawings and be as specified in standard tram track drawings.
621c8971-a8be-5f7f-9aa0-cfbd12089808 | note | – – – – – – – – –
5f542931-f966-57da-a2c5-a62d0803da1f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09 STD_T9010
152f60ef-2223-5bd8-bb66-55027d4c5ed5 | note | – – – – – – – – –
12e9bca9-dead-5adf-ba97-2ce68d67e260 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
372b22c0-33bf-5260-9205-3d8ba2dd4e0c | note | – – – – – – – – –
4699e5cb-8de3-569f-b2e3-09933d42d623 | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
9fcbbe33-ebc1-5d1c-979c-3545e240b678 | note | – – – – – – – – –
0088de17-89b8-56e9-8f81-95ae6287921f | note | HP*
0b03a4f3-6fe8-5e70-94eb-9117d1a5de0b | note | – – – – – – – – –
c2acdf6d-a0da-585b-ab9b-8b5dfedbabc6 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
c44cd1aa-635c-58b1-8af4-89cd0a33bb2f | note | – – – – – – – – –
e37aea2c-893e-5084-a964-e0aebda7e992 | textbox | DATE:
043fa327-10a1-4a6a-bfff-b90e3f477410 | checkpoint | 2.3 Delivery of Mix
b16415b0-8a45-5cde-980d-05bf0c6371d7 | note | FREQUENCY: Each load
b4dbaa80-9506-5aa0-8219-ed68e0cd5fd0 | note | – – – – – – – – –
adbf83cf-e747-5ade-8641-6399b78ce5f3 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
a88bd5d0-f3a3-5ca9-a2ef-96864dc0b842 | note | – – – – – – – – –
037911d7-b282-5e44-adda-8b36f75b7e7a | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20 Table 407.111
8bd2700a-ad3a-5454-bb56-4cae5e3d222f | note | – – – – – – – – –
56da7d1b-503d-529a-bcd6-847d2d68b8a5 | note | INSPECTION/TEST METHOD: Visual Inspection
4173df7a-9584-590e-afa5-ac076027a51d | note | – – – – – – – – –
52bf561f-44b0-5dc0-94fc-a61c96e11244 | note | RECORD OF CONFORMITY: Delivery Docket
c23fd2ef-64d3-5f8b-ba52-d2c55e346468 | note | – – – – – – – – –
9d12eb23-7832-50c1-a4dd-6dcd69b0b542 | note | WP
15adf1dd-a473-5ad1-af9c-f7bfe61d79a3 | note | – – – – – – – – –
bc975bc8-d075-51c6-986f-ff99795438a4 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
126fad89-31de-5bcf-8e61-108f791c0e21 | note | – – – – – – – – –
8b021180-8e8f-57fe-902d-4a7dc5bf9af8 | textbox | DATE:
49595050-ad01-4523-a671-32948ea8d721 | checkpoint | 2.4 Traceability
9c8f22d0-0447-5953-9767-6165801a46a8 | note | FREQUENCY: Each lot
3796c140-9f59-57dd-b5cf-9f7ed5ec97b6 | note | – – – – – – – – –
3391f3e9-c684-5d67-a89e-7eb61abee7cf | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
a91dc8d7-8f26-5139-b6a2-300980b21b19 | note | – – – – – – – – –
1d8be6b9-f383-59fc-aa4c-3750eb310dc8 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
c04664f3-133a-5c32-8c8b-db70bdc81349 | note | – – – – – – – – –
ddf03f5c-38a1-5b12-be0c-1dc60024eb47 | note | INSPECTION/TEST METHOD: Verify
14bcce53-e6c3-5ac4-8d06-f0f81dc25b82 | note | – – – – – – – – –
e8589e75-6a45-5918-b419-c91c5e69d166 | note | RECORD OF CONFORMITY: Daily Lot Record
49a8798d-746e-5836-b8f6-00c0f6ec78a7 | note | – – – – – – – – –
638ec7d6-40b3-5c10-acf2-8fa4598b3477 | note | IP
fa973084-ffae-584a-a293-f67628d27c6b | note | – – – – – – – – –
5f48aa88-93c8-5b6d-b756-fac2335086b7 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
fbf5e771-ee1a-5a06-9a12-a55a96fed528 | note | – – – – – – – – –
064b67c7-0496-5c45-b8b4-5fa331be88d1 | textbox | DATE:
5912eb0f-17a7-44d8-8b50-be513abef043 | checkpoint | 2.5 Layer Thickness and Level Control
42451787-e5a8-5b28-b767-b58019b7bbfc | note | FREQUENCY: Regularly during paving
85c74896-62f8-51f0-a561-9390aef2f982 | note | – – – – – – – – –
de8e04a8-391a-5bdd-87e5-923883369bd5 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
96dc6785-0075-5172-a251-a8ca8287e151 | note | – – – – – – – – –
6eaee0eb-cd40-5564-865f-c01dc1611e4c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
7c0b1e01-4c27-52be-a903-66af0919770e | note | – – – – – – – – –
1c5f88c7-3782-5eb6-8918-7ca0782c9822 | note | INSPECTION/TEST METHOD: Verify
6164b576-a531-59ee-b19b-7dedf3af1c91 | note | – – – – – – – – –
0f624a6d-a677-58d6-a46d-120becbbedaf | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
8d1ad5fd-0c49-58b4-a6c7-1ff5e006b822 | note | – – – – – – – – –
a78ad95d-8482-5702-9a5a-b375e303ab4c | note | WP
6c1ae18c-3ec9-57aa-99b8-17e652e2c0c6 | note | – – – – – – – – –
646f6144-9150-55d1-a4d4-975c895a738f | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
aff40ac7-aa82-52da-9ca6-22fb321a9fd8 | note | – – – – – – – – –
4d290aef-d3a5-5713-96d4-435f8a5580f0 | textbox | DATE:
f1a38348-088c-4fba-b5e0-4c6b9298569b | checkpoint | 2.6 Surface Finish of Wearing Course
5f131282-68de-50bd-af0e-549f2abd3c66 | note | FREQUENCY: During paving and after final roll
4f9cb65f-3b56-589a-baba-2a6fb1c151a4 | note | – – – – – – – – –
b7da6a97-2ada-56b3-8c07-194b5a6f9e4e | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
0d20328e-aadb-54ec-ab14-16296428c891 | note | – – – – – – – – –
b8336e7b-9f43-5eb6-bd8d-19d2ef71c37b | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
ed661db1-f9ef-5dfb-a51f-48c69e74ee15 | note | – – – – – – – – –
4bccd4ad-2665-52a2-b70c-eddcafecc099 | note | INSPECTION/TEST METHOD: Visual Inspection
e7225e7a-c858-5688-9752-37c2b2eb288b | note | – – – – – – – – –
d7c10bb5-6a00-5aea-8cd7-b95eed1f0fa8 | note | RECORD OF CONFORMITY: ITP Signed
0a592cb8-152b-5e2d-b504-96d85cd9e6ec | note | – – – – – – – – –
6734527b-4359-5e6d-8eb7-06325a0302ac | note | WP
ab65414c-7d22-5ad0-89e7-6abba753d882 | note | – – – – – – – – –
c9be4ce0-ab45-519c-8a7b-dce677132269 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
805cf4cc-6eb4-58d8-a3e6-a18e409a2ac9 | note | – – – – – – – – –
ee616819-cf06-53a7-8dfd-515b73037f5c | textbox | DATE:
22a3125f-689a-43a9-b9c5-7973bb6ca2da | checkpoint | 2.7 Alignment of layers not placed against concrete edge
c09a4929-7c0f-5eb9-9548-68c6cf0e88fa | note | FREQUENCY: During paving and at completion of work
47a70d8e-339a-5c54-9b9a-f3ddc3f2d9e9 | note | – – – – – – – – –
0266c7c7-1aae-5983-b465-5127774c9832 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
5e761d24-4bb7-5ff8-9533-e156a4c64d93 | note | – – – – – – – – –
c42fb1d3-ac8b-56e5-8dd3-dcb127bc3ff4 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv) Drawings
4138dceb-ee09-53d2-a2aa-a3a943802077 | note | – – – – – – – – –
89612f37-d736-5e3f-8720-c6ef5143caa2 | note | INSPECTION/TEST METHOD: Visual Inspection
c9cc344b-085e-58a4-98d3-b52f875a65af | note | – – – – – – – – –
1a5b5df4-5976-5cec-a4ed-18bc3987afe4 | note | RECORD OF CONFORMITY: ITP Signed
8154fc9f-0caf-5353-a35d-c4403c9e16c2 | note | – – – – – – – – –
b1d56df3-ea54-5775-8083-183378ae93c4 | note | IP
65132a16-7832-5cf1-a3af-50787688e44c | note | – – – – – – – – –
d10374cb-5788-5aab-a878-cc6017024869 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
9352e64f-72dc-50c5-964f-484c765286cc | note | – – – – – – – – –
2d822e83-42ef-50d8-90da-8e2793c594d3 | textbox | DATE:
ccc0c08e-f085-480c-89ac-70c5b1b17251 | section | 3 - Testing
ecb0fa6b-b1fd-4949-b869-c429ab9604e1 | checkpoint | 3.1 Compaction
eda76481-15a8-569c-8990-a78165b7ed0e | note | FREQUENCY: Per Lot
03dfe31b-cc29-5ca5-a28a-6b71ee7eabd2 | note | – – – – – – – – –
08eeaa51-d591-5112-96f3-3e79d8be703e | note | ACCEPTANCE CRITERIA:
507bc64e-dccc-59d2-8857-6f111eb74042 | note | ○ For wearing course layers <50mm, if characteristic density ratio is:
5401ebd9-629e-5b58-9516-af62d15f23c3 | note | • 94.0% or greater Accept lot
67387c2e-1808-5690-9237-651d2308efe6 | note | • 91.0% to 93.9% Lot may be accepted at reduced rate
3bc015ad-87e4-54e0-a80c-b57523bb1bd4 | note | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
8451d6f9-f6ca-5614-b87b-ea4065bfd4bc | note | – – – – – – – – –
376f3c0a-8999-5cbb-bd6e-75fb048fc7c9 | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
09223167-130d-5543-9c59-f2b1cb43fb62 | note | – – – – – – – – –
826fe862-ff3a-5cc0-836d-aa2540a4cf60 | note | INSPECTION/TEST METHOD: Verify
fa0358e8-508d-571b-85a0-090002587a71 | note | – – – – – – – – –
1438ce9a-eb69-5b53-91c5-6435103b618a | note | RECORD OF CONFORMITY: Test Report
14085b82-1339-5a41-a16e-41ffddddfa36 | note | – – – – – – – – –
e380982a-7db1-5167-b9cd-6304241043a4 | note | TP
52d406ab-a0d1-5c98-9b53-b66d70c48bee | note | – – – – – – – – –
e230ff84-9551-5dee-bade-15ce892b5a32 | note | RESPONSIBILITY: Site Engineer / FH Lab Technician
b3d0cf95-b603-577b-9e51-a1259e190e48 | note | – – – – – – – – –
aeaf60f0-6800-5f3d-94c9-116ba20e94cb | textbox | DATE:
4179d23b-9e72-4a95-8e7a-eb7db415a594 | checkpoint | Final Inspection
9fd87725-abe5-54e0-8a2f-e60b9be13cdf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb5845a4-d4a9-5bbf-ba05-fbd8fff3d6f3 | textbox | Print Name:
a2110f3e-62fc-5b40-b807-ec9e1a5e159a | textbox | Position:
631a2c99-5ff5-546f-9bff-2a670c9deb04 | textbox | Date:
47b54975-aefb-4e83-9902-9629168bae57 | checklist | ITP-009 - Waterproofing Rev2 | itp | ITP-009 - Waterproofing
6ba1274e-12fc-4971-a3ce-d713692528db | section | 1 - Preliminary Works
ea6578a1-5d75-4393-be00-312cbf319b0c | checkpoint | 1.1 Check for correct documentation
5d2941de-7ddf-5068-bd57-8e3ae0ac2781 | note | FREQUENCY: Prior to commencing any activity
4c6197df-1d1b-535a-884a-32118f8f2104 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
3f8875c4-0ac5-5228-a9c8-0047a476233f | note | – using the correct and complete set of drawings
0ed7194e-2c4d-5c78-959f-c10e497587e4 | note | – all drawings are the latest revision
a29a61f1-ed04-5a07-a322-cf9f61609d96 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9cfe5f43-513b-572e-83a5-4d5f980dae69 | note | INSPECTION/TEST METHOD: Visual inspection
476b4ee4-067e-530f-a0bb-17a9b80755bc | note | RECORD OF CONFORMITY: This ITP signed off
819306d2-a797-584b-a344-884062d7131a | note | HP*
a4431ae7-d846-5b97-afb1-61065d3b0533 | note | RESPONSIBILITY: Fulton Hogan Engineer
5b5a29ba-0374-582e-8417-f5c69ae10a41 | textbox | Date Completed:
ea439c13-6681-4097-b663-d4f1420e5353 | checkpoint | 1.2 Submission & Approval of waterproofing materials and procedures.
dc9ec8a9-81ab-5237-bfda-57efda0625f9 | note | FREQUENCY: Prior to commencing any waterproofing activity.
30a9b62e-d315-535d-9773-382e11c0797e | note | ACCEPTANCE CRITERIA: Waterproofing systems shall not take place untill the Contractor's proposed materials and procedures and surface preparation in accordance with Section 691.08 and have been reviewed and accepted by the Superintendent.
8474e416-8974-509c-88d0-7a1d3c0c2acf | note | REFERENCE DOCUMENTS: DTP Section 691.05
a247e3c7-e7f9-57a8-94c7-de3e879573d6 | note | INSPECTION/TEST METHOD: Verify
025b8021-743a-597e-8030-4e8a2baeb40d | note | RECORD OF CONFORMITY: This ITP signed off
16f1b5ba-9f5b-5a38-b848-8c42b1e087ea | note | HP*
6ad67d42-b218-5e5c-8ed1-ed89464fba26 | note | RESPONSIBILITY: FH Engineer / Superintendent
c628a5c3-9de5-50e1-a740-059271daf770 | textbox | Date Completed:
6d684e78-5bb6-452c-acb6-fe74b8285e0f | section | 2 - Construction Works
19592878-8195-4d1a-9c5c-d50eb9cfd1ff | checkpoint | 2.1 Weather Monitoring
839e6999-9b9c-56cb-81eb-a9e6a3aae4d5 | note | FREQUENCY: Prior to start
1c221c69-4416-546b-9d16-2f9937af7b42 | note | ACCEPTANCE CRITERIA: Waterproofing systems shall not be applied under any of the following conditions:
a23609ec-867a-5988-8c76-6b7e0c5f3330 | note | (a) windy conditions where over spray and/or spatter may be generated.
aa116651-514d-5c66-91fa-180ca47775ee | note | (b) when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane.
57b6e68a-796e-5b9f-9942-c593e2bd5b44 | note | (c) when the ambient temperature exceeds 35°C or below 10°C, unless specified in writing by the manufacturer.
85807250-128a-5dc5-a1a2-c75f95c5729f | note | (d) when the humidity exceeds 85% or where it may exceed 85% during the 12 hour curing period.
46ae5a2d-4a08-5528-9f2f-6db7ea8eb254 | note | (e) when rain spatter or run-off, including leakage through deck joints may contaminate the surface affecting the adhesion of the substrate.
68b545b0-402f-5876-95ae-da7848d2c965 | note | (f) when the substrate is wet or damp, unless the waterproofing system is required to be applied on damp concrete in accordance with clause 691.05
d6c46dd7-505d-5e73-b9b5-40027506c4fb | note | (g) the surface temperature of the substrate is less than 3°C above the dew point calculated in accordance with AS/NZS 2312 (Fig. 8.1) or exceeds 40°C.
9f90d8d5-08e0-5407-9a23-82449573165e | note | REFERENCE DOCUMENTS: DTP Section 691.14
0f52eaaf-e4f2-51cc-a003-e7617747fb47 | note | INSPECTION/TEST METHOD: Verify
396df0b5-7d37-5737-8aa8-55a53259c69a | note | RECORD OF CONFORMITY: This ITP signed off
fbe5d071-75a5-5437-8ed9-3c39072d6c81 | note | HP
ddd78186-9ab5-52ee-a7f7-17b63551d570 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
a82b6c3c-7010-51fa-a9da-eaa812f93310 | textbox | Date Completed:
e58f3045-fc03-4302-ba52-36eb0560c410 | signoff | HOLD POINT AUTHORITY
fbdcfabb-63ec-4531-bc45-51a917d11eba | checkpoint | 2.2 Trial Application
54aad883-8300-5794-9229-243ea5b37d69 | note | ACCEPTANCE CRITERIA: A trial application of the waterproofing membrane system shall be conducted on a test area of the actual substrate of not less than 10m2. The test area shall be prepared and membrane applied by the Contractor to satisfy the requirements of clause 691.08, 691.09, 691.14,691.17 and 691.18
85fec37d-24cb-5100-a83a-cede0535715a | note | REFERENCE DOCUMENTS: DTP Section 691.16
3b4c7e66-c65e-5300-8b6c-4b8e55db49c1 | note | INSPECTION/TEST METHOD: Verify
11310c54-66db-5a1b-bebb-e8c2344c71e1 | note | RECORD OF CONFORMITY: This ITP signed off
f16a62a7-5067-547c-8f11-64c6609a8282 | note | HP
6253c3dc-de35-5c1b-b9b7-17615b3b2127 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
babf0a96-2dbd-513d-9ab2-9defc17ac698 | textbox | Date Completed:
cdc582a7-cfa8-4a6c-beb8-094cf9621fe5 | signoff | HOLD POINT AUTHORITY
06215e28-36d8-41c7-aca0-f81087bffa7f | checkpoint | 2.3 Surface Preperation
72570937-d05d-5eb8-8f1d-7d870dd895e0 | note | FREQUENCY: Prior to start
75533f2b-5fc1-5118-9ca4-60004994db7b | note | ACCEPTANCE CRITERIA: The surface preperation shall be done in accordance with manufacturer's recommendations for the waterproofing membrane system.
2734629c-6bf4-50d0-ab4a-e22008cecba2 | note | ○ Concrete surfaces shall be dry, clean, sound and free of dust or loose particles. Weak or loose surface layers shall be removed and repaired in accordance with DTP Section 689. Rough spots shall be removed with an angle grinder.
5f1d1f06-49fd-5ec9-8339-e5dfba1e1e67 | note | ○ Primer shall be applied in accordance with manufacturer's recommendations and installed by using a brush, mop, broom or spray.
324aa113-7206-53ca-93a2-f9724294d5a2 | note | ○ Only areas where the waterproofing membrane is to be applied on the same day is to be primed.
1551f624-2478-5ac7-9b6a-01d0576b0e28 | note | REFERENCE DOCUMENTS: DTP Section 691.08
4840f18a-33d9-58a2-a0ee-1012cf33434c | note | INSPECTION/TEST METHOD: Verify
06c985c8-26c3-54ec-9820-7fc04786c5f7 | note | RECORD OF CONFORMITY: This ITP signed off
33f50849-8995-52e9-9da5-3195dfcef12f | note | HP
e06b1653-b2ba-57e5-bb6b-8a5fb451c339 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent / DTP Representative
50787dc7-6243-571d-a3da-f54e973f9218 | textbox | Date Completed:
2aceb20c-f38b-4699-aba0-92d7d3770f36 | signoff | HOLD POINT AUTHORITY
edbd14d1-fbde-4412-b869-93f3f04fb866 | checkpoint | 2.3 Installation of Waterproofing Membrane
06cc23dd-6914-5921-b7bd-c4db2e2dc8bf | note | FREQUENCY: Where Required
c535bd02-2a2b-565f-9b9a-61f77bcaae42 | note | ACCEPTANCE CRITERIA: ○Waterproofing membrane shall be applied and prepared in accordance with manufacturer's recommendations.
4d95bb35-6a28-5bab-90ab-f3d8d4141075 | note | ○ The waterproofing membrane must form a seamless film with uniform thickness and complete coverage.
452d0f73-3123-5211-a205-5200d5249025 | note | ○ Coverage of the waterproofing membrane must be continuous over the entire deck area.
0954f7ab-df21-5759-8b31-b2da37fdce74 | note | ○ Sidelaps shall be 80mm and end laps shall be 120mm to ensure membrane is waterproof, as per manufacturers instructions.
bc563b43-97f9-57ba-9202-9966ad55079f | note | ○ Waterproofing membrane shall not be installed on wet concrete surfaces.
fe47aa62-bdba-5579-a371-c1c9314f31b3 | note | ○ Surface shall be protected against contamination and rain or expected rain if water proofing is not undertaken within 24 hours.
0dea7eeb-fc77-59dd-a93f-ef54c6fc65bc | note | REFERENCE DOCUMENTS: DTP Section 691.09 & 691.10
35ae39b0-4031-5f0c-96a8-ef01e34d8435 | note | INSPECTION/TEST METHOD: Verify
88d90fce-55f2-5a9b-83b7-418cc469436f | note | RECORD OF CONFORMITY: This ITP signed off
dc8e6a96-3b42-5eac-ba29-caafb6e37719 | note | IP
706f9a34-4230-5192-bf27-44acd781d7cf | note | RESPONSIBILITY: Fulton Hogan Engineer
081f5446-e315-5339-bc3c-89dc33df9dcb | textbox | Date Completed:
40cc6436-0c69-4c9a-9581-8ba7149872d1 | checkpoint | 2.4 Drying and Curing
96bca089-cf9c-52ca-ab09-0271b379dc34 | note | FREQUENCY: Where Required
547b91b6-afcc-59ce-b475-17f1ded71c1c | note | ACCEPTANCE CRITERIA: ○The curing shall adhere to the manufacturer's instructions regarding drying and curing, and overcoating time intervals, for the prevailing weather conditions.
bc4ed307-74ce-5204-8859-d1c4704d2c1e | note | REFERENCE DOCUMENTS: DTP Section 691.13
3144664d-3183-5d0d-b79a-936f501a94e9 | note | INSPECTION/TEST METHOD: Verify
f8f221cf-c459-50ec-bf2a-9e9a803ea70e | note | RECORD OF CONFORMITY: This ITP signed off
6914ee64-a4a0-58a6-8f09-24d542a543bc | note | IP
0c90e8e0-e91d-5fc0-b284-616de0d07f6f | note | RESPONSIBILITY: Fulton Hogan Engineer
83d1bac5-58b4-5991-ad23-c9aea849f327 | textbox | Date Completed:
d52d434e-c954-486c-878c-2e310294cf8d | checkpoint | 2.5 Testing
67cbed2a-1e4a-5459-930c-58489f379527 | note | FREQUENCY: Each Lot
0065a3c6-3a73-5652-984e-36dcf9ee3afc | note | ACCEPTANCE CRITERIA: Testing shall be conducted in atleast 1m2 test area in accordance with Section 691.17.
9064e79f-406a-561a-aaae-4bd131b80050 | note | ○ Testing after Application the bond strength to the substrate shall be tested using aluminium dollies with a minimum diameter of 50mm in accordance with AS1580.408.5. A circular hole cutter of diameter slightly larger than the diameter of the aluminium dolly shall be used, to cut through the preformed waterproofing membrane to the substrate around the dolly. The bond strength shall be greater than 0.75 MPa, seven days after the application and curing process.
57bcd2db-f70f-5a0e-8c7a-326f8654acea | note | REFERENCE DOCUMENTS: DTP Section 691.17 & 691.18
6a7a4d3b-9c8e-5629-997f-b5d37647dae2 | note | INSPECTION/TEST METHOD: Test
1a33ab71-188c-53e8-9c23-77ac259049c2 | note | RECORD OF CONFORMITY: This ITP signed off
7305b2e1-c478-5320-9fb4-42c5228d409b | note | IP
20337cc8-6fd8-5ff5-94f1-74179fc436b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
3d57d159-932f-5be6-9a4f-2547ee10d8bf | textbox | Date Completed:
1cd8dad9-2207-46fb-a2b9-acaf985dea1d | checkpoint | 2.6 Post Pour Inspection
db01722d-2f10-5cd6-b639-3356fa294219 | note | FREQUENCY: Each Lot
d9af2e1f-78d1-5df1-b380-1bea6f1f6b2c | note | ACCEPTANCE CRITERIA: Ensure finished surface of waterproofing membrane is of high standard, with a uniform and level surface in accordance with manufacturer specification
13229ba8-8099-5639-a397-bc0f2d955222 | note | ○ Ensure no defects are present in membrane.
b65c189a-4c6c-546b-b108-a5a7c305c798 | note | REFERENCE DOCUMENTS: DTP Section 691.17
efd56ada-f3e1-5883-a84c-4a76f9420c3c | note | INSPECTION/TEST METHOD: Visual Inspection
13556ea0-801a-5251-91f1-e818ffd6d4a1 | note | RECORD OF CONFORMITY: This ITP signed off
02d7d747-9acc-5795-b8f7-384c601ef3c9 | note | IP
a1ff30ab-8570-5893-8970-477d1d050f88 | note | RESPONSIBILITY: Fulton Hogan Engineer
0c4b18cc-1d5f-53b3-8b72-dcee3a6908f1 | textbox | Date Completed:
0850993c-d934-4c96-9d51-53ef55670f6d | checkpoint | Final Inspection
7de5e2d1-2969-5ad0-86da-0ba8793d1432 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
06a70ef7-2399-54d1-b3d4-c6bae5176b76 | textbox | Print Name:
2acf1cc5-bfc6-58b3-8875-0e7116871bd1 | textbox | Position:
14b78be7-d40a-5040-937a-01820df50fa2 | textbox | Date:
695fb9d4-7195-4fe9-89c7-9121cf6397b0 | checklist | ITP-010 - Bonded Anchors Rev6 | itp | ITP-010 - Bonded Anchors
3a715992-92a4-460d-b0f1-18291ccb9886 | section | 1 - Preliminary Works
c61efd39-3667-4551-8442-f9ea3a8dea07 | checkpoint | 1.1 Check for correct documentation & Materials
6eae306e-07aa-51c5-aa4d-23729196f139 | note | FREQUENCY: Prior to commencing any activity
d43d1e93-92ff-5a1b-a18f-cb25c529e85d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
92bd07af-9cad-5bed-a639-164d4ce4bc48 | note | – using the correct and complete set of drawings
8e3c7fca-a917-5149-88ab-f847c35eb1a9 | note | – all drawings are the latest revision
d307229b-771f-512b-b942-89b9d1f3514c | note | – Drill bits to be carbide or diamond.
38016e9b-b7ce-5da0-8a7a-2e6d45a534e6 | note | – Allocate work crew to each span.
ed15100e-fcf0-5d97-80d5-f7ca872db25d | note | ○ Toolbox to be conducted with workcrew to run through ITP/WMS/HILTI TDS and reinforcing no cutting. SRG and Hilti Rep to be present and sign on to toolbox.
c26dc49d-a09d-52b5-99ac-1fa50522b29a | note | REFERENCE DOCUMENTS: Drawings and drawing registers, Section 680.05
02a3789c-1dc0-5e9b-a076-7c3ad784158d | note | INSPECTION/TEST METHOD: Visual inspection
6ea520b6-a734-5952-8f50-ca2f10fcabb3 | note | RECORD OF CONFORMITY: This ITP signed off
f5d3f956-5cf3-595e-8d33-4277a1576405 | note | HP*
72655d43-eb27-5665-a7a1-136db87d7b8b | note | RESPONSIBILITY: Fulton Hogan Engineer
6586baff-8e25-58fd-a45b-5d006f154107 | textbox | Date Completed:
3c60ac0a-3f8d-4991-9f87-d9f517ca3b7b | checkpoint | 1.2 Submission & Approval of Design/WMS/ITP
773b6b7c-f9bf-581d-b012-47765288fb65 | note | FREQUENCY: Prior to start
905c76cb-899e-5334-a528-ff34c86ed7b4 | note | ACCEPTANCE CRITERIA: Subject to the requirements of BTN006, if it is proposed to use bonded anchors in tension , shear, compression, combined tension and shear or fatigue applications as described in BTN006, the Contractor shall submit full details of the proposal, including a Proof Engineering Certificate of Compliance, for the approval of the Superintendent.
3b6a4399-2500-5fad-b9af-d7891701b4e2 | note | ○ The Contractor shall not proceed with drilling holes into the concrete, installation or removal of bonded anchor works until the WMS and ITPs have been reviewed and approved by the Superintendent.
4e1ad957-2dd2-5931-9d5e-9300837f138f | note | REFERENCE DOCUMENTS: Section 680.04 & 680.11
75d1bd5a-17fd-56a5-b9c1-e763b31ed1e0 | note | INSPECTION/TEST METHOD: Verify
e47bd7f1-9a33-5b08-9b85-52f843f447e8 | note | RECORD OF CONFORMITY: This ITP signed off
b5a8fea0-73c4-5961-8048-a72a1ff46641 | note | HP*
2de30d80-232f-522b-a265-b1469c1fe369 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent/DTP Superintendent
ce2b61fd-554d-55a6-9afa-343ae0f4d72a | textbox | Date Completed:
e6f8f758-82c9-412c-a4cc-f8950570abc6 | section | 2 - Construction Works
d70c189a-d631-4ad2-98dc-a443794a34ac | checkpoint | 2.1 Weather Monitoring
c1053b8e-b0a1-5bc4-80ef-8973e026ca40 | note | FREQUENCY: Prior to start
7b098aff-d926-50cd-97ce-d3910c3ff3d9 | note | ACCEPTANCE CRITERIA: Installation of adhesive shall not occur while ambient air temperature is <-5C or > 40°C.
cdd87e60-44d5-5a49-9930-5ad55d8a72da | note | ○ Where there is rain forecasted, tents shall be setup to ensure that the drill hole is protected from the elements.
b2aef88c-16a7-5152-b2fe-fbca4ca7d03e | note | REFERENCE DOCUMENTS: Section 680.08 & Hilti TDS
c5c68aa7-48f8-51b6-bf97-40efd3120a9b | note | INSPECTION/TEST METHOD: Verify
eb5cc72a-b307-5eda-97d8-cc32f6cefa49 | note | RECORD OF CONFORMITY: This ITP signed off
d7869830-e6ce-53ce-b48a-d046e2c03fc6 | note | IP
4133864d-6af2-5189-a2b0-824859c99c67 | note | RESPONSIBILITY: Fulton Hogan Engineer
25fc1b15-2fcb-5dc4-abb1-f76706e0643c | textbox | Date Completed:
c70662b6-0004-4ce7-985d-93672de8c91d | checkpoint | 2.2 Trial Installation
0d9aaaf9-a967-55e4-a801-bae1ed8d1a4a | note | FREQUENCY: Prior to start
3af326b8-82a2-551c-a82c-f699ec8f1793 | note | ACCEPTANCE CRITERIA: 5 Bonded anchors shall be conducted by each work crew of installers, seperately for each type of bonded anchor system used in the works.
fb36b4ef-969e-5374-ba52-92661157029d | note | ○ The trial batch shall also be tested to comply with 680.09.
ff0a67e5-53b8-52c8-8a3f-c0825e6de4ab | note | REFERENCE DOCUMENTS: Section 680.12
8d69e35b-c7b7-5fe0-bc1f-1effe25d0e7d | note | INSPECTION/TEST METHOD: Verify
b4fe9e4e-8818-5935-8c55-27aba8ecbe48 | note | RECORD OF CONFORMITY: This ITP signed off
ce2acff9-e267-5fcd-bf9c-e9d142b94c62 | note | HP
1c39f20d-fea2-56ae-99c7-de5c278d5c13 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent/DTP Superintendent
b2979609-815c-59cb-9930-46a4dd9372e8 | textbox | Date Completed:
106f9590-aa56-4826-95db-df05f1e2c439 | signoff | HOLD POINT AUTHORITY
6244364d-10f3-428a-ab22-be106deefa94 | checkpoint | 2.3 Setting Out
39569373-4ae4-54e2-a963-f45f6eda6832 | note | FREQUENCY: Prior to start
9508f4cf-fcd3-5fcd-abfb-2fa679ba9b81 | note | ACCEPTANCE CRITERIA: Reinforcing bars that lie within the depth of the drill hole shall be accurately located by reference to available as-constructed drawings and/or by the use of concrete cover meters or ground penetrating radars.
dd01f103-9291-55b5-b319-500ae237f82f | note | ○ Position of bonded anchor shall be away from any existing reinforcing bar.
576816a5-49ab-52e4-aa11-018ad10adabd | note | ○ A drill guide shall be used to ensure the drill angle is as per design.
370a6cc4-8443-515a-bcca-c35980541767 | note | REFERENCE DOCUMENTS: Section 680.08 / B-P.23.1738-00-STR-DRG-1005
22cd3263-8b69-5044-aab3-03cccd5edcce | note | INSPECTION/TEST METHOD: Verify
64f2d93a-9d89-5796-8795-56a401571360 | note | RECORD OF CONFORMITY: This ITP signed off
e49a0c1b-6162-5ead-8df2-a6d72e68d859 | note | IP
b694896c-187d-5029-8ada-404b42274230 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
f48f1b2e-6c3c-55c4-85a8-c6ee298e5989 | textbox | Date Completed:
b40fa97c-bdd5-44f9-9899-0a87964dfc99 | checkpoint | 2.4 Drilling
a6623aab-04e1-5c6e-b904-721eefdf8de9 | note | FREQUENCY: Prior to start
bc224078-cc97-50f9-bdb6-836a12c01b58 | note | ACCEPTANCE CRITERIA: A 14mm hole shall be drilled at a 45 degree angle. Depth of the drill shall be as specified in the design drawing and allow for 350mm embedment
9e5c5557-f782-51d4-b939-702c0938e30a | note | REFERENCE DOCUMENTS: Section 680.08 / B-P.23.1738-00-STR-DRG-1005
fa8acdf7-3529-5afc-848e-a5714829e9de | note | INSPECTION/TEST METHOD: Verify
50139d34-11df-5e51-af33-c6ff57ab2afe | note | RECORD OF CONFORMITY: This ITP signed off
5d0d572a-d392-569d-9407-2ad90ae7442f | note | WP
7a6fa5ee-6b86-5f52-aba2-c270014662bc | note | RESPONSIBILITY: Fulton Hogan Engineer
ed6dff65-d394-54d4-8d7a-d9955a7e6151 | textbox | Date Completed:
5ee1f9d1-f82c-4293-918c-6a6bfa21d824 | checkpoint | 2.5 Cleaning
6b33427b-3cfd-5596-821c-240337212d4d | note | FREQUENCY: Where Required
29e6201c-5c68-5db3-b2e1-7ab83f086e2c | note | ACCEPTANCE CRITERIA: Compressed Air Cleaning:
d358107e-44b9-5eea-9883-92b133edda35 | note | – using compressed air, blow two times from the back of the hole over the hole length with oil-free compressed air until return air is free of noticeable dust.
9b8ccabf-de00-54e5-800b-86555703c370 | note | – Brush 4 times with the specified brush by inserting the steel brush to the back of the hole (if needed with extension) in a twisting motion and removing it.
001087f0-e657-55dc-b606-687009ca8580 | note | – Blow 2 times from back of the hole over the hole length with oil-free compressed air until return air stream is free from noticeable dust.
82de5d49-acf1-5196-b5dd-483af28cb450 | note | REFERENCE DOCUMENTS: Section 680.08/Hilti TDS
5e82a846-92f4-5e0b-b412-3f3251701414 | note | INSPECTION/TEST METHOD: Verify
c90a5005-c353-51c7-9ddb-6ff417264ab5 | note | RECORD OF CONFORMITY: This ITP signed off
32a190d5-2360-5e9e-91ac-c5ac9e736df2 | note | IP
e051b5c4-91e7-5a53-bf69-7315f3ffeedc | note | RESPONSIBILITY: Fulton Hogan Engineer
9ea915ce-cd05-5768-824a-4499ca604470 | textbox | Date Completed:
135e08d2-3825-402f-95eb-97e858e808a8 | checkpoint | 2.6 Placement of adhesive and anchor.
7dcf7f18-1d93-5e0a-b461-f64b412c9d65 | note | FREQUENCY: Where Required
1099e2c3-6b4e-586e-9626-c4df930b8a15 | note | ACCEPTANCE CRITERIA: -Anchor shall be placed immediately following the cleaning process and after checking for sufficient depth.
1616e74d-e0e5-5e27-86e5-c45f98054e91 | note | – Chemical adhesive shall not be injected into the drilled hole until it is thoroughly mixed using the proprietary equipment to a uniform consistency, colour and appearance in accordance with the manufacturer's installation requirements.
997d685c-1cdd-5d79-858d-2e9eaac1c032 | note | – The initial discharge of Chemical adhesive from the mixing nozzle and for every new mixing nozzle used thereafter must be discarded. Only mixing nozzles that come with the Chemical adhesive and which are designed specifically to mix the components of the specific product must be used
f7ce08f4-9e8d-5d81-83ec-246b9bf55a65 | note | – The Chemical shall be injected into the hole using the appropriate nozzles as specified by the manufacturer. the adhesive shall be installed from the back of the hole towards the front and slowly withdraw the nozzle step by step after each trigger pull.
628a523a-eafd-5ae0-aadf-1abd9abebf13 | note | – Each hole shall be checked visually to ensure that the chemical adhesive is injected to the correct depth (typically 2/3 of the hole depth) prior to insertion of the metal anchor rod.
3d5a1e4b-c723-5c0b-8a88-a32995fd8c4f | note | – The reinforcement can now be inserted into the Drill hole while slowly twisting until the embedment mark is at the concrete surface level.
7d2bf687-cdae-5abc-8d9d-a80174b6c023 | note | – The final embedment depth of the anchor must be verified based on the length of the projected portion of the anchor from the concrete surface as shown on the drawings. 350mm embedment required.
2f0eefcb-a184-5192-a881-28a7186185fb | note | – Anchors must be secured in the centre of the holes such that a uniform thickness (bond line thickness) of adhesive is maintained between the Anchor and the sides of the hole until the Chemical adhesive has cured.
545c3b9e-8d6b-5b82-8f0c-af9507f6c917 | note | – Any excessive adhesive shall be removed from the concrete and Anchor rod surfaces after installation.
8ca03a1a-1b9f-5325-b731-b05e661b1e0f | note | – Fingertip test the hole for dust, and if dust is still present, Brush clean and air-flush until all dust is removed. Including a potential dust plug at the bottom of the hole which reduces embedment depth. at the end of the cleaning process, the hole shall be clean and free of debris, dust particles, oil and other contaminants over its full depth. Avoid over brushing to prevent polishing in the inside.
cf452996-dc93-577a-9966-087a59ef3352 | note | REFERENCE DOCUMENTS: Section 680.08/Hilti TDS
cdc818a6-2d9e-5441-8057-aff4c86b2587 | note | INSPECTION/TEST METHOD: Verify
23ee8bb8-b910-5af9-bc8a-dbdd907f4989 | note | RECORD OF CONFORMITY: This ITP signed off
e94c016a-5538-5daf-8645-57c2bc106f9b | note | IP
3110a152-8715-5811-bbf8-60d2042353f8 | note | RESPONSIBILITY: Fulton Hogan Engineer
dce1b399-38fe-50ee-9bfc-91ab185d78b9 | textbox | Date Completed:
e4cc4822-81fa-4ca0-b0c2-19a0d3bcb524 | checkpoint | 2.7 Curing
c2681c26-be7e-54e8-87c2-0f6fc0449aed | note | FREQUENCY: Where Required
3c8fb794-b892-56f9-822c-d53bfe4967b2 | note | ACCEPTANCE CRITERIA: Anchors shall not be moved or disturbed during the curing period.
5e139a7c-4709-5a64-8bb2-3f3be66b00df | note | Anchors shall be cured as per the manufacturer's instructions and confirmed in writing by supplier.
94e8ad22-bd32-5a28-bd89-b1d9c449388d | note | ○ '5degree <Tbm<9degree - 24 hours curing
eb5ba4d1-76c8-52fe-956c-25372b3f3876 | note | ○ '10degrees<Tbm<14degrees - 16 hours curing
2547a8f3-6371-5f03-ae55-92d202dd9f05 | note | REFERENCE DOCUMENTS: Section 680.08 & Hilti TDS
1634c5bd-0aa8-5beb-95a0-a397cfc12e27 | note | INSPECTION/TEST METHOD: Verify
a117ff7c-85d7-54b6-aef6-024d6677ec24 | note | RECORD OF CONFORMITY: This ITP signed off
4bf3f276-7aad-5d86-82ff-bad70be7567e | note | IP
0d30b350-8a01-5623-be95-b10f6f108a70 | note | RESPONSIBILITY: Fulton Hogan Engineer
1aed83e5-c79e-5ff7-9a0f-37f5685bed11 | textbox | Date Completed:
4e2f1556-9c3f-489a-a25e-8d60da173f2c | checkpoint | 2.8 Testing Methodology
fa9ab85d-d316-5a7f-ae4b-120afedb9475 | note | FREQUENCY: Post Installation
93728f12-88c4-5ecf-a0ca-a7022a6fbe5e | note | ACCEPTANCE CRITERIA: Details of the test method including load increments and duration of sustained loading shall be submitted to the Superintendent for review including the calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devices to be used.
bd64f876-5548-5342-9c20-9650d6194242 | note | REFERENCE DOCUMENTS: Section 680.09
8491d6da-1d09-5372-9aa6-4aa068d905b9 | note | INSPECTION/TEST METHOD: Checklist
6574faf7-4d82-5446-8cf6-2832e19c8e9e | note | RECORD OF CONFORMITY: This ITP signed off
6ad5e82a-a036-5f71-970f-58a8fe96ba8d | note | HP
8723ef19-44bc-551a-bcac-f06146e4e554 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent/DTP Superintendent
8b88c29a-fd98-5ed3-8b39-2b0176bdbfab | textbox | Date Completed:
59712fa8-e756-4464-90a4-dbd90becf7fc | signoff | HOLD POINT AUTHORITY
82cd0e1f-98a6-496b-afef-023532d11b9b | checkpoint | 2.9 Proof Load Testing
f882abb3-61ac-5c53-b2f6-320c3fc2843b | note | FREQUENCY: Post Installation
2b93b9a9-9246-5312-86f9-43e4b7e7dca4 | note | ACCEPTANCE CRITERIA: Proof Load Testing of anchors shall be conducted in accordance with Section 680. A test rig using baseplates and cross bracing shall be used to ensure testing on a 45 degree angle is met.
84d7de1f-6736-5c31-b67e-ce028756b0e9 | note | ○ Testing shall not occur prior to completion of curing time stated by the manufacturer's installation instructions.
e2e8b44f-a9bf-5923-9ac4-f75bc42460a2 | note | ○ The application of load shall occur smoothly with the proof load being achieved between one to three minutes from commencement. The proof load shall be maintained for a minimum period of 60 seconds.
bdc11cc5-e6b0-5acf-84de-6701d14e882e | note | ○ Bonded anchors shall be proof load tested to 1.5 x the maximum serviceability design load certified by the designer.
2c231391-e0fa-505b-b776-69fa39b1fd4f | note | ○ Number of Anchors to be test shall be in accordance with Section 680.091.
16c4152d-c805-5305-877a-6dcfe250f0f2 | note | ○ In the event that the bonded anchor fails, the Contractor shall submit rectification proposals for review by the Superintendent prior to any further bonded anchor installation.
885c6516-bd29-581a-9ee1-cec32cf502e4 | note | REFERENCE DOCUMENTS: Section 680.09
95fa3538-ce7f-5d8c-b082-0e8074d15a20 | note | INSPECTION/TEST METHOD: Checklist
32c53b2d-aef3-5388-8f54-3c71528f21cd | note | RECORD OF CONFORMITY: This ITP signed off
cc090607-a725-52b3-8512-4d64d860d280 | note | TP
803d8f36-585f-537c-9160-7b37d3abd228 | note | RESPONSIBILITY: Fulton Hogan Engineer
8e410398-89d6-557a-8a06-71501ed3d9b0 | textbox | Date Completed:
fd7d877e-b144-46e9-8a64-a0dd11f0869f | checkpoint | 2.10 Reinstatement
35668bfb-a6a5-5ffa-b6a5-fb9be407ef64 | note | FREQUENCY: Each Anchor
0ceca10f-5a41-58c5-9bac-cf1d27f3877f | note | ACCEPTANCE CRITERIA: Compliant bonded anchors shall be cut down flush with the concrete deck height.
f833d4d0-ed22-54ff-add5-feb2b4b61a03 | note | ○ Bonded anchors to then be drilled down 6mm below the concrete surface level. Holes to then be cleaned out and filled with Renderoc ST06.
43712efd-7e49-5f97-b8da-e4aa93fcd752 | note | ○ Any failed drill holes shall be cleaned out and filled with Hilti RE 500 V4 as per the manufacturer's TDS
395b9284-e8eb-5ac0-be97-1c441b592ad3 | note | REFERENCE DOCUMENTS: Section 680.10
1719426a-504c-5fae-b7ba-e9601d1e4def | note | INSPECTION/TEST METHOD: Visual Inspection
f58c5d0e-c588-5a90-b37e-6270125e8d1f | note | RECORD OF CONFORMITY: Post pour checklist
0cbc1171-2e01-5a7a-81e4-28c8bfc62311 | note | WP
00053217-c7e5-5b83-94a2-c4c415bce84e | note | RESPONSIBILITY: Fulton Hogan Engineer
3f1b035e-e7b8-509e-bf5a-77168bd286a8 | textbox | Date Completed:
083142ea-8fa0-45e3-bcc8-6e64cc5e518d | checkpoint | Final Inspection
842de826-6b9a-534a-9779-02c7416e402c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0d1b063b-d685-5c44-b58c-781df20b930b | textbox | Print Name:
3d5c6eed-aa02-5310-9c28-276cc6862661 | textbox | Position:
dce47776-544c-5742-9751-464d4b740cb1 | textbox | Date:
932c3588-1a35-4c07-b634-99030d17b134 | checklist | ITP-010 - Bridge Concrete Deck Repair Rev1 | itp | ITP-010 - Bridge Concrete Deck Repair
ecd540e3-1f3f-4330-86b1-5756552f5f9b | section | 1 - Preliminary Works
bf538986-a72c-4d83-aa4d-a0abd3c9f107 | checkpoint | 1.1 Check for correct documentation
33d05cb9-cb44-5e1e-a7f1-e568bcdde353 | note | FREQUENCY: Prior to commencing any activity
f676af62-34f6-5e07-9a5b-c1b78920b988 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
2a9c6c6d-80d9-54d6-bfcc-c69355505698 | note | – using the correct and complete set of drawings
146924aa-193d-5188-b7fd-a98e7420d6af | note | – all drawings are the latest revision
6f0b58a7-89e7-5831-ae1b-837e7863265e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b387e2d4-c97b-51d1-a0c2-233b127b1d34 | note | INSPECTION/TEST METHOD: Visual inspection
046d968d-24db-5332-ad7b-c3ac8730b4c5 | note | RECORD OF CONFORMITY: This ITP signed off
7e2095d9-9c5f-5ee2-a18a-accc68d3fd9e | note | HP*
d17ecf04-81a3-55dd-8cd7-aa3d3296bb3f | note | RESPONSIBILITY: Fulton Hogan Engineer
5c557dcf-36be-5238-b5f6-67b484473554 | textbox | Date Completed:
b74753cf-db1f-43c7-8386-b30ec9ad9b03 | checkpoint | 1.2 Submission & Approval of Patch Repair Material Prior to Commencement of Project
9230f4ae-1fe5-5612-a67c-f651dc88c8d9 | note | FREQUENCY: Prior to first concrete pour
2840cb69-fbf3-5652-82a4-b136c638e274 | note | ACCEPTANCE CRITERIA: Patch repair material submitted and approved at least 2 weeks prior to first pour.
826fb31a-548b-5e9c-ac73-5eb1bc4f2d38 | note | ○ Mix shall be minimum 50MPa.
0c0b6d3e-5dd2-5a49-945c-33bb537f2fa0 | note | ○ Concrete shall be installed as per manufacturers specifications.
1d67d313-5e56-567a-83a1-b930fb303f79 | note | REFERENCE DOCUMENTS: Section 689
83ce7e71-bc56-5d90-9e00-00a8e91ebcc1 | note | INSPECTION/TEST METHOD: Verify
e25c19fb-9eef-5817-8d55-ee35913c41bd | note | RECORD OF CONFORMITY: Email confirmation from Superintendent.
e642a3df-5bd4-590e-ad3b-98e94a1f6097 | note | HP*
8cd2e8a3-2a18-548e-8363-68df2abcc8dd | note | RESPONSIBILITY: FH Engineer / Superintendent
5fbeeda9-fb4a-55ef-a500-1f4039af70e2 | textbox | Date Completed:
f42777cf-eaab-4880-b657-937b110e5623 | section | 2 - Construction Works
5cff4e57-6db3-4acb-afef-256d34b27469 | checkpoint | 2.1 Weather Monitoring
25b92989-e2c6-5102-91e8-c245fed95c21 | note | FREQUENCY: Prior to start
7aa94565-db8d-543f-8de0-63edb4280ec7 | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
08a8c997-d07b-5054-81b0-1f6068b09186 | note | REFERENCE DOCUMENTS: Section 689
981aa809-9f29-5085-b557-3aae12b1b465 | note | INSPECTION/TEST METHOD: Verify
198e21b0-ed8e-55cb-aae6-a8a298fba2cd | note | RECORD OF CONFORMITY: This ITP signed off
85c381fb-79dd-5ec4-b0e7-1f7857a91737 | note | HP
ff6f5317-70fe-5524-8a91-23215ed3c839 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
058ffd7f-f10c-5603-9e36-734f0a36cd82 | textbox | Date Completed:
45048404-5e97-4b47-b09e-89b1896ac980 | signoff | HOLD POINT AUTHORITY
eb469258-0ac1-41fd-a894-a3a6b424208e | checkpoint | 2.2 Surface Preperation
8ec0ea2e-ad0a-58e2-bd54-2ff811b506ca | note | FREQUENCY: Prior to start
d4f699ff-3c51-599d-85a9-2b5fdd5e569a | note | ACCEPTANCE CRITERIA: For all types of patch repair, all defective an delaminated concrete and existing repair materials shall be broken back to a sound and dense concrete surface.
00c60b9b-fa53-5e93-9f42-763f1f4df79c | note | ○ All concrete surfaces and mortar substrates shall be sound, clean and free from dust, oils, and grease and surface contaminants. All loose and unsound materials and surface laitance shall be removed.
b39fa614-2273-55be-8e66-865144155b39 | note | ○ A 15mm flat face along the edge to be formed around the non-conforming areas by sawcutting/grinding.
68a996be-2405-5f71-b8e3-744cad8ad480 | note | REFERENCE DOCUMENTS: Section 689
c9be9833-e0cf-5e14-922c-7ae6e6fa50b6 | note | INSPECTION/TEST METHOD: Verify
ff462e0c-e661-54ea-a859-edd21e0bafce | note | RECORD OF CONFORMITY: This ITP signed off
e5f4b223-6d5c-5e39-b071-5cc730729fb1 | note | IP
144abb21-b154-5c14-8615-a65db754bc83 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
410c5544-366d-5734-94c6-328e0df5c706 | textbox | Date Completed:
48b111da-8627-4f9e-b6aa-6772d0f3a168 | checkpoint | 2.3 Pre-Pour Inspection
50e6d773-5cfc-5b15-961c-e3590613b513 | note | FREQUENCY: Prior to start
231d9339-ad9c-5b48-8994-67cc01aa0f8f | note | ACCEPTANCE CRITERIA: Superintendent to review the depth of removal of concrete or defective concrete repair and the amount of exposure of steel reinforcement prior to commencement of application of repair materials
c4b3e090-354b-5121-8ac1-67f2dcd1696e | note | REFERENCE DOCUMENTS: Section 689
f1e026b7-c811-5025-b7a5-6e031776fa7d | note | INSPECTION/TEST METHOD: Verify
00279804-3711-5563-9c37-7ae3ef341e1f | note | RECORD OF CONFORMITY: This ITP signed off
eb741ae3-4ce3-5827-88b5-88dab2704e8f | note | HP
23cdbefa-7703-5c76-82e6-b55467902eec | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
be7a3992-a51b-5600-b63e-8b5b52311f59 | textbox | Date Completed:
6adee64c-7d39-4070-a620-e3642d6e9226 | signoff | HOLD POINT AUTHORITY
200c195b-a0cb-48a0-a13a-f952fc145892 | checkpoint | 2.4 Application of Reinforcing Protection and Substrate-Bonding Coat
cb07125f-2323-5ce3-b48c-0b6384cc8c58 | note | FREQUENCY: Prior to pour
c72ac65b-a8f9-5fe6-baef-546d55e39391 | note | ACCEPTANCE CRITERIA: All exposed steel reinforcement shall be coated immediately following preparation and cleaning with a primer which forms part of the propreitary repair system to provide immediate protection against coroosion. The steel primer shall be adequately applied to the back of the steel reinforcement where it is fully exposed and where steel bars are tied together.
d1ae3d07-6696-50a8-9aa2-273d3cf605f8 | note | ○ A substrate-bonding coat which also forms part of the proprietary repair system shall be worked into the concrete substrate using a short bristle brush to enhance the bond at the repair interface.
42893183-331d-5db6-ba70-4906823d224a | note | REFERENCE DOCUMENTS: Section 689
5174afc2-f436-5ecf-b22d-0031507f95aa | note | INSPECTION/TEST METHOD: Verify
b702c7e4-6678-5d6d-8a86-ce6ec38e1dcd | note | RECORD OF CONFORMITY: This ITP signed off
7a029e6d-6970-5149-82cf-e2b649fedb75 | note | WP
0cccf6ed-50bd-5e9b-8156-38dadcb5d0a4 | note | RESPONSIBILITY: Fulton Hogan Engineer
ee0244ea-7178-53f9-b640-58792818f8f0 | textbox | Date Completed:
065f5377-c870-47ab-a988-64b474325d9a | checkpoint | 2.5 Pre-pour Inspection
74dc6e20-b563-5270-b609-134fd73fc28a | note | FREQUENCY: Where Required
567acb66-a617-52dd-9f40-4c2bce40aa1f | note | ACCEPTANCE CRITERIA: Reinstatement of prepared areas shall not commence untill:
eba787cf-82c1-592b-a221-3bdde4d3f30f | note | (i) a joint measurement of the repair area by the Superintendent and the Contractor has taken place;
565a0fcf-3b40-5406-9390-ac9441c03bee | note | (ii) evidence that the preparation of the repair area confirms to the requirments and specification
6be205a0-ae39-5fd5-a513-bb7b59cb047b | note | (iii) the Contractor's quality procedures has been sighted by the Superintendent.
0c1adb20-23bb-5cca-8016-f86fe3b18564 | note | REFERENCE DOCUMENTS: Section 689
9d625f9d-a82e-5685-a7c2-63feb2aea707 | note | INSPECTION/TEST METHOD: Verify
ebd855d1-3a34-5b3a-9156-811607694028 | note | RECORD OF CONFORMITY: This ITP signed off
fa55ca5e-e972-5a2d-914a-503fdadf7c8e | note | HP
2dd89904-54eb-5b8b-82e4-51f8630d2748 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
c87542a9-f393-5a57-b51a-0614212176d3 | textbox | Date Completed:
df665f55-4c3c-405b-855c-bfe83d04bd9a | signoff | HOLD POINT AUTHORITY
32e0addd-7004-452b-9bac-81543c251c50 | checkpoint | 2.10 Placement of Repair Mortar
6fa4b79a-ff1e-57cd-94e7-d1d18fd1e427 | note | FREQUENCY: Each Lot
5f764ac6-4e1a-5b24-bce9-54bd8b79d993 | note | ACCEPTANCE CRITERIA: Patch repair mortar shall be prepared as per the manufacturer's guidelines.
893e4557-d66b-51b3-b6bf-83042f35c670 | note | ○ Patch repair mortar shall be placed within 20 minutes of mixing.
ae81dcfe-ea6e-5d08-adcc-71de8fcb9a85 | note | – Patrchroc C only suitable for depths 25mm-200mm
a790d520-a5dc-5ccc-b666-f853086c0c61 | note | – Patrchroc GP only suitable for depths 25mm-200mm
cb82ebb8-7cd4-527c-a047-d39d9f4e2c6f | note | – Bluecem HE80AG
8091a122-ed2b-5010-bb51-994700053109 | note | REFERENCE DOCUMENTS: Section 689
4732feaa-5c3d-5251-b5e2-d242fe22e391 | note | INSPECTION/TEST METHOD: Visual Inspection
fe2619b2-890b-505d-957e-02de20275ece | note | RECORD OF CONFORMITY: This ITP signed off
fe48f3cc-f84f-54ee-932b-5e381701ec10 | note | WP
b4fe9d07-7a77-5a76-bea1-698c97b03001 | note | RESPONSIBILITY: Fulton Hogan Engineer
316e1369-9fae-57a8-81c2-e507150ef7a8 | textbox | Date Completed:
70ddb0d4-e628-4aa6-9c06-1795acf693f6 | checkpoint | 2.11 Testing
23e83d59-1574-54f0-8941-284cc2ca9d06 | note | FREQUENCY: Each Lot
509068ff-9d39-5969-9846-522ddc003070 | note | ACCEPTANCE CRITERIA: Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. The cubes shall be cured for 7 days under laboratory-controlled conditions. Two cubes shall be tested at 7 days and the third cube at 28 days to confirm compliance with the minimum compressive strength requirements as specified in Table 689.061. Test cubes shall be made and cured in accordance with AS 1012.8.3 and tested in accordance with AS 1012.9.
a0384b0a-71e2-59ab-a30f-4893300d8799 | note | REFERENCE DOCUMENTS: Section 689
c62793a3-7bdf-5026-8ee2-f41a02d3f48e | note | INSPECTION/TEST METHOD: Visual Inspection
04287dee-56e5-5f50-b91c-e1ecc4ebe8c3 | note | RECORD OF CONFORMITY: This ITP signed off
3946e454-fc62-567f-b292-c87d3542bd44 | note | WP
7da06e4f-02a3-54a9-81b7-2cdba6cf9b0e | note | RESPONSIBILITY: Fulton Hogan Engineer
c4a8c6c8-abe6-50b3-b6d6-3bf52154bc91 | textbox | Date Completed:
761c53a6-f72e-4e64-8dfb-4eae8929273b | checkpoint | 2.12 Curing
7a7b4cea-0a7f-55f8-87de-5732a47b656e | note | FREQUENCY: Each pour
27327c6c-a028-5495-99ae-a83a94a9387e | note | ACCEPTANCE CRITERIA: Immediately after placement and for seven days thereafter, the repair material shall be cured and protected from drying out and against the harmful effects of water movement and weather, including rain and rapid temperature changes.
d892ffde-191b-5593-8ce0-bd989b137990 | note | REFERENCE DOCUMENTS: Section 689
07c28cfa-248a-5f01-8f5c-1c47440914c7 | note | INSPECTION/TEST METHOD: Checklist
fa5853c8-3329-55a3-ac2b-6949d4321ed5 | note | RECORD OF CONFORMITY: This ITP signed off, Vibration report, Concrete testing report
b3814eb5-cc75-57fa-bd66-517b99e747cb | note | IP
d28181b7-f61a-5cff-bfab-a106962c781b | note | RESPONSIBILITY: Fulton Hogan Engineer
383e6ad5-9c95-5c40-894c-f14bbe04936b | textbox | Date Completed:
9c04d22e-14cc-4241-90dd-71fa9fbf3803 | checkpoint | 2.13 Finishing and Surface Condition
9d50dd04-97ef-5a8d-9f0f-bfb0a25aae21 | note | FREQUENCY: Each pour
beb49154-790f-558b-a761-6bd78f4cb27d | note | ACCEPTANCE CRITERIA: All surfaces shall match surrounding surface finish by use of steel forms or steel trowel finish.
3e3c45ee-3f9b-5af8-af3a-4df05950f00c | note | ○ The surface of the concrete repair shall not have cracks of width greater than 0.10 mm measured at the concrete surface nor craze cracking covering a significant area of the repair at the completion of the curing period.
a03c258c-381d-5be2-b16a-71dd6250bcb9 | note | REFERENCE DOCUMENTS: Section 689
dd83da19-4ea5-5233-9ef5-6291b2fb2b2d | note | INSPECTION/TEST METHOD: Visual Inspection
01b12653-5e90-5430-9e81-9fc4b30d4a56 | note | RECORD OF CONFORMITY: This ITP signed off
5d3e8e9f-f7dc-5dfe-b1a4-41021d2b8ac2 | textbox | Date Completed:
677bec9c-9ba1-42f2-8824-61f3d398f82f | checkpoint | 2.14 Tolerances
160b7c01-d074-5844-821b-d3cb418ba8c5 | note | FREQUENCY: Each concrete pour
c2325552-7fcf-566f-94a1-da9e09cf8947 | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
2abb6806-e094-5b57-bff8-e8b89a51fea1 | note | ○ Finished level of slab +3,-3mm
dd47fa43-b510-53b7-b9e9-502a616341b0 | note | REFERENCE DOCUMENTS: Section 689
411aa6eb-2088-5024-bd69-418847a969c3 | note | INSPECTION/TEST METHOD: Checklist
cc795c1d-abc7-5ed1-92c1-a8b30bf4d972 | note | RECORD OF CONFORMITY: This ITP signed off
6502e6ab-30ff-5fe6-beb2-a91b20b05778 | note | IP
8c1e93b7-f553-54d6-920b-0ad397fecf04 | note | RESPONSIBILITY: Fulton Hogan Engineer
baf8dc66-bb88-5bf4-8f27-0c64b3732b9a | textbox | Date Completed:
52bea7d4-b4c3-4dd2-b562-99428fe1dd7f | checkpoint | Final Inspection
3040a230-f3a2-5852-9422-5669b77256ad | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b254ca0d-d2d9-5efa-9f51-34f3a2a3e5fb | textbox | Print Name:
d0d2964b-5f04-50f2-ae91-f7ad1d8b2ff2 | textbox | Position:
49de2d5b-d094-5862-888c-46b376564136 | textbox | Date:
53b5bd12-b8f5-40dc-8e4e-c89205d23345 | checklist | ITP-019 - Line Marking Rev3 | itp | ITP-019 - Line Marking
c333197b-4b37-4bc2-877c-63e7e2a5cb41 | section | 1 - Preliminary Works
39c7a9a2-59cb-4f63-8560-f8486361a183 | checkpoint | 1.1 Check for correct documentation
859b73a0-bb32-5974-b0c6-d9d67f1fa0d3 | note | FREQUENCY: Prior to commencing any activity
aa2e5789-29a2-589a-9b0e-2373135149d9 | note | – – – – – – – – –
d0838437-d108-5786-9497-c05f4d766c7b | note | ACCEPTANCE CRITERIA:
6a145315-a5e5-5db2-90ce-fad45952c11c | note | • Ensure that all employees and subcontractors are:
8aef68cd-e8b0-5e1e-87e2-73e420f34b8e | note | – using the correct and complete set of drawings
8c1930a7-e415-5626-820e-e58dd45dc675 | note | – all drawings are the latest revision
8aabadd3-51d5-571f-ad5a-26138d7ccaae | note | – – – – – – – – –
b0dc9599-008b-5f47-9369-08a4d13f483c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
58b44213-66c6-59b6-92ac-eed2ef5a7c6b | note | – – – – – – – – –
2ea4ddd7-0112-5561-b304-c2944702fae4 | note | INSPECTION/TEST METHOD: Visual inspection
c4ce92e8-e90b-5bcc-8d47-1c29c56e9bfe | note | – – – – – – – – –
42e68f4c-2741-5276-87ef-6a6de3c2de8c | note | RECORD OF CONFORMITY: This ITP signed off
7c1c0443-7265-58df-8ef9-cf72ea14f473 | note | – – – – – – – – –
b4d485c2-fa68-534e-bb3a-e6b6254c45ee | note | WP
75ffbbb3-2a52-5567-9208-e4ba41fc12da | note | – – – – – – – – –
88cdf8b4-4f5b-5031-93bd-da94e76d7eec | note | RESPONSIBILITY: Fulton Hogan Engineer
ac304ec4-85d8-5920-b7a7-81a4faec4579 | note | – – – – – – – – –
046ff6c9-c27c-53b6-9181-6e0935abf205 | textbox | DATE:
0c96f5de-02c3-4a3e-849a-fe73262a6e5b | checkpoint | 1.2 Implementation of all measures and controls
bd9b69b4-f21a-59e7-8154-ea5cd36a5d77 | note | FREQUENCY: Prior to commencing any activity
1d006d4b-16c6-5aae-84ec-30cddac01522 | note | – – – – – – – – –
3d2459ae-44a9-5df3-aedc-ab19d2ef48a6 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
4c52a0d4-7846-5a7a-bc0d-fe748d990e4c | note | – – – – – – – – –
f46301e4-a551-52a9-a7b1-fb9c9180eac3 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
4d11d5ca-c7b0-5dac-993a-d707c58a239b | note | – – – – – – – – –
8e3a1bdb-7d37-50a5-893c-b29e23288035 | note | INSPECTION/TEST METHOD: Visual Inspection
91058d4b-c360-5615-966e-d843903a997a | note | – – – – – – – – –
dc4e04f8-7007-589b-af7d-c4e3dce91b8b | note | RECORD OF CONFORMITY: This ITP signed off
feacbe32-eda0-5ee4-8783-db6dbb6baa2f | note | – – – – – – – – –
bd3d7976-870f-56d3-9a99-4fceb5868d93 | note | WP
110f2e09-bffe-5d42-a47e-0b8fee5135a5 | note | – – – – – – – – –
35510ca2-e6c6-54d6-aeb8-aa8d63f4b6b0 | note | RESPONSIBILITY: Fulton Hogan Engineer
31624242-9475-5fe3-b385-4aba6d643f4c | note | – – – – – – – – –
72da6511-8a34-5ec4-8b84-145ee0b32eab | textbox | DATE:
89e25256-b4c0-4d80-b4a6-6094e849c6e3 | section | 2 - Construction Works
5870b843-cc7a-4fc4-9150-be2cf80d4c5b | checkpoint | 2.1 Setting Out
f341e104-e201-593f-9fd1-a17703555d2a | note | FREQUENCY: Prior to start
f14731e1-2563-5953-9db1-cc19430dfe86 | note | – – – – – – – – –
b757428a-1625-5409-ba59-50fc03a95dc4 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
0ef28156-d62d-5752-91d1-47043d868b2c | note | – – – – – – – – –
4f4c2d95-a2cd-5f02-8112-dbe090d7ff80 | note | REFERENCE DOCUMENTS: Drawings
064b0cb8-f620-5abd-a5f4-d02a3f3a2dc9 | note | – – – – – – – – –
e422bb76-cd07-5f33-8942-cb04ecb28c41 | note | INSPECTION/TEST METHOD: Visual Inspection
f1d8b42e-5d82-555b-992a-dfb917c12949 | note | – – – – – – – – –
89345a0f-e9eb-5d01-a958-c90f2651cf8e | note | RECORD OF CONFORMITY: This ITP signed off
83af6db8-8a47-53ec-83c8-d315ddf03569 | note | – – – – – – – – –
348a6e69-f992-5f66-9671-ac080920bf74 | note | IP
6034a75a-cb20-5306-a992-7dc5c340cdce | note | – – – – – – – – –
8fe8e4e9-f145-5aaf-b584-fed18f17f2b1 | note | RESPONSIBILITY: Fulton Hogan Engineer
a89d6a58-4c3c-550c-88c3-9e0681dd51e9 | note | – – – – – – – – –
fbb819ec-315d-5a4d-9d1d-ce3e2ac8400c | textbox | DATE:
37eba590-7fa1-4cb5-8683-d63c651990f8 | checkpoint | 2.2 Position of Markings
bbce3099-a8c8-57b5-9581-36cd8b505698 | note | FREQUENCY: Prior to application
a8e1ad57-15ce-591c-8209-16edadf99689 | note | – – – – – – – – –
86383220-3eab-5ee2-855a-c0ba8079d857 | note | ACCEPTANCE CRITERIA:
f6a719cd-21bc-5d68-9a84-99b1ffcd8052 | note | • Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
cea0e6b5-6a28-5590-8470-4533954f1014 | note | • Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the
6358ced7-3a5f-53cb-8abc-7a8a189932c5 | note | • VicRoads Traffic Engineering Manual Volume 2.
cf60ef53-e2f3-5c5a-b7c5-388c4691db8f | note | – – – – – – – – –
5ed37d5f-18ec-5b0b-9ee6-c75d7f36eeb4 | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010
e84c53b1-d5f2-5142-a75d-eb85ebb55685 | note | – – – – – – – – –
7352d7f8-91f2-50a5-a8a7-8220cf01a711 | note | INSPECTION/TEST METHOD: Visual inspection
4ed88e69-c01b-5693-9b41-1399c1023f74 | note | – – – – – – – – –
4184de50-1be8-5a76-a7e5-618fd096da49 | note | RECORD OF CONFORMITY: This ITP signed off
671cfa5e-eb83-52fc-9dd3-bb7098cc8574 | note | – – – – – – – – –
b5c2afaf-7649-5e55-ad84-192dcd35fff8 | note | HP
7fe357c4-965a-500d-aa69-617d69b5b48d | note | – – – – – – – – –
a20a64d8-d371-544b-9a54-1228b159095b | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
2ffb7c34-8491-5fba-802c-1411159388ea | note | – – – – – – – – –
f64d78f6-79c1-5196-a095-a50b0156a94d | textbox | DATE:
c4566728-7da1-4a5d-9a47-e7075787ce14 | signoff | HOLD POINT AUTHORITY
6d4c6efd-67ed-489b-8563-115c6239bf6d | checkpoint | 2.3 Tolerance of Pavement Markings
76dc4ee0-089b-5893-93a9-9704e9cf481b | note | FREQUENCY: Each lot
ffd68b0b-86b2-5625-b905-dd3e4535c1d1 | note | – – – – – – – – –
9d54a281-1f70-5c82-afbe-587d39a8a758 | note | ACCEPTANCE CRITERIA:
4d5c504a-ca79-5ba5-9d4c-473e1e8ef371 | note | • The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings.
8fae1102-ee25-53ae-a9ad-bee2451b3334 | note | • The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
db51b7fc-98e7-5586-9bc0-55fae65c06b8 | note | – – – – – – – – –
e033d5b3-cb1a-5eeb-8454-376b356ca3f6 | note | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
e308dc4f-5a0f-5bd2-ae56-6f9339f4663f | note | – – – – – – – – –
f761846c-b9a2-5750-89aa-1669f8ec15f2 | note | INSPECTION/TEST METHOD: Visual inspection
e0de7836-82f9-5215-a558-0a00b6dde371 | note | – – – – – – – – –
7970d78b-83a6-5968-bb55-40558571685e | note | RECORD OF CONFORMITY: This ITP signed off
69336748-581a-5298-af72-e261594ed328 | note | – – – – – – – – –
715e19a1-deef-59d9-b73b-3a5779534036 | note | IP
16f0bfad-adca-55da-b6e3-7598736194f9 | note | – – – – – – – – –
740745fb-9631-5d49-9532-57967d40e0a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
1af87735-1167-5a12-896b-468479dc2928 | note | – – – – – – – – –
777503a4-d222-5fec-ae4a-2d9750961ba2 | textbox | DATE:
2d277e33-31c2-4b77-adc0-5958fc38477b | checkpoint | 2.4 Preliminary Works Raised Pavement Markings
241b9a85-89d0-5959-aa2c-d2483ebb8513 | note | FREQUENCY: Each lot
82100d8d-df2c-5b5f-b383-edfdca6744a3 | note | – – – – – – – – –
0361b2a6-cda3-53f8-8fe0-d23d4f785fc9 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
95c45c2d-9c1e-5e6e-90d6-478c08499be7 | note | – – – – – – – – –
48896ac9-5801-59dc-a96f-cc90d27fbb29 | note | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
9ead3f28-bc70-5e27-95e8-0d4ebf41593b | note | – – – – – – – – –
d2057a55-517c-549c-aa45-c5f6533b68de | note | INSPECTION/TEST METHOD: Visual inspection
2220a745-aa6c-5610-abe1-493f02f9572a | note | – – – – – – – – –
7f81f35b-d7d5-5362-8778-d0d0f497aeb7 | note | RECORD OF CONFORMITY: This ITP signed off
1527090b-eb8e-5b79-b214-ae8e2ca2720b | note | – – – – – – – – –
b58dbf16-9343-56a0-8125-5b583dea5ff7 | note | IP
1051e38d-7236-59db-bdf8-1b470b117bfa | note | – – – – – – – – –
2be56757-8984-552f-abb0-f80f1986575d | note | RESPONSIBILITY: Fulton Hogan Engineer
ef47a874-7c9e-50e2-83e6-898e5f8af30d | note | – – – – – – – – –
41d835c4-ab0d-5556-90c8-2ced6a32cbd9 | textbox | DATE:
85a9ea44-5e21-4d2b-833e-1c97cfc16f77 | checkpoint | Final Inspection
cfc8c898-358d-54e5-9d9d-fae1071d6f5d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d0932b43-5f8b-5a89-add2-9a92bbaeeb88 | textbox | Print Name:
45ce201c-9503-5812-b105-cbef59e45401 | textbox | Position:
f2db0e07-d575-5cda-a2b9-d2542156b444 | textbox | Date:
37b1108b-6668-4342-9834-fbe88e6c8d6f | checklist | ITP-041 - Rail Expansion Joint Installation | itp | ITP-041 - Rail Expansion Joint Installation
4a2d8e5e-7962-48ef-ae28-5fcc8f282f69 | section | 1 - Preliminary Works
edfb34b1-6b3b-4df4-a1f5-220de58553d8 | checkpoint | 1.1 Check for correct documentation
92c7b112-cb28-555d-98c2-016f73297193 | note | FREQUENCY: Prior to commencing works
5f27de4d-a061-5643-a1cd-ce0249b09853 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
00cd58d0-6323-5df1-92d0-318c79fa551a | note | REFERENCE DOCUMENTS: Design Drawings and Register
d17f72cf-2692-537d-8710-2d92843bd492 | note | INSPECTION/TEST METHOD: Visual Inspection
832c1a18-d76a-5d33-8cd5-bf03b9c389b8 | note | RECORD OF CONFORMITY: This ITP Signed Off
047e51e2-ebc4-5399-aeaf-329771b21856 | note | HP*
e13ca15d-db9f-5643-9c92-1f5001455036 | note | RESPONSIBILITY: Fulton Hogan Engineer
03a7c231-2c45-5e27-92e8-143466ea9eb3 | textbox | Date Completed:
2d452b9a-da5d-43ff-92b2-7b4e684a70f5 | checkpoint | 1.2 Implementation of all measures and controls
4483f183-7b8a-5d64-b842-ee98a0651428 | note | FREQUENCY: Prior to commencing works
1c572c47-a3f7-5576-a47e-12d1c0bb6e4d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
6ebad4d4-e8a0-55d8-bee7-c8631269a4fb | note | ○ Ensure that all employees and contractor involved in the welding process and are signed onto the relevent hot works permit
2511c872-96e6-5f05-bdbb-5d2a86b7463c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0fbfeb07-4fb7-5a59-bde0-e0ede59d4a71 | note | INSPECTION/TEST METHOD: Visual Inspection
b0f6fddf-56f7-5411-b9a4-a4f39f41208a | note | RECORD OF CONFORMITY: This ITP Signed Off
ae0c367d-e050-5e8b-8c35-b91aa3955e55 | note | IP
b55d3061-08d5-54cd-af39-53a669e7e648 | note | RESPONSIBILITY: Fulton Hogan Engineer
92a8ceae-c61d-51d5-b61f-0f22847eddde | textbox | Date Completed:
85ec613f-786f-446b-88b0-7c6fa9f81b24 | checkpoint | 1.3 Check materials and expansion joint systems
f1201c66-d454-582c-8018-6be2f6a0a9a8 | note | FREQUENCY: Prior to commencing works
e31e65a5-e6a9-52a8-80d3-cc190a1592da | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
d492582e-3297-5820-9318-2a137e2785ad | note | ○ Check condition of rail sleepers / pandrols
7b732bd7-5c62-5e7a-ad33-2c6e4aba2983 | note | ○ Ensure rail jewellery is of sound condition
867ad518-a3ff-5a23-b1d8-d016e7ccff21 | note | ○ Ensure expansion joint box are of adequate condition
c73a99b5-f7be-5fb9-bb6a-cf913f07fe30 | note | REFERENCE DOCUMENTS: AS 1085 IFC Drawings
5b362b84-f4d5-5337-96b1-4856ac54578d | note | INSPECTION/TEST METHOD: Visual Inspection
5c777beb-7ffe-5276-91d7-2e064a7fa6ae | note | RECORD OF CONFORMITY: This ITP Signed Off
52621143-f7a5-5de3-a67a-82860ae21699 | note | HP*
db3ff43b-70f7-5de8-918d-6219d4ec2001 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
c8946792-88b8-535e-96b2-fe67f98d49d5 | textbox | Date Completed:
c57b8abf-1260-4933-9f18-07a2a08aa3b7 | checkpoint | 1.4 Welders qualifications
9a288cb1-ffdc-5124-8528-aaed33277d05 | note | FREQUENCY: Prior to commencing works
b521952c-8aa6-59ee-a988-05e5d0f89a35 | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
99943023-b010-50f0-975f-8d36b470d6b8 | note | – TLIW2012 Grind Rails
4a4a3aea-d586-56ac-8449-8e7c7e296fd0 | note | – TLIW3015 Weld Rails using Aluminothermic welding process
c7555e73-607f-5dff-8366-ba9ddd5d801f | note | – TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
42695c00-1fd2-52cf-a957-ca5bf45d4341 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
4a8b1131-8508-56b4-8a86-d5ee369219c5 | note | INSPECTION/TEST METHOD: Verify
1c01b949-93ed-5c61-9114-9fc342f6e9c0 | note | RECORD OF CONFORMITY: This ITP Signed Off
1c4abbc7-d1b8-5763-817b-b500429f5adc | note | HP*
c218b4de-d1b1-5a5c-a095-4d29d0ba4800 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccc316c9-be05-5b4c-b306-4bf318048593 | textbox | Date Completed:
b11f653b-eec0-439d-86e6-e0c55c43800f | checkpoint | 1.5 Ultrasonic testers qualifications
39c9ac05-6c20-5e82-835e-9f67d7640b29 | note | FREQUENCY: Prior to commencing works
0a471e55-c509-5057-a341-daafb3da0287 | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
a3276482-f306-55fd-b23d-dcb98ac7c3c6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
20f5d748-f0ad-5150-a3d9-7000c86ff7dd | note | INSPECTION/TEST METHOD: Verify
92add7da-905c-5479-b630-d1f9afe941d7 | note | RECORD OF CONFORMITY: This ITP Signed Off
20d56603-c7c8-5c78-a900-e4b5939a2015 | note | HP*
c2d681fb-554f-5985-b5f8-4aae2a139eb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
0bf384ef-7136-5b5f-91f3-8b1e955a23c1 | textbox | Date Completed:
2d186074-591c-4bee-ab27-5cf8083774cc | section | 2 - Expansion Joints Works
466c18ce-c609-4517-a787-2d6c9d7a9b8e | checkpoint | 2.1 Gap setting
cc9ddaaf-bdbf-5c2a-b538-3acea15b1ccd | note | FREQUENCY: Each box
21250849-3eb0-5339-bf76-b790411d714d | note | ACCEPTANCE CRITERIA: Ensure the box is set to the manufacturer's gap setting and temperature criteria. As below;
c23aa91c-369c-5de8-8ab8-44ea72066232 | note | – – – – – – – – –
0feeec73-2d23-5c22-b1f2-bca37e9b5ff7 | note | TABLE 1 - GAP SETTING
e891c58d-5ff4-5ff3-9238-c6209a0fefb0 | note | TEMPERATURE (C°) ¦¦ GAP (mm) ¦¦ SLIDING FEED (mm)
66611af3-57b6-5468-bd83-f4a860ce4d80 | note | – – – – – – – – –
50730ac9-3ce8-58ee-ae54-fbfe7dfb8547 | note | -3 ¦¦ 26 ¦¦ 100 (LIMIT)
63efff88-e5b9-5eac-9c35-5eef3cdea7f0 | note | 10 ¦¦ 21 ¦¦ 80
9e773f8f-2b34-562b-b860-f8bb8e0111c5 | note | 15 ¦¦ 18.5 ¦¦ 72
1a32122e-5347-5611-b1b7-3d455280b100 | note | 20 ¦¦ 16 ¦¦ 63
9680cd52-8807-509f-83f4-21d784914f1c | note | 25 ¦¦ 14 ¦¦ 56
98af6317-96e7-52da-ab43-e2034c42689d | note | 30 ¦¦ 12 ¦¦ 48
1f260a8f-c764-501e-8e6a-8f45d2e2ab2a | note | 60 ¦¦ 0 ¦¦ 0 (LIMIT)
bc9ed4c4-a727-5355-af9c-43a93ed811f3 | note | – – – – – – – – –
c8ab1522-18fe-53ad-87a7-cb2e45ab9362 | note | REFERENCE DOCUMENTS: Prazska Drawing 1PA.031.000.00.00.1, IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
3419d64c-2389-501e-9c11-7c988ad9503f | note | INSPECTION/TEST METHOD: Visual Inspection
2ad8f934-531b-5e53-8cc5-368922535758 | note | RECORD OF CONFORMITY: This ITP Signed Off
4978a0a1-04a1-51f8-8567-7ebd065dd698 | note | IP
a970107c-188a-52bd-8299-77534a34623b | note | RESPONSIBILITY: Fulton Hogan Engineer
dbf3c8bc-fa20-5c98-aae8-120122338ce5 | textbox | Date Completed:
8738dd84-9c0d-433b-b03c-b98e28eb66e6 | checkpoint | 2.2 Installation of expansion joint system
706860ce-bd4d-5705-a653-8f408b7448e8 | note | FREQUENCY: Each expansion joint box
b6d23838-fe8e-54d7-8a2a-1c6b7ca624d2 | note | ACCEPTANCE CRITERIA: Ensure the expansion joints are installed in the correct direction. I.e., moving and fixed end are in correct orientation.
23f8cb01-e6ca-55c5-9b72-e7176726f891 | note | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
3e933a9c-7f5b-5ad2-9155-f38a32dbc2a0 | note | INSPECTION/TEST METHOD: Visual Inspection
eb3b5dd3-26cd-5e05-9012-d6baa262dd2c | note | RECORD OF CONFORMITY: This ITP Signed Off
c853795e-ae39-5526-aa77-8ae7a211eee1 | note | HP*
a9b0ee15-d147-54bc-a36c-b8dc5d1f0580 | note | RESPONSIBILITY: Fulton Hogan Engineer
deb67808-beee-5081-8a6b-2f8c5ccd4361 | textbox | Date Completed:
9bf90853-667a-447f-8705-471471a6f436 | checkpoint | 2.3 Grouting
57757c80-b2c3-5cb7-beae-f168ed305da2 | note | FREQUENCY: Each box
fc5ce0a4-b79c-52a0-88f7-de3cf78fd5df | note | ACCEPTANCE CRITERIA: Contractor to ensure that non-shrinking grout fill is installed between bridge deck and rail expansion joint system.
216f70e4-d5ba-5c57-ac5d-3737f00d844c | note | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
dcc1c0b8-cc6e-54c7-ba04-e8a45d7f1b1c | note | INSPECTION/TEST METHOD: Visual Inspection
ea524431-cf30-5370-845a-8e067f5da116 | note | RECORD OF CONFORMITY: This ITP Signed Off
583c1136-7a00-50d6-bb9d-c8dc1d18f08b | note | HP*
6f86df04-536e-588c-833d-3bf8f5fefcae | note | RESPONSIBILITY: Fulton Hogan Engineer
b919753f-317d-5b43-829d-24a5d624f58e | textbox | Date Completed:
8f269267-45b6-4796-a99b-6a65c9e162c9 | checkpoint | 2.4 Construction of expansion joint
a245f6cb-dfa3-5ad7-8ba1-c46f4438b2a6 | note | FREQUENCY: Each expansion joint box
4ba90769-f5db-52a2-85ed-83349dc47242 | note | ACCEPTANCE CRITERIA: Ensure rubber boots are installed per manufacturers requirements prior to concreting.
1033fac0-b2a6-518e-8a43-30b985d88e1a | note | ○ Use anchoring plates to hold the rail expansion joints in position. Ensure that all collapsed grooves are reformed.
bbcc1cb5-fda4-5a0c-b382-54e469fa4de3 | note | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
3585d0c0-ba27-57fd-872f-e9005314bf87 | note | INSPECTION/TEST METHOD: Verify
52c9d40e-c746-51e9-b1ce-4f895ed1acd6 | note | RECORD OF CONFORMITY: This ITP Signed Off
ed3f87c1-f0c2-5881-b72c-849b989442fd | note | HP*
56ed0e56-b99e-5b38-83d1-2d51e83dc893 | note | RESPONSIBILITY: Fulton Hogan Engineer
ca406d11-d617-5b31-bfa3-aa45f782547f | textbox | Date Completed:
84f29a37-3e0d-44d1-939d-2546faf2c8c2 | checkpoint | 2.5 Expansion joint bonding system
7d84f543-a509-56ff-973a-c515e2ca9e5f | note | FREQUENCY: Each lot
57b54232-0740-593d-9ec5-b7de73840a4e | note | ACCEPTANCE CRITERIA: Ensure bonds are sealed as per agreed method with Yarra Trams
e538d25d-e4db-5265-9837-9291c8359e04 | note | ○ Ensure the rail bond is correctly positioned from old 41kg rail
fe2797aa-b620-5948-91d1-ed48d961bc39 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4, IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
4be3ee01-f0e2-5f84-9003-ff9ed08c1b2f | note | INSPECTION/TEST METHOD: Inspection / Test Method
d6403bef-cbec-5b62-bdc5-aafa500f85bf | note | RECORD OF CONFORMITY: This ITP Signed Off
8dc1a065-fe2a-57ed-a6e7-37292f904181 | note | IP
1b073358-b1e2-5bde-a6f8-d84358aed73c | note | RESPONSIBILITY: Fulton Hogan Engineer
dc346c31-cab4-5241-9654-d684de382db3 | textbox | Date Completed:
b9cc79ce-b5dd-40a3-ac4d-0190405d62e3 | section | 3 - Construction Works
0a1b1f4e-1bdc-4435-b2a0-cdd8f132663d | checkpoint | 3.1 Installation of pandrol plate
55982f4c-3f2b-5cef-9949-261b01f79f8a | note | FREQUENCY: Each lot
a1b1e370-b813-525f-ad8b-6ac38fbde0be | note | ACCEPTANCE CRITERIA: Pandrol plates to be installed as required/instructed by the client
72fefb0d-ce84-5ce5-b7f7-0e7ddf8c55f4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.3
93e3e6cf-379c-566a-a7fb-a99b8cb1c19d | note | INSPECTION/TEST METHOD: Visual Inspection
6e48ae44-7c28-53e1-ac7c-8404a5ddb170 | note | RECORD OF CONFORMITY: This ITP Signed Off
b96eb1e0-dfe9-5e9b-acc8-f65e7b09a8af | note | IP
67613ab6-9d34-5bac-b400-0434ccbba712 | note | RESPONSIBILITY: Fulton Hogan Engineer
9d27da16-40cd-515b-a769-4bd0cdb29ffe | textbox | Date Completed:
55c36cad-1477-4932-90ab-e29ced0239e3 | checkpoint | 3.2 Placement of rail
9536253a-3484-5288-8d2c-ee910b286510 | note | FREQUENCY: Each lot
f63b3640-268a-54bf-b4c8-5f479da55f70 | note | ACCEPTANCE CRITERIA: All track work, including expansion joint systems shall confrom to alignment, offset, level and cant as per design drawings and track charts
d9d085c0-9e03-58b6-9a9c-0d29c3f30a81 | note | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
5223cc2e-287e-5f52-bb25-c615a6baa032 | note | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
378be340-4272-5266-a5a5-280c47e756f6 | note | ○ Geometry tolerances as follows:
55460753-bf8d-57e1-bb78-d677a57ef5a6 | note | – Centreline location: +/- 3mm
8d813e9a-723a-542f-b2fc-2028e24b9e22 | note | – Level: +/- 3mm
675cb4f6-5d06-537c-a91e-9fc8df91337f | note | – Line measured (>10m chord): +/- 3mm
c5949ed1-3055-5222-9f39-8ac8aba502c7 | note | – Twist (3.5m chord): +/- 2mm
0865646b-8e8c-558f-ba5e-b7a65a3e605c | note | – Cant: +/- 3mm
b58a1bc2-9b08-529c-99ac-c17def5d6eb5 | note | – Gauge (open track): +3mm, -0mm
d6fd185d-babb-519a-a3ea-68b0e21c6fb0 | note | Note: Cant shall be applied uniformly over transitions
ab81472b-6922-520d-8268-b2f1f8f38be8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
b16e08c6-3832-5b72-a978-cd3aec49d02d | note | INSPECTION/TEST METHOD: Visual Inspection
1a8f7d4e-8218-5afb-a8e7-3aabf515b5fb | note | RECORD OF CONFORMITY: Completion of track charts
3942ab7b-15b4-598e-8a80-897bb13b6183 | note | HP*
0e9bce98-9f7b-5201-a975-3e668e27031d | note | RESPONSIBILITY: Fulton Hogan Engineer
28b96085-c871-5e24-86ee-b7cef0fbf509 | textbox | Date Completed:
18fff682-8405-4efe-b507-f8678a566022 | checkpoint | 3.3 Placement of jewellery
4347187a-b5c8-585a-ba23-619dc64099bc | note | FREQUENCY: Each lot
ebeae349-d401-58cb-8741-971b18c79dd6 | note | ACCEPTANCE CRITERIA: Each pandrol shall be fastened to track with approved jewellery and rail clips
69983c5a-2cc2-5172-a134-0099b9acb9d3 | note | ○ Clips shall be installed with panpuller or equivalent
3f4fad2c-d95c-5196-9cd9-fe01b49ab1b8 | note | ○ All fasteners shall be sealed as per agreed method with Yarra Trams
ce9c1cd9-175d-522a-93ba-47ef924ff042 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
392bf953-61d4-594e-b668-0341052f2bc1 | note | INSPECTION/TEST METHOD: Visual Inspection
cf22495e-564f-5983-a2b5-b06f4e0bb35f | note | RECORD OF CONFORMITY: This ITP Signed Off
cf8ff44f-eee8-57ef-8090-e0291db85daa | note | WP
e3d33412-9851-5c8d-ae92-cced1cbb5628 | note | RESPONSIBILITY: Fulton Hogan Engineer
9bdc8e55-61fd-5d9f-b889-bb7d1131782e | textbox | Date Completed:
7674373c-a28c-40d0-9da9-2cf4571605f3 | checkpoint | 3.4 Rail end preparation
cb239235-d250-5b07-850d-38169b8b49cc | note | FREQUENCY: Each lot
10e5d52c-a10e-539c-9839-62908fafd09a | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
1f2a17d4-9f01-5cc9-93cd-b7e2dbf801cb | note | ○ Minimum closure length from proximity of welds shall be 2m
b1e273ef-921f-5406-bf99-08241969a774 | note | ○ Rail end conditions shall match (i.e flame cut - flame cut)
fc8ff8a7-cbaf-5057-bd87-a63583e431ce | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
41db1f27-5ca2-5c6b-a79e-8b3e2c663b32 | note | INSPECTION/TEST METHOD: Visual Inspection
aeca8894-114a-5087-9e29-01cbf9e609f3 | note | RECORD OF CONFORMITY: This ITP Signed Off
7e1df97a-8bfc-5b35-9b22-206eb0247d19 | note | WP
9be6fbe5-6f44-5056-8853-66211e53d00a | note | RESPONSIBILITY: Fulton Hogan Engineer
fcfa85a0-4d7d-5b2d-aad9-bd385cc4adaf | textbox | Date Completed:
888d5050-f4f1-40d1-9812-d4fb8d139e86 | checkpoint | 3.5 Welding of rail
88b9c6ee-c658-5443-8de9-f0386060b5e7 | note | FREQUENCY: Each lot
de0b97fa-7fc4-5b1b-975c-81c0c0e1be38 | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
10e2ed6e-b2ce-5154-8710-7142017db246 | note | ○ Maximum skew at square joints shall be 65mm
eeb4f2e6-6451-5379-bda9-5c005e07eee1 | note | ○ Portions shall match rail type (i.e HHR, Ordinary)
10485235-f1d9-555c-92d3-0cfd18007db9 | note | ○ Welds shall not be within:
df952967-74fb-51db-8bee-e0b874140b5d | note | – 3m of another weld
841816d5-b865-54b7-85a1-c8fc0d996be2 | note | – 3m of a rail end
968b5882-a88d-54b0-a2d4-b2d2a6a1dcf4 | note | – 1.5m of a glued insulation joint assembly
80284bb8-b5ab-54a9-a0b3-98b5de06d292 | note | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
238ea2cf-6d4d-598d-a2f6-74b40ade2738 | note | ○ Weld Return forms shall be completed by qualified welder
54014b32-c68c-5b0d-85c5-846d2ef42129 | note | ○ Welds shall be grinded after 1 hour
c81385b4-68b3-5ef8-b47d-6d30c52c21d3 | note | ○ Welds shall be free of water
a77bfdd9-75eb-5dac-80fc-339f0ddf6c26 | note | ○ Post grinding, welds shall be cleaned for visual inspection
9eaff916-52d5-51b7-8e58-901c4fc13fe0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
04eced7e-ed11-5272-aadd-9478d219d902 | note | INSPECTION/TEST METHOD: Visual Inspection
d38a610c-e091-5e0e-876a-fa9d72807359 | note | RECORD OF CONFORMITY: This ITP Signed Off
906c8034-5454-57e2-9209-49f915ef27b4 | note | TP
4499e5cc-8a32-5356-bb4f-4feb26b66a13 | note | RESPONSIBILITY: Fulton Hogan Engineer
41f4bcc9-55da-5820-b547-326642fe3bc0 | textbox | Date Completed:
73a39f53-fe60-4c40-808e-887f6affaa5d | checkpoint | 3.6 Grinding & cleaning welds
a3509e3b-c98c-560d-8d55-c88174122f6c | note | FREQUENCY: Each lot
f814f2da-fe55-54e9-bdfb-8d7ffa220c62 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
aa7469ff-6582-5466-9dbf-bc991abf8c1c | note | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
618a3354-c6f7-5a90-b0d7-821edcad6c03 | note | ○ The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
243169b1-7f9c-5e89-b233-40b276c5ae65 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
2756ed07-a9f0-5bf4-b0d8-e58d48e77ec7 | note | INSPECTION/TEST METHOD: Visual Inspection
a4c0044a-638d-544c-a33c-eaa135754bd4 | note | RECORD OF CONFORMITY: This ITP Signed Off
50f3520a-154b-50fb-bfbb-dae4b6fc5186 | note | IP
7cc3536d-0d51-5b9b-a377-1526c3acf81b | note | RESPONSIBILITY: Fulton Hogan Engineer
63097533-2498-5d2b-b454-e03521544539 | textbox | Date Completed:
45ed9b51-54d4-4305-b730-bb1953fe1875 | checkpoint | 3.7 Track adjustment
d6633136-e29e-5176-acbb-fd667a27b7c7 | note | FREQUENCY: Each lot
79d91f53-126e-5154-b268-dbc8f5f54e95 | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths.
90b5a894-e846-5d08-bc76-1186c29dedcc | note | ○ In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
3c145092-6d1e-58aa-a471-896de918269b | note | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
0885c497-5a0c-5a71-9531-477e2ee967e6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
170233c9-f5a2-5e58-b611-e1a881efa36d | note | INSPECTION/TEST METHOD: Visual Inspection
791fdd23-2ac7-5c11-8b91-dab13a8e7a92 | note | RECORD OF CONFORMITY: This ITP Signed Off
577971db-78e6-5232-8b23-0fdf53794051 | note | IP
ebbea9c9-5bce-55e9-949b-66d44b097a4a | note | RESPONSIBILITY: Fulton Hogan Engineer
9fd9e246-4637-56d7-b037-0820a2d20850 | textbox | Date Completed:
4306d9a8-025a-4737-8dc6-daf4923083e2 | checkpoint | 3.8 Reinforcement
627595f9-df25-594c-a7cd-2960adba24d2 | note | FREQUENCY: Each lot
065530f0-9295-5c1b-81aa-2c5cb143c83f | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
ec4838e0-98c3-5c67-b068-ea09babcaf55 | note | ○ All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
f2eeee3e-a196-5411-92b6-86c7b6d71f0a | note | ○ Reinforcing mesh shall be handled carefully to prevent distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
ae1a1cc9-6650-5a8e-bbae-cf310b555107 | note | ○ Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
d7f61f79-21cc-5d61-8dc1-c605a39daf73 | note | ○ Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
ba8ec0bf-7d5d-546a-89c9-9c1d415cf1ea | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
bf96ad39-805a-5821-b07e-3404dfec05e5 | note | INSPECTION/TEST METHOD: Verify
c74544f6-e9b4-5d1e-a8f5-39c253fa54d3 | note | RECORD OF CONFORMITY: This ITP Signed Off
6114b318-1532-5783-8c59-6adc867f3408 | note | IP
da4c2b96-2416-5863-a084-905b7a0a584c | note | RESPONSIBILITY: Fulton Hogan Engineer
18d4a6eb-f125-59ee-a8cf-16ad96d2580d | textbox | Date Completed:
1abdcc4c-ddb7-4f6a-9e90-a77be3d64aa1 | checkpoint | 3.9 Dowels
9526077f-9e9a-5343-9262-da0779a30f6c | note | FREQUENCY: Where Required
dbcd2a45-33d2-54f2-aa48-05c3e09bd2e5 | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
e6b73aaa-7ec2-50a0-bb73-3945e17926ba | note | ○ All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
0b8b086c-5950-53b1-b8e9-954feaad9ace | note | ○ Dowels shall be clean and free from mill scale, loose rust or oil.
23b98454-51fb-567a-81b6-537e420bea8e | note | ○ Ensure that all dowels are securely held in their correct position until the concrete has set.
1c167356-627d-51ec-8527-7abea2c7b83f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
9fafba6c-6bf0-5078-a30f-9fc807b8f039 | note | INSPECTION/TEST METHOD: Verify
b79958f6-7c71-513c-9cca-00abf15485b0 | note | RECORD OF CONFORMITY: This ITP signed off
304fe44e-67b4-52c5-becf-8be3b05cf983 | note | IP
3ad4f46d-ed22-5c7b-bd13-ea3dc57cd334 | note | RESPONSIBILITY: Fulton Hogan Engineer
6ff24d73-7cf8-5caa-ab9a-ab22e09d6a39 | textbox | Date Completed:
3eb0c746-a68e-4181-bfaa-d204e6d0d978 | checkpoint | 3.10 Pre pour inspection
7d8697c6-1544-5b7e-9a74-dd490f66b8b9 | note | FREQUENCY: Prior to start
5609cc57-339d-5297-a3fc-bf17215775f8 | note | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
7b20a125-ddbe-5a29-95d5-8ea54aabb24d | note | ○ Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, system drainage are satisfactory for the expansion joint systems
588b2506-5351-576e-8f3a-71f9421e6d13 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
c504ad4f-e415-55c6-b899-18bc6d4ccee5 | note | INSPECTION/TEST METHOD: Inspection / Test Method
9b902563-2cb6-52fd-bcba-bbcc2c36dc5b | note | RECORD OF CONFORMITY: FH Track Inspection
8d3b0424-7b36-58bf-9af7-469452bef806 | note | HP
645cd79b-1f19-51e5-966f-3005a39f855e | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
dd391615-56ba-51e8-a67b-82628bc5b08f | textbox | Date Completed:
5233db4e-33cf-46ed-93b2-10cef036101d | signoff | HOLD POINT AUTHORITY
6667396d-44f0-4d0f-850b-2101a1291e67 | checkpoint | 3.11 Post pour inspection
ebde5b56-b5dc-52b2-8745-8b772cdc950d | note | FREQUENCY: Each Lot
6153f43b-43e4-56bb-81ba-592bd1d514fb | note | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
94d209f7-d478-5791-9e81-2444e3fc80ef | note | ○ Ensure no defects are present in slab
ce6f4eab-e7e8-50fb-a014-eb4a654110b1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
419774e0-570c-570d-8387-5dc453df2bae | note | INSPECTION/TEST METHOD: Visual Inspection
8add8994-388d-5b13-a838-e43433803f1d | note | RECORD OF CONFORMITY: Post pour checklist
1a29d18d-8fe9-523b-834e-6ac82fd3033f | note | IP
129ff921-83a4-5b5c-aae4-c69f214f8e92 | note | RESPONSIBILITY: Fulton Hogan Engineer
869fb090-476f-5aae-9ffc-6e823c10d144 | textbox | Date Completed:
ddd75db4-eac9-43f7-951a-dfaebe985ba9 | section | 4 - Testing
e5107abb-c681-4f6f-9778-1848413a0e5a | checkpoint | 4.1 Track testing
9074ff6c-b229-5390-a5df-2870a771d7b5 | note | FREQUENCY: Each weld
96f287c9-b82a-58f4-ad45-a136a579d423 | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator.
c215a874-2c40-590a-9908-15a4303ccfe9 | note | ○ Failed welds shall be cut out and replaced
21ff985e-6a7a-53e8-9b3d-21b37e2af1e6 | note | ○ Testing documentation shall be recorded and supplied to the superintendent
b5cee557-11cb-552c-8678-b0878374478d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
38081e62-fe5f-59ee-8caa-1f0feb0ac2d1 | note | INSPECTION/TEST METHOD: Inspection / Test Method
85b749ac-c881-5e05-bb41-481e737a1476 | note | RECORD OF CONFORMITY: This ITP Signed Off
215e2ae8-c4d9-5e47-adbf-b553ac2d9b9d | note | TP
74e5a539-d402-5930-a75a-3e889c86be91 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
78167ea7-ae0d-5dae-8019-91f9d9823ee4 | textbox | DATE:
ce0125e7-afc3-4c94-bbb3-1326b86abea4 | checkpoint | Final Inspection
ada03254-a8d5-555a-a7a2-d917cf125698 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d75540b5-7405-5f56-b562-b11653bd65c6 | textbox | Print Name:
6146b875-13f7-525f-9006-6d4ec0de39e6 | textbox | Position:
8d6e155b-e785-5a06-9958-ea6bf3114285 | textbox | Date:
617d610c-9400-4902-bbc6-aac91786e7fd | checklist | Order Acceptance Certificate |  | Order Acceptance Certificate
04ad3683-f6fc-454d-8775-370783a7cb81 | section | Details
f690fd0a-c16d-40df-a00f-69b9dda629c5 | checkpoint | Order Acceptance Certificate - Details:
b9ed0498-1fff-5346-9681-054be898a6eb | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
a2df5a74-d778-5d49-ac76-59f5123a9f9d | textbox | Order No.:
db068c1a-a967-5d75-ab7e-7d75483d4021 | textbox | Delivery Site:
ac071b2d-59c1-5cf3-ab57-33d8da24200e | textbox | Date on which materials delivered:
e21cc896-c0f8-564b-859e-5beb0db20b82 | textbox | Delivery vehicle (registration number):
e9ac62b8-3a07-53f3-ab14-2ae865723c74 | textbox | Subcontractor's delivery personnel (full name)
dabaf040-4593-4d63-a0cb-fa34b5cc56d2 | checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
e9fccad6-f86d-40f9-bc86-89c54fe0bb02 | section | Packaging Inspection
dc6021f7-719d-41ce-86e3-9684087e25f5 | checkpoint | Fault ID:
02493488-a0e3-5b22-96fb-8aa661df8051 | note | OK = Meets all criteria
cdbf5d45-d188-52e4-ad27-1039e98d2598 | note | QI = Quantity incorrect
95b9c507-52d9-570f-b558-a3937970ec0f | note | IN = Item incomplete
7663cfb4-2b3b-599d-b2cd-aca6f8781b18 | note | MI = Make or type incorrect
6ad8f618-4652-53ed-9a78-724aabc59fcf | note | TD = Damaged in transit
0dd0f120-5b14-541c-b4b6-2162553b75e3 | note | NI = Not properly Identified
933c1064-707c-4dc6-9bda-ba3f231db7dd | checkpoint | 1)
60c7ee67-14b4-54a6-98e2-e6325c784e86 | textbox | Item ID:
e99dc020-6003-5dab-b19c-3b202f4e5069 | textbox | Item description:
2499553f-b94e-5e87-826a-c662dc1df600 | textbox | Units ordered:
a28ee37a-b432-511d-9089-738962c6708f | textbox | Units delivered:
da29fdd0-658f-5408-936e-0a755f60af20 | textbox | Special Storage/ Handling Requirements?
823b3756-f85d-534e-9a61-39b78e703b4d | note | The following is for completion by Fulton Hogan
1848bdb8-5c6b-53a0-b5fa-be7b93bee95f | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
748ca54e-6822-55b2-ac76-caefd2ad43fc | textbox | QA Docs Delivered?
4b6205d2-3f34-5df2-847d-9b2cbf205100 | textbox | Defective?
56bc6692-4a36-5fcb-9979-edfa3edea01a | textbox | Number Accepted / Number Rejected?
28b12607-d8f7-58f2-aa2a-a00e46b92c54 | button | Fault ID: | IN, MI, NI, QI, TD,OK
f044fe8d-534d-479c-be73-d68e049ffe50 | checkpoint | 2)
0a674aa5-7eed-501a-8350-8f3ac083ee27 | textbox | Item ID:
8cf00ba3-d74e-51c0-a1b8-f87074a63295 | textbox | Item description:
0a07cb38-3d99-5ffc-b2d6-d668e963be74 | textbox | Units ordered:
e203d50d-0872-527e-9168-c71fc8f94d26 | textbox | Units delivered:
94da1b72-f479-5d99-8010-9f4f10e41d03 | textbox | Special Storage/ Handling Requirements?
6fa28e6f-de05-5dd7-aa09-ab980dd4466c | note | The following is for completion by Fulton Hogan
87842268-d9a1-5c8d-8e53-dee79834bc18 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
c51712aa-4fd4-5b99-9a55-2f9e317f1c83 | textbox | QA Docs Delivered?
69c5bb0d-b562-515a-8002-27539378e8ec | textbox | Defective?
6cf59ac5-3234-50fe-b51c-410086099f51 | textbox | Number Accepted / Number Rejected?
94fc3a6c-6a55-56d6-81cb-c434ab2b74e6 | button | Fault ID: | IN, MI, NI, QI, TD,OK
315d25d8-4455-4cc4-bb7f-44bc19185156 | checkpoint | 3)
fff09420-6028-526e-a776-d363044cc599 | textbox | Item ID:
2ef171af-fb72-5984-9f2c-ea2be20ae685 | textbox | Item description:
f090fe5c-3455-5114-9808-3432cc1cfa10 | textbox | Units ordered:
e4f0b81f-d1d1-5182-a3af-0d4e8d0c6491 | textbox | Units delivered:
b5ea9870-e33b-5f53-8668-282d35cd4695 | textbox | Special Storage/ Handling Requirements?
5f531dc3-fca5-57e4-ac9f-afb77c34446f | note | The following is for completion by Fulton Hogan
0ac7625a-73d3-5e6c-a32e-1c19eabbdc6f | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
ad382e5d-b805-5b17-ac87-afd5c47bf814 | textbox | QA Docs Delivered?
54b2fdea-b623-59f4-801c-334251140b31 | textbox | Defective?
24fb0e9c-db3a-558f-9759-beb05fafc56a | textbox | Number Accepted / Number Rejected?
8091442b-c7db-55db-96a8-bb09ce73370c | button | Fault ID: | IN, MI, NI, QI, TD,OK
0b23fdf7-5704-435a-91bc-9a767ce0b7f1 | checkpoint | 4)
f93b93d0-556c-5e40-9621-c8efbffb759e | textbox | Item ID:
7f1c3a7c-e2ac-5966-9ecb-ffaefe755049 | textbox | Item description:
0fefb678-0e26-535f-a9a2-565f092f95c1 | textbox | Units ordered:
b7183b94-ba5c-51eb-accc-9c815b10abb1 | textbox | Units delivered:
a2d088ba-c3a2-551d-a9b5-b203c3f224a1 | textbox | Special Storage/ Handling Requirements?
1ec143a8-4560-598b-8a68-8e20239a1780 | note | The following is for completion by Fulton Hogan
b06db03d-2d94-5bd9-b5bb-bc8a7af97389 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
6efd3164-fc1b-51fd-825b-67debc4be56e | textbox | QA Docs Delivered?
11913bec-813f-5580-9ecb-63729e66b9a4 | textbox | Defective?
523d88ef-f392-5fc9-af78-f4cfded5cc7c | textbox | Number Accepted / Number Rejected?
a0e97e01-182d-5a92-b4c7-22709697d53b | button | Fault ID: | IN, MI, NI, QI, TD,OK
2e4f1c68-8840-4956-bde7-b0092af7e880 | checkpoint | 5)
ba418346-0a4d-5f34-88a3-675ee3a6de59 | textbox | Item ID:
990a7d19-4d3b-5ee0-aaf9-59d2501d3306 | textbox | Item description:
94ed7e63-f332-5f90-aa3b-52cd80da6cad | textbox | Units ordered:
1be8fe42-72e8-5369-b11a-f971fe73a635 | textbox | Units delivered:
e0e1daba-eb27-5847-be21-5eb32e45282f | textbox | Special Storage/ Handling Requirements?
8181c404-3901-5c3b-9488-adde459333df | note | The following is for completion by Fulton Hogan
29805a96-19c6-5450-9022-043779b6bfd6 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
d1992036-41a9-5489-8676-14cdd0e1d867 | textbox | QA Docs Delivered?
c61137ad-4ee9-54ee-9d22-6143986ee2dd | textbox | Defective?
c21f0840-01f2-55bd-8629-af866185cfe5 | textbox | Number Accepted / Number Rejected?
d7520235-f32a-5d00-92dd-8598eba39433 | button | Fault ID: | IN, MI, NI, QI, TD,OK
47957907-f6e0-4818-b6b4-62f7811bb2c9 | checkpoint | 6)
9c02582f-b889-5521-9ee7-b63e6a14c858 | textbox | Item ID:
5be92e56-f766-5d36-9a3d-f21baa4c2bf3 | textbox | Item description:
2184ae4b-3e82-5dfb-8d65-8d6607c31940 | textbox | Units ordered:
e7235e4e-6d75-590e-ab5b-2b8cde7405f2 | textbox | Units delivered:
d3f62b66-07d3-5d0f-8714-6d02a4bd5086 | textbox | Special Storage/ Handling Requirements?
565729e7-9c88-5e6f-8912-c855ffd9b05f | note | The following is for completion by Fulton Hogan
c88f3abe-88eb-5b3b-b7f0-aed97c1e5f98 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
247eacf7-a3e0-57ce-9521-3f2572d8e5ba | textbox | QA Docs Delivered?
b6462d65-0c35-54c0-825f-3df3f8a26e93 | textbox | Defective?
eb1a5141-2f61-5e02-8b65-7cfd42c4b1f0 | textbox | Number Accepted / Number Rejected?
0bf4a4fd-54e0-57eb-8a90-941fe2a45af3 | button | Fault ID: | IN, MI, NI, QI, TD,OK
49aa0f6b-0cab-4a9c-906c-a84d50d369fe | checkpoint | 7)
53ced6e8-952b-52ef-9dbe-cb75bf869ad6 | textbox | Item ID:
55ebe0bd-4802-5349-81d5-0aa12476bf96 | textbox | Item description:
1ac0554e-7186-564b-a8c0-b3558dbce543 | textbox | Units ordered:
e6bbf63b-e735-5931-8430-d76d57f75769 | textbox | Units delivered:
2dc3f935-dcd6-552c-b6a3-b9080f5295af | textbox | Special Storage/ Handling Requirements?
056e7615-ebac-583b-9d1d-98664c16034d | note | The following is for completion by Fulton Hogan
9d828777-038e-5369-a271-8c7402411acf | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
002a43da-fe34-58aa-a8b0-c62f7ef93163 | textbox | QA Docs Delivered?
aa623434-fb1c-509f-87f2-f0364476c18b | textbox | Defective?
dbe7365b-16ad-5974-83ca-66f818bbaaa9 | textbox | Number Accepted / Number Rejected?
b0b1a18c-aa97-5fb9-b076-3c68e1a74dc1 | button | Fault ID: | IN, MI, NI, QI, TD,OK
23fb09f2-d2fe-40b5-a445-c99b93b1f324 | checkpoint | 8)
7f738ee9-07bc-59c8-968e-bdaa7106461b | textbox | Item ID:
c1c207e8-1824-5229-96b2-d372f1317a37 | textbox | Item description:
18a94de2-e0ee-574a-9107-d94f6be23a8a | textbox | Units ordered:
e659dc05-bd2a-536d-ab9b-39dc96b84191 | textbox | Units delivered:
37fee92f-87ef-53cc-a5b6-1e92ab8da32a | textbox | Special Storage/ Handling Requirements?
a0c74ad0-17cb-5e08-bbdd-49dfb034d0b9 | note | The following is for completion by Fulton Hogan
a33c78da-d72b-547d-846a-11b6ad797933 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
6c956576-4baf-54c5-8784-f8444dc1e58d | textbox | QA Docs Delivered?
5aa9875c-58ab-5492-ac67-928b5e52f074 | textbox | Defective?
e8ad1df4-5b1f-583b-afba-0195b5a3fe07 | textbox | Number Accepted / Number Rejected?
54ea139e-cf5a-573b-aa75-bf565cef6133 | button | Fault ID: | IN, MI, NI, QI, TD,OK
058d2a28-689f-4cc2-acdc-9221d55c0360 | checkpoint | 9)
708e1d7e-537b-5289-8e39-45fe0877cc26 | textbox | Item ID:
8bc73834-cc2d-5605-a320-46bbafca77a8 | textbox | Item description:
a2b1834d-7dd7-5e62-aa3e-107e0adcbf9d | textbox | Units ordered:
b05a1525-8790-5314-ab7c-eb919eff5532 | textbox | Units delivered:
59e8bb72-9b7d-5edf-b06d-4258845d6a4e | textbox | Special Storage/ Handling Requirements?
9f0dc27a-a306-5653-9efa-aca0f4cb7f88 | note | The following is for completion by Fulton Hogan
05f7a5eb-4a27-54a7-95df-1625f818740d | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
860dd9cf-dd04-5a5d-9a4d-9602c9baa9dc | textbox | QA Docs Delivered?
0e565ce2-3b7d-5a8f-9873-892fface1009 | textbox | Defective?
6e582531-1e50-53cc-907a-6d1fa206adbc | textbox | Number Accepted / Number Rejected?
ba1daf16-ef60-55e9-9e9f-0fa2bc319155 | button | Fault ID: | IN, MI, NI, QI, TD,OK
2a53f88e-d97e-4527-ac90-b752e14f7384 | checkpoint | 10)
a6d7ee77-6755-5de9-af00-1a77bb523cc3 | textbox | Item ID:
16e9b6ed-c7ac-586c-ae5b-9f2efd8544d6 | textbox | Item description:
d824e899-7201-5fc6-ac3a-62b6638eed3f | textbox | Units ordered:
0932e6ba-548a-516c-8bc6-70748f72ea78 | textbox | Units delivered:
5bf2a793-6c96-5013-9c5a-ee98f6593402 | textbox | Special Storage/ Handling Requirements?
cb075035-959c-58a5-b5a4-6931e50321f5 | note | The following is for completion by Fulton Hogan
fc1e1244-4028-50ef-8691-870d492a0b80 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
57d83fbd-cf7b-5047-9274-1529dfc68c5e | textbox | QA Docs Delivered?
d99252ab-041a-5c06-a354-32e667844a45 | textbox | Defective?
cbb564e0-1b00-545f-8139-47d96a5370ec | textbox | Number Accepted / Number Rejected?
e1c315de-bbba-5fda-97c0-4069aa2a6acc | button | Fault ID: | IN, MI, NI, QI, TD,OK
76453c6b-0cac-4ed1-9953-d1f7f71d522b | section | Sign Off
076b93f7-ad09-4f1c-9d56-e07ed6ea468d | checkpoint | Accepted by Fulton Hogan
af79844a-8cde-4bf7-ad0a-7ee62e878716 | signoff | Sign Off