## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release
7f694258-afd9-4882-9923-f3d688de732a | checklist | ITP-000 - Client Pre-Construction Checklist Rev1 | itp | ITP-000 - Client Pre-Construction Checklist
18c558c8-c92f-4d3c-9cfd-51f942e9ce95 | section | 1 - Pre - Construction Works
c7f6031a-3745-4e38-959b-d053a3b8e4d5 | checkpoint | 1.1 Asphalt - submission of asphalt mix design
c2594028-97cf-5fa2-acab-acd92cc39fdb | note | FREQUENCY: Prior to commencing asphalt
bd24936f-bf8e-5b32-b288-0a638fc4b9d6 | note | ACCEPTANCE CRITERIA: Ensure the mix design/s have been registered and are approved by Superintendent prior to laying mix.
e8aa614f-89c0-5d87-8482-389f69f08164 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09. RAP DoT letter from production plant
7765a7af-0fd0-507e-a078-998e68d34ba1 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from the RAP DoT Letter.
c436bb80-b790-5812-b274-56df02ed9787 | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
d889d90c-00e5-53a7-90bb-935b4faea868 | note | HP
a9aa9830-2293-5edc-9131-cb694914c38e | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
1da9b33d-651c-5b62-80e0-14832bac8d98 | textbox | DATE:
44a5d687-1032-488b-8058-b12cb5e5b812 | signoff | HOLD POINT AUTHORITY
8b70a8b9-b974-47ae-a65a-88db30658f62 | checkpoint | 1.2 Concrete - submission & approval of concrete mix design prior to commencement of project
b92324ec-58d2-54e5-b7d8-eefd0b988c1a | note | FREQUENCY: Prior to first concrete pour
47dac52e-3d8c-50ce-9fd3-4a1f9b61493a | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix shall contain minimum 460 kg/m3 cement content. Special 50 mPa mix is to be VS502B25MET1 with a suitably flowable design slump agreed prior to construction.
3f0d0394-a7e2-547e-8f9d-e0d9109033c4 | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 VicRoads Spec. Cl. 503.04
249206f0-88b9-54f6-ad50-b08a2179584a | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from supplier
196bde20-a4fb-5c4b-8a54-109c8d28c48e | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
ee0d4f79-3664-500c-bc6c-ca2fa9361154 | note | HP
ab13a186-472a-52f9-b6c3-661587f83c4d | note | RESPONSIBILITY: FH Engineer / Superintendent
315e6ab5-664b-54d0-b097-f4d1d972d6fe | textbox | DATE:
f92f8325-bc73-4e4a-8a2e-ac849b2a2f8f | signoff | HOLD POINT AUTHORITY
2f20c85d-4394-40fa-ba3c-1107a5fb9276 | checkpoint | 1.3 Welders qualifications, competencies & work methodology
a6151f76-188f-5695-a576-d22bbed71d1a | note | FREQUENCY: Prior to commencing works
6c84e434-94d0-5a21-ad15-2679e2e6e643 | note | ACCEPTANCE CRITERIA: Weld methodology to be submitted prior to commencement of works. Welders shall be trained and compliant in Australian aluminothermic welding competencies as outlined below;
afee8c04-5835-5f88-a122-7cde90ddf15b | note | – TLIW2012 Grind Rails
f1b75cde-cf05-5e3a-bf7e-acaf3d792278 | note | – TLIW3015 Weld Rails using Aluminothermic welding process
d9607035-89dc-5b81-aa39-c1838384a8c2 | note | – TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
0ae696c2-b9c5-523b-a1ab-1ac373fb3f04 | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 Appendix C
c7d62929-6548-5df0-bfc7-925f9ba1b7ee | note | INSPECTION/TEST METHOD: Welding methodology
5519079a-9e9d-582d-871f-0bc5d0a54fc2 | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
6ec838d8-5398-55d5-ad99-7ac0945707ca | note | HP
c01aa2a1-0954-536c-8686-12878dc639e1 | note | RESPONSIBILITY: FH Engineer / Superintendent
88a2ca52-b5ce-5dcf-b778-1503863c3268 | textbox | DATE:
37ed168d-9a63-44ac-946d-88b7878e4657 | signoff | HOLD POINT AUTHORITY
c4512c79-40ec-4c01-ac1c-8d8ee79958ba | checkpoint | Final Inspection
cb680214-aa47-5ba5-bbde-67e7e449fedc | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7d5ea351-9ebc-5536-ac1a-11af7d34f8de | textbox | Print Name:
6e498d8c-a293-5c9e-8c4b-d8488af39bcd | textbox | Position:
b7a2db9a-6256-5f12-ad8f-9d843cc0b978 | textbox | Date:
f929064e-568a-44b8-9265-f24f2a8a1d28 | checklist | ITP-001 - Subgrade Preparation Rev2 | itp | ITP-001 - Subgrade Preparation
001dd911-d937-48b2-98d3-800d71131449 | section | 1 - Preliminary Works
08e0024d-231b-4647-9a6e-d43302fb49fd | checkpoint | 1.1 Prior to commencing any activity
62f9d2a2-eb0f-5668-a613-e424ef6d3bfc | note | FREQUENCY:
d1deab9c-1c5f-588a-bb14-8b70511a5ce7 | note | ACCEPTANCE CRITERIA:
1579c397-9798-5825-be1e-814e75f24c77 | note | • Ensure that all employees and subcontractors are:
106e3cdb-ff1c-54fb-9698-e73a571a32a1 | note | – using the correct and complete set of drawings
0734c511-b115-5d62-b9ac-44a90f4937f4 | note | – all drawings are the latest revision
0ddf6bb1-41dd-5e60-a227-f2fcb0938263 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
73a3f299-75e2-5df7-8a02-8f600426869a | note | INSPECTION/TEST METHOD: Visual inspection
da8a8733-2ce8-5f1f-86ee-e504c77e76f8 | note | RECORD OF CONFORMITY: This ITP signed off
4e76c56b-50ee-5eaa-89cd-a866be104203 | note | WP
e4bc8fea-7824-5a24-a472-3acf23feaf9d | note | RESPONSIBILITY: Fulton Hogan
77e8f216-8afd-5162-9926-208f3cdabaca | textbox | DATE:
e14f2d41-5934-4e94-b41a-356c38a4340d | checkpoint | 1.2 Implementation of all measures and controls
f122a68a-35cb-5b64-835c-26e7638f23d9 | note | FREQUENCY: Prior to commencing any activity
b59eee26-c887-5111-abe8-cc1f482e5c2e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
696a264e-24dc-5277-b46c-5dc95b4190fd | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e3c12262-f245-5553-b3c6-a36159b175f8 | note | INSPECTION/TEST METHOD: Visual Inspection
04fe345a-688b-56aa-ab33-7f70914e6bc5 | note | RECORD OF CONFORMITY: This ITP signed off
b5b255c7-1f7f-56ce-a8c9-3bffe07da55e | note | WP
e4fa5ec5-eb0d-58e6-8d7e-30f8176caa7b | note | RESPONSIBILITY: Fulton Hogan
8ea1ef1d-bca5-51a3-85fb-e223293bb64c | textbox | DATE:
89b1c2e3-80b1-415f-b4b7-f68a08c4ceb3 | checkpoint | 1.3 Selection and approval of Disposal Site
7892b0ae-154a-5f04-be8b-da8253677e7c | note | FREQUENCY: Prior to commencing any activity
e8301558-c3f3-5870-85ba-07ee8f58e5ca | note | ACCEPTANCE CRITERIA:
883c2214-a136-5332-820b-a871f747e7f8 | note | • Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
4294df9a-93f3-5892-a985-666f23a3d0ba | note | • It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
fa799b54-8fd5-5e73-a1cd-44bdb5a8768e | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019ST-0033 CL. 4.2.1.5.
c58f5fe8-4d8b-57aa-9c7c-68f2f7415a23 | note | INSPECTION/TEST METHOD: Verify
78b91ef3-1683-5bab-a89f-5f19cda169d5 | note | RECORD OF CONFORMITY: This ITP signed off
782a07ef-35f7-563c-98a6-13a22cc9a8be | note | WP
96f78f6a-d6d1-5547-9ea1-f0b7cd36ddb1 | note | RESPONSIBILITY: Fulton Hogan
ee8f6c8a-c918-5fd9-8091-a94761fe2b6a | textbox | DATE:
165cd49f-4c12-478d-8bd3-99ed859ad1aa | section | 2 - Construction Works
6ead4c3d-1f76-4041-98b9-735797e5e66a | checkpoint | 2.1 Excavation
04a24fd2-5b00-51d7-a9ca-c9aa717f319a | note | FREQUENCY: Each lot
efb94f2e-cd37-5320-8a6e-d0de104247e9 | note | ACCEPTANCE CRITERIA:
baa863f2-d1c9-5a5c-b146-8343f22e29d3 | note | • Plant and equipment shall be appropriate for the task.
9c40d5dd-dc67-5291-82d7-3ee417c0d39d | note | • Excavation operations shall not disturb areas outside the limit of works
c2d626ef-e9a1-518f-a3de-79624e2d314e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3., 4.2.4. Subgrade Preparation Work Procedure
0f3001c4-d5be-5e9c-9fd3-8d6ee43abf80 | note | INSPECTION/TEST METHOD: Verify
06a955ff-b6d8-5e17-96cf-92e5f236b8ac | note | RECORD OF CONFORMITY: This ITP Signed Off
f026da7f-121b-5bdc-8149-f050f061d70a | note | IP
2635c1b0-40d0-53fe-bb25-835a7dc906e3 | note | RESPONSIBILITY: Fulton Hogan
2fc52efc-3c8d-503c-8f9c-dbaaafb5fa9e | textbox | DATE:
802ca758-3ed1-49cc-b623-d176b80ca889 | checkpoint | 2.2 Reinstatement of bonds
b2f18abf-29ff-5c3c-8b2b-617b0b15d20d | note | FREQUENCY: –
1611c3e7-3fd9-5250-835c-4f5d3dabcb40 | note | ACCEPTANCE CRITERIA:
c56f39e4-6f45-57e0-82a0-4e725de86474 | note | • Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
ba86160b-c645-526a-818d-babb46b3cb50 | note | • All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
2db21435-71e8-55f6-94ff-0ae774c83bed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
b05afce8-1d41-5aef-9b80-4cb06cea6376 | note | INSPECTION/TEST METHOD: Verify
47abd4dc-af42-5443-a15b-f395a277951a | note | RECORD OF CONFORMITY: This ITP Signed Off
7b78c6ce-2524-5562-b24a-7198fd2e4651 | note | IP
1b1bf03c-2c0a-5a77-ac2b-045cbe47602a | note | RESPONSIBILITY: Fulton Hogan
21166443-ea74-569e-900e-144e71da9eae | textbox | DATE:
aa819b0f-1537-40ff-8ff0-f28640a7253e | checkpoint | 2.3 Inspection of Subgrade Material
9e19d421-f547-5b12-b685-5339217907b1 | note | FREQUENCY: Each lot
6db22b10-27f3-59ce-acd5-9ca5c8f8ba01 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
5da3edb5-abe4-565e-bd14-4f32ee34d3e7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
cfa6d697-5076-5877-9dfb-4d1e1f694f91 | note | INSPECTION/TEST METHOD: Verify
fe75f356-711b-5278-84ba-856975c88e52 | note | RECORD OF CONFORMITY: This ITP Signed Off
2f4cbba4-8165-5e31-89fd-9360b2b07247 | note | HP
5514190b-9b13-5929-a8da-70c531b745c0 | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
d6d7c255-3e25-5623-841c-ba0fdb9c2169 | textbox | DATE:
8d227978-c3fd-4821-9092-b79b3a2a723d | signoff | HOLD POINT AUTHORITY
de70ef90-206d-417a-bbae-d4a027f4aa30 | checkpoint | 2.4 Width and Level conformity
a94a2e99-32c1-5406-8109-bec445d72519 | note | FREQUENCY: Each Lot
5b68f9bf-3a2e-5301-8d68-fa6d3f28eaaa | note | ACCEPTANCE CRITERIA:
37e97c70-0483-572a-8ed3-d3d8f2f8a989 | note | • The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings.
bb29ddde-bd63-5bba-bac4-9e4b46f82e37 | note | • No point in the general surface shall vary more than 12mm from a 3m straight edge.
1525af19-3354-5a0b-aa93-4625836b8e10 | note | • Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
78c26b8d-8d93-5c84-a9b7-4d659afd965f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
05b5309a-e090-5069-8281-6f28f3100869 | note | INSPECTION/TEST METHOD: Survey Report
2b4df271-387b-5333-9d89-792db466b974 | note | RECORD OF CONFORMITY: Survey Record
d69316af-172f-51cd-9f5d-29ae147e860e | note | IP
e31c514f-1589-5939-a702-b18e3976e687 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
91b5070b-f523-5c2f-86b4-837a5523bdf6 | textbox | DATE:
9354554c-477f-46cc-80f3-fd6152b7dbb3 | checkpoint | Final Inspection
982e8627-7db0-5628-bc49-d17e69663b91 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e0019a79-27e0-597e-a9f1-a27028318fe2 | textbox | Print Name:
9af4c584-2dc1-5ed8-900b-5cacb3c76a9e | textbox | Position:
240943ab-196e-5849-a9b3-471e09479da2 | textbox | Date:
4bd53acd-6405-4e3e-a599-dc5d4aa54a1a | checklist | ITP-002 - Feeder Conduits and Pits Rev2 | itp | ITP-002 - Feeder Conduits and Pits
c0fdca6c-9fb3-4ae7-913f-6a4b051a60ac | section | 1 - Preliminary Works
a46884c7-852b-4bc8-8107-83cbce107959 | checkpoint | 1.1 Check for correct documentation
1dd02b6f-cb20-50b0-af91-29c941336207 | note | FREQUENCY: Prior to commencing any activity
74d3e9ed-67fe-5385-abae-33733cce56ae | note | ACCEPTANCE CRITERIA:
cb06cb9c-ec2f-56c7-ac67-68dc8af70f95 | note | • Ensure that all employees and subcontractors are:
7edbdd30-85f5-5bb3-a6ff-93580d65be30 | note | – using the correct and complete set of drawings
ef193c2a-8d93-5c32-8590-d75b06db3c49 | note | – all drawings are the latest revision
930331f8-238c-59e6-b164-afd483b350d6 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
62de1c25-2d66-5785-ab8b-edb723f6c9b6 | note | INSPECTION/TEST METHOD: Visual inspection
3796e4e2-e520-5904-8cbe-3c6218e6ca9a | note | RECORD OF CONFORMITY: This ITP signed off
c9939422-5637-5878-93db-86a8bc3de6e3 | note | HP*
bb638971-8de7-5b83-a139-01a79b71c691 | note | RESPONSIBILITY: Fulton Hogan Engineer
5abb1941-da2c-5861-bb51-10776769e729 | textbox | DATE:
9b0cad6e-a5d1-45a0-b1c4-0af4c94088a4 | checkpoint | 1.2 Implementation of all measures and controls
0c73006f-2171-5f13-8e75-af39e9451324 | note | FREQUENCY: Prior to commencing any activity
db30c66d-9b03-55e2-8fd0-49c81aa634fa | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
ea979269-855e-5d61-8c31-93defbcadb3c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
ff0a736e-cf31-5f75-84c3-90ef359b193d | note | INSPECTION/TEST METHOD: Visual Inspection
6d4bc889-2df9-52f1-b3df-66d87db0aa9b | note | RECORD OF CONFORMITY: This ITP signed off
50a3cc96-050f-5cd9-bd0d-ada92a712982 | note | HP*
03e3e14d-2f87-5273-91ed-600a1dc081d5 | note | RESPONSIBILITY: Fulton Hogan Engineer
3510f2fe-8b18-5c80-8b30-7f212bd7ed29 | textbox | DATE:
51127dad-de18-408a-b4b8-8c4bd7cead89 | checkpoint | 1.3 Materials
cd71f4d7-f62a-5521-909e-683d75311c6f | note | FREQUENCY: Per Batch
89cbbdc6-5627-5fa3-abb7-de1601ef85a0 | note | ACCEPTANCE CRITERIA:
477fe3bc-18c4-5c50-8a8e-77ecbab99503 | note | • Electrical supply conduit to be Orange
0187fab5-714c-5479-9541-206fb528cfdf | note | • Heavy Duty 100mm diameter UPVC
31a6bd62-579b-5e79-b740-9ef6d5e62d9b | note | • Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw
e17d7cc9-f5ca-55bb-9df5-8e91e376ff4b | note | • All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
695bf958-fdf2-568a-a789-be08fcfd8844 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4AS 2053
f76b0ca7-4bf5-5269-b265-69d34d90254a | note | INSPECTION/TEST METHOD: Verify
6c41a7b2-6e51-5498-ba67-cad5a1b5f70c | note | RECORD OF CONFORMITY: This ITP signed
a4ec63bf-b7cf-5bf3-a7ae-33cca2f6165f | note | HP*
dc835441-3994-5f4b-9d73-a8281cf2e1c4 | note | RESPONSIBILITY: Fulton Hogan Engineer
d567f42e-33df-5466-af48-b2c30a899760 | textbox | DATE:
1033c23c-c402-49ae-b26d-ec1c7717fbb5 | section | 2 - Construction Works
5ba0b3f0-ba25-4425-9842-d89ba5ecff7b | checkpoint | 2.1 Survey set-out
f4301acb-d642-58c3-9c91-54e6dda108bf | note | FREQUENCY: As required
c9e86ae9-3028-5f15-91c5-41e83d3d343c | note | ACCEPTANCE CRITERIA:
3a1642b3-eb16-54a4-8bef-8a45a510c6c1 | note | • Work is set out in accordance with drawings.
34f1a8d2-dc7e-58c9-87a8-3f5712644582 | note | • Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
c501af14-d912-57c5-9578-d28bcac86dc4 | note | REFERENCE DOCUMENTS: Work procedure
37426b98-c29d-5140-aaf8-33c6a9350155 | note | INSPECTION/TEST METHOD: Verify
0444e3f3-2ca7-5856-bdfd-0454c0f20988 | note | RECORD OF CONFORMITY: This ITP signed
a8e1d7fc-d755-5fc0-b698-932d2cb53031 | note | HP*
60e27b74-8d7f-50a1-9694-994558cbde7b | note | RESPONSIBILITY: Fulton Hogan Engineer
4a9e3882-895f-517a-b27f-0902b2a0e8bc | textbox | DATE:
e149b514-72a0-41c2-bc41-44211afed155 | checkpoint | 2.2 Excavation and Trenching
d257f2e6-1587-54ce-b5a0-e39009ff8322 | note | FREQUENCY: Prior to Installation
4ca53c3d-c27e-5042-9cb5-a1d5afcdb073 | note | ACCEPTANCE CRITERIA:
65eb0d15-fb8e-518a-a50c-9181451805e3 | note | • Minimum cover for underground conduits shall be 600mm
617eee52-1727-5330-a011-7de41c7b7a95 | note | • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
7c9fcdfe-8631-5290-9ac2-4cdf29b46ba0 | note | • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
137dc1b8-5945-5b7f-85a8-c2bfcf127aaf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
551c3555-25ba-52c0-a31b-a904f3b38f4e | note | INSPECTION/TEST METHOD: Verify
3d12bbcf-bf4e-5aee-8b23-40657afa4424 | note | RECORD OF CONFORMITY: This ITP signed
6df89054-41bc-5053-b592-6943742e5374 | note | WP
9628fea1-0b93-57d6-9347-e9177e8555da | note | RESPONSIBILITY: Fulton Hogan Engineer
9b6da768-b289-544b-9893-e07ad0d1c3bb | textbox | DATE:
7225e839-da4a-45a2-948a-60d6e7fb480b | checkpoint | 2.3 Installation of Conduits and pits
c832c8ba-8e13-5576-b77e-7d707229268e | note | FREQUENCY: Each Lot
c099495d-eafe-56ac-8c2f-54a3d87f2750 | note | ACCEPTANCE CRITERIA:
8bbddfbc-3ff5-5233-93c7-ddab287bdaab | note | • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
1dda2e31-5566-53b8-b178-5c4c90ba0066 | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
b77f9ef5-236e-5f41-b82a-107c9789d2df | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
25cb1706-cb3c-5884-826d-79b4c50b6512 | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
63a37aaf-930b-52fd-9b3f-71e527be293f | note | • Conduits shall not be subject to construction loadings
44ac61d9-f53d-58e7-bfcc-cf22ed64914e | note | • Pits shall be constructed as to allow for class D rated covers
d7ca8d42-7294-50a1-bec9-a00e641e6864 | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
86a38c3b-55b5-5563-a9b5-85eb1a3ca008 | note | • Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mmbeyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
1693d599-26a2-5db9-bcea-e91a55976d89 | note | • Conduits shal be placed a minimum of 100mm above pit floor
4a76aea0-ab91-5d46-97d4-b73b3d27525d | note | • Conduits installed for future connections shall be installed to the track Margin
6de82dee-719c-50e1-adff-3adc0e3a5481 | note | • 100mm of concrete around and under pit lid
f6c9a846-0382-5487-84d3-383deda05fa8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
73ca6c71-6ee6-5294-9efa-9ecd1ef6bd36 | note | INSPECTION/TEST METHOD: Visual inspection
b15e974f-0393-5c44-a5a9-c666a7888569 | note | RECORD OF CONFORMITY: This ITP signed
aacf2caa-b99c-581d-8649-036b5c2f9696 | note | WP
342950e6-b2ad-50ad-81a3-93406401b868 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
50280934-0bb4-5a28-bae4-e322d738a3ee | textbox | DATE:
037ee90b-47cd-42e5-b832-d64d6cf4d41b | checkpoint | 2.4 Inspection of conduit installation
680d57be-c1a2-5bee-bc0d-b26d7dea7497 | note | FREQUENCY: Each Lot
4ab9713a-916a-5125-b601-5df2b9f9db40 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
50502878-4ef2-51e2-86aa-35a7391036bc | note | REFERENCE DOCUMENTS: Work procedure
77266c6f-dbf5-53db-8d4f-02ade1712c3e | note | INSPECTION/TEST METHOD: Visual Inspection
6a65f469-134c-52c1-9015-f83457acf783 | note | RECORD OF CONFORMITY: This ITP Signed
f9e33d29-3934-5a49-8280-75a3730388fc | note | HP*
44ea229e-2696-590a-8891-6c3ec09cf3e1 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
e58453ef-ea0a-56a5-82e5-d0d577fd9df4 | textbox | DATE:
0460ee88-5f82-4f99-8d42-74966ffdabe9 | checkpoint | 2.5 Back Fill of Trenches
38e9b78a-16b7-5fde-af32-b7769317baad | note | FREQUENCY: Each Lot
884f29c0-fcad-5d0b-9059-07402f3ad160 | note | ACCEPTANCE CRITERIA:
6ff2836d-94f8-52fb-8f48-92a0277edb60 | note | • Backfilling (Only to be used for road crossing trenches)
05b9fd81-93a7-5f3b-9473-b7510d25335c | note | – conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
cb73b548-e6f7-5136-9398-1cd7b2baa95f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
b2852812-e46c-58d7-bc73-e4fb38df8f1f | note | INSPECTION/TEST METHOD: Verify
16e3ab25-2e01-53a0-ac5c-89c16803e07c | note | RECORD OF CONFORMITY: This ITP signed
9e89c5b6-a8fc-5ba9-a9d7-ba483bb284ea | note | WP
c3c2a196-db26-574b-9c63-29c835e28373 | note | RESPONSIBILITY: Fulton Hogan Engineer
fa22bae2-4241-5ca1-aad0-5315d4ef74da | textbox | DATE:
7c08edda-a5ad-4374-8060-88d932440622 | checkpoint | 2.6 Installation of Draw Cords
c267afaa-f569-5831-b99c-9af873e02a53 | note | FREQUENCY: Each Lot
14ae882d-8c13-517a-abf4-9d30b6d45ae9 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
207eecf7-9b02-50bc-82f9-f09b75523e68 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
44b04b8f-37b1-5cf7-9709-4e339847763b | note | INSPECTION/TEST METHOD: Verify
01a3ef3d-2436-5787-ac79-7c0574dcdc79 | note | RECORD OF CONFORMITY: This ITP signed
4ca78694-0202-5ed5-a302-b5be118da294 | note | WP
0259af1f-8864-555e-b3a6-f5844ebef30e | note | RESPONSIBILITY: Fulton Hogan Engineer
4d65725d-06e0-5a21-9c13-792fcc4ff712 | textbox | DATE:
5d7709fb-6c38-465e-848f-7c16d40450d5 | checkpoint | 2.7 Compaction
d7d9a326-831e-5775-b3da-348c1bffcae0 | note | FREQUENCY: Each Lot
9807efd3-112e-593f-b589-1dff7bb37bb2 | note | ACCEPTANCE CRITERIA: Bedding and backfill material to be compacted using mechanical plant During compaction optimum moisture content of bedding and select fill is within 85% to 115%
c34562e0-142d-5685-a626-26cc94b2c679 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
aee163b4-25cc-5e10-b899-03b7c19b3c93 | note | INSPECTION/TEST METHOD: Verify
0d3c485b-a2a1-54f3-84df-3308a9f41e1e | note | RECORD OF CONFORMITY: This ITP signed
2162a43f-01ce-5819-861f-91f4860501a9 | note | IP
898fb964-89ac-50e9-abb3-f20b564b9095 | note | RESPONSIBILITY: Fulton Hogan Engineer
3eaea696-d67b-5800-82ff-271f3f19d4a6 | textbox | DATE:
81757977-3546-4c59-9538-3d82d7ecce0b | checkpoint | 2.8 Feeder Pits & Pit Lids
c50215c1-1617-561d-bb94-f0fd734cde58 | note | FREQUENCY: Each Lot
43ef3cfd-e862-5fbe-b64d-e4e707668cac | note | ACCEPTANCE CRITERIA:
71c052cd-dd63-5c3a-80cb-1054046c039f | note | • Feeder Pits constructed and installed as per drawings
7b82e055-38aa-5ef6-be3a-fb7831423ff8 | note | • All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
222acd19-d724-5a6d-aa9e-6d288a7e831b | note | • Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
ca0a7b13-836d-5154-ab69-03806ad53bbb | note | • Gatic pit lids shall be filled with structural grade concrete
f82b7bf3-9e96-5151-b848-2e2cce6ad230 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
0cd1206e-f5b9-5de5-a0fa-7f4eb70a1b28 | note | INSPECTION/TEST METHOD: Verify
0c6f21e3-2390-5f81-9378-5a8f9999ae3f | note | RECORD OF CONFORMITY: This ITP signed
b0fdb187-67b6-59c7-9072-db596abf1337 | note | WP
89ae9fbd-0fc5-5489-b2a4-1c3553c6b966 | note | RESPONSIBILITY: Fulton Hogan Engineer
79ade2eb-391a-5102-8175-d1d419475791 | textbox | DATE:
78da752a-3eb2-409b-ad7c-09e0da86c9fe | checkpoint | Final Inspection
4889b1e6-cdf7-5283-836b-dff8808bd0b4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4adbe82e-a0db-58fb-8417-21fd7ca999a6 | textbox | Print Name:
a6714e63-3953-5b7b-9188-a6f235fc564a | textbox | Position:
81671e29-e7a6-5830-b391-36e62c60ca03 | textbox | Date:
5c9dd9ae-5d73-40a9-950e-78a5209e1f91 | checklist | ITP-004a - Class 2 Base Course Placement Rev2 | itp | ITP-004a - Class 2 Base Course Placement
a58d392b-8507-40de-9d14-3b67c45a49a7 | section | 1 - Preliminary Works
a0bc2d42-8bdf-4ec6-9419-cfdd9492eb6b | checkpoint | 1.1 Check for correct documentation
cfc7655d-31c0-5ef5-9b85-4c1b13e35450 | note | FREQUENCY: Prior to commencing any activity
877f7fa9-4440-5784-a2c8-ff7bac9f47b6 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
f8b78a94-e4ac-588c-ad41-0a17b533ea6b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8fbb0231-0f9f-5ada-97dd-09062d57d0cc | note | INSPECTION/TEST METHOD: Visual inspection
3c2e8f40-9c97-5315-9a51-b2f35bc9a093 | note | RECORD OF CONFORMITY: This ITP signed
b244c56e-594d-5115-9d53-662078c07aff | note | HP*
69edf44d-eea9-5f41-927a-da07444e7b58 | note | RESPONSIBILITY: FH Engineer
fd19d9fc-3881-54d1-b8a9-b70957a4ef5e | textbox | DATE:
8ba63960-72ad-4383-bedc-6a5e1372d6dc | checkpoint | 1.2 Implementation of all measures and controls
81499de5-c2ea-54ff-99a6-394c122a494c | note | FREQUENCY: Prior to commencing any activity
f033dcb3-ab7a-5857-9b95-9f5491bff488 | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
99004b8b-70de-5e30-b481-efc1041a83f0 | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
29e229c9-c2c9-544b-8d0c-b05f2a97423e | note | INSPECTION/TEST METHOD: Verify
f0511825-d3d7-5f4f-b8fe-9ad6cfbfe248 | note | RECORD OF CONFORMITY: This ITP signed
41f03478-21c6-5aef-be12-bc84ae2bafd3 | note | HP*
03436fbc-38f6-558e-9495-f3e9bd2c4017 | note | RESPONSIBILITY: FH Engineer
1b6845b7-a41d-5132-951b-8b9701356648 | textbox | DATE:
87d949dc-2830-48c0-b747-8a917df29c15 | checkpoint | 1.3 Material Compliance
ebc0ad7e-0456-551e-9108-304475bfac37 | note | FREQUENCY: Prior to commencing any activity
1a030818-daf6-5f04-848e-55bf6e19538e | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
28a65559-40f7-5ad3-aafa-c956e08804c7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
bf9ca5f6-e30c-535b-ba40-7ce54b6e4a11 | note | INSPECTION/TEST METHOD: Document Review
6641289e-a7c0-5286-8c12-94256845e0a2 | note | RECORD OF CONFORMITY: Test Reports from supplier
33e4dd9c-9921-59e2-9e88-06b30e17a1e6 | note | HP*
ebcda4f4-0f98-51b0-9118-753cf1627287 | note | RESPONSIBILITY: FH Engineer
b30d4ba7-737b-5463-81db-08d011866f06 | textbox | DATE:
c172d805-d207-43d4-aed3-7c9670e3552f | section | 2 - Construction Works
c42f5f2d-b785-411e-8046-58394baa62b5 | checkpoint | 2.1 Sub Base
1931267d-5f09-547f-b16c-5da4aba88d9b | note | FREQUENCY: Each Lot
12dc0943-5075-5493-98ec-9a0913072a6d | note | ACCEPTANCE CRITERIA:
48c7c843-5094-5515-b8cc-3eb2160e7b27 | note | • Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
256db458-d0da-582d-8e25-aaed8a6e205f | note | • ITP-001 HP for subgrade inspection signed off
b03c7a17-7d05-569d-99c2-6439ed0c4630 | note | REFERENCE DOCUMENTS: VicRoads 173.03
6da3be09-e99e-52cf-a3b3-c5e6a1efaf31 | note | INSPECTION/TEST METHOD: Inspection / Test Method
03092c90-505a-5fa3-9c1b-dab4a78237a0 | note | RECORD OF CONFORMITY: This ITP signed
983dc9a8-2f1a-55ed-99f7-ca07a0918aea | note | HP*
94dedd20-06df-5e6b-a341-25b18c15719e | note | RESPONSIBILITY: Fulton Hogan Engineer
41ad4f56-063a-58ac-acc0-296ceaf1b53e | textbox | DATE:
a1a5d84c-f77d-4e4e-ae09-f4a9321a5261 | checkpoint | 2.2 Spreading material
84ac2692-cdef-5671-9456-e16195efb4bd | note | FREQUENCY: Each lot
ceff4e8b-e578-54d7-b1c8-3b6f36615167 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
3eae7764-84fd-5b6c-b1d2-126190303569 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
c34e6c29-1c2b-519c-9410-96334de72c6c | note | INSPECTION/TEST METHOD: Visual Inspection
ac44c65a-3739-5c7c-bc54-763cdfc87946 | note | RECORD OF CONFORMITY: This ITP signed off
c7644079-7a2e-5d70-9010-a355eb42c336 | note | IP
516c3949-346f-595e-9d89-48ba7a4c3687 | note | RESPONSIBILITY: FH Engineer
5156023a-c1c9-5204-bdf4-53c2d98ad483 | textbox | DATE:
572e7028-e482-4943-ad91-e52782625161 | checkpoint | 2.3 Compaction
673e7657-0522-55cd-a622-dc41073ef5dd | note | FREQUENCY: Each lot
c8f0e426-c1dc-5ec0-9fc3-e492f4cb10c9 | note | ACCEPTANCE CRITERIA:
a509639f-6459-5ddb-b58e-5c9952d38def | note | • Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
bb9dbfae-479a-520a-8638-eaac678a6126 | note | • Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
5960acb8-3e6c-505b-a1ac-336eaf54b8ef | note | • Compaction testing shall be carried out once per days production and shall comprise of three samples
86fce273-ce6e-52b3-aaa2-0d6835f03983 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
dfd3fdd1-1332-55f5-8912-2467ce47fdd5 | note | INSPECTION/TEST METHOD: Visual Inspection
9ebae320-ea6d-5604-a88e-aadcff2b330e | note | RECORD OF CONFORMITY: Test Results
4b82f3d3-37bd-57f5-90f0-c99c7edbed38 | note | TP
944594dd-90fe-5726-b182-d9c206975c1f | note | RESPONSIBILITY: FH Engineer
21f839e9-dbe8-50d9-905e-787b53f5424e | textbox | DATE:
e6117e45-8595-44e6-ae79-c6b1c18d4864 | checkpoint | 2.4 Level Checking and Conformance
d56a8dd0-cbc5-5337-b8d8-43e4f2d86673 | note | FREQUENCY: –
5575175d-22d6-5214-a176-e98f03bdc4cd | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
e611c6f5-4751-5c2d-b9ad-a8cdd69b68b0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
985d9c8a-91ca-5086-a6a3-09396f04505a | note | INSPECTION/TEST METHOD: Verify
cd98ffe2-3de9-57d7-aaf0-52996d1b5ea5 | note | RECORD OF CONFORMITY: This ITP signed off
7a325358-5e60-5ce0-8540-8ae1c855f6ff | note | IP
aa6504a8-6c3d-55cd-beab-9345ff21957b | note | RESPONSIBILITY: FH Engineer
f6cc034f-6986-54d4-8344-9de2cb47192e | textbox | DATE:
f182fe4e-a413-4ec4-82d3-d06dc37b9fbb | checkpoint | 2.5 Finished surface
4693e9a1-a7ce-5bfc-8da9-072d7c390a86 | note | FREQUENCY: Each lot
4d20fba5-5d41-5dcd-9a95-4ac8e377977d | note | ACCEPTANCE CRITERIA:
925c6e80-b4c8-5971-a3fd-20af26a5da0e | note | • Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
a199d8d7-19d3-5b31-a4fc-e1592c050bee | note | • Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
6b76877c-f125-582a-9763-1d9b46a8f714 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.2.8, Contract drawings
a6146de9-63ab-5fd8-b760-dcb3f722a84b | note | INSPECTION/TEST METHOD: Visual inspection
c00f6a9f-01d2-5e18-ab68-4473fb53beb9 | note | RECORD OF CONFORMITY: This ITP signed off
ec355f4a-79fe-55d0-bcd5-fcceb0d0e493 | note | SCP
aed36dce-5bc9-5fe9-9e63-ed0dca903c81 | note | RESPONSIBILITY: Surveyor / FH Engineer
dfe46485-20a0-5e51-b688-aec1711188c8 | textbox | DATE:
93e27ce4-99e1-4d66-9166-5e0ee7344ec8 | checkpoint | Final Inspection
5bc85d36-b360-5cf7-b83b-e172be71d23c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e6de64b2-703b-5106-b870-c404047499c8 | textbox | Print Name:
a0b9fbd1-9a45-56f2-87d0-e2fb12b7ffee | textbox | Position:
ccf506c9-7755-5475-bbb8-b581f86b8f59 | textbox | Date:
a563a155-1a21-45f9-8d21-358c5ace7ef7 | checklist | ITP-005 -Track Drains | itp | ITP-005 -Track Drains
28dc7dd8-264a-4baf-94a8-6c3cca55f804 | section | 1 - Preliminary Works
2ed9b094-7e3d-4e4b-a438-ffa3fd5fd2f5 | checkpoint | 1.1 Check for correct documentation
2a0a260e-6f85-54a1-b1f1-969b5fd32fd0 | note | FREQUENCY: Prior to commencing any activity
33e51d44-8297-5ae9-a818-bbafe2bf426d | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent
56fb834a-49d5-59c4-8002-fc1f95cb00d1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
304930ed-bcea-539e-b8e6-55b6ff33ff22 | note | INSPECTION/TEST METHOD: Visual inspection
6ec65096-2e14-549b-aa84-2b724d3b3705 | note | RECORD OF CONFORMITY: This ITP signed off
1a3b062d-70da-52df-bcd7-7497a61f0ac9 | note | HP*
b954a024-da7a-5989-90a0-3e1fa0ede1d4 | note | RESPONSIBILITY: Fulton Hogan Engineer
4b8c11da-f012-5919-8e0b-f24482093151 | textbox | DATE:
7e8efe72-068d-49e9-8653-35d95f5b1d04 | checkpoint | 1.3 Materials Check
906c90ea-da5c-593f-bf60-408cfccb9e67 | note | FREQUENCY: Prior to commencing any activity
20eafd1e-d5c3-56db-97b3-0a87e06016a1 | note | ACCEPTANCE CRITERIA:
f8bb0c34-0b1b-5a29-83ec-3d0dbcb7082c | note | • Ensure drainage pipes are of correct classification and are without damage
f33c625d-53e8-5b08-80a2-75b15f8f9e3b | note | • Check triangle drains are of adequate quality, and are design according Ri57A rail profile
56667528-cb83-53f7-ac1b-7c2536921ffc | note | • Ensure lid and j-bolts being used are in accordance with STD T9022
5061905d-9d55-53a3-b634-c9ebbe7a3f63 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
542479bf-95f8-5fa1-b429-16c4b3a77099 | note | INSPECTION/TEST METHOD: Visual inspection, Inspection Checklist
cb7a08f9-ab79-5a60-b022-4be9e12f4aa9 | note | RECORD OF CONFORMITY: This ITP signed off, Recievable Inspection Checklist
bcde4652-4b49-56fe-8e0a-3a1692f04803 | note | HP*
c84eb8e7-1a88-50f0-a790-3cfd616c7124 | note | RESPONSIBILITY: Fulton Hogan Engineer
415d66c1-303a-5c31-80ef-c7faf3554bd5 | textbox | DATE:
ef9ed69c-d7b7-45f5-88dd-6e7debe8c2c9 | checkpoint | 1.4 Bedding Sand
84dab116-e1ff-5ad1-aa75-9f915b5d9032 | note | FREQUENCY: Prior to commencing any activity
2bd41323-99ad-538c-b021-3fe39762ba9c | note | ACCEPTANCE CRITERIA:
48cdd688-0a69-5eb7-82ec-a606456d5a0f | note | • The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following:
d9a59f6e-51c3-512c-ab59-bd97e8974560 | note | • Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities,Consisting of hard durable particles, and well graded.
aba81991-e612-57e1-86c5-635c65519828 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
6befffa5-90e7-5588-a927-eba9460a63c8 | note | INSPECTION/TEST METHOD: Visual inspection
e6f64653-3e60-5ffa-be8a-67f4222e33ee | note | RECORD OF CONFORMITY: This ITP signed off
1f5d64e5-5d39-5ef4-a94d-349fde006fd2 | note | HP*
577ea088-0746-5502-8e15-027ca5ce09bb | note | RESPONSIBILITY: Fulton Hogan Engineer
ee763750-562b-5de5-a5cc-fdedd8845aba | textbox | DATE:
910fd00a-c512-4cf8-ab84-4e9e9220d618 | section | 2 - Construction Works
fa4c2b33-3d57-442b-a957-fa512a32278b | checkpoint | 2.1 Set out drainage
853356a7-92b8-5218-87f7-e87b8bfee7de | note | FREQUENCY: Prior to commencing any activity
c41b2925-f8d2-5312-8d5b-20515c2f21c9 | note | ACCEPTANCE CRITERIA:
83a4a16c-f976-5002-b3ac-a5171040a192 | note | • The position of all drainage lines are to be confirmed with the superintendent
6eb2a5f5-9bb0-586a-9f44-f44326f7347a | note | • Track drain locations are to be identified and based off IFC drawings and sections.
75ed57c2-6252-571a-b0e7-af5f895204ab | note | REFERENCE DOCUMENTS: Design Drawings and Register
69f4ce93-ea1e-52af-a99d-0a9eda1bf4e8 | note | INSPECTION/TEST METHOD: Visual inspection
f531681e-e2a3-5f9c-bb53-162909c23ebe | note | RECORD OF CONFORMITY: This ITP signed off
d772f973-5a24-5b53-a101-454d05f2a4bf | note | HP*
51399e3d-3c46-5807-ba7e-de163b685560 | note | RESPONSIBILITY: Fulton Hogan Engineer
8112d44c-c88b-5c3d-a177-6f8059e339eb | textbox | DATE:
8299c231-888a-4272-a7c9-81bb40e4d403 | checkpoint | 2.2 Excavation (pipes)
8950d38c-76b7-5c14-9d88-ddc030b68b58 | note | FREQUENCY: Each Trench
1429795c-1eeb-5be8-91a5-8d9fdadc059f | note | ACCEPTANCE CRITERIA:
3fb56a77-318c-532f-b85b-e8ee46e2447c | note | • Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe
4ebbaa4c-c42c-54c7-b109-ebc80719164a | note | • Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
b062b583-0b18-5d09-a042-28cf4b43ef64 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
cd0a65d9-dce0-52d8-870b-7a4aa5dd78cd | note | INSPECTION/TEST METHOD: Visual Inspection
398beb1e-f81e-54dc-949e-a28635ea31a4 | note | RECORD OF CONFORMITY: This ITP signed off
c6185d67-229c-58cb-9145-db87c36af4ee | note | IP
d1821562-2541-5373-aee7-1f4dd13c4a89 | note | RESPONSIBILITY: Fulton Hogan Engineer
64ba9bfa-190a-5b8f-88f5-a570a075c2d2 | textbox | DATE:
255e607e-f341-462b-b452-021c3b2da001 | checkpoint | 2.3 Bedding
88c3073d-04ce-502a-9197-b1132fa421cb | note | FREQUENCY: Each lot
2589139a-7c1d-5317-94b0-9cdc03fdc1b5 | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
204cf9dd-513b-52a4-a1c7-640a2a1d00d8 | note | REFERENCE DOCUMENTS: STD T9021A
5467c70d-e4a6-5390-80b9-f82d2fd9611a | note | INSPECTION/TEST METHOD: Visual inspection
1e527b60-b87c-527c-97bf-d857784e4fbc | note | RECORD OF CONFORMITY: This ITP signed off
3fc05fe8-7c31-59ba-9e56-afef071590f3 | note | IP
31027811-b127-5672-b6e8-ac3c565b29b4 | note | RESPONSIBILITY: Fulton Hogan Engineer
e314e674-2629-5c33-bd21-8d5e2deb4e88 | textbox | DATE:
72ce173f-77a8-4d30-b261-c7a426d4d5ff | checkpoint | 2.4 Joining
5c138dab-ca1d-5ac9-a0b1-9bc218860f2b | note | FREQUENCY: Each lot
624876a9-09a6-5e44-9e9c-ccb7082d79f8 | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
b0fafc96-de50-519f-a749-44b6cb444b97 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
3a1fc85b-fd08-5174-97d1-b4f00aa6db5c | note | INSPECTION/TEST METHOD: Verify
04777b75-4fa9-5fc6-a5f4-69dbe409e97a | note | RECORD OF CONFORMITY: This ITP signed off
47f35d09-7ff7-5eaa-a30c-ae2f9f586f99 | note | IP
85c9fc51-5e91-5431-a7ba-d7dfeefc7c83 | note | RESPONSIBILITY: Fulton Hogan Engineer
9c3f1e18-dc23-5a99-b6e8-2d523d3c187c | textbox | DATE:
0ad4a57d-4d96-4fc3-811e-0db2c72500c5 | checkpoint | 2.5 Track Drain Installation
fa567ec2-c404-5998-8677-ef7dca4f8a4e | note | FREQUENCY: Each Lot
585b8830-c34c-5b46-9102-c7c9b3e6a091 | note | ACCEPTANCE CRITERIA:
0fa3b107-ba7d-538f-bd68-430095306a49 | note | • Track drains shall be welded to designated positions, and cleaned of all weld splatter.
44b8d623-5c93-5b15-bd95-b9f2f672cf85 | note | • Weld shall be sealed after installation
25f6c6c9-aa36-5c2e-abb0-3a3d44b900e7 | note | • Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
e8e30589-8a5f-530c-a402-cc09989ef5b1 | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
7b43a569-19a4-51eb-ab58-507d7a9c7a3f | note | INSPECTION/TEST METHOD: Visual inspection
9fc9f5b5-4e0c-5ba7-b012-b3f4856f1f8c | note | RECORD OF CONFORMITY: This ITP signed off
b19e20c6-21ed-5542-9cb9-27d5282540ff | note | IP
f13e9ec9-0eb7-5f19-92ea-61291c57ec08 | note | RESPONSIBILITY: Fulton Hogan Engineer
a6bd4a4a-74e5-539e-ad39-903f17514487 | textbox | DATE:
46272b0d-a0d3-4eee-b599-58644dacbb70 | checkpoint | 2.6 Points Drainage
0e03d372-e268-53aa-8d19-1aa9e6327cf6 | note | FREQUENCY: Where required
f7d685ed-19d0-5722-bca6-3f23169618b6 | note | ACCEPTANCE CRITERIA:
4af86203-361a-5c80-a9bf-6c8cee24b3fa | note | • The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit.
2378823b-00c0-5549-af0b-7350a03c7cad | note | • Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
800785e3-b21d-5606-84b5-91514bca3080 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
3888db01-39d5-5ce8-8293-48ea687e193c | note | INSPECTION/TEST METHOD: Visual inspection
efc5dd61-cd5c-57d2-a0c5-79e1f2a55bab | note | RECORD OF CONFORMITY: This ITP signed off
1c09bc8f-dded-5684-a09f-164ed984eb7f | note | IP
3858509a-cddb-520c-9ec8-a9ffd2cb7e53 | note | RESPONSIBILITY: Fulton Hogan Engineer
d37fff4d-dc20-58e6-9e7a-06e0c0c04619 | textbox | DATE:
715fd835-37e2-4788-a02d-c536cdfa267d | checkpoint | 2.7 Concrete Pour
bc65749f-5d22-5acf-b46e-78bd14e77465 | note | FREQUENCY: Each Lot
6159f91a-e058-5999-bd7e-81333448e0f6 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
6646ae7a-f64b-55ba-b79d-71bea1993102 | note | REFERENCE DOCUMENTS: STD T9021A
a6921e60-ce42-5711-9889-89274e2fc93a | note | INSPECTION/TEST METHOD: Visual inspection
26b79637-5ad5-5e52-99c6-061997fdeb83 | note | RECORD OF CONFORMITY: This ITP Signed off
05eada67-20d0-5171-a708-bc0da3b7e2e6 | note | IP
bd5cf79e-5cdb-5839-805b-b1545aefa149 | note | RESPONSIBILITY: Fulton Hogan Engineer
343c186d-13ae-5f08-a25d-aeaa9673c0df | textbox | DATE:
568099d6-d37d-4100-a6fc-5ce443174c2c | checkpoint | 2.8 Connection to local drainage
0030c7e6-62da-5f04-adbd-d0e3221ee40e | note | FREQUENCY: Each Lot
e538a49e-be64-51da-9781-6c34d22606c1 | note | ACCEPTANCE CRITERIA:
3ce4c5b2-64c8-5fdb-b24e-53eb6a2dc4bb | note | • Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority.
7f4ea20f-b504-5bac-b679-ce2a283306ff | note | • The minimum pipe size shall be 150 mm.
fcf19655-ceec-5163-aec1-7a0db975991a | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
a0974d67-6578-5657-a2b0-74252a9189b6 | note | INSPECTION/TEST METHOD: Visual inspection
93c019b4-134c-53f3-b6ca-850c377fbf46 | note | RECORD OF CONFORMITY: This ITP Signed off
a8d3c658-952e-5b5d-b4c4-6c996ea2b627 | note | IP
2c0d0166-dd87-57e1-a419-519f73b4db5f | note | RESPONSIBILITY: Fulton Hogan Engineer
78f0b8b2-aff0-581b-8ed4-2883b6164769 | textbox | DATE:
f2d50830-b040-477d-b00c-23ff20d32a6f | checkpoint | Final Inspection
de7e82da-bde4-5df6-a0b5-10ae36eab927 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb65f8cc-1c7b-5d1d-8040-42a0d013f749 | textbox | Print Name:
1ce0ef8b-9490-5619-a354-392eff6531f7 | textbox | Position:
cc45c789-89ae-5dd4-9119-ec911347a826 | textbox | Date:
1ab0257c-0850-40e9-9843-d5785dd440b2 | checklist | ITP-006 - Track Placement Rev3 | itp | ITP-006 - Track Placement
24667aaa-d1b7-4d25-9b62-4e0bc150964b | section | 1 - Preliminary Works
9c400344-52c6-40bf-ae01-913f3a4e1f54 | checkpoint | 1.1 Check for Correct Documentation
db8224fe-760d-56e8-be3f-c35ea8bd6134 | note | FREQUENCY: Prior to Commencing Works
9423663b-e936-5294-a2f3-3ac475e8c971 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
8cfe857e-68ea-5096-8ff8-45a81ebb2f9a | note | REFERENCE DOCUMENTS: Design Drawings and Register
055f4d45-66c5-54ef-9cda-6836c07f498d | note | INSPECTION/TEST METHOD: Visual Inspection
b2372165-6cba-5731-abf8-af5f1c863197 | note | RECORD OF CONFORMITY: This ITP Signed Off
02123363-0acd-59ee-9137-113d159cee59 | note | HP*
6f060038-265e-56a0-861f-b91ac57541bb | note | RESPONSIBILITY: Fulton Hogan Engineer
43adeb5b-d86e-5ad3-b13b-aeda88a4b9db | textbox | DATE:
193e432a-536f-44c3-884a-3963203868d2 | checkpoint | 1.2 Check Materials
a33d4c53-1966-59d5-a266-07e334632c55 | note | FREQUENCY: Prior to Commencing Works
bb2e6fb8-a026-5d7b-95ad-76854b956eb4 | note | ACCEPTANCE CRITERIA:
fff18da3-e323-55ba-9ef0-23aa9e6a5374 | note | • Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
b55ad6b1-6a87-5cce-8f85-daa58cf74914 | note | • Check condition of rail sleepers
db4294a7-e1fb-5645-be23-ea9e9add3a6d | note | • Ensure rail jewellery is of sound condition
5ababb39-93a8-571e-898b-90b94814edc8 | note | REFERENCE DOCUMENTS: AS 1085
f51ffe29-45a2-51b8-8c6f-4da578e5a6b3 | note | INSPECTION/TEST METHOD: Visual Inspection
de76202f-68bd-5bca-bebc-00212cfb8d02 | note | RECORD OF CONFORMITY: This ITP Signed Off
3d7eb362-050d-5c19-ae55-0950b30216bd | note | HP*
ff3d44c7-42d6-5789-b2c4-e9b7d7a96aca | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
73e8a78e-d3b9-58cf-8c05-dcd8acff29c8 | textbox | DATE:
aecea445-dfed-42c3-a1b4-de7166e36fb1 | checkpoint | 1.3 Check Special Works Components
94067da2-367d-503a-af89-dea921692605 | note | FREQUENCY: Prior to Commencing Works
83941dd3-dc82-5358-b210-d34b19cc1275 | note | ACCEPTANCE CRITERIA:
2e8d3510-6927-5946-bf6d-93bff793a30e | note | • Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
75e97d9d-2e85-59f5-b507-a5df256ba356 | note | • Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails.
414b2b05-36d2-592a-b5bc-ea5becacc100 | note | • Superintendent to visit yard from intial inspection of the rail and fabrication plans.
35c1abb2-75ce-581d-85f5-db5dfca4bc0e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
f094d12f-8c56-5208-b838-f7d38e67b6c2 | note | INSPECTION/TEST METHOD: Verify
ff91bfc6-c048-5881-9d18-575874c85f37 | note | RECORD OF CONFORMITY: This ITP Signed Off
4f25c9bc-71eb-53bb-84a7-58ae68e6dee6 | note | IP
70c0613f-e26f-5594-9625-86e5d3f2581c | note | RESPONSIBILITY: Fulton Hogan Engineer
32a88e8f-4fce-5e8b-8cfb-d245d70b9bf7 | textbox | DATE:
a5606e24-0038-4bd0-b861-5a7366e7015e | checkpoint | 1.4 Check Curved rail
c058526c-5c98-5411-8a56-a2d740193281 | note | FREQUENCY: Prior to Commencing Works
bbd5e121-bab7-5248-91f5-8e022c3f67a1 | note | ACCEPTANCE CRITERIA:
2ebbd81c-f77e-57bb-bc95-6b9af228feb0 | note | • Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
8891fbd4-0b67-569d-b5fc-d09ffa63e667 | note | • Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
e911eb58-f044-5937-985a-f49f2ce005ed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
592300eb-d6bf-5453-baec-33a454cea07f | note | INSPECTION/TEST METHOD: Verify
d6ee1093-f56f-5c36-a439-a41af172a325 | note | RECORD OF CONFORMITY: This ITP Signed Off
a13a2365-5f7d-5244-a8bd-df7434f4e280 | note | HP*
32fefc3e-5e15-5c45-a40d-5dc8b811498e | note | RESPONSIBILITY: Fulton Hogan Engineer
ccacca26-b530-5b18-b3e0-ea05bf8a00eb | textbox | DATE:
d8c01044-dd90-44be-bb29-42ba8278bf1a | checkpoint | 1.5 Welders Qualifications
edfec91f-1ea0-5aec-97bd-79fcbf128874 | note | FREQUENCY: Prior to Commencing Works
ba6d92c1-b3b2-5b5b-83ff-53a4a05687d0 | note | ACCEPTANCE CRITERIA:
a94592f9-da4c-5165-a2f2-292bcde76179 | note | • Welders shall be trained and compliant in Aluminothermic Welding Requirements;
2f9cad02-1224-596e-b9d9-e49e601914d1 | note | ○ TLIW2012 Grind Rails
60d0ad60-d686-5926-bfe4-41e005636176 | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
591a803b-d2a2-5748-9aaa-eefa8371ad0b | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
b1a92464-e928-5305-b51d-a98f6f8870a6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
03542f16-2868-5594-b7d4-9dcabcacfe4d | note | INSPECTION/TEST METHOD: Verify
f3ffbbd6-1937-5756-a196-921cf681142f | note | RECORD OF CONFORMITY: This ITP Signed Off
b365a5df-a9ea-5518-82a6-9bb3241cded2 | note | HP*
7e914d8f-b698-5186-90bf-a9ce64f0772c | note | RESPONSIBILITY: Fulton Hogan Engineer
4286c1d7-57a7-548c-88c5-70991556e4a8 | textbox | DATE:
54af46ea-156e-45de-9eb3-a499855d7f10 | checkpoint | 1.6 Ultrasonic Testers Qualifications
3363028e-acec-5dee-88e8-fe30f11a9d9b | note | FREQUENCY: Prior to Commencing Works
932e5319-d770-56a6-8f35-cab15629edb7 | note | ACCEPTANCE CRITERIA:
a6c8458f-b0ca-541c-82ec-56aa38922076 | note | • Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing.
a6bda1e3-a65f-5c6f-b83d-559f1f018293 | note | • Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
90448311-3bc3-5945-9cbc-d51a111df8d1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
8777db36-6b6e-5665-923c-d05ab2d1058f | note | INSPECTION/TEST METHOD: Verify
559a73ce-948e-5a92-83d6-534682e95d79 | note | RECORD OF CONFORMITY: This ITP Signed Off
6c095786-6c4a-549c-880c-2cfca1d3be29 | note | HP*
b0e7b29d-8377-5c49-9b81-ce4955221abc | note | RESPONSIBILITY: Fulton Hogan Engineer
7c86e8bb-232b-56fd-a3ff-bfaf2b0b7ce3 | textbox | DATE:
10de851d-eb4d-4d46-8f9e-0fc4f0a1cf20 | section | 2 - Construction Works
e10da0a0-f38f-4d02-a895-424b5d96c307 | checkpoint | 2.1 Installation of Sleeper
1ce74de5-67fc-5aa4-a6e9-f5c4adf264c0 | note | FREQUENCY: Each Lot
db80831e-5ee3-510d-9134-97411297b1b0 | note | ACCEPTANCE CRITERIA:
612e7b95-78a2-50f9-975d-faf46fa6051d | note | • Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
cf3aeee1-b20a-5f3c-be94-c7d8af589f02 | note | • Dual block sleepers shall also comply with the design offsets at each chainage
aa4387e1-01ff-59aa-801f-bcd7b396dad3 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
421af280-dace-5577-a813-afdbdb145ff6 | note | INSPECTION/TEST METHOD: Visual Inspection
b56d6101-d15c-5be6-8059-49678a55f52c | note | RECORD OF CONFORMITY: This ITP Signed Off
ed9a27b0-9a1d-5888-9bf4-c6a5bf5cac2e | note | IP
a1f91dad-7952-50b0-9bf6-439f2efe63a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a419f03-c656-5ff1-a660-5023ddf22fc5 | textbox | DATE:
1c631e1e-578a-43ef-9bb8-9f44fd09889f | checkpoint | 2.2 Placement of Rail
db1d57cf-0e11-5374-80c7-a7ba90d2a275 | note | FREQUENCY: Each Lot
d3f8a0aa-8c67-55e7-929a-5cf2b700bae1 | note | ACCEPTANCE CRITERIA:
4894d7a2-86b0-564b-81a1-86ffa9434541 | note | Ensure rail strings conform to rail plan
f712775d-8d7f-50a1-96c5-b78b606e0aaa | note | • All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
d55813af-cae5-501c-bc0a-6ab2190e63d3 | note | • Bottom of rail and bearing surface shall be clean of foreign materials before laying
670ba4e6-6238-59a1-b025-e19c343112b9 | note | • Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
36079b7d-6d25-545f-832d-6b78d4761da8 | note | • Geometry tolerances as follows:
782b0f96-c951-59d7-9594-bf8026a11248 | note | – Centreline location: +/- 3mm
ee655657-83dd-59fa-917e-fb7c9ec9db5a | note | – Level: +/- 3mm - Line measured (>10m chord): +/- 3mm
541946f4-b7fb-5e46-b071-6072e7bb9314 | note | – Twist (3.5m chord): +/- 2mm
2260fa2e-dd2f-5acc-89ac-e7c7d194f052 | note | – Cant: +/- 3mm
38b7db40-024b-56bf-887a-a6deab3b235e | note | – Gauge (open track): +3mm, -0mm
efddf516-1a37-5eca-82f4-5b7597159fef | note | – Gauge,Turnouts (opposite crossings): +2, -0mm
e52b8cef-b120-5919-adba-e0e37d89bff3 | note | – Gauge, Diamonds and ‘H’ Crossings: +2, -0mm
ea42293a-bed3-5118-b5e9-11f7b95603a6 | note | • Note: Cant shall be applied uniformly over transitions
4c6f2b9f-c165-5600-acff-5327e064e8b7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
4476a817-b081-5068-a678-14898f87b369 | note | INSPECTION/TEST METHOD: Visual Inspection
8a20974e-bd51-5d75-a9db-6eb184b665b4 | note | RECORD OF CONFORMITY: Completion of track charts
36f89d78-cc91-5acb-ada4-5f2a70f2ad13 | note | HP*
a7003db7-c302-538e-9180-23998c856924 | note | RESPONSIBILITY: Fulton Hogan Engineer
c66b666f-32f4-5e2b-9510-3d367f0f5136 | textbox | DATE:
21e36e42-f22a-40eb-a09e-e8d1e04982aa | checkpoint | 2.3 Placement of Jewellery
fd7a3ea0-aeeb-5a28-9518-3738346b0f19 | note | FREQUENCY: Each Lot
592104b9-8cc9-5648-b134-6f54d88bc7df | note | ACCEPTANCE CRITERIA:
75e5d90e-452d-5d22-a131-cfad40516ad5 | note | • Each sleeper shall be fastened to track with approved jewellery and rail clips
81949c41-e487-5f95-9517-8ccf6e4b21ff | note | • Clips shall be installed with panpuller or equivalent
7c9790e7-c26a-512e-bc3f-366cffcedf28 | note | • All fasteners shall be sealed as per agreed method with Yarra Trams
0cd89289-0778-527f-8e99-9e2d27d9941d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
39fc205c-9506-5761-b65e-8c4518e5f66c | note | INSPECTION/TEST METHOD: Visual Inspection
c100f020-fb1e-52c4-a391-692b959cb1ad | note | RECORD OF CONFORMITY: This ITP Signed Off
7a67c57d-5ce5-5d60-a351-99fd18695342 | note | WP
9ffb41b1-a7c0-5a84-afa0-5514cd5d4d2b | note | RESPONSIBILITY: Fulton Hogan Engineer
d64984af-80d8-53ec-b33e-4e58039aee4d | textbox | DATE:
fa5d72bf-fb56-4eb7-9442-6c2338c7854a | checkpoint | 2.4 Rail End Preparation
6520c8ed-7ab8-563b-8f2c-ac945f8dc478 | note | FREQUENCY: Each Lot
eb701765-5fe5-5491-9b9e-1bd08af6956e | note | ACCEPTANCE CRITERIA:
ef3331be-a510-5387-b4f9-6415b2cf9844 | note | • Rails shall be saw cut or flame cut
66bd05d9-f613-5830-a604-21a78692ddfa | note | • Minimum closure length from proximity of welds shall be 2m
934b1414-12e8-5e09-a0c0-ce37eb444450 | note | • Rail end conditions shall match (i.e flame cut - flame cut)
c04748f7-8cce-54a7-8775-f32c80b92977 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
6a48df45-8a34-5166-a989-2042be7b853e | note | INSPECTION/TEST METHOD: Visual Inspection
6031e11b-0735-5134-b4f5-cb8ab933f613 | note | RECORD OF CONFORMITY: This ITP Signed Off
ee50323e-f388-57f6-8c90-a0de7c663324 | note | WP
70fe89bd-c591-5b4e-92f3-23293c731f10 | note | RESPONSIBILITY: Fulton Hogan Engineer
ba1d898b-2636-51ef-9bb1-f65fb15dda48 | textbox | DATE:
9ebcb9ac-c985-4ab6-9049-366d01d1884c | checkpoint | 2.5 Welding of Rail
24bf2b42-4070-5626-838d-78d45fcd2128 | note | FREQUENCY: Each Weld
541bd01d-1feb-5613-8c5f-43ce15772ae8 | note | ACCEPTANCE CRITERIA:
b12593f0-3af1-5833-8141-c9d7ca9d51ab | note | • Joints shall be square across the track
84aea222-77e5-5d86-9af9-e710a3b38a1e | note | • Maximum skew at square joints shall be 65mm
9cf9638c-dab5-529b-9a49-73bba91bb8c4 | note | • Portions shall match rail type (i.e HHR, Ordinary)
5a89bb8d-7e8a-51b1-991d-b75313913907 | note | • Welds shall not be within:
fd4cd6ed-779d-5d6d-a063-b257535e0c67 | note | – 3m of another weld
32626221-d20e-5c1b-89e9-a5cfe89c6743 | note | – 3m of a rail end
aa20ba8f-dff0-5f1a-bfbc-b3b7bcd854ac | note | – 1.5m of a glued insulation joint assembly
8c5c9ff3-1401-5c5a-98f8-02a2749c102b | note | • Field welds shall be +/- 50mm from centre of bay between sleepers
30ce5beb-d597-5e3e-9f00-522f8bcf4a34 | note | • Weld Return forms shall be completed by qualified welder
bf67bd38-06c4-5d00-9c25-aafcce3f6581 | note | • Welds shall be grinded after 1 hour
7b331555-43a0-5379-bf48-0aeebb0a4c26 | note | • Welds shall be free of water
986ee10a-179f-56fe-a3ec-1455c1126e2b | note | • Post grinding, welds shall be cleaned for visual inspection
2cc9d23d-e78e-530a-8a4f-5aa8140adc78 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
e872a7d9-795e-5aab-b7ea-63a064dd4686 | note | INSPECTION/TEST METHOD: Visual Inspection
4d49d749-afd8-537e-a737-d968f5a8375c | note | RECORD OF CONFORMITY: This ITP Signed Off
09b1bd1a-5f80-51b0-8ca2-ebaf820f6469 | note | TP
f6187a2e-41fb-54ab-a7be-8f41f09c70df | note | RESPONSIBILITY: Fulton Hogan Engineer
bac10196-6c3a-5187-a312-5ef1b01f00a9 | textbox | DATE:
08e68919-3478-4a68-91d6-cac2113a1dc3 | checkpoint | 2.6 Grinding & Cleaning Welds
8c376fa6-863a-5156-a7ef-d4eae4f599ad | note | FREQUENCY: Each Weld
184cc1b9-2c97-5049-940b-9f8747228089 | note | ACCEPTANCE CRITERIA:
93b122d2-3a90-524f-bf44-af176b1f6692 | note | • The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring).
1058848f-292a-5c08-9fb1-6b8d3c9274de | note | • The grinding stroke should not exceed 500 mm to each side of the weld.Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
deee0f02-5705-53be-818d-0c1718e980ac | note | • The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
155f370c-c196-5a7a-8feb-ad6ab362e309 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
f3f12c43-2a88-58f0-ad8d-7d8584177fef | note | INSPECTION/TEST METHOD: Visual Inspection
d8930176-742e-5622-9fdf-36bde22fe704 | note | RECORD OF CONFORMITY: This ITP Signed Off
8fd45468-447d-5a93-9c76-ff56f557ad09 | note | IP
768a09bc-3c5e-5936-96af-464b698aabb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
f44b95d1-7ecf-510c-af69-4ad1dfe9c4d4 | textbox | DATE:
c26bfe7a-6a22-407b-8870-72b1570bb1ba | checkpoint | 2.7 Track Adjustment
d4b177aa-0861-555f-9b41-cec52507672e | note | FREQUENCY: When required
98921c26-2e06-5cea-87f8-c5edfe2f680d | note | ACCEPTANCE CRITERIA:
4a1be384-751e-5f25-824c-88d89503b7ea | note | Allowance must be made for expansion and contraction of rail to control stress.
aae339f6-bace-52f9-b449-e58058d5ef62 | note | The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with anapproved type of thermometer.
74961083-62c0-514e-817a-adef213000ff | note | In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
5655633e-6686-5b15-8c2c-0a116bb43efe | note | Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
d5e6d340-1153-5291-8bec-b77ef0eca6e5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
f60878cd-6883-5b28-9074-a571cbb383bd | note | INSPECTION/TEST METHOD: Visual Inspection
9447dec2-76d3-5b5f-bdfe-e1e22d04dd95 | note | RECORD OF CONFORMITY: This ITP Signed Off
9eef05a8-f497-500a-9143-87594b3c6309 | note | IP
b6f508e8-321b-52c5-ae3e-9a839c255180 | note | RESPONSIBILITY: Fulton Hogan Engineer
b96bb69d-444a-5a8d-9f56-5a555cc464c5 | textbox | DATE:
fe33f82d-7e03-4fb2-b2d6-c80e19557ab3 | checkpoint | 2.8 Track Bonds
00a27bb3-586f-5449-b5b5-6dc6cf6c73aa | note | FREQUENCY: Each Lot
ae55cb6b-b78b-547e-9107-08d7fc5c9078 | note | ACCEPTANCE CRITERIA:
0410b825-7510-56ab-92e9-c77a0329a1c4 | note | • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
0044ca8c-04cb-561c-96c7-752ff464134d | note | • Ensure bonds are sealed as per agreed method with Yarra Trams
f2d93732-9a9e-580a-8496-0919974899e5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
bb18a3a4-8b0e-5222-b868-00e08979b99e | note | INSPECTION/TEST METHOD: Inspection / Test Method
891b6129-4acc-550c-bbbb-42dafc22d734 | note | RECORD OF CONFORMITY: This ITP Signed Off
b2a76721-f678-5889-bcca-fbdc3548a495 | note | IP
6017e730-13e3-5926-99f2-eacd803b9fb0 | note | RESPONSIBILITY: Fulton Hogan Engineer
09b73312-724f-5a13-bf0d-b2d1a2faf039 | textbox | DATE:
1fc1df1f-deda-4b40-a8e7-a7bb49c2d9ee | section | 3 - Testing
d97e47ed-12b8-4f7d-be16-5072be6d98a7 | checkpoint | 3.1 Track Testing
380b4d38-59cf-53fb-a49c-2b9491893d69 | note | FREQUENCY: Each Weld
fd992515-0e55-5955-842c-71eae10e2a10 | note | ACCEPTANCE CRITERIA:
faee323b-e8b6-5acd-939a-11aac6280f34 | note | • All welds shall be tested by qualified NDT operator
a0bd9fb3-9aff-585d-8400-b816ebd21228 | note | • Failed welds shall be cut out and replaced
c029a1ec-cd28-5bbe-9168-8ae818e25ac4 | note | • Testing documentation shall be recorded and supplied to the superintendent
de2ce446-c03e-56f0-872c-20407c42cbcd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
e4a23fa8-2d96-528f-ba2e-0b0c6f115e81 | note | INSPECTION/TEST METHOD: Inspection / Test Method
2d757200-529f-5817-aa52-42d5309e51f8 | note | RECORD OF CONFORMITY: This ITP Signed Off
591f49e3-969c-5b62-b10f-77ba34675571 | note | TP
ed141fcf-1eb5-5874-9ac7-2c6bb18214fc | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
0c07b41e-cff9-5fe6-9173-31b457431926 | textbox | DATE:
0bd4e755-898a-4fc4-bff9-7a97cfa4176f | checkpoint | Final Inspection
bb6075ab-180b-52c5-902d-6756af51a345 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
74e77242-1f9f-5fc4-9208-4edecd1f318f | textbox | Print Name:
88b50e03-f51f-52fe-9531-42434547c4af | textbox | Position:
e0d81f1e-7814-59f6-a4c0-7160da1ee96a | textbox | Date:
392e700a-0e07-457f-9d5c-6df20c50074a | checklist | ITP-007 - Concrete Track Slab Pour Rev2 | itp | ITP-007 - Concrete Track Slab Pour
d816c0f7-b1df-4e84-a8b0-135f87e77d72 | section | 1 - Preliminary Works
8b7e3a7a-1c26-4ff2-9e3d-b88692e4e2f6 | checkpoint | 1.1 Check for correct documentation
da623a02-195d-5cc8-bb9d-848331945cc4 | note | FREQUENCY: Prior to commencing any activity
f882b465-7c94-5aec-b8ee-33997dc9c117 | note | ACCEPTANCE CRITERIA:
f408d9bf-dcee-5c86-b16a-c77f6d24a881 | note | • Ensure that all employees and subcontractors are:
07da9231-eee4-5b47-a1f1-920f74869379 | note | – using the correct and complete set of drawings
76ee42f3-06f4-5018-9769-b91c289112dd | note | – all drawings are the latest revision
cfd01961-9ffe-56d1-9452-ef808917cc2c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
946e2740-ba09-5632-ba3c-bf96e55b36c9 | note | INSPECTION/TEST METHOD: Visual inspection
6f1f4114-0319-5626-99fd-bf5db0bc2eb2 | note | RECORD OF CONFORMITY: This ITP signed off
967f66c5-e4bb-591f-a1fd-2e73f009434d | note | HP*
b2295147-3511-5691-bfc4-c858941ca5b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
22b1cb72-cace-58ce-a249-9da547c11856 | textbox | DATE:
5e2a8c67-ec8b-4d54-a1c6-56724d1f16e6 | checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
9e7cbbc3-deb9-5d2c-b288-476c67ad6887 | note | FREQUENCY: Prior to first concrete pour
876d56d7-f0e8-502e-bfbf-d0708b8cd6f3 | note | ACCEPTANCE CRITERIA:
763ac6cb-11fd-56bb-8510-da1da35c21a7 | note | • Concrete mix design submitted and approved at least 2 weeks prior to first pour.
b278e546-eac7-56c2-a0ed-ccde8d41f7ec | note | • Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
c08540de-a400-5764-81bb-ac6dedfac803 | note | • Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
4645dd56-daf8-50df-892e-85711f4f113b | note | REFERENCE DOCUMENTS: CE-019-ST-0033
4631ee45-28af-5cd8-beb5-cbbdf5a256b1 | note | INSPECTION/TEST METHOD: Verify
7d087f2a-2a5e-5a5c-bbbc-0815514632c3 | note | RECORD OF CONFORMITY: Mix Design ITP
7b246dee-1224-5866-95c8-51c40c6aed60 | note | HP*
3c5e65be-e60a-53a8-8a2e-433dc9c19324 | note | RESPONSIBILITY: FH Engineer / Superintendent
ebe9b3f8-4a6d-523d-b547-996c1ded0cc4 | textbox | DATE:
92c47959-556f-4807-addc-9a82406769ec | section | 2 - Construction Works
006a8104-c40f-46e1-acb8-3d6a85b22956 | checkpoint | 2.1 Weather Monitoring
fddb9bfd-4543-52a3-8e6f-191e7be8abfd | note | FREQUENCY: Prior to start
55b8c580-ab2b-564c-ab22-bfe758771e0f | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
ed39fe34-09a6-5d64-b875-ab3dd0356dcb | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
c49a9b1d-00c1-5a8c-8517-9c1fd5f2aec4 | note | INSPECTION/TEST METHOD: Verify
5106412f-fbd9-5e03-a469-66135b61bf61 | note | RECORD OF CONFORMITY: This ITP signed off
83c43ccf-7ee7-50df-b8ad-602ccc848cf7 | note | HP
11a32ef4-f50e-5d14-9c82-f9c84224ed48 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
539404fe-b6bc-54d4-9d00-e759eeab1aa8 | textbox | DATE:
d606af13-4759-4ec2-8eb5-6aa035b281d6 | signoff | HOLD POINT AUTHORITY
c56e2f7c-82ff-4a0e-aa6b-3d3f1391d877 | checkpoint | 2.2 Surface Preparation
37688fb9-01cb-5f20-bdb0-02d4c6798c4d | note | FREQUENCY: Prior to start
bb317480-2244-5caa-b798-48a1fafe88f9 | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
22fa3543-3552-56b7-bb25-efe05579f137 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
a46a1075-61a5-51c5-b1c8-313be48630fe | note | INSPECTION/TEST METHOD: Verify
f08cd20b-844d-50c4-8aac-694308b9449d | note | RECORD OF CONFORMITY: This ITP signed off
a75415ee-dfa4-5092-a748-406277451f6f | note | IP
4f2d9fdc-980b-5036-9d80-b9478fad958d | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
b19bc243-4421-554c-9514-bf1668d505e6 | textbox | DATE:
47762765-f5e6-4c3e-9ac9-e096cea3f90f | checkpoint | 2.3 Setting Out
4e5e43e8-7781-599f-b838-b8277d13b927 | note | FREQUENCY: Prior to start
f1b64c0d-9356-5b29-926d-42c39cc2fdfe | note | ACCEPTANCE CRITERIA:
e0cd6f89-a9d2-53f6-8213-7b062a19d3ea | note | • Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications.
9a1e3697-6d44-5451-8a22-658ef3467b4e | note | • No survey/level pegs to be removed by any persons until completion of works.
4fedf475-9254-5a15-b380-aaf49045ba73 | note | • Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
6230c80e-ea0f-596a-ba5c-fbf5b24ce1e2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
abd73cbd-5e19-5981-9fee-5d93fff9a9c2 | note | INSPECTION/TEST METHOD: Verify
2fa26f37-f158-545c-8763-be1eab7b873d | note | RECORD OF CONFORMITY: This ITP signed off
bdb64609-9cda-53a1-bb8b-30172e514263 | note | IP
87f8c103-7267-51df-8188-75e3985aa519 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
296e2bdc-daf3-554f-94df-3e039c1451ff | textbox | DATE:
434802ee-7f89-48ff-94e8-17d63f3e9a34 | checkpoint | 2.4 Preliminary Works Formwork
153d5e8c-d557-5ef7-9880-83b89f44b6cc | note | FREQUENCY: Prior to start
713d571c-6c9e-5d13-bf51-8cf7221ab080 | note | ACCEPTANCE CRITERIA:
bb00d26f-429a-554a-9c9a-9ce7316a5e50 | note | • Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
f9a94a03-c76e-50cf-b0df-36bcf6931dd9 | note | • The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
6ddbf664-6c32-5a3c-9cda-bc0990cc3147 | note | • Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent
d42e7ba5-4bea-59b9-b39b-621a6f4f5ba8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
c552fec3-4493-5072-bca4-2f18a730d038 | note | INSPECTION/TEST METHOD: Verify
d750bf38-c787-561f-ad2d-1a5edf5a3f8c | note | RECORD OF CONFORMITY: This ITP signed off
19062975-285c-5996-9688-b417bbe8f845 | note | WP
2a0157b1-c14e-5a11-9f11-2cca112767fd | note | RESPONSIBILITY: Fulton Hogan Engineer
4e9a9be5-1145-53a4-9b33-b00c24a1015f | textbox | DATE:
30bc8d5e-205e-4995-bc52-5f5d5144c140 | checkpoint | 2.5 Reinforcement
856bd8c7-e33c-52d6-bddd-85689f08d4d0 | note | FREQUENCY: Where Required
df6f01ee-0fcf-5253-aea0-54c3ac6de1eb | note | ACCEPTANCE CRITERIA:
d91bf87d-479c-592c-84a1-9ac20857af4c | note | • Ensure that all reinforcement is placed as specified by construction drawings.
66d6de07-1770-5556-bd4a-b03dd698cd66 | note | • All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
caa48137-23de-53ff-8fc3-21e8d23cd09c | note | • Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
82956558-82f3-5a1a-a994-21c63912c62d | note | • Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
abb464fe-4f91-5d27-9262-78eb8aa2c18c | note | • Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
cc829126-1fcc-57fe-a87e-baf1ab2aeb43 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
f0b61a55-2605-5326-b034-601edeb7a63a | note | INSPECTION/TEST METHOD: Verify
4737760f-13f7-51b9-87d0-5b744eb58534 | note | RECORD OF CONFORMITY: This ITP signed off
2e2de00e-ab16-5e60-af2f-575a811abac4 | note | IP
a4b7e142-4e05-5a91-aa57-eab8b47b1ebc | note | RESPONSIBILITY: Fulton Hogan Engineer
9d83033c-eb95-571c-98a2-84893f92c4d0 | textbox | DATE:
63f86f0c-1482-4685-9c0a-140565c7ae05 | checkpoint | 2.6 Dowels
349486b6-e4e7-50c8-a1cb-31c41dbe5253 | note | FREQUENCY: Where Required
7867be7c-34b4-50a4-9eaa-0d6c423c5f15 | note | ACCEPTANCE CRITERIA:
dc056be6-9217-5328-aa5a-1ed33f172472 | note | • Ensure that all dowels are placed as specified in the construction drawings
ce22260d-04d1-56f5-a4c2-1926042e548e | note | • All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
78fcc105-07c2-5aff-a3f6-c929d2d1f693 | note | • Dowels shall be clean and free from mill scale, loose rust or oil.
74ec8d08-789c-53ca-8b42-b7e7facdefba | note | • Ensure that all dowels are securely held in their correct position until the concrete has set.
2503dc0f-4aaa-5412-ad7e-5b015de3d0c9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
0b05ab62-1d5f-544b-8fd8-85bc940b83de | note | INSPECTION/TEST METHOD: Verify
fd78a592-ab0d-5f0a-a76d-5c5a93dd3a20 | note | RECORD OF CONFORMITY: This ITP signed off
dd0907e0-c0a2-55fd-89de-2d2c3c75bcde | note | IP
b8ec194e-1712-5993-81b5-6993cd7207e2 | note | RESPONSIBILITY: Fulton Hogan Engineer
b1de681e-10f0-55c8-9f0b-e62fe852c84c | textbox | DATE:
5d934988-df15-4410-a1ca-034f4ea45192 | checkpoint | 2.7 Pre Pour Inspection
7595135b-396d-505f-ae92-6320721c15df | note | FREQUENCY: Prior to start
659aba80-27e9-5dd0-8d62-d20285dec797 | note | ACCEPTANCE CRITERIA:
e9504930-7c77-51e3-a4a2-693ec9532f34 | note | • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
725c6e83-7006-5a8e-b9a5-0b038837d244 | note | • Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
65e348ec-dec3-5a90-a011-e0b1a3c5afa5 | note | • Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
94f17f36-ed9d-5ff2-9a79-3bfdbe3531ab | note | REFERENCE DOCUMENTS: CE-019-ST-0033
ada6659c-594f-5d81-be3a-7ed7a3f07654 | note | INSPECTION/TEST METHOD: Inspection / Test Method
79e187bd-7595-585a-8e16-b197ed6e52d4 | note | RECORD OF CONFORMITY: FH Track Inspection
54eb841d-2db9-5602-9a04-752a0ee465de | note | HP
8de0f025-2f32-5053-97a8-d3cf035f4c21 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
dc1a95ec-479e-5c23-ac5e-97f08fd9ea05 | textbox | DATE:
c4382ff7-3a48-4c7e-8bd2-7f2021aa803c | signoff | HOLD POINT AUTHORITY
fa63ce95-3aed-4d3a-a055-8d4bcac337e8 | checkpoint | 2.8 Preliminary Works Carry out sampling of concrete
d159a2bc-5aac-5449-bb8a-8d4d3343f10e | note | FREQUENCY: Each concrete pour
1f30f459-5a24-5518-b00a-a088134d6393 | note | ACCEPTANCE CRITERIA:
9ffa275e-8d3a-5aa8-8a71-a14e795dbcfb | note | Slump:
f409e95f-c07d-5c4e-8e1a-9a3263569342 | note | ○ Concrete Slump shall be 100mm +/-20 Compressive Strength:
4e44b77c-5857-5309-b38a-e898230b572e | note | • Shall be measured in accordance with CE-019-ST-0033
c5f4928e-5b27-5d83-b47b-310285ca6264 | note | ○ Testing frquency =
44ea80fb-8dc9-5cfe-9333-98e0372b6abe | note | • 0-50m3, 1 sample
8ca6b213-a325-5985-b91d-9615e8b97ddc | note | • 50-100m3, 2 samples
cde820e1-2a0c-5648-a32b-bfd0888c232a | note | • 100m3+, 3 samples
986eb4ea-7c00-5ecd-a258-e1c233bd318a | note | ○ Each sample shall consist of 4 cylinders
3241dcda-10a7-5934-be2e-c1e8b37e6dd0 | note | ○ Test Results will be provided to the Superintendent
13b94abf-7fd3-52a3-80d7-5e0a69e98b83 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
de9850df-9041-5612-b276-ef41528c4ea5 | note | INSPECTION/TEST METHOD: Verify
62581a55-6557-5ee4-95fd-64ebcc6e3691 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
f0d43b75-2edd-5cc1-b4bb-0e2e47692fbc | note | TP
38d1d668-55ac-5d8e-8505-031ff829f4b1 | note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
5f647234-cacc-5b1e-aaff-ed348591ca7c | textbox | DATE:
7eafd0ec-1291-4ee4-bfb7-512d7c759ce6 | checkpoint | 2.9 Concrete Placement
3c08400f-9400-5e1e-ab2d-9dc240edb6fd | note | FREQUENCY: Each Lot
5cbecd56-7670-5f98-b726-065385798e07 | note | ACCEPTANCE CRITERIA:
8845c671-f94c-5580-b9ec-34c8213704d5 | note | • Ensure formwork is clean
206657ef-5c13-5523-9e73-7126dc3b2ddd | note | • Concrete shall be entirely discharged 60 minutes after batching,
208ad92a-1d76-56f2-bf2b-6f0649e187d3 | note | • Ensure that pouring does not occur from a height greater than 1200mm
f2e86bb6-d059-56c9-95b3-d7046a15efbf | note | • Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
be961c01-332b-543e-acee-630f893d4b56 | note | • The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
bd35c7f8-d0be-5867-8233-61127d9d3662 | note | • There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
16ab02f2-09a6-5e20-8a5a-f3f5d1df8165 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
62800ce3-632d-5dce-8a23-32ecacfc30d2 | note | INSPECTION/TEST METHOD: Visual Inspection
47563973-c16d-5f5f-b7de-651d33c24491 | note | RECORD OF CONFORMITY: This ITP signed off
db5f3109-d899-5a59-be9a-78e29f029edd | note | WP
cbc36dd6-0a73-5e50-b2f3-64fcd23a302f | note | RESPONSIBILITY: Fulton Hogan Engineer
35835311-a566-58aa-913b-4e552bab9069 | textbox | DATE:
26d17f9e-6baa-4b63-b6d9-68a597b576c0 | checkpoint | 2.10 Compaction
8b13d60d-c330-5f73-b3c3-3e14310ed98b | note | FREQUENCY: Each Lot
5885daa7-199c-510c-a5bb-fe063e0481a8 | note | ACCEPTANCE CRITERIA:
c20c1eba-c2fa-553c-aafe-91693f4ebd52 | note | • Immediately after concrete placement, compaction shall take place with an approved vibrator
ecc22a7a-8dbe-57e0-b0b0-895c39d2b690 | note | • Vibration shall take place until exposed concrete surface is free from air voids
4b494ffa-a72e-56db-b40d-069a24251e4e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
e5858f3f-236f-5c08-b0c0-1f2ce70f4188 | note | INSPECTION/TEST METHOD: Visual inspection
d1605d42-c5d4-5102-ae1a-1967989600ab | note | RECORD OF CONFORMITY: This ITP signed off
88ad8298-5a10-5bee-a40d-3fb341c8d9e8 | note | IP
9beffd52-9583-5ddf-965b-c458a4c3cad0 | note | RESPONSIBILITY: Fulton Hogan Engineer
501786d5-ca93-5ee2-9765-d90e7142d879 | textbox | DATE:
6f92c0b7-735c-4982-a5a2-f440acea19c8 | checkpoint | 2.11 Record location of each batch
70d70acd-8207-5329-8e68-7600e1b29aa1 | note | FREQUENCY: Each concrete pour
112f16cc-ddbd-5eaa-a154-4d810a190998 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
feb02ac8-b29e-5163-86eb-09acaccd4dfa | note | REFERENCE DOCUMENTS: CE-019-ST-0033
7232cf55-53ba-5eba-b3fc-20626c5f919a | note | INSPECTION/TEST METHOD: Checklist
4753f193-32bd-50a1-bb37-b2257fb1d81d | note | RECORD OF CONFORMITY: This ITP signed off
c5ee5368-2364-5820-a653-e4fc3ade8046 | note | IP
6a86f560-a93c-5db8-9f2c-d650218e3a8e | note | RESPONSIBILITY: Fulton Hogan Engineer
4cc23669-ac84-5129-b07d-daef6535af47 | textbox | DATE:
2d9cd346-e83e-4142-aab9-a19329541ebe | checkpoint | 2.12 Curing
6bfaa850-068b-5dcd-9833-02d2d73bcbf0 | note | FREQUENCY: Each concrete pour
17512eee-e017-5452-95d0-bd62f6c4484c | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
6adbe97b-53ef-5d46-a35a-f1259a524738 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
67e712b0-628e-5c34-98db-6d2000a9dd93 | note | INSPECTION/TEST METHOD: Checklist
8180e0f6-b57a-551a-8db4-d1a8541565c5 | note | RECORD OF CONFORMITY: This ITP signed off
22cb404f-29b7-5015-891d-4ee040fa6292 | note | IP
f96b1205-7cb3-55e1-8a5b-4da3684320ba | note | RESPONSIBILITY: Fulton Hogan Engineer
a9b60ca8-df1a-5567-8615-1635e7f2c441 | textbox | DATE:
10920819-ce05-4179-b156-c6a446b7299b | checkpoint | 2.13 Tolerances
0fa08a55-052c-510e-9105-0dbb57771722 | note | FREQUENCY: Each concrete pour
eb004f46-277e-595a-afd2-ae47b4338426 | note | ACCEPTANCE CRITERIA:
b2ec4ce1-33d3-59a4-b407-3fb971642faa | note | All concrete shall finish true to the dimensions, the following tolerances apply:
ab1c3bc0-00c4-5c78-8368-0914bbf79c16 | note | • Plan dimension of slab +10,-10mm
fa48bcd0-cdd8-5079-b9cb-323f9c3265e1 | note | • Thickness of slab +10,-10mm
57f1a84b-f3d7-55a1-aeae-590d49927334 | note | • Cover to reinforcement +5,-3mm
146eab0c-742e-57fa-a966-20aec350999a | note | • Finished level of slab +3,-3mm
6de3f730-a467-5833-849d-a29e4fc0f138 | note | • Foundation level of slab +0,-20mm
6066ab88-55f0-50c7-bdfc-d1c575695eaf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
299389a4-7b61-580c-9302-b9356e1e7011 | note | INSPECTION/TEST METHOD: Checklist
ce112561-7635-59d0-b861-a044885f2a6e | note | RECORD OF CONFORMITY: This ITP signed off
5bc2968a-49dd-5986-baad-d5c1f1690ce1 | note | IP
b09a8220-c6f1-5395-a29e-8e6bd286f632 | note | RESPONSIBILITY: Fulton Hogan Engineer
feb85f66-767c-597d-9611-44ae8534457b | textbox | DATE:
4d8cdc57-0afb-46d5-8450-bdcac4062ed5 | checkpoint | 2.14 Preliminary Works Slab finish
a49027b5-2cbc-5251-b501-ffd78a4a67cd | note | FREQUENCY: Where appilcable - if track is Type 1 structure
55ad13b4-cb53-5ab2-8946-5123810cb490 | note | ACCEPTANCE CRITERIA:
95c70e0b-c629-5cd7-a4ee-a5d271149273 | note | • Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities.
3ff4d398-f8db-5993-97f8-b92ff262f903 | note | • All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
7afe6cd7-fdd5-588d-91cf-dc0309b30b12 | note | • A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
301f4cb5-0010-5914-8fe5-02ee74d084b4 | note | • The slab surfaces shall be broomed to provide a non-slip finish.
f2e00634-77b8-5c6f-9f33-2c33e833d074 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
7d309d11-93c6-5d8a-8ff4-bba0213368b8 | note | INSPECTION/TEST METHOD: Checklist
93e50471-263a-56a7-9cfe-5279bb19f529 | note | RECORD OF CONFORMITY: This ITP signed off
afcfcec0-5ab6-5bf9-9283-5e0193f267a1 | note | IP
8a2b2c2e-3e65-52e3-ac7e-b6194afa542b | note | RESPONSIBILITY: Fulton Hogan Engineer
6162f3e6-c690-55a7-8c6a-f935fc047dbc | textbox | DATE:
68aecfe1-314d-4d5d-a9a6-6a2290bf9b3f | checkpoint | 2.15 Post Pour Inspection
4a428604-1531-5fcd-99c6-d38e8df125f9 | note | FREQUENCY: Each Lot
b3e8e416-092c-592a-a4e5-f61216c94943 | note | ACCEPTANCE CRITERIA:
329bfe77-5570-54bf-8313-35cff188c792 | note | • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
23355c68-cf73-5ce2-8b43-137d038aee28 | note | • Ensure no defects are present in slab
a131b245-0bd3-536f-92eb-bc703727ae65 | note | • Complete Fulton Hogan Post Pour Checklist
38c2d995-2db9-5b12-8ea4-8ae1d95726da | note | REFERENCE DOCUMENTS: CE-019-ST-0033
214e0585-5d53-5ff8-a22f-d5729219a9e2 | note | INSPECTION/TEST METHOD: Visual Inspection
7fe7b8fb-b935-5d26-bb04-5250966bba34 | note | RECORD OF CONFORMITY: Post pour checklist
194f6ab8-1f58-5aba-a251-51a0aa209822 | note | IP
3a0f0283-bf4d-5f48-81bf-2f6ca4ff36d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
c4b69e3b-9706-5051-9d93-c80795b2096e | textbox | DATE:
4acfc0c9-64a1-4788-8713-f05d45a50594 | checkpoint | Final Inspection
358805e0-7c71-5807-8bc9-7011d48e1b06 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications
627f3738-85c9-53b3-b153-c6eefd37139a | textbox | Print Name:
eaeba2eb-ec3a-5cfc-b9b9-b6d1a5219dea | textbox | Position:
fc212994-23a9-5008-9855-74fad5260c98 | textbox | Date:
f3edb058-0f89-482e-ad4a-ea66af7d1fdd | checklist | ITP-008 - Hot Mix Asphalt Rev2 | itp | ITP-008 - Hot Mix Asphalt
52c1fe73-6c81-4067-8a95-47f415a0d055 | section | 1 - Construction Works
9ce87d74-9207-444e-8bcf-478ea75136e1 | checkpoint | 1.1 Submission of Mix Design
3c7d5a74-4fa9-59cc-b9de-2a80b0f383f6 | note | FREQUENCY: Prior to commencing paving
1e8ccf90-9d35-5559-bf28-bb356cfe1d92 | note | ACCEPTANCE CRITERIA: Ensure the correct mix design has been registered and is approved by Superintendent prior to laying mix according to standard track structure drawings
5c7aa9f0-26d2-5590-bd78-09776ebea4ac | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
db931383-e7a0-5379-86b3-051bd78e569c | note | INSPECTION/TEST METHOD: Correspondance of receival of mix design
5b75cd4b-2bd0-5209-8903-09c18f817fba | note | RECORD OF CONFORMITY: Superintendent approval Completed ITP
b9c2944f-c129-56bc-9747-6cfaca3e3017 | note | HP
681e9169-fb4d-59a2-ac70-e855b1d7230b | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor / Superintendent
4097e28c-0cb4-5d37-9db1-07704948aa00 | textbox | DATE:
ead1f852-1d69-4ebd-8233-6587e73d8bce | signoff | HOLD POINT AUTHORITY
5aafd120-be26-4304-9984-ace39ef74d78 | checkpoint | 1.2 Site Inspection and Base Condition
9d5137ff-87ac-5abc-9ef2-96264a988ee8 | note | FREQUENCY: Prior to commencing paving
c29d74a8-2484-5201-80a0-2016aa74496e | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
adc4ec6d-9cc2-54dc-a95a-5f1369633022 | note | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
0c8acdf1-c13f-574d-a43a-e1d086153683 | note | INSPECTION/TEST METHOD: Visual Inspection
d04b131a-8a80-57ff-b388-0485a90d9eba | note | RECORD OF CONFORMITY: ITP Signed
baf0933a-54a9-5603-be57-6d2d55cdd5ae | note | WP
4729ad8d-cdfc-5a9a-88d3-f9677ea78522 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
993126bd-393c-5ad3-9c75-77dea26b88bb | textbox | DATE:
e2163b8e-eb5f-4e4b-bf0c-8b5399ec4e18 | checkpoint | 1.3 Ambient Conditions for Placing
4a59601e-8715-54be-b076-e5b72c37a001 | note | FREQUENCY: Prior to commencing paving
9aac1bae-69c4-5a58-a82a-31693a7cb3d5 | note | ACCEPTANCE CRITERIA:
44bbd0ab-b0b0-5a36-99d2-3bf816fbca3a | note | • The majority of the surface area to be paved has a temperature greater than or equal to the following:
32f1c26b-c835-552a-9719-e286532ae680 | note | – Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
2456e870-6136-5671-a9fd-c9f4ab091e32 | note | – Wearing Courses: 10°C for conventional binders or 15°C for PMBs
6f9dcb72-d89a-5990-9869-b9508e45b70b | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
099f250d-9dda-59ff-aa00-ae70547bf988 | note | INSPECTION/TEST METHOD: Verify
3b11cf6f-fdbf-5482-bb46-3eddb72f122a | note | RECORD OF CONFORMITY: Thermometer
6db2748c-3c28-5f14-ab62-d3e5b12ac71c | note | IP
1828ad3f-627d-55e3-a51a-b08e30f8393f | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
37ee4f90-ed9e-54e7-aea5-4ed3f04c92b3 | textbox | DATE:
747e67b6-7683-453d-8e95-d5b520d49c15 | checkpoint | 1.4 Planning of Joints
28c924f4-7be5-582b-9f7e-5287d4dcbe61 | note | FREQUENCY: Prior to commencing paving
5a728779-ca49-54c9-9108-993b6806df4d | note | ACCEPTANCE CRITERIA:
ce1e8a2d-1704-582c-9469-cfb8163e6122 | note | ○ Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
d84b83d1-0a6d-557d-86be-e543fa2a4383 | note | • Transverse Joints Offset from layer to layer by at least 2m
4aadf958-2d35-576d-a8e3-4aa677ffabe3 | note | • Longitudinal Joints Offset from layer to layer by at least
02e4d722-fd84-55b0-889b-168020443efe | note | • 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
ec22bb5a-716a-5d81-b536-0d5493e0da13 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c) Pavement Drawings
b21775d5-9d48-5864-8249-6493685ba5e5 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
c1116d1c-18fa-540c-9567-9f0400f2a953 | note | RECORD OF CONFORMITY: Paving Plan
db96e033-dd2b-5026-bdda-4bda1d7d7065 | note | WP
0316f915-0495-537a-badf-8ea1775b97af | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
ec8187e5-22ec-56bf-8638-bfb24e68289e | textbox | DATE:
eb90047d-9f8b-4dc9-bf88-d2504d15494f | checkpoint | 1.5 Longitudinal Joints with existing Pavement
4f6a5bb9-c6c6-517f-9c58-48b8783ec6c2 | note | FREQUENCY: Prior to commencing paving
e9925f27-870c-5163-9293-0bdd69332a5e | note | ACCEPTANCE CRITERIA:
dfb7fbd5-cf01-5b23-a0bb-2abfe6299a9d | note | • Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
30bf793a-98b5-5869-b6bb-7de148cb49e5 | note | • Depth of step to be cut to the full depth of each indiviual layer.
7e763025-4b35-5c62-b08e-5f0c67cc404c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c) Project Specs. Section 3040.06 (d)(vii)
5cea51ad-2677-5c38-87d9-f5d96987afcf | note | INSPECTION/TEST METHOD: Visual Inspection
c96f4c6b-f27d-56d9-9a35-da52c0ae432e | note | RECORD OF CONFORMITY: ITP Signed
00b37b54-eb4a-5e61-8c1f-3a4d4077aad8 | note | WP
3c358c4d-c12e-5ac5-a4fb-e9ce7ce8e1c5 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
9718ba3f-737d-5022-9a2d-d42b8779c5d1 | textbox | DATE:
4831288f-8945-46e7-8d57-6587f1a4b64c | section | 2 - Asphalt Placement works
09e92ab4-48e4-493d-bb70-5a03f96bb317 | checkpoint | 2.1 Commencement of Placing
ef707d7e-1250-5ca3-aa31-f9ccb1db8783 | note | FREQUENCY: Prior to commencing Paving
78aca2a6-d74b-546f-a119-21a0bc0954e0 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
1a015b04-4c4d-5ac8-941a-c7617191de0e | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
19af8369-53b9-5a6e-92f5-76fe112922fb | note | INSPECTION/TEST METHOD: Visual Inspection
90236489-3370-5a72-82a7-57c529964cf6 | note | RECORD OF CONFORMITY: ITP Signed
f6e42286-5ddb-5091-b2e9-ea68365f703e | note | HP
b083fd84-1907-560e-a93e-685aff53ac02 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor / Superintendent
af4060a4-596d-5372-a85e-20691fa00488 | textbox | DATE:
5a76f65d-30a8-4373-a427-a1546a24cf18 | signoff | HOLD POINT AUTHORITY
066a912c-a82a-42bb-8f7c-ddf7a099727e | checkpoint | 2.2 Mix Design Confirmation
715e22b3-4876-5ced-860b-a76c1a9da9b8 | note | FREQUENCY: Each lot
aa987ecc-fc8f-5fc9-ad80-8f470f679eab | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt wearing and base layer mixes must abide to IFC drawings and be as specified in standard tram track drawings.
5f542931-f966-57da-a2c5-a62d0803da1f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09 STD_T9010
12e9bca9-dead-5adf-ba97-2ce68d67e260 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
4699e5cb-8de3-569f-b2e3-09933d42d623 | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
0088de17-89b8-56e9-8f81-95ae6287921f | note | HP*
c2acdf6d-a0da-585b-ab9b-8b5dfedbabc6 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
e37aea2c-893e-5084-a964-e0aebda7e992 | textbox | DATE:
043fa327-10a1-4a6a-bfff-b90e3f477410 | checkpoint | 2.3 Delivery of Mix
b16415b0-8a45-5cde-980d-05bf0c6371d7 | note | FREQUENCY: Each load
adbf83cf-e747-5ade-8641-6399b78ce5f3 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
037911d7-b282-5e44-adda-8b36f75b7e7a | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20 Table 407.111
56da7d1b-503d-529a-bcd6-847d2d68b8a5 | note | INSPECTION/TEST METHOD: Visual Inspection
52bf561f-44b0-5dc0-94fc-a61c96e11244 | note | RECORD OF CONFORMITY: Delivery Docket
9d12eb23-7832-50c1-a4dd-6dcd69b0b542 | note | WP
bc975bc8-d075-51c6-986f-ff99795438a4 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
8b021180-8e8f-57fe-902d-4a7dc5bf9af8 | textbox | DATE:
49595050-ad01-4523-a671-32948ea8d721 | checkpoint | 2.4 Traceability
9c8f22d0-0447-5953-9767-6165801a46a8 | note | FREQUENCY: Each lot
3391f3e9-c684-5d67-a89e-7eb61abee7cf | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
1d8be6b9-f383-59fc-aa4c-3750eb310dc8 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ddf03f5c-38a1-5b12-be0c-1dc60024eb47 | note | INSPECTION/TEST METHOD: Verify
e8589e75-6a45-5918-b419-c91c5e69d166 | note | RECORD OF CONFORMITY: Daily Lot Record
638ec7d6-40b3-5c10-acf2-8fa4598b3477 | note | IP
5f48aa88-93c8-5b6d-b756-fac2335086b7 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
064b67c7-0496-5c45-b8b4-5fa331be88d1 | textbox | DATE:
5912eb0f-17a7-44d8-8b50-be513abef043 | checkpoint | 2.5 Layer Thickness and Level Control
42451787-e5a8-5b28-b767-b58019b7bbfc | note | FREQUENCY: Regularly during paving
de8e04a8-391a-5bdd-87e5-923883369bd5 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
6eaee0eb-cd40-5564-865f-c01dc1611e4c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
1c5f88c7-3782-5eb6-8918-7ca0782c9822 | note | INSPECTION/TEST METHOD: Verify
0f624a6d-a677-58d6-a46d-120becbbedaf | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
a78ad95d-8482-5702-9a5a-b375e303ab4c | note | WP
646f6144-9150-55d1-a4d4-975c895a738f | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
4d290aef-d3a5-5713-96d4-435f8a5580f0 | textbox | DATE:
f1a38348-088c-4fba-b5e0-4c6b9298569b | checkpoint | 2.6 Surface Finish of Wearing Course
5f131282-68de-50bd-af0e-549f2abd3c66 | note | FREQUENCY: During paving and after final roll
b7da6a97-2ada-56b3-8c07-194b5a6f9e4e | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
b8336e7b-9f43-5eb6-bd8d-19d2ef71c37b | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
4bccd4ad-2665-52a2-b70c-eddcafecc099 | note | INSPECTION/TEST METHOD: Visual Inspection
d7c10bb5-6a00-5aea-8cd7-b95eed1f0fa8 | note | RECORD OF CONFORMITY: ITP Signed
6734527b-4359-5e6d-8eb7-06325a0302ac | note | WP
c9be4ce0-ab45-519c-8a7b-dce677132269 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
ee616819-cf06-53a7-8dfd-515b73037f5c | textbox | DATE:
22a3125f-689a-43a9-b9c5-7973bb6ca2da | checkpoint | 2.7 Alignment of layers not placed against concrete edge
c09a4929-7c0f-5eb9-9548-68c6cf0e88fa | note | FREQUENCY: During paving and at completion of work
0266c7c7-1aae-5983-b465-5127774c9832 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
c42fb1d3-ac8b-56e5-8dd3-dcb127bc3ff4 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv) Drawings
89612f37-d736-5e3f-8720-c6ef5143caa2 | note | INSPECTION/TEST METHOD: Visual Inspection
1a5b5df4-5976-5cec-a4ed-18bc3987afe4 | note | RECORD OF CONFORMITY: ITP Signed
b1d56df3-ea54-5775-8083-183378ae93c4 | note | IP
d10374cb-5788-5aab-a878-cc6017024869 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
2d822e83-42ef-50d8-90da-8e2793c594d3 | textbox | DATE:
ccc0c08e-f085-480c-89ac-70c5b1b17251 | section | 3 - Testing
ecb0fa6b-b1fd-4949-b869-c429ab9604e1 | checkpoint | 3.1 Compaction
eda76481-15a8-569c-8990-a78165b7ed0e | note | FREQUENCY: Per Lot
08eeaa51-d591-5112-96f3-3e79d8be703e | note | ACCEPTANCE CRITERIA:
507bc64e-dccc-59d2-8857-6f111eb74042 | note | ○ For wearing course layers <50mm, if characteristic density ratio is:
5401ebd9-629e-5b58-9516-af62d15f23c3 | note | • 94.0% or greater Accept lot
67387c2e-1808-5690-9237-651d2308efe6 | note | • 91.0% to 93.9% Lot may be accepted at reduced rate
3bc015ad-87e4-54e0-a80c-b57523bb1bd4 | note | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
376f3c0a-8999-5cbb-bd6e-75fb048fc7c9 | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
826fe862-ff3a-5cc0-836d-aa2540a4cf60 | note | INSPECTION/TEST METHOD: Verify
1438ce9a-eb69-5b53-91c5-6435103b618a | note | RECORD OF CONFORMITY: Test Report
e380982a-7db1-5167-b9cd-6304241043a4 | note | TP
e230ff84-9551-5dee-bade-15ce892b5a32 | note | RESPONSIBILITY: Site Engineer / FH Lab Technician
aeaf60f0-6800-5f3d-94c9-116ba20e94cb | textbox | DATE:
4179d23b-9e72-4a95-8e7a-eb7db415a594 | checkpoint | Final Inspection
9fd87725-abe5-54e0-8a2f-e60b9be13cdf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb5845a4-d4a9-5bbf-ba05-fbd8fff3d6f3 | textbox | Print Name:
a2110f3e-62fc-5b40-b807-ec9e1a5e159a | textbox | Position:
631a2c99-5ff5-546f-9bff-2a670c9deb04 | textbox | Date:
47b54975-aefb-4e83-9902-9629168bae57 | checklist | ITP-009 - Waterproofing Rev2 | itp | ITP-009 - Waterproofing
6ba1274e-12fc-4971-a3ce-d713692528db | section | 1 - Preliminary Works
ea6578a1-5d75-4393-be00-312cbf319b0c | checkpoint | 1.1 Check for correct documentation
5d2941de-7ddf-5068-bd57-8e3ae0ac2781 | note | FREQUENCY: Prior to commencing any activity
4c6197df-1d1b-535a-884a-32118f8f2104 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
3f8875c4-0ac5-5228-a9c8-0047a476233f | note | – using the correct and complete set of drawings
0ed7194e-2c4d-5c78-959f-c10e497587e4 | note | – all drawings are the latest revision
a29a61f1-ed04-5a07-a322-cf9f61609d96 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9cfe5f43-513b-572e-83a5-4d5f980dae69 | note | INSPECTION/TEST METHOD: Visual inspection
476b4ee4-067e-530f-a0bb-17a9b80755bc | note | RECORD OF CONFORMITY: This ITP signed off
819306d2-a797-584b-a344-884062d7131a | note | HP*
a4431ae7-d846-5b97-afb1-61065d3b0533 | note | RESPONSIBILITY: Fulton Hogan Engineer
5b5a29ba-0374-582e-8417-f5c69ae10a41 | textbox | Date Completed:
ea439c13-6681-4097-b663-d4f1420e5353 | checkpoint | 1.2 Submission & Approval of waterproofing materials and procedures.
dc9ec8a9-81ab-5237-bfda-57efda0625f9 | note | FREQUENCY: Prior to commencing any waterproofing activity.
30a9b62e-d315-535d-9773-382e11c0797e | note | ACCEPTANCE CRITERIA: Waterproofing systems shall not take place untill the Contractor's proposed materials and procedures and surface preparation in accordance with Section 691.08 and have been reviewed and accepted by the Superintendent.
8474e416-8974-509c-88d0-7a1d3c0c2acf | note | REFERENCE DOCUMENTS: DTP Section 691.05
a247e3c7-e7f9-57a8-94c7-de3e879573d6 | note | INSPECTION/TEST METHOD: Verify
025b8021-743a-597e-8030-4e8a2baeb40d | note | RECORD OF CONFORMITY: This ITP signed off
16f1b5ba-9f5b-5a38-b848-8c42b1e087ea | note | HP*
6ad67d42-b218-5e5c-8ed1-ed89464fba26 | note | RESPONSIBILITY: FH Engineer / Superintendent
c628a5c3-9de5-50e1-a740-059271daf770 | textbox | Date Completed:
6d684e78-5bb6-452c-acb6-fe74b8285e0f | section | 2 - Construction Works
19592878-8195-4d1a-9c5c-d50eb9cfd1ff | checkpoint | 2.1 Weather Monitoring
839e6999-9b9c-56cb-81eb-a9e6a3aae4d5 | note | FREQUENCY: Prior to start
1c221c69-4416-546b-9d16-2f9937af7b42 | note | ACCEPTANCE CRITERIA: Waterproofing systems shall not be applied under any of the following conditions:
a23609ec-867a-5988-8c76-6b7e0c5f3330 | note | (a) windy conditions where over spray and/or spatter may be generated.
aa116651-514d-5c66-91fa-180ca47775ee | note | (b) when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane.
57b6e68a-796e-5b9f-9942-c593e2bd5b44 | note | (c) when the ambient temperature exceeds 35°C or below 10°C, unless specified in writing by the manufacturer.
85807250-128a-5dc5-a1a2-c75f95c5729f | note | (d) when the humidity exceeds 85% or where it may exceed 85% during the 12 hour curing period.
46ae5a2d-4a08-5528-9f2f-6db7ea8eb254 | note | (e) when rain spatter or run-off, including leakage through deck joints may contaminate the surface affecting the adhesion of the substrate.
68b545b0-402f-5876-95ae-da7848d2c965 | note | (f) when the substrate is wet or damp, unless the waterproofing system is required to be applied on damp concrete in accordance with clause 691.05
d6c46dd7-505d-5e73-b9b5-40027506c4fb | note | (g) the surface temperature of the substrate is less than 3°C above the dew point calculated in accordance with AS/NZS 2312 (Fig. 8.1) or exceeds 40°C.
9f90d8d5-08e0-5407-9a23-82449573165e | note | REFERENCE DOCUMENTS: DTP Section 691.14
0f52eaaf-e4f2-51cc-a003-e7617747fb47 | note | INSPECTION/TEST METHOD: Verify
396df0b5-7d37-5737-8aa8-55a53259c69a | note | RECORD OF CONFORMITY: This ITP signed off
fbe5d071-75a5-5437-8ed9-3c39072d6c81 | note | HP
ddd78186-9ab5-52ee-a7f7-17b63551d570 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
a82b6c3c-7010-51fa-a9da-eaa812f93310 | textbox | Date Completed:
e58f3045-fc03-4302-ba52-36eb0560c410 | signoff | HOLD POINT AUTHORITY
fbdcfabb-63ec-4531-bc45-51a917d11eba | checkpoint | 2.2 Trial Application
54aad883-8300-5794-9229-243ea5b37d69 | note | ACCEPTANCE CRITERIA: A trial application of the waterproofing membrane system shall be conducted on a test area of the actual substrate of not less than 10m2. The test area shall be prepared and membrane applied by the Contractor to satisfy the requirements of clause 691.08, 691.09, 691.14,691.17 and 691.18
85fec37d-24cb-5100-a83a-cede0535715a | note | REFERENCE DOCUMENTS: DTP Section 691.16
3b4c7e66-c65e-5300-8b6c-4b8e55db49c1 | note | INSPECTION/TEST METHOD: Verify
11310c54-66db-5a1b-bebb-e8c2344c71e1 | note | RECORD OF CONFORMITY: This ITP signed off
f16a62a7-5067-547c-8f11-64c6609a8282 | note | HP
6253c3dc-de35-5c1b-b9b7-17615b3b2127 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
babf0a96-2dbd-513d-9ab2-9defc17ac698 | textbox | Date Completed:
cdc582a7-cfa8-4a6c-beb8-094cf9621fe5 | signoff | HOLD POINT AUTHORITY
06215e28-36d8-41c7-aca0-f81087bffa7f | checkpoint | 2.3 Surface Preperation
72570937-d05d-5eb8-8f1d-7d870dd895e0 | note | FREQUENCY: Prior to start
75533f2b-5fc1-5118-9ca4-60004994db7b | note | ACCEPTANCE CRITERIA: The surface preperation shall be done in accordance with manufacturer's recommendations for the waterproofing membrane system.
2734629c-6bf4-50d0-ab4a-e22008cecba2 | note | ○ Concrete surfaces shall be dry, clean, sound and free of dust or loose particles. Weak or loose surface layers shall be removed and repaired in accordance with DTP Section 689. Rough spots shall be removed with an angle grinder.
5f1d1f06-49fd-5ec9-8339-e5dfba1e1e67 | note | ○ Primer shall be applied in accordance with manufacturer's recommendations and installed by using a brush, mop, broom or spray.
324aa113-7206-53ca-93a2-f9724294d5a2 | note | ○ Only areas where the waterproofing membrane is to be applied on the same day is to be primed.
1551f624-2478-5ac7-9b6a-01d0576b0e28 | note | REFERENCE DOCUMENTS: DTP Section 691.08
4840f18a-33d9-58a2-a0ee-1012cf33434c | note | INSPECTION/TEST METHOD: Verify
06c985c8-26c3-54ec-9820-7fc04786c5f7 | note | RECORD OF CONFORMITY: This ITP signed off
33f50849-8995-52e9-9da5-3195dfcef12f | note | HP
e06b1653-b2ba-57e5-bb6b-8a5fb451c339 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent / DTP Representative
50787dc7-6243-571d-a3da-f54e973f9218 | textbox | Date Completed:
2aceb20c-f38b-4699-aba0-92d7d3770f36 | signoff | HOLD POINT AUTHORITY
edbd14d1-fbde-4412-b869-93f3f04fb866 | checkpoint | 2.3 Installation of Waterproofing Membrane
06cc23dd-6914-5921-b7bd-c4db2e2dc8bf | note | FREQUENCY: Where Required
c535bd02-2a2b-565f-9b9a-61f77bcaae42 | note | ACCEPTANCE CRITERIA: ○Waterproofing membrane shall be applied and prepared in accordance with manufacturer's recommendations.
4d95bb35-6a28-5bab-90ab-f3d8d4141075 | note | ○ The waterproofing membrane must form a seamless film with uniform thickness and complete coverage.
452d0f73-3123-5211-a205-5200d5249025 | note | ○ Coverage of the waterproofing membrane must be continuous over the entire deck area.
0954f7ab-df21-5759-8b31-b2da37fdce74 | note | ○ Sidelaps shall be 80mm and end laps shall be 120mm to ensure membrane is waterproof, as per manufacturers instructions.
bc563b43-97f9-57ba-9202-9966ad55079f | note | ○ Waterproofing membrane shall not be installed on wet concrete surfaces.
fe47aa62-bdba-5579-a371-c1c9314f31b3 | note | ○ Surface shall be protected against contamination and rain or expected rain if water proofing is not undertaken within 24 hours.
0dea7eeb-fc77-59dd-a93f-ef54c6fc65bc | note | REFERENCE DOCUMENTS: DTP Section 691.09 & 691.10
35ae39b0-4031-5f0c-96a8-ef01e34d8435 | note | INSPECTION/TEST METHOD: Verify
88d90fce-55f2-5a9b-83b7-418cc469436f | note | RECORD OF CONFORMITY: This ITP signed off
dc8e6a96-3b42-5eac-ba29-caafb6e37719 | note | IP
706f9a34-4230-5192-bf27-44acd781d7cf | note | RESPONSIBILITY: Fulton Hogan Engineer
081f5446-e315-5339-bc3c-89dc33df9dcb | textbox | Date Completed:
40cc6436-0c69-4c9a-9581-8ba7149872d1 | checkpoint | 2.4 Drying and Curing
96bca089-cf9c-52ca-ab09-0271b379dc34 | note | FREQUENCY: Where Required
547b91b6-afcc-59ce-b475-17f1ded71c1c | note | ACCEPTANCE CRITERIA: ○The curing shall adhere to the manufacturer's instructions regarding drying and curing, and overcoating time intervals, for the prevailing weather conditions.
bc4ed307-74ce-5204-8859-d1c4704d2c1e | note | REFERENCE DOCUMENTS: DTP Section 691.13
3144664d-3183-5d0d-b79a-936f501a94e9 | note | INSPECTION/TEST METHOD: Verify
f8f221cf-c459-50ec-bf2a-9e9a803ea70e | note | RECORD OF CONFORMITY: This ITP signed off
6914ee64-a4a0-58a6-8f09-24d542a543bc | note | IP
0c90e8e0-e91d-5fc0-b284-616de0d07f6f | note | RESPONSIBILITY: Fulton Hogan Engineer
83d1bac5-58b4-5991-ad23-c9aea849f327 | textbox | Date Completed:
d52d434e-c954-486c-878c-2e310294cf8d | checkpoint | 2.5 Testing
67cbed2a-1e4a-5459-930c-58489f379527 | note | FREQUENCY: Each Lot
0065a3c6-3a73-5652-984e-36dcf9ee3afc | note | ACCEPTANCE CRITERIA: Testing shall be conducted in atleast 1m2 test area in accordance with Section 691.17.
9064e79f-406a-561a-aaae-4bd131b80050 | note | ○ Testing after Application the bond strength to the substrate shall be tested using aluminium dollies with a minimum diameter of 50mm in accordance with AS1580.408.5. A circular hole cutter of diameter slightly larger than the diameter of the aluminium dolly shall be used, to cut through the preformed waterproofing membrane to the substrate around the dolly. The bond strength shall be greater than 0.75 MPa, seven days after the application and curing process.
57bcd2db-f70f-5a0e-8c7a-326f8654acea | note | REFERENCE DOCUMENTS: DTP Section 691.17 & 691.18
6a7a4d3b-9c8e-5629-997f-b5d37647dae2 | note | INSPECTION/TEST METHOD: Test
1a33ab71-188c-53e8-9c23-77ac259049c2 | note | RECORD OF CONFORMITY: This ITP signed off
7305b2e1-c478-5320-9fb4-42c5228d409b | note | IP
20337cc8-6fd8-5ff5-94f1-74179fc436b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
3d57d159-932f-5be6-9a4f-2547ee10d8bf | textbox | Date Completed:
1cd8dad9-2207-46fb-a2b9-acaf985dea1d | checkpoint | 2.6 Post Pour Inspection
db01722d-2f10-5cd6-b639-3356fa294219 | note | FREQUENCY: Each Lot
d9af2e1f-78d1-5df1-b380-1bea6f1f6b2c | note | ACCEPTANCE CRITERIA: Ensure finished surface of waterproofing membrane is of high standard, with a uniform and level surface in accordance with manufacturer specification
13229ba8-8099-5639-a397-bc0f2d955222 | note | ○ Ensure no defects are present in membrane.
b65c189a-4c6c-546b-b108-a5a7c305c798 | note | REFERENCE DOCUMENTS: DTP Section 691.17
efd56ada-f3e1-5883-a84c-4a76f9420c3c | note | INSPECTION/TEST METHOD: Visual Inspection
13556ea0-801a-5251-91f1-e818ffd6d4a1 | note | RECORD OF CONFORMITY: This ITP signed off
02d7d747-9acc-5795-b8f7-384c601ef3c9 | note | IP
a1ff30ab-8570-5893-8970-477d1d050f88 | note | RESPONSIBILITY: Fulton Hogan Engineer
0c4b18cc-1d5f-53b3-8b72-dcee3a6908f1 | textbox | Date Completed:
0850993c-d934-4c96-9d51-53ef55670f6d | checkpoint | Final Inspection
7de5e2d1-2969-5ad0-86da-0ba8793d1432 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
06a70ef7-2399-54d1-b3d4-c6bae5176b76 | textbox | Print Name:
2acf1cc5-bfc6-58b3-8875-0e7116871bd1 | textbox | Position:
14b78be7-d40a-5040-937a-01820df50fa2 | textbox | Date:
695fb9d4-7195-4fe9-89c7-9121cf6397b0 | checklist | ITP-010 - Bonded Anchors Rev6 | itp | ITP-010 - Bonded Anchors
3a715992-92a4-460d-b0f1-18291ccb9886 | section | 1 - Preliminary Works
c61efd39-3667-4551-8442-f9ea3a8dea07 | checkpoint | 1.1 Check for correct documentation & Materials
6eae306e-07aa-51c5-aa4d-23729196f139 | note | FREQUENCY: Prior to commencing any activity
d43d1e93-92ff-5a1b-a18f-cb25c529e85d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
92bd07af-9cad-5bed-a639-164d4ce4bc48 | note | – using the correct and complete set of drawings
8e3c7fca-a917-5149-88ab-f847c35eb1a9 | note | – all drawings are the latest revision
d307229b-771f-512b-b942-89b9d1f3514c | note | – Drill bits to be carbide or diamond.
38016e9b-b7ce-5da0-8a7a-2e6d45a534e6 | note | – Allocate work crew to each span.
ed15100e-fcf0-5d97-80d5-f7ca872db25d | note | ○ Toolbox to be conducted with workcrew to run through ITP/WMS/HILTI TDS and reinforcing no cutting. SRG and Hilti Rep to be present and sign on to toolbox.
c26dc49d-a09d-52b5-99ac-1fa50522b29a | note | REFERENCE DOCUMENTS: Drawings and drawing registers, Section 680.05
02a3789c-1dc0-5e9b-a076-7c3ad784158d | note | INSPECTION/TEST METHOD: Visual inspection
6ea520b6-a734-5952-8f50-ca2f10fcabb3 | note | RECORD OF CONFORMITY: This ITP signed off
f5d3f956-5cf3-595e-8d33-4277a1576405 | note | HP*
72655d43-eb27-5665-a7a1-136db87d7b8b | note | RESPONSIBILITY: Fulton Hogan Engineer
6586baff-8e25-58fd-a45b-5d006f154107 | textbox | Date Completed:
3c60ac0a-3f8d-4991-9f87-d9f517ca3b7b | checkpoint | 1.2 Submission & Approval of Design/WMS/ITP
773b6b7c-f9bf-581d-b012-47765288fb65 | note | FREQUENCY: Prior to start
905c76cb-899e-5334-a528-ff34c86ed7b4 | note | ACCEPTANCE CRITERIA: Subject to the requirements of BTN006, if it is proposed to use bonded anchors in tension , shear, compression, combined tension and shear or fatigue applications as described in BTN006, the Contractor shall submit full details of the proposal, including a Proof Engineering Certificate of Compliance, for the approval of the Superintendent.
3b6a4399-2500-5fad-b9af-d7891701b4e2 | note | ○ The Contractor shall not proceed with drilling holes into the concrete, installation or removal of bonded anchor works until the WMS and ITPs have been reviewed and approved by the Superintendent.
4e1ad957-2dd2-5931-9d5e-9300837f138f | note | REFERENCE DOCUMENTS: Section 680.04 & 680.11
75d1bd5a-17fd-56a5-b9c1-e763b31ed1e0 | note | INSPECTION/TEST METHOD: Verify
e47bd7f1-9a33-5b08-9b85-52f843f447e8 | note | RECORD OF CONFORMITY: This ITP signed off
b5a8fea0-73c4-5961-8048-a72a1ff46641 | note | HP*
2de30d80-232f-522b-a265-b1469c1fe369 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent/DTP Superintendent
ce2b61fd-554d-55a6-9afa-343ae0f4d72a | textbox | Date Completed:
e6f8f758-82c9-412c-a4cc-f8950570abc6 | section | 2 - Construction Works
d70c189a-d631-4ad2-98dc-a443794a34ac | checkpoint | 2.1 Weather Monitoring
c1053b8e-b0a1-5bc4-80ef-8973e026ca40 | note | FREQUENCY: Prior to start
7b098aff-d926-50cd-97ce-d3910c3ff3d9 | note | ACCEPTANCE CRITERIA: Installation of adhesive shall not occur while ambient air temperature is <-5C or > 40°C.
cdd87e60-44d5-5a49-9930-5ad55d8a72da | note | ○ Where there is rain forecasted, tents shall be setup to ensure that the drill hole is protected from the elements.
b2aef88c-16a7-5152-b2fe-fbca4ca7d03e | note | REFERENCE DOCUMENTS: Section 680.08 & Hilti TDS
c5c68aa7-48f8-51b6-bf97-40efd3120a9b | note | INSPECTION/TEST METHOD: Verify
eb5cc72a-b307-5eda-97d8-cc32f6cefa49 | note | RECORD OF CONFORMITY: This ITP signed off
d7869830-e6ce-53ce-b48a-d046e2c03fc6 | note | IP
4133864d-6af2-5189-a2b0-824859c99c67 | note | RESPONSIBILITY: Fulton Hogan Engineer
25fc1b15-2fcb-5dc4-abb1-f76706e0643c | textbox | Date Completed:
c70662b6-0004-4ce7-985d-93672de8c91d | checkpoint | 2.2 Trial Installation
0d9aaaf9-a967-55e4-a801-bae1ed8d1a4a | note | FREQUENCY: Prior to start
3af326b8-82a2-551c-a82c-f699ec8f1793 | note | ACCEPTANCE CRITERIA: 5 Bonded anchors shall be conducted by each work crew of installers, seperately for each type of bonded anchor system used in the works.
fb36b4ef-969e-5374-ba52-92661157029d | note | ○ The trial batch shall also be tested to comply with 680.09.
ff0a67e5-53b8-52c8-8a3f-c0825e6de4ab | note | REFERENCE DOCUMENTS: Section 680.12
8d69e35b-c7b7-5fe0-bc1f-1effe25d0e7d | note | INSPECTION/TEST METHOD: Verify
b4fe9e4e-8818-5935-8c55-27aba8ecbe48 | note | RECORD OF CONFORMITY: This ITP signed off
ce2acff9-e267-5fcd-bf9c-e9d142b94c62 | note | HP
1c39f20d-fea2-56ae-99c7-de5c278d5c13 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent/DTP Superintendent
b2979609-815c-59cb-9930-46a4dd9372e8 | textbox | Date Completed:
106f9590-aa56-4826-95db-df05f1e2c439 | signoff | HOLD POINT AUTHORITY
6244364d-10f3-428a-ab22-be106deefa94 | checkpoint | 2.3 Setting Out
39569373-4ae4-54e2-a963-f45f6eda6832 | note | FREQUENCY: Prior to start
9508f4cf-fcd3-5fcd-abfb-2fa679ba9b81 | note | ACCEPTANCE CRITERIA: Reinforcing bars that lie within the depth of the drill hole shall be accurately located by reference to available as-constructed drawings and/or by the use of concrete cover meters or ground penetrating radars.
dd01f103-9291-55b5-b319-500ae237f82f | note | ○ Position of bonded anchor shall be away from any existing reinforcing bar.
576816a5-49ab-52e4-aa11-018ad10adabd | note | ○ A drill guide shall be used to ensure the drill angle is as per design.
370a6cc4-8443-515a-bcca-c35980541767 | note | REFERENCE DOCUMENTS: Section 680.08 / B-P.23.1738-00-STR-DRG-1005
22cd3263-8b69-5044-aab3-03cccd5edcce | note | INSPECTION/TEST METHOD: Verify
64f2d93a-9d89-5796-8795-56a401571360 | note | RECORD OF CONFORMITY: This ITP signed off
e49a0c1b-6162-5ead-8df2-a6d72e68d859 | note | IP
b694896c-187d-5029-8ada-404b42274230 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
f48f1b2e-6c3c-55c4-85a8-c6ee298e5989 | textbox | Date Completed:
b40fa97c-bdd5-44f9-9899-0a87964dfc99 | checkpoint | 2.4 Drilling
a6623aab-04e1-5c6e-b904-721eefdf8de9 | note | FREQUENCY: Prior to start
bc224078-cc97-50f9-bdb6-836a12c01b58 | note | ACCEPTANCE CRITERIA: A 14mm hole shall be drilled at a 45 degree angle. Depth of the drill shall be as specified in the design drawing and allow for 350mm embedment
9e5c5557-f782-51d4-b939-702c0938e30a | note | REFERENCE DOCUMENTS: Section 680.08 / B-P.23.1738-00-STR-DRG-1005
fa8acdf7-3529-5afc-848e-a5714829e9de | note | INSPECTION/TEST METHOD: Verify
50139d34-11df-5e51-af33-c6ff57ab2afe | note | RECORD OF CONFORMITY: This ITP signed off
5d0d572a-d392-569d-9407-2ad90ae7442f | note | WP
7a6fa5ee-6b86-5f52-aba2-c270014662bc | note | RESPONSIBILITY: Fulton Hogan Engineer
ed6dff65-d394-54d4-8d7a-d9955a7e6151 | textbox | Date Completed:
5ee1f9d1-f82c-4293-918c-6a6bfa21d824 | checkpoint | 2.5 Cleaning
6b33427b-3cfd-5596-821c-240337212d4d | note | FREQUENCY: Where Required
29e6201c-5c68-5db3-b2e1-7ab83f086e2c | note | ACCEPTANCE CRITERIA: Compressed Air Cleaning:
d358107e-44b9-5eea-9883-92b133edda35 | note | – using compressed air, blow two times from the back of the hole over the hole length with oil-free compressed air until return air is free of noticeable dust.
9b8ccabf-de00-54e5-800b-86555703c370 | note | – Brush 4 times with the specified brush by inserting the steel brush to the back of the hole (if needed with extension) in a twisting motion and removing it.
001087f0-e657-55dc-b606-687009ca8580 | note | – Blow 2 times from back of the hole over the hole length with oil-free compressed air until return air stream is free from noticeable dust.
82de5d49-acf1-5196-b5dd-483af28cb450 | note | REFERENCE DOCUMENTS: Section 680.08/Hilti TDS
5e82a846-92f4-5e0b-b412-3f3251701414 | note | INSPECTION/TEST METHOD: Verify
c90a5005-c353-51c7-9ddb-6ff417264ab5 | note | RECORD OF CONFORMITY: This ITP signed off
32a190d5-2360-5e9e-91ac-c5ac9e736df2 | note | IP
e051b5c4-91e7-5a53-bf69-7315f3ffeedc | note | RESPONSIBILITY: Fulton Hogan Engineer
9ea915ce-cd05-5768-824a-4499ca604470 | textbox | Date Completed:
135e08d2-3825-402f-95eb-97e858e808a8 | checkpoint | 2.6 Placement of adhesive and anchor.
7dcf7f18-1d93-5e0a-b461-f64b412c9d65 | note | FREQUENCY: Where Required
1099e2c3-6b4e-586e-9626-c4df930b8a15 | note | ACCEPTANCE CRITERIA: -Anchor shall be placed immediately following the cleaning process and after checking for sufficient depth.
1616e74d-e0e5-5e27-86e5-c45f98054e91 | note | – Chemical adhesive shall not be injected into the drilled hole until it is thoroughly mixed using the proprietary equipment to a uniform consistency, colour and appearance in accordance with the manufacturer's installation requirements.
997d685c-1cdd-5d79-858d-2e9eaac1c032 | note | – The initial discharge of Chemical adhesive from the mixing nozzle and for every new mixing nozzle used thereafter must be discarded. Only mixing nozzles that come with the Chemical adhesive and which are designed specifically to mix the components of the specific product must be used
f7ce08f4-9e8d-5d81-83ec-246b9bf55a65 | note | – The Chemical shall be injected into the hole using the appropriate nozzles as specified by the manufacturer. the adhesive shall be installed from the back of the hole towards the front and slowly withdraw the nozzle step by step after each trigger pull.
628a523a-eafd-5ae0-aadf-1abd9abebf13 | note | – Each hole shall be checked visually to ensure that the chemical adhesive is injected to the correct depth (typically 2/3 of the hole depth) prior to insertion of the metal anchor rod.
3d5a1e4b-c723-5c0b-8a88-a32995fd8c4f | note | – The reinforcement can now be inserted into the Drill hole while slowly twisting until the embedment mark is at the concrete surface level.
7d2bf687-cdae-5abc-8d9d-a80174b6c023 | note | – The final embedment depth of the anchor must be verified based on the length of the projected portion of the anchor from the concrete surface as shown on the drawings. 350mm embedment required.
2f0eefcb-a184-5192-a881-28a7186185fb | note | – Anchors must be secured in the centre of the holes such that a uniform thickness (bond line thickness) of adhesive is maintained between the Anchor and the sides of the hole until the Chemical adhesive has cured.
545c3b9e-8d6b-5b82-8f0c-af9507f6c917 | note | – Any excessive adhesive shall be removed from the concrete and Anchor rod surfaces after installation.
8ca03a1a-1b9f-5325-b731-b05e661b1e0f | note | – Fingertip test the hole for dust, and if dust is still present, Brush clean and air-flush until all dust is removed. Including a potential dust plug at the bottom of the hole which reduces embedment depth. at the end of the cleaning process, the hole shall be clean and free of debris, dust particles, oil and other contaminants over its full depth. Avoid over brushing to prevent polishing in the inside.
cf452996-dc93-577a-9966-087a59ef3352 | note | REFERENCE DOCUMENTS: Section 680.08/Hilti TDS
cdc818a6-2d9e-5441-8057-aff4c86b2587 | note | INSPECTION/TEST METHOD: Verify
23ee8bb8-b910-5af9-bc8a-dbdd907f4989 | note | RECORD OF CONFORMITY: This ITP signed off
e94c016a-5538-5daf-8645-57c2bc106f9b | note | IP
3110a152-8715-5811-bbf8-60d2042353f8 | note | RESPONSIBILITY: Fulton Hogan Engineer
dce1b399-38fe-50ee-9bfc-91ab185d78b9 | textbox | Date Completed:
e4cc4822-81fa-4ca0-b0c2-19a0d3bcb524 | checkpoint | 2.7 Curing
c2681c26-be7e-54e8-87c2-0f6fc0449aed | note | FREQUENCY: Where Required
3c8fb794-b892-56f9-822c-d53bfe4967b2 | note | ACCEPTANCE CRITERIA: Anchors shall not be moved or disturbed during the curing period.
5e139a7c-4709-5a64-8bb2-3f3be66b00df | note | Anchors shall be cured as per the manufacturer's instructions and confirmed in writing by supplier.
94e8ad22-bd32-5a28-bd89-b1d9c449388d | note | ○ '5degree <Tbm<9degree - 24 hours curing
eb5ba4d1-76c8-52fe-956c-25372b3f3876 | note | ○ '10degrees<Tbm<14degrees - 16 hours curing
2547a8f3-6371-5f03-ae55-92d202dd9f05 | note | REFERENCE DOCUMENTS: Section 680.08 & Hilti TDS
1634c5bd-0aa8-5beb-95a0-a397cfc12e27 | note | INSPECTION/TEST METHOD: Verify
a117ff7c-85d7-54b6-aef6-024d6677ec24 | note | RECORD OF CONFORMITY: This ITP signed off
4bf3f276-7aad-5d86-82ff-bad70be7567e | note | IP
0d30b350-8a01-5623-be95-b10f6f108a70 | note | RESPONSIBILITY: Fulton Hogan Engineer
1aed83e5-c79e-5ff7-9a0f-37f5685bed11 | textbox | Date Completed:
4e2f1556-9c3f-489a-a25e-8d60da173f2c | checkpoint | 2.8 Testing Methodology
fa9ab85d-d316-5a7f-ae4b-120afedb9475 | note | FREQUENCY: Post Installation
93728f12-88c4-5ecf-a0ca-a7022a6fbe5e | note | ACCEPTANCE CRITERIA: Details of the test method including load increments and duration of sustained loading shall be submitted to the Superintendent for review including the calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devices to be used.
bd64f876-5548-5342-9c20-9650d6194242 | note | REFERENCE DOCUMENTS: Section 680.09
8491d6da-1d09-5372-9aa6-4aa068d905b9 | note | INSPECTION/TEST METHOD: Checklist
6574faf7-4d82-5446-8cf6-2832e19c8e9e | note | RECORD OF CONFORMITY: This ITP signed off
6ad5e82a-a036-5f71-970f-58a8fe96ba8d | note | HP
8723ef19-44bc-551a-bcac-f06146e4e554 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent/DTP Superintendent
8b88c29a-fd98-5ed3-8b39-2b0176bdbfab | textbox | Date Completed:
59712fa8-e756-4464-90a4-dbd90becf7fc | signoff | HOLD POINT AUTHORITY
82cd0e1f-98a6-496b-afef-023532d11b9b | checkpoint | 2.9 Proof Load Testing
f882abb3-61ac-5c53-b2f6-320c3fc2843b | note | FREQUENCY: Post Installation
2b93b9a9-9246-5312-86f9-43e4b7e7dca4 | note | ACCEPTANCE CRITERIA: Proof Load Testing of anchors shall be conducted in accordance with Section 680. A test rig using baseplates and cross bracing shall be used to ensure testing on a 45 degree angle is met.
84d7de1f-6736-5c31-b67e-ce028756b0e9 | note | ○ Testing shall not occur prior to completion of curing time stated by the manufacturer's installation instructions.
e2e8b44f-a9bf-5923-9ac4-f75bc42460a2 | note | ○ The application of load shall occur smoothly with the proof load being achieved between one to three minutes from commencement. The proof load shall be maintained for a minimum period of 60 seconds.
bdc11cc5-e6b0-5acf-84de-6701d14e882e | note | ○ Bonded anchors shall be proof load tested to 1.5 x the maximum serviceability design load certified by the designer.
2c231391-e0fa-505b-b776-69fa39b1fd4f | note | ○ Number of Anchors to be test shall be in accordance with Section 680.091.
16c4152d-c805-5305-877a-6dcfe250f0f2 | note | ○ In the event that the bonded anchor fails, the Contractor shall submit rectification proposals for review by the Superintendent prior to any further bonded anchor installation.
885c6516-bd29-581a-9ee1-cec32cf502e4 | note | REFERENCE DOCUMENTS: Section 680.09
95fa3538-ce7f-5d8c-b082-0e8074d15a20 | note | INSPECTION/TEST METHOD: Checklist
32c53b2d-aef3-5388-8f54-3c71528f21cd | note | RECORD OF CONFORMITY: This ITP signed off
cc090607-a725-52b3-8512-4d64d860d280 | note | TP
803d8f36-585f-537c-9160-7b37d3abd228 | note | RESPONSIBILITY: Fulton Hogan Engineer
8e410398-89d6-557a-8a06-71501ed3d9b0 | textbox | Date Completed:
fd7d877e-b144-46e9-8a64-a0dd11f0869f | checkpoint | 2.10 Reinstatement
35668bfb-a6a5-5ffa-b6a5-fb9be407ef64 | note | FREQUENCY: Each Anchor
0ceca10f-5a41-58c5-9bac-cf1d27f3877f | note | ACCEPTANCE CRITERIA: Compliant bonded anchors shall be cut down flush with the concrete deck height.
f833d4d0-ed22-54ff-add5-feb2b4b61a03 | note | ○ Bonded anchors to then be drilled down 6mm below the concrete surface level. Holes to then be cleaned out and filled with Renderoc ST06.
43712efd-7e49-5f97-b8da-e4aa93fcd752 | note | ○ Any failed drill holes shall be cleaned out and filled with Hilti RE 500 V4 as per the manufacturer's TDS
395b9284-e8eb-5ac0-be97-1c441b592ad3 | note | REFERENCE DOCUMENTS: Section 680.10
1719426a-504c-5fae-b7ba-e9601d1e4def | note | INSPECTION/TEST METHOD: Visual Inspection
f58c5d0e-c588-5a90-b37e-6270125e8d1f | note | RECORD OF CONFORMITY: Post pour checklist
0cbc1171-2e01-5a7a-81e4-28c8bfc62311 | note | WP
00053217-c7e5-5b83-94a2-c4c415bce84e | note | RESPONSIBILITY: Fulton Hogan Engineer
3f1b035e-e7b8-509e-bf5a-77168bd286a8 | textbox | Date Completed:
083142ea-8fa0-45e3-bcc8-6e64cc5e518d | checkpoint | Final Inspection
842de826-6b9a-534a-9779-02c7416e402c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0d1b063b-d685-5c44-b58c-781df20b930b | textbox | Print Name:
3d5c6eed-aa02-5310-9c28-276cc6862661 | textbox | Position:
dce47776-544c-5742-9751-464d4b740cb1 | textbox | Date:
932c3588-1a35-4c07-b634-99030d17b134 | checklist | ITP-010 - Bridge Concrete Deck Repair Rev1 | itp | ITP-010 - Bridge Concrete Deck Repair
ecd540e3-1f3f-4330-86b1-5756552f5f9b | section | 1 - Preliminary Works
bf538986-a72c-4d83-aa4d-a0abd3c9f107 | checkpoint | 1.1 Check for correct documentation
33d05cb9-cb44-5e1e-a7f1-e568bcdde353 | note | FREQUENCY: Prior to commencing any activity
f676af62-34f6-5e07-9a5b-c1b78920b988 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
2a9c6c6d-80d9-54d6-bfcc-c69355505698 | note | – using the correct and complete set of drawings
146924aa-193d-5188-b7fd-a98e7420d6af | note | – all drawings are the latest revision
6f0b58a7-89e7-5831-ae1b-837e7863265e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b387e2d4-c97b-51d1-a0c2-233b127b1d34 | note | INSPECTION/TEST METHOD: Visual inspection
046d968d-24db-5332-ad7b-c3ac8730b4c5 | note | RECORD OF CONFORMITY: This ITP signed off
7e2095d9-9c5f-5ee2-a18a-accc68d3fd9e | note | HP*
d17ecf04-81a3-55dd-8cd7-aa3d3296bb3f | note | RESPONSIBILITY: Fulton Hogan Engineer
5c557dcf-36be-5238-b5f6-67b484473554 | textbox | Date Completed:
b74753cf-db1f-43c7-8386-b30ec9ad9b03 | checkpoint | 1.2 Submission & Approval of Patch Repair Material Prior to Commencement of Project
9230f4ae-1fe5-5612-a67c-f651dc88c8d9 | note | FREQUENCY: Prior to first concrete pour
2840cb69-fbf3-5652-82a4-b136c638e274 | note | ACCEPTANCE CRITERIA: Patch repair material submitted and approved at least 2 weeks prior to first pour.
826fb31a-548b-5e9c-ac73-5eb1bc4f2d38 | note | ○ Mix shall be minimum 50MPa.
0c0b6d3e-5dd2-5a49-945c-33bb537f2fa0 | note | ○ Concrete shall be installed as per manufacturers specifications.
1d67d313-5e56-567a-83a1-b930fb303f79 | note | REFERENCE DOCUMENTS: Section 689
83ce7e71-bc56-5d90-9e00-00a8e91ebcc1 | note | INSPECTION/TEST METHOD: Verify
e25c19fb-9eef-5817-8d55-ee35913c41bd | note | RECORD OF CONFORMITY: Email confirmation from Superintendent.
e642a3df-5bd4-590e-ad3b-98e94a1f6097 | note | HP*
8cd2e8a3-2a18-548e-8363-68df2abcc8dd | note | RESPONSIBILITY: FH Engineer / Superintendent
5fbeeda9-fb4a-55ef-a500-1f4039af70e2 | textbox | Date Completed:
f42777cf-eaab-4880-b657-937b110e5623 | section | 2 - Construction Works
5cff4e57-6db3-4acb-afef-256d34b27469 | checkpoint | 2.1 Weather Monitoring
25b92989-e2c6-5102-91e8-c245fed95c21 | note | FREQUENCY: Prior to start
7aa94565-db8d-543f-8de0-63edb4280ec7 | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
08a8c997-d07b-5054-81b0-1f6068b09186 | note | REFERENCE DOCUMENTS: Section 689
981aa809-9f29-5085-b557-3aae12b1b465 | note | INSPECTION/TEST METHOD: Verify
198e21b0-ed8e-55cb-aae6-a8a298fba2cd | note | RECORD OF CONFORMITY: This ITP signed off
85c381fb-79dd-5ec4-b0e7-1f7857a91737 | note | HP
ff6f5317-70fe-5524-8a91-23215ed3c839 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
058ffd7f-f10c-5603-9e36-734f0a36cd82 | textbox | Date Completed:
45048404-5e97-4b47-b09e-89b1896ac980 | signoff | HOLD POINT AUTHORITY
eb469258-0ac1-41fd-a894-a3a6b424208e | checkpoint | 2.2 Surface Preperation
8ec0ea2e-ad0a-58e2-bd54-2ff811b506ca | note | FREQUENCY: Prior to start
d4f699ff-3c51-599d-85a9-2b5fdd5e569a | note | ACCEPTANCE CRITERIA: For all types of patch repair, all defective an delaminated concrete and existing repair materials shall be broken back to a sound and dense concrete surface.
00c60b9b-fa53-5e93-9f42-763f1f4df79c | note | ○ All concrete surfaces and mortar substrates shall be sound, clean and free from dust, oils, and grease and surface contaminants. All loose and unsound materials and surface laitance shall be removed.
b39fa614-2273-55be-8e66-865144155b39 | note | ○ A 15mm flat face along the edge to be formed around the non-conforming areas by sawcutting/grinding.
68a996be-2405-5f71-b8e3-744cad8ad480 | note | REFERENCE DOCUMENTS: Section 689
c9be9833-e0cf-5e14-922c-7ae6e6fa50b6 | note | INSPECTION/TEST METHOD: Verify
ff462e0c-e661-54ea-a859-edd21e0bafce | note | RECORD OF CONFORMITY: This ITP signed off
e5f4b223-6d5c-5e39-b071-5cc730729fb1 | note | IP
144abb21-b154-5c14-8615-a65db754bc83 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
410c5544-366d-5734-94c6-328e0df5c706 | textbox | Date Completed:
48b111da-8627-4f9e-b6aa-6772d0f3a168 | checkpoint | 2.3 Pre-Pour Inspection
50e6d773-5cfc-5b15-961c-e3590613b513 | note | FREQUENCY: Prior to start
231d9339-ad9c-5b48-8994-67cc01aa0f8f | note | ACCEPTANCE CRITERIA: Superintendent to review the depth of removal of concrete or defective concrete repair and the amount of exposure of steel reinforcement prior to commencement of application of repair materials
c4b3e090-354b-5121-8ac1-67f2dcd1696e | note | REFERENCE DOCUMENTS: Section 689
f1e026b7-c811-5025-b7a5-6e031776fa7d | note | INSPECTION/TEST METHOD: Verify
00279804-3711-5563-9c37-7ae3ef341e1f | note | RECORD OF CONFORMITY: This ITP signed off
eb741ae3-4ce3-5827-88b5-88dab2704e8f | note | HP
23cdbefa-7703-5c76-82e6-b55467902eec | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
be7a3992-a51b-5600-b63e-8b5b52311f59 | textbox | Date Completed:
6adee64c-7d39-4070-a620-e3642d6e9226 | signoff | HOLD POINT AUTHORITY
200c195b-a0cb-48a0-a13a-f952fc145892 | checkpoint | 2.4 Application of Reinforcing Protection and Substrate-Bonding Coat
cb07125f-2323-5ce3-b48c-0b6384cc8c58 | note | FREQUENCY: Prior to pour
c72ac65b-a8f9-5fe6-baef-546d55e39391 | note | ACCEPTANCE CRITERIA: All exposed steel reinforcement shall be coated immediately following preparation and cleaning with a primer which forms part of the propreitary repair system to provide immediate protection against coroosion. The steel primer shall be adequately applied to the back of the steel reinforcement where it is fully exposed and where steel bars are tied together.
d1ae3d07-6696-50a8-9aa2-273d3cf605f8 | note | ○ A substrate-bonding coat which also forms part of the proprietary repair system shall be worked into the concrete substrate using a short bristle brush to enhance the bond at the repair interface.
42893183-331d-5db6-ba70-4906823d224a | note | REFERENCE DOCUMENTS: Section 689
5174afc2-f436-5ecf-b22d-0031507f95aa | note | INSPECTION/TEST METHOD: Verify
b702c7e4-6678-5d6d-8a86-ce6ec38e1dcd | note | RECORD OF CONFORMITY: This ITP signed off
7a029e6d-6970-5149-82cf-e2b649fedb75 | note | WP
0cccf6ed-50bd-5e9b-8156-38dadcb5d0a4 | note | RESPONSIBILITY: Fulton Hogan Engineer
ee0244ea-7178-53f9-b640-58792818f8f0 | textbox | Date Completed:
065f5377-c870-47ab-a988-64b474325d9a | checkpoint | 2.5 Pre-pour Inspection
74dc6e20-b563-5270-b609-134fd73fc28a | note | FREQUENCY: Where Required
567acb66-a617-52dd-9f40-4c2bce40aa1f | note | ACCEPTANCE CRITERIA: Reinstatement of prepared areas shall not commence untill:
eba787cf-82c1-592b-a221-3bdde4d3f30f | note | (i) a joint measurement of the repair area by the Superintendent and the Contractor has taken place;
565a0fcf-3b40-5406-9390-ac9441c03bee | note | (ii) evidence that the preparation of the repair area confirms to the requirments and specification
6be205a0-ae39-5fd5-a513-bb7b59cb047b | note | (iii) the Contractor's quality procedures has been sighted by the Superintendent.
0c1adb20-23bb-5cca-8016-f86fe3b18564 | note | REFERENCE DOCUMENTS: Section 689
9d625f9d-a82e-5685-a7c2-63feb2aea707 | note | INSPECTION/TEST METHOD: Verify
ebd855d1-3a34-5b3a-9156-811607694028 | note | RECORD OF CONFORMITY: This ITP signed off
fa55ca5e-e972-5a2d-914a-503fdadf7c8e | note | HP
2dd89904-54eb-5b8b-82e4-51f8630d2748 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
c87542a9-f393-5a57-b51a-0614212176d3 | textbox | Date Completed:
df665f55-4c3c-405b-855c-bfe83d04bd9a | signoff | HOLD POINT AUTHORITY
32e0addd-7004-452b-9bac-81543c251c50 | checkpoint | 2.10 Placement of Repair Mortar
6fa4b79a-ff1e-57cd-94e7-d1d18fd1e427 | note | FREQUENCY: Each Lot
5f764ac6-4e1a-5b24-bce9-54bd8b79d993 | note | ACCEPTANCE CRITERIA: Patch repair mortar shall be prepared as per the manufacturer's guidelines.
893e4557-d66b-51b3-b6bf-83042f35c670 | note | ○ Patch repair mortar shall be placed within 20 minutes of mixing.
ae81dcfe-ea6e-5d08-adcc-71de8fcb9a85 | note | – Patrchroc C only suitable for depths 25mm-200mm
a790d520-a5dc-5ccc-b666-f853086c0c61 | note | – Patrchroc GP only suitable for depths 25mm-200mm
cb82ebb8-7cd4-527c-a047-d39d9f4e2c6f | note | – Bluecem HE80AG
8091a122-ed2b-5010-bb51-994700053109 | note | REFERENCE DOCUMENTS: Section 689
4732feaa-5c3d-5251-b5e2-d242fe22e391 | note | INSPECTION/TEST METHOD: Visual Inspection
fe2619b2-890b-505d-957e-02de20275ece | note | RECORD OF CONFORMITY: This ITP signed off
fe48f3cc-f84f-54ee-932b-5e381701ec10 | note | WP
b4fe9d07-7a77-5a76-bea1-698c97b03001 | note | RESPONSIBILITY: Fulton Hogan Engineer
316e1369-9fae-57a8-81c2-e507150ef7a8 | textbox | Date Completed:
70ddb0d4-e628-4aa6-9c06-1795acf693f6 | checkpoint | 2.11 Testing
23e83d59-1574-54f0-8941-284cc2ca9d06 | note | FREQUENCY: Each Lot
509068ff-9d39-5969-9846-522ddc003070 | note | ACCEPTANCE CRITERIA: Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. The cubes shall be cured for 7 days under laboratory-controlled conditions. Two cubes shall be tested at 7 days and the third cube at 28 days to confirm compliance with the minimum compressive strength requirements as specified in Table 689.061. Test cubes shall be made and cured in accordance with AS 1012.8.3 and tested in accordance with AS 1012.9.
a0384b0a-71e2-59ab-a30f-4893300d8799 | note | REFERENCE DOCUMENTS: Section 689
c62793a3-7bdf-5026-8ee2-f41a02d3f48e | note | INSPECTION/TEST METHOD: Visual Inspection
04287dee-56e5-5f50-b91c-e1ecc4ebe8c3 | note | RECORD OF CONFORMITY: This ITP signed off
3946e454-fc62-567f-b292-c87d3542bd44 | note | WP
7da06e4f-02a3-54a9-81b7-2cdba6cf9b0e | note | RESPONSIBILITY: Fulton Hogan Engineer
c4a8c6c8-abe6-50b3-b6d6-3bf52154bc91 | textbox | Date Completed:
761c53a6-f72e-4e64-8dfb-4eae8929273b | checkpoint | 2.12 Curing
7a7b4cea-0a7f-55f8-87de-5732a47b656e | note | FREQUENCY: Each pour
27327c6c-a028-5495-99ae-a83a94a9387e | note | ACCEPTANCE CRITERIA: Immediately after placement and for seven days thereafter, the repair material shall be cured and protected from drying out and against the harmful effects of water movement and weather, including rain and rapid temperature changes.
d892ffde-191b-5593-8ce0-bd989b137990 | note | REFERENCE DOCUMENTS: Section 689
07c28cfa-248a-5f01-8f5c-1c47440914c7 | note | INSPECTION/TEST METHOD: Checklist
fa5853c8-3329-55a3-ac2b-6949d4321ed5 | note | RECORD OF CONFORMITY: This ITP signed off, Vibration report, Concrete testing report
b3814eb5-cc75-57fa-bd66-517b99e747cb | note | IP
d28181b7-f61a-5cff-bfab-a106962c781b | note | RESPONSIBILITY: Fulton Hogan Engineer
383e6ad5-9c95-5c40-894c-f14bbe04936b | textbox | Date Completed:
9c04d22e-14cc-4241-90dd-71fa9fbf3803 | checkpoint | 2.13 Finishing and Surface Condition
9d50dd04-97ef-5a8d-9f0f-bfb0a25aae21 | note | FREQUENCY: Each pour
beb49154-790f-558b-a761-6bd78f4cb27d | note | ACCEPTANCE CRITERIA: All surfaces shall match surrounding surface finish by use of steel forms or steel trowel finish.
3e3c45ee-3f9b-5af8-af3a-4df05950f00c | note | ○ The surface of the concrete repair shall not have cracks of width greater than 0.10 mm measured at the concrete surface nor craze cracking covering a significant area of the repair at the completion of the curing period.
a03c258c-381d-5be2-b16a-71dd6250bcb9 | note | REFERENCE DOCUMENTS: Section 689
dd83da19-4ea5-5233-9ef5-6291b2fb2b2d | note | INSPECTION/TEST METHOD: Visual Inspection
01b12653-5e90-5430-9e81-9fc4b30d4a56 | note | RECORD OF CONFORMITY: This ITP signed off
5d3e8e9f-f7dc-5dfe-b1a4-41021d2b8ac2 | textbox | Date Completed:
677bec9c-9ba1-42f2-8824-61f3d398f82f | checkpoint | 2.14 Tolerances
160b7c01-d074-5844-821b-d3cb418ba8c5 | note | FREQUENCY: Each concrete pour
c2325552-7fcf-566f-94a1-da9e09cf8947 | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
2abb6806-e094-5b57-bff8-e8b89a51fea1 | note | ○ Finished level of slab +3,-3mm
dd47fa43-b510-53b7-b9e9-502a616341b0 | note | REFERENCE DOCUMENTS: Section 689
411aa6eb-2088-5024-bd69-418847a969c3 | note | INSPECTION/TEST METHOD: Checklist
cc795c1d-abc7-5ed1-92c1-a8b30bf4d972 | note | RECORD OF CONFORMITY: This ITP signed off
6502e6ab-30ff-5fe6-beb2-a91b20b05778 | note | IP
8c1e93b7-f553-54d6-920b-0ad397fecf04 | note | RESPONSIBILITY: Fulton Hogan Engineer
baf8dc66-bb88-5bf4-8f27-0c64b3732b9a | textbox | Date Completed:
52bea7d4-b4c3-4dd2-b562-99428fe1dd7f | checkpoint | Final Inspection
3040a230-f3a2-5852-9422-5669b77256ad | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b254ca0d-d2d9-5efa-9f51-34f3a2a3e5fb | textbox | Print Name:
d0d2964b-5f04-50f2-ae91-f7ad1d8b2ff2 | textbox | Position:
49de2d5b-d094-5862-888c-46b376564136 | textbox | Date:
53b5bd12-b8f5-40dc-8e4e-c89205d23345 | checklist | ITP-019 - Line Marking Rev3 | itp | ITP-019 - Line Marking
c333197b-4b37-4bc2-877c-63e7e2a5cb41 | section | 1 - Preliminary Works
39c7a9a2-59cb-4f63-8560-f8486361a183 | checkpoint | 1.1 Check for correct documentation
859b73a0-bb32-5974-b0c6-d9d67f1fa0d3 | note | FREQUENCY: Prior to commencing any activity
aa2e5789-29a2-589a-9b0e-2373135149d9 | note | – – – – – – – – –
d0838437-d108-5786-9497-c05f4d766c7b | note | ACCEPTANCE CRITERIA:
6a145315-a5e5-5db2-90ce-fad45952c11c | note | • Ensure that all employees and subcontractors are:
8aef68cd-e8b0-5e1e-87e2-73e420f34b8e | note | – using the correct and complete set of drawings
8c1930a7-e415-5626-820e-e58dd45dc675 | note | – all drawings are the latest revision
8aabadd3-51d5-571f-ad5a-26138d7ccaae | note | – – – – – – – – –
b0dc9599-008b-5f47-9369-08a4d13f483c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
58b44213-66c6-59b6-92ac-eed2ef5a7c6b | note | – – – – – – – – –
2ea4ddd7-0112-5561-b304-c2944702fae4 | note | INSPECTION/TEST METHOD: Visual inspection
c4ce92e8-e90b-5bcc-8d47-1c29c56e9bfe | note | – – – – – – – – –
42e68f4c-2741-5276-87ef-6a6de3c2de8c | note | RECORD OF CONFORMITY: This ITP signed off
7c1c0443-7265-58df-8ef9-cf72ea14f473 | note | – – – – – – – – –
b4d485c2-fa68-534e-bb3a-e6b6254c45ee | note | WP
75ffbbb3-2a52-5567-9208-e4ba41fc12da | note | – – – – – – – – –
88cdf8b4-4f5b-5031-93bd-da94e76d7eec | note | RESPONSIBILITY: Fulton Hogan Engineer
ac304ec4-85d8-5920-b7a7-81a4faec4579 | note | – – – – – – – – –
046ff6c9-c27c-53b6-9181-6e0935abf205 | textbox | DATE:
0c96f5de-02c3-4a3e-849a-fe73262a6e5b | checkpoint | 1.2 Implementation of all measures and controls
bd9b69b4-f21a-59e7-8154-ea5cd36a5d77 | note | FREQUENCY: Prior to commencing any activity
1d006d4b-16c6-5aae-84ec-30cddac01522 | note | – – – – – – – – –
3d2459ae-44a9-5df3-aedc-ab19d2ef48a6 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
4c52a0d4-7846-5a7a-bc0d-fe748d990e4c | note | – – – – – – – – –
f46301e4-a551-52a9-a7b1-fb9c9180eac3 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
4d11d5ca-c7b0-5dac-993a-d707c58a239b | note | – – – – – – – – –
8e3a1bdb-7d37-50a5-893c-b29e23288035 | note | INSPECTION/TEST METHOD: Visual Inspection
91058d4b-c360-5615-966e-d843903a997a | note | – – – – – – – – –
dc4e04f8-7007-589b-af7d-c4e3dce91b8b | note | RECORD OF CONFORMITY: This ITP signed off
feacbe32-eda0-5ee4-8783-db6dbb6baa2f | note | – – – – – – – – –
bd3d7976-870f-56d3-9a99-4fceb5868d93 | note | WP
110f2e09-bffe-5d42-a47e-0b8fee5135a5 | note | – – – – – – – – –
35510ca2-e6c6-54d6-aeb8-aa8d63f4b6b0 | note | RESPONSIBILITY: Fulton Hogan Engineer
31624242-9475-5fe3-b385-4aba6d643f4c | note | – – – – – – – – –
72da6511-8a34-5ec4-8b84-145ee0b32eab | textbox | DATE:
89e25256-b4c0-4d80-b4a6-6094e849c6e3 | section | 2 - Construction Works
5870b843-cc7a-4fc4-9150-be2cf80d4c5b | checkpoint | 2.1 Setting Out
f341e104-e201-593f-9fd1-a17703555d2a | note | FREQUENCY: Prior to start
f14731e1-2563-5953-9db1-cc19430dfe86 | note | – – – – – – – – –
b757428a-1625-5409-ba59-50fc03a95dc4 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
0ef28156-d62d-5752-91d1-47043d868b2c | note | – – – – – – – – –
4f4c2d95-a2cd-5f02-8112-dbe090d7ff80 | note | REFERENCE DOCUMENTS: Drawings
064b0cb8-f620-5abd-a5f4-d02a3f3a2dc9 | note | – – – – – – – – –
e422bb76-cd07-5f33-8942-cb04ecb28c41 | note | INSPECTION/TEST METHOD: Visual Inspection
f1d8b42e-5d82-555b-992a-dfb917c12949 | note | – – – – – – – – –
89345a0f-e9eb-5d01-a958-c90f2651cf8e | note | RECORD OF CONFORMITY: This ITP signed off
83af6db8-8a47-53ec-83c8-d315ddf03569 | note | – – – – – – – – –
348a6e69-f992-5f66-9671-ac080920bf74 | note | IP
6034a75a-cb20-5306-a992-7dc5c340cdce | note | – – – – – – – – –
8fe8e4e9-f145-5aaf-b584-fed18f17f2b1 | note | RESPONSIBILITY: Fulton Hogan Engineer
a89d6a58-4c3c-550c-88c3-9e0681dd51e9 | note | – – – – – – – – –
fbb819ec-315d-5a4d-9d1d-ce3e2ac8400c | textbox | DATE:
37eba590-7fa1-4cb5-8683-d63c651990f8 | checkpoint | 2.2 Position of Markings
bbce3099-a8c8-57b5-9581-36cd8b505698 | note | FREQUENCY: Prior to application
a8e1ad57-15ce-591c-8209-16edadf99689 | note | – – – – – – – – –
86383220-3eab-5ee2-855a-c0ba8079d857 | note | ACCEPTANCE CRITERIA:
f6a719cd-21bc-5d68-9a84-99b1ffcd8052 | note | • Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
cea0e6b5-6a28-5590-8470-4533954f1014 | note | • Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the
6358ced7-3a5f-53cb-8abc-7a8a189932c5 | note | • VicRoads Traffic Engineering Manual Volume 2.
cf60ef53-e2f3-5c5a-b7c5-388c4691db8f | note | – – – – – – – – –
5ed37d5f-18ec-5b0b-9ee6-c75d7f36eeb4 | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010
e84c53b1-d5f2-5142-a75d-eb85ebb55685 | note | – – – – – – – – –
7352d7f8-91f2-50a5-a8a7-8220cf01a711 | note | INSPECTION/TEST METHOD: Visual inspection
4ed88e69-c01b-5693-9b41-1399c1023f74 | note | – – – – – – – – –
4184de50-1be8-5a76-a7e5-618fd096da49 | note | RECORD OF CONFORMITY: This ITP signed off
671cfa5e-eb83-52fc-9dd3-bb7098cc8574 | note | – – – – – – – – –
b5c2afaf-7649-5e55-ad84-192dcd35fff8 | note | HP
7fe357c4-965a-500d-aa69-617d69b5b48d | note | – – – – – – – – –
a20a64d8-d371-544b-9a54-1228b159095b | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
2ffb7c34-8491-5fba-802c-1411159388ea | note | – – – – – – – – –
f64d78f6-79c1-5196-a095-a50b0156a94d | textbox | DATE:
c4566728-7da1-4a5d-9a47-e7075787ce14 | signoff | HOLD POINT AUTHORITY
6d4c6efd-67ed-489b-8563-115c6239bf6d | checkpoint | 2.3 Tolerance of Pavement Markings
76dc4ee0-089b-5893-93a9-9704e9cf481b | note | FREQUENCY: Each lot
ffd68b0b-86b2-5625-b905-dd3e4535c1d1 | note | – – – – – – – – –
9d54a281-1f70-5c82-afbe-587d39a8a758 | note | ACCEPTANCE CRITERIA:
4d5c504a-ca79-5ba5-9d4c-473e1e8ef371 | note | • The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings.
8fae1102-ee25-53ae-a9ad-bee2451b3334 | note | • The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
db51b7fc-98e7-5586-9bc0-55fae65c06b8 | note | – – – – – – – – –
e033d5b3-cb1a-5eeb-8454-376b356ca3f6 | note | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
e308dc4f-5a0f-5bd2-ae56-6f9339f4663f | note | – – – – – – – – –
f761846c-b9a2-5750-89aa-1669f8ec15f2 | note | INSPECTION/TEST METHOD: Visual inspection
e0de7836-82f9-5215-a558-0a00b6dde371 | note | – – – – – – – – –
7970d78b-83a6-5968-bb55-40558571685e | note | RECORD OF CONFORMITY: This ITP signed off
69336748-581a-5298-af72-e261594ed328 | note | – – – – – – – – –
715e19a1-deef-59d9-b73b-3a5779534036 | note | IP
16f0bfad-adca-55da-b6e3-7598736194f9 | note | – – – – – – – – –
740745fb-9631-5d49-9532-57967d40e0a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
1af87735-1167-5a12-896b-468479dc2928 | note | – – – – – – – – –
777503a4-d222-5fec-ae4a-2d9750961ba2 | textbox | DATE:
2d277e33-31c2-4b77-adc0-5958fc38477b | checkpoint | 2.4 Preliminary Works Raised Pavement Markings
241b9a85-89d0-5959-aa2c-d2483ebb8513 | note | FREQUENCY: Each lot
82100d8d-df2c-5b5f-b383-edfdca6744a3 | note | – – – – – – – – –
0361b2a6-cda3-53f8-8fe0-d23d4f785fc9 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
95c45c2d-9c1e-5e6e-90d6-478c08499be7 | note | – – – – – – – – –
48896ac9-5801-59dc-a96f-cc90d27fbb29 | note | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
9ead3f28-bc70-5e27-95e8-0d4ebf41593b | note | – – – – – – – – –
d2057a55-517c-549c-aa45-c5f6533b68de | note | INSPECTION/TEST METHOD: Visual inspection
2220a745-aa6c-5610-abe1-493f02f9572a | note | – – – – – – – – –
7f81f35b-d7d5-5362-8778-d0d0f497aeb7 | note | RECORD OF CONFORMITY: This ITP signed off
1527090b-eb8e-5b79-b214-ae8e2ca2720b | note | – – – – – – – – –
b58dbf16-9343-56a0-8125-5b583dea5ff7 | note | IP
1051e38d-7236-59db-bdf8-1b470b117bfa | note | – – – – – – – – –
2be56757-8984-552f-abb0-f80f1986575d | note | RESPONSIBILITY: Fulton Hogan Engineer
ef47a874-7c9e-50e2-83e6-898e5f8af30d | note | – – – – – – – – –
41d835c4-ab0d-5556-90c8-2ced6a32cbd9 | textbox | DATE:
85a9ea44-5e21-4d2b-833e-1c97cfc16f77 | checkpoint | Final Inspection
cfc8c898-358d-54e5-9d9d-fae1071d6f5d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d0932b43-5f8b-5a89-add2-9a92bbaeeb88 | textbox | Print Name:
45ce201c-9503-5812-b105-cbef59e45401 | textbox | Position:
f2db0e07-d575-5cda-a2b9-d2542156b444 | textbox | Date:
37b1108b-6668-4342-9834-fbe88e6c8d6f | checklist | ITP-041 - Rail Expansion Joint Installation | itp | ITP-041 - Rail Expansion Joint Installation
4a2d8e5e-7962-48ef-ae28-5fcc8f282f69 | section | 1 - Preliminary Works
edfb34b1-6b3b-4df4-a1f5-220de58553d8 | checkpoint | 1.1 Check for correct documentation
92c7b112-cb28-555d-98c2-016f73297193 | note | FREQUENCY: Prior to commencing works
5f27de4d-a061-5643-a1cd-ce0249b09853 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
00cd58d0-6323-5df1-92d0-318c79fa551a | note | REFERENCE DOCUMENTS: Design Drawings and Register
d17f72cf-2692-537d-8710-2d92843bd492 | note | INSPECTION/TEST METHOD: Visual Inspection
832c1a18-d76a-5d33-8cd5-bf03b9c389b8 | note | RECORD OF CONFORMITY: This ITP Signed Off
047e51e2-ebc4-5399-aeaf-329771b21856 | note | HP*
e13ca15d-db9f-5643-9c92-1f5001455036 | note | RESPONSIBILITY: Fulton Hogan Engineer
03a7c231-2c45-5e27-92e8-143466ea9eb3 | textbox | Date Completed:
2d452b9a-da5d-43ff-92b2-7b4e684a70f5 | checkpoint | 1.2 Implementation of all measures and controls
4483f183-7b8a-5d64-b842-ee98a0651428 | note | FREQUENCY: Prior to commencing works
1c572c47-a3f7-5576-a47e-12d1c0bb6e4d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
6ebad4d4-e8a0-55d8-bee7-c8631269a4fb | note | ○ Ensure that all employees and contractor involved in the welding process and are signed onto the relevent hot works permit
2511c872-96e6-5f05-bdbb-5d2a86b7463c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
0fbfeb07-4fb7-5a59-bde0-e0ede59d4a71 | note | INSPECTION/TEST METHOD: Visual Inspection
b0f6fddf-56f7-5411-b9a4-a4f39f41208a | note | RECORD OF CONFORMITY: This ITP Signed Off
ae0c367d-e050-5e8b-8c35-b91aa3955e55 | note | IP
b55d3061-08d5-54cd-af39-53a669e7e648 | note | RESPONSIBILITY: Fulton Hogan Engineer
92a8ceae-c61d-51d5-b61f-0f22847eddde | textbox | Date Completed:
85ec613f-786f-446b-88b0-7c6fa9f81b24 | checkpoint | 1.3 Check materials and expansion joint systems
f1201c66-d454-582c-8018-6be2f6a0a9a8 | note | FREQUENCY: Prior to commencing works
e31e65a5-e6a9-52a8-80d3-cc190a1592da | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
d492582e-3297-5820-9318-2a137e2785ad | note | ○ Check condition of rail sleepers / pandrols
7b732bd7-5c62-5e7a-ad33-2c6e4aba2983 | note | ○ Ensure rail jewellery is of sound condition
867ad518-a3ff-5a23-b1d8-d016e7ccff21 | note | ○ Ensure expansion joint box are of adequate condition
c73a99b5-f7be-5fb9-bb6a-cf913f07fe30 | note | REFERENCE DOCUMENTS: AS 1085 IFC Drawings
5b362b84-f4d5-5337-96b1-4856ac54578d | note | INSPECTION/TEST METHOD: Visual Inspection
5c777beb-7ffe-5276-91d7-2e064a7fa6ae | note | RECORD OF CONFORMITY: This ITP Signed Off
52621143-f7a5-5de3-a67a-82860ae21699 | note | HP*
db3ff43b-70f7-5de8-918d-6219d4ec2001 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
c8946792-88b8-535e-96b2-fe67f98d49d5 | textbox | Date Completed:
c57b8abf-1260-4933-9f18-07a2a08aa3b7 | checkpoint | 1.4 Welders qualifications
9a288cb1-ffdc-5124-8528-aaed33277d05 | note | FREQUENCY: Prior to commencing works
b521952c-8aa6-59ee-a988-05e5d0f89a35 | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
99943023-b010-50f0-975f-8d36b470d6b8 | note | – TLIW2012 Grind Rails
4a4a3aea-d586-56ac-8449-8e7c7e296fd0 | note | – TLIW3015 Weld Rails using Aluminothermic welding process
c7555e73-607f-5dff-8366-ba9ddd5d801f | note | – TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
42695c00-1fd2-52cf-a957-ca5bf45d4341 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
4a8b1131-8508-56b4-8a86-d5ee369219c5 | note | INSPECTION/TEST METHOD: Verify
1c01b949-93ed-5c61-9114-9fc342f6e9c0 | note | RECORD OF CONFORMITY: This ITP Signed Off
1c4abbc7-d1b8-5763-817b-b500429f5adc | note | HP*
c218b4de-d1b1-5a5c-a095-4d29d0ba4800 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccc316c9-be05-5b4c-b306-4bf318048593 | textbox | Date Completed:
b11f653b-eec0-439d-86e6-e0c55c43800f | checkpoint | 1.5 Ultrasonic testers qualifications
39c9ac05-6c20-5e82-835e-9f67d7640b29 | note | FREQUENCY: Prior to commencing works
0a471e55-c509-5057-a341-daafb3da0287 | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
a3276482-f306-55fd-b23d-dcb98ac7c3c6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
20f5d748-f0ad-5150-a3d9-7000c86ff7dd | note | INSPECTION/TEST METHOD: Verify
92add7da-905c-5479-b630-d1f9afe941d7 | note | RECORD OF CONFORMITY: This ITP Signed Off
20d56603-c7c8-5c78-a900-e4b5939a2015 | note | HP*
c2d681fb-554f-5985-b5f8-4aae2a139eb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
0bf384ef-7136-5b5f-91f3-8b1e955a23c1 | textbox | Date Completed:
2d186074-591c-4bee-ab27-5cf8083774cc | section | 2 - Expansion Joints Works
466c18ce-c609-4517-a787-2d6c9d7a9b8e | checkpoint | 2.1 Gap setting
cc9ddaaf-bdbf-5c2a-b538-3acea15b1ccd | note | FREQUENCY: Each box
21250849-3eb0-5339-bf76-b790411d714d | note | ACCEPTANCE CRITERIA: Ensure the box is set to the manufacturer's gap setting and temperature criteria. As below;
c23aa91c-369c-5de8-8ab8-44ea72066232 | note | – – – – – – – – –
0feeec73-2d23-5c22-b1f2-bca37e9b5ff7 | note | TABLE 1 - GAP SETTING
e891c58d-5ff4-5ff3-9238-c6209a0fefb0 | note | TEMPERATURE (C°) ¦¦ GAP (mm) ¦¦ SLIDING FEED (mm)
66611af3-57b6-5468-bd83-f4a860ce4d80 | note | – – – – – – – – –
50730ac9-3ce8-58ee-ae54-fbfe7dfb8547 | note | -3 ¦¦ 26 ¦¦ 100 (LIMIT)
63efff88-e5b9-5eac-9c35-5eef3cdea7f0 | note | 10 ¦¦ 21 ¦¦ 80
9e773f8f-2b34-562b-b860-f8bb8e0111c5 | note | 15 ¦¦ 18.5 ¦¦ 72
1a32122e-5347-5611-b1b7-3d455280b100 | note | 20 ¦¦ 16 ¦¦ 63
9680cd52-8807-509f-83f4-21d784914f1c | note | 25 ¦¦ 14 ¦¦ 56
98af6317-96e7-52da-ab43-e2034c42689d | note | 30 ¦¦ 12 ¦¦ 48
1f260a8f-c764-501e-8e6a-8f45d2e2ab2a | note | 60 ¦¦ 0 ¦¦ 0 (LIMIT)
bc9ed4c4-a727-5355-af9c-43a93ed811f3 | note | – – – – – – – – –
c8ab1522-18fe-53ad-87a7-cb2e45ab9362 | note | REFERENCE DOCUMENTS: Prazska Drawing 1PA.031.000.00.00.1, IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
3419d64c-2389-501e-9c11-7c988ad9503f | note | INSPECTION/TEST METHOD: Visual Inspection
2ad8f934-531b-5e53-8cc5-368922535758 | note | RECORD OF CONFORMITY: This ITP Signed Off
4978a0a1-04a1-51f8-8567-7ebd065dd698 | note | IP
a970107c-188a-52bd-8299-77534a34623b | note | RESPONSIBILITY: Fulton Hogan Engineer
dbf3c8bc-fa20-5c98-aae8-120122338ce5 | textbox | Date Completed:
8738dd84-9c0d-433b-b03c-b98e28eb66e6 | checkpoint | 2.2 Installation of expansion joint system
706860ce-bd4d-5705-a653-8f408b7448e8 | note | FREQUENCY: Each expansion joint box
b6d23838-fe8e-54d7-8a2a-1c6b7ca624d2 | note | ACCEPTANCE CRITERIA: Ensure the expansion joints are installed in the correct direction. I.e., moving and fixed end are in correct orientation.
23f8cb01-e6ca-55c5-9b72-e7176726f891 | note | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
3e933a9c-7f5b-5ad2-9155-f38a32dbc2a0 | note | INSPECTION/TEST METHOD: Visual Inspection
eb3b5dd3-26cd-5e05-9012-d6baa262dd2c | note | RECORD OF CONFORMITY: This ITP Signed Off
c853795e-ae39-5526-aa77-8ae7a211eee1 | note | HP*
a9b0ee15-d147-54bc-a36c-b8dc5d1f0580 | note | RESPONSIBILITY: Fulton Hogan Engineer
deb67808-beee-5081-8a6b-2f8c5ccd4361 | textbox | Date Completed:
9bf90853-667a-447f-8705-471471a6f436 | checkpoint | 2.3 Grouting
57757c80-b2c3-5cb7-beae-f168ed305da2 | note | FREQUENCY: Each box
fc5ce0a4-b79c-52a0-88f7-de3cf78fd5df | note | ACCEPTANCE CRITERIA: Contractor to ensure that non-shrinking grout fill is installed between bridge deck and rail expansion joint system.
216f70e4-d5ba-5c57-ac5d-3737f00d844c | note | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
dcc1c0b8-cc6e-54c7-ba04-e8a45d7f1b1c | note | INSPECTION/TEST METHOD: Visual Inspection
ea524431-cf30-5370-845a-8e067f5da116 | note | RECORD OF CONFORMITY: This ITP Signed Off
583c1136-7a00-50d6-bb9d-c8dc1d18f08b | note | HP*
6f86df04-536e-588c-833d-3bf8f5fefcae | note | RESPONSIBILITY: Fulton Hogan Engineer
b919753f-317d-5b43-829d-24a5d624f58e | textbox | Date Completed:
8f269267-45b6-4796-a99b-6a65c9e162c9 | checkpoint | 2.4 Construction of expansion joint
a245f6cb-dfa3-5ad7-8ba1-c46f4438b2a6 | note | FREQUENCY: Each expansion joint box
4ba90769-f5db-52a2-85ed-83349dc47242 | note | ACCEPTANCE CRITERIA: Ensure rubber boots are installed per manufacturers requirements prior to concreting.
1033fac0-b2a6-518e-8a43-30b985d88e1a | note | ○ Use anchoring plates to hold the rail expansion joints in position. Ensure that all collapsed grooves are reformed.
bbcc1cb5-fda4-5a0c-b382-54e469fa4de3 | note | REFERENCE DOCUMENTS: IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
3585d0c0-ba27-57fd-872f-e9005314bf87 | note | INSPECTION/TEST METHOD: Verify
52c9d40e-c746-51e9-b1ce-4f895ed1acd6 | note | RECORD OF CONFORMITY: This ITP Signed Off
ed3f87c1-f0c2-5881-b72c-849b989442fd | note | HP*
56ed0e56-b99e-5b38-83d1-2d51e83dc893 | note | RESPONSIBILITY: Fulton Hogan Engineer
ca406d11-d617-5b31-bfa3-aa45f782547f | textbox | Date Completed:
84f29a37-3e0d-44d1-939d-2546faf2c8c2 | checkpoint | 2.5 Expansion joint bonding system
7d84f543-a509-56ff-973a-c515e2ca9e5f | note | FREQUENCY: Each lot
57b54232-0740-593d-9ec5-b7de73840a4e | note | ACCEPTANCE CRITERIA: Ensure bonds are sealed as per agreed method with Yarra Trams
e538d25d-e4db-5265-9837-9291c8359e04 | note | ○ Ensure the rail bond is correctly positioned from old 41kg rail
fe2797aa-b620-5948-91d1-ed48d961bc39 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4, IFC Drawings 1674-TC-202, 1674-TC-203, 1674-TC-204
4be3ee01-f0e2-5f84-9003-ff9ed08c1b2f | note | INSPECTION/TEST METHOD: Inspection / Test Method
d6403bef-cbec-5b62-bdc5-aafa500f85bf | note | RECORD OF CONFORMITY: This ITP Signed Off
8dc1a065-fe2a-57ed-a6e7-37292f904181 | note | IP
1b073358-b1e2-5bde-a6f8-d84358aed73c | note | RESPONSIBILITY: Fulton Hogan Engineer
dc346c31-cab4-5241-9654-d684de382db3 | textbox | Date Completed:
b9cc79ce-b5dd-40a3-ac4d-0190405d62e3 | section | 3 - Construction Works
0a1b1f4e-1bdc-4435-b2a0-cdd8f132663d | checkpoint | 3.1 Installation of pandrol plate
55982f4c-3f2b-5cef-9949-261b01f79f8a | note | FREQUENCY: Each lot
a1b1e370-b813-525f-ad8b-6ac38fbde0be | note | ACCEPTANCE CRITERIA: Pandrol plates to be installed as required/instructed by the client
72fefb0d-ce84-5ce5-b7f7-0e7ddf8c55f4 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.3
93e3e6cf-379c-566a-a7fb-a99b8cb1c19d | note | INSPECTION/TEST METHOD: Visual Inspection
6e48ae44-7c28-53e1-ac7c-8404a5ddb170 | note | RECORD OF CONFORMITY: This ITP Signed Off
b96eb1e0-dfe9-5e9b-acc8-f65e7b09a8af | note | IP
67613ab6-9d34-5bac-b400-0434ccbba712 | note | RESPONSIBILITY: Fulton Hogan Engineer
9d27da16-40cd-515b-a769-4bd0cdb29ffe | textbox | Date Completed:
55c36cad-1477-4932-90ab-e29ced0239e3 | checkpoint | 3.2 Placement of rail
9536253a-3484-5288-8d2c-ee910b286510 | note | FREQUENCY: Each lot
f63b3640-268a-54bf-b4c8-5f479da55f70 | note | ACCEPTANCE CRITERIA: All track work, including expansion joint systems shall confrom to alignment, offset, level and cant as per design drawings and track charts
d9d085c0-9e03-58b6-9a9c-0d29c3f30a81 | note | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
5223cc2e-287e-5f52-bb25-c615a6baa032 | note | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
378be340-4272-5266-a5a5-280c47e756f6 | note | ○ Geometry tolerances as follows:
55460753-bf8d-57e1-bb78-d677a57ef5a6 | note | – Centreline location: +/- 3mm
8d813e9a-723a-542f-b2fc-2028e24b9e22 | note | – Level: +/- 3mm
675cb4f6-5d06-537c-a91e-9fc8df91337f | note | – Line measured (>10m chord): +/- 3mm
c5949ed1-3055-5222-9f39-8ac8aba502c7 | note | – Twist (3.5m chord): +/- 2mm
0865646b-8e8c-558f-ba5e-b7a65a3e605c | note | – Cant: +/- 3mm
b58a1bc2-9b08-529c-99ac-c17def5d6eb5 | note | – Gauge (open track): +3mm, -0mm
d6fd185d-babb-519a-a3ea-68b0e21c6fb0 | note | Note: Cant shall be applied uniformly over transitions
ab81472b-6922-520d-8268-b2f1f8f38be8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
b16e08c6-3832-5b72-a978-cd3aec49d02d | note | INSPECTION/TEST METHOD: Visual Inspection
1a8f7d4e-8218-5afb-a8e7-3aabf515b5fb | note | RECORD OF CONFORMITY: Completion of track charts
3942ab7b-15b4-598e-8a80-897bb13b6183 | note | HP*
0e9bce98-9f7b-5201-a975-3e668e27031d | note | RESPONSIBILITY: Fulton Hogan Engineer
28b96085-c871-5e24-86ee-b7cef0fbf509 | textbox | Date Completed:
18fff682-8405-4efe-b507-f8678a566022 | checkpoint | 3.3 Placement of jewellery
4347187a-b5c8-585a-ba23-619dc64099bc | note | FREQUENCY: Each lot
ebeae349-d401-58cb-8741-971b18c79dd6 | note | ACCEPTANCE CRITERIA: Each pandrol shall be fastened to track with approved jewellery and rail clips
69983c5a-2cc2-5172-a134-0099b9acb9d3 | note | ○ Clips shall be installed with panpuller or equivalent
3f4fad2c-d95c-5196-9cd9-fe01b49ab1b8 | note | ○ All fasteners shall be sealed as per agreed method with Yarra Trams
ce9c1cd9-175d-522a-93ba-47ef924ff042 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
392bf953-61d4-594e-b668-0341052f2bc1 | note | INSPECTION/TEST METHOD: Visual Inspection
cf22495e-564f-5983-a2b5-b06f4e0bb35f | note | RECORD OF CONFORMITY: This ITP Signed Off
cf8ff44f-eee8-57ef-8090-e0291db85daa | note | WP
e3d33412-9851-5c8d-ae92-cced1cbb5628 | note | RESPONSIBILITY: Fulton Hogan Engineer
9bdc8e55-61fd-5d9f-b889-bb7d1131782e | textbox | Date Completed:
7674373c-a28c-40d0-9da9-2cf4571605f3 | checkpoint | 3.4 Rail end preparation
cb239235-d250-5b07-850d-38169b8b49cc | note | FREQUENCY: Each lot
10e5d52c-a10e-539c-9839-62908fafd09a | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
1f2a17d4-9f01-5cc9-93cd-b7e2dbf801cb | note | ○ Minimum closure length from proximity of welds shall be 2m
b1e273ef-921f-5406-bf99-08241969a774 | note | ○ Rail end conditions shall match (i.e flame cut - flame cut)
fc8ff8a7-cbaf-5057-bd87-a63583e431ce | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
41db1f27-5ca2-5c6b-a79e-8b3e2c663b32 | note | INSPECTION/TEST METHOD: Visual Inspection
aeca8894-114a-5087-9e29-01cbf9e609f3 | note | RECORD OF CONFORMITY: This ITP Signed Off
7e1df97a-8bfc-5b35-9b22-206eb0247d19 | note | WP
9be6fbe5-6f44-5056-8853-66211e53d00a | note | RESPONSIBILITY: Fulton Hogan Engineer
fcfa85a0-4d7d-5b2d-aad9-bd385cc4adaf | textbox | Date Completed:
888d5050-f4f1-40d1-9812-d4fb8d139e86 | checkpoint | 3.5 Welding of rail
88b9c6ee-c658-5443-8de9-f0386060b5e7 | note | FREQUENCY: Each lot
de0b97fa-7fc4-5b1b-975c-81c0c0e1be38 | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
10e2ed6e-b2ce-5154-8710-7142017db246 | note | ○ Maximum skew at square joints shall be 65mm
eeb4f2e6-6451-5379-bda9-5c005e07eee1 | note | ○ Portions shall match rail type (i.e HHR, Ordinary)
10485235-f1d9-555c-92d3-0cfd18007db9 | note | ○ Welds shall not be within:
df952967-74fb-51db-8bee-e0b874140b5d | note | – 3m of another weld
841816d5-b865-54b7-85a1-c8fc0d996be2 | note | – 3m of a rail end
968b5882-a88d-54b0-a2d4-b2d2a6a1dcf4 | note | – 1.5m of a glued insulation joint assembly
80284bb8-b5ab-54a9-a0b3-98b5de06d292 | note | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
238ea2cf-6d4d-598d-a2f6-74b40ade2738 | note | ○ Weld Return forms shall be completed by qualified welder
54014b32-c68c-5b0d-85c5-846d2ef42129 | note | ○ Welds shall be grinded after 1 hour
c81385b4-68b3-5ef8-b47d-6d30c52c21d3 | note | ○ Welds shall be free of water
a77bfdd9-75eb-5dac-80fc-339f0ddf6c26 | note | ○ Post grinding, welds shall be cleaned for visual inspection
9eaff916-52d5-51b7-8e58-901c4fc13fe0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
04eced7e-ed11-5272-aadd-9478d219d902 | note | INSPECTION/TEST METHOD: Visual Inspection
d38a610c-e091-5e0e-876a-fa9d72807359 | note | RECORD OF CONFORMITY: This ITP Signed Off
906c8034-5454-57e2-9209-49f915ef27b4 | note | TP
4499e5cc-8a32-5356-bb4f-4feb26b66a13 | note | RESPONSIBILITY: Fulton Hogan Engineer
41f4bcc9-55da-5820-b547-326642fe3bc0 | textbox | Date Completed:
73a39f53-fe60-4c40-808e-887f6affaa5d | checkpoint | 3.6 Grinding & cleaning welds
a3509e3b-c98c-560d-8d55-c88174122f6c | note | FREQUENCY: Each lot
f814f2da-fe55-54e9-bdfb-8d7ffa220c62 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
aa7469ff-6582-5466-9dbf-bc991abf8c1c | note | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
618a3354-c6f7-5a90-b0d7-821edcad6c03 | note | ○ The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
243169b1-7f9c-5e89-b233-40b276c5ae65 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
2756ed07-a9f0-5bf4-b0d8-e58d48e77ec7 | note | INSPECTION/TEST METHOD: Visual Inspection
a4c0044a-638d-544c-a33c-eaa135754bd4 | note | RECORD OF CONFORMITY: This ITP Signed Off
50f3520a-154b-50fb-bfbb-dae4b6fc5186 | note | IP
7cc3536d-0d51-5b9b-a377-1526c3acf81b | note | RESPONSIBILITY: Fulton Hogan Engineer
63097533-2498-5d2b-b454-e03521544539 | textbox | Date Completed:
45ed9b51-54d4-4305-b730-bb1953fe1875 | checkpoint | 3.7 Track adjustment
d6633136-e29e-5176-acbb-fd667a27b7c7 | note | FREQUENCY: Each lot
79d91f53-126e-5154-b268-dbc8f5f54e95 | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths.
90b5a894-e846-5d08-bc76-1186c29dedcc | note | ○ In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
3c145092-6d1e-58aa-a471-896de918269b | note | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
0885c497-5a0c-5a71-9531-477e2ee967e6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
170233c9-f5a2-5e58-b611-e1a881efa36d | note | INSPECTION/TEST METHOD: Visual Inspection
791fdd23-2ac7-5c11-8b91-dab13a8e7a92 | note | RECORD OF CONFORMITY: This ITP Signed Off
577971db-78e6-5232-8b23-0fdf53794051 | note | IP
ebbea9c9-5bce-55e9-949b-66d44b097a4a | note | RESPONSIBILITY: Fulton Hogan Engineer
9fd9e246-4637-56d7-b037-0820a2d20850 | textbox | Date Completed:
4306d9a8-025a-4737-8dc6-daf4923083e2 | checkpoint | 3.8 Reinforcement
627595f9-df25-594c-a7cd-2960adba24d2 | note | FREQUENCY: Each lot
065530f0-9295-5c1b-81aa-2c5cb143c83f | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
ec4838e0-98c3-5c67-b068-ea09babcaf55 | note | ○ All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
f2eeee3e-a196-5411-92b6-86c7b6d71f0a | note | ○ Reinforcing mesh shall be handled carefully to prevent distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
ae1a1cc9-6650-5a8e-bbae-cf310b555107 | note | ○ Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
d7f61f79-21cc-5d61-8dc1-c605a39daf73 | note | ○ Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
ba8ec0bf-7d5d-546a-89c9-9c1d415cf1ea | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
bf96ad39-805a-5821-b07e-3404dfec05e5 | note | INSPECTION/TEST METHOD: Verify
c74544f6-e9b4-5d1e-a8f5-39c253fa54d3 | note | RECORD OF CONFORMITY: This ITP Signed Off
6114b318-1532-5783-8c59-6adc867f3408 | note | IP
da4c2b96-2416-5863-a084-905b7a0a584c | note | RESPONSIBILITY: Fulton Hogan Engineer
18d4a6eb-f125-59ee-a8cf-16ad96d2580d | textbox | Date Completed:
1abdcc4c-ddb7-4f6a-9e90-a77be3d64aa1 | checkpoint | 3.9 Dowels
9526077f-9e9a-5343-9262-da0779a30f6c | note | FREQUENCY: Where Required
dbcd2a45-33d2-54f2-aa48-05c3e09bd2e5 | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
e6b73aaa-7ec2-50a0-bb73-3945e17926ba | note | ○ All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
0b8b086c-5950-53b1-b8e9-954feaad9ace | note | ○ Dowels shall be clean and free from mill scale, loose rust or oil.
23b98454-51fb-567a-81b6-537e420bea8e | note | ○ Ensure that all dowels are securely held in their correct position until the concrete has set.
1c167356-627d-51ec-8527-7abea2c7b83f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
9fafba6c-6bf0-5078-a30f-9fc807b8f039 | note | INSPECTION/TEST METHOD: Verify
b79958f6-7c71-513c-9cca-00abf15485b0 | note | RECORD OF CONFORMITY: This ITP signed off
304fe44e-67b4-52c5-becf-8be3b05cf983 | note | IP
3ad4f46d-ed22-5c7b-bd13-ea3dc57cd334 | note | RESPONSIBILITY: Fulton Hogan Engineer
6ff24d73-7cf8-5caa-ab9a-ab22e09d6a39 | textbox | Date Completed:
3eb0c746-a68e-4181-bfaa-d204e6d0d978 | checkpoint | 3.10 Pre pour inspection
7d8697c6-1544-5b7e-9a74-dd490f66b8b9 | note | FREQUENCY: Prior to start
5609cc57-339d-5297-a3fc-bf17215775f8 | note | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
7b20a125-ddbe-5a29-95d5-8ea54aabb24d | note | ○ Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, system drainage are satisfactory for the expansion joint systems
588b2506-5351-576e-8f3a-71f9421e6d13 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
c504ad4f-e415-55c6-b899-18bc6d4ccee5 | note | INSPECTION/TEST METHOD: Inspection / Test Method
9b902563-2cb6-52fd-bcba-bbcc2c36dc5b | note | RECORD OF CONFORMITY: FH Track Inspection
8d3b0424-7b36-58bf-9af7-469452bef806 | note | HP
645cd79b-1f19-51e5-966f-3005a39f855e | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
dd391615-56ba-51e8-a67b-82628bc5b08f | textbox | Date Completed:
5233db4e-33cf-46ed-93b2-10cef036101d | signoff | HOLD POINT AUTHORITY
6667396d-44f0-4d0f-850b-2101a1291e67 | checkpoint | 3.11 Post pour inspection
ebde5b56-b5dc-52b2-8745-8b772cdc950d | note | FREQUENCY: Each Lot
6153f43b-43e4-56bb-81ba-592bd1d514fb | note | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
94d209f7-d478-5791-9e81-2444e3fc80ef | note | ○ Ensure no defects are present in slab
ce6f4eab-e7e8-50fb-a014-eb4a654110b1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
419774e0-570c-570d-8387-5dc453df2bae | note | INSPECTION/TEST METHOD: Visual Inspection
8add8994-388d-5b13-a838-e43433803f1d | note | RECORD OF CONFORMITY: Post pour checklist
1a29d18d-8fe9-523b-834e-6ac82fd3033f | note | IP
129ff921-83a4-5b5c-aae4-c69f214f8e92 | note | RESPONSIBILITY: Fulton Hogan Engineer
869fb090-476f-5aae-9ffc-6e823c10d144 | textbox | Date Completed:
ddd75db4-eac9-43f7-951a-dfaebe985ba9 | section | 4 - Testing
e5107abb-c681-4f6f-9778-1848413a0e5a | checkpoint | 4.1 Track testing
9074ff6c-b229-5390-a5df-2870a771d7b5 | note | FREQUENCY: Each weld
96f287c9-b82a-58f4-ad45-a136a579d423 | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator.
c215a874-2c40-590a-9908-15a4303ccfe9 | note | ○ Failed welds shall be cut out and replaced
21ff985e-6a7a-53e8-9b3d-21b37e2af1e6 | note | ○ Testing documentation shall be recorded and supplied to the superintendent
b5cee557-11cb-552c-8678-b0878374478d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
38081e62-fe5f-59ee-8caa-1f0feb0ac2d1 | note | INSPECTION/TEST METHOD: Inspection / Test Method
85b749ac-c881-5e05-bb41-481e737a1476 | note | RECORD OF CONFORMITY: This ITP Signed Off
215e2ae8-c4d9-5e47-adbf-b553ac2d9b9d | note | TP
74e5a539-d402-5930-a75a-3e889c86be91 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
78167ea7-ae0d-5dae-8019-91f9d9823ee4 | textbox | DATE:
ce0125e7-afc3-4c94-bbb3-1326b86abea4 | checkpoint | Final Inspection
ada03254-a8d5-555a-a7a2-d917cf125698 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d75540b5-7405-5f56-b562-b11653bd65c6 | textbox | Print Name:
6146b875-13f7-525f-9006-6d4ec0de39e6 | textbox | Position:
8d6e155b-e785-5a06-9958-ea6bf3114285 | textbox | Date:
617d610c-9400-4902-bbc6-aac91786e7fd | checklist | Order Acceptance Certificate |  | Order Acceptance Certificate
04ad3683-f6fc-454d-8775-370783a7cb81 | section | Details
f690fd0a-c16d-40df-a00f-69b9dda629c5 | checkpoint | Order Acceptance Certificate - Details:
b9ed0498-1fff-5346-9681-054be898a6eb | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
a2df5a74-d778-5d49-ac76-59f5123a9f9d | textbox | Order No.:
db068c1a-a967-5d75-ab7e-7d75483d4021 | textbox | Delivery Site:
ac071b2d-59c1-5cf3-ab57-33d8da24200e | textbox | Date on which materials delivered:
e21cc896-c0f8-564b-859e-5beb0db20b82 | textbox | Delivery vehicle (registration number):
e9ac62b8-3a07-53f3-ab14-2ae865723c74 | textbox | Subcontractor's delivery personnel (full name)
dabaf040-4593-4d63-a0cb-fa34b5cc56d2 | checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
e9fccad6-f86d-40f9-bc86-89c54fe0bb02 | section | Packaging Inspection
dc6021f7-719d-41ce-86e3-9684087e25f5 | checkpoint | Fault ID:
02493488-a0e3-5b22-96fb-8aa661df8051 | note | OK = Meets all criteria
cdbf5d45-d188-52e4-ad27-1039e98d2598 | note | QI = Quantity incorrect
95b9c507-52d9-570f-b558-a3937970ec0f | note | IN = Item incomplete
7663cfb4-2b3b-599d-b2cd-aca6f8781b18 | note | MI = Make or type incorrect
6ad8f618-4652-53ed-9a78-724aabc59fcf | note | TD = Damaged in transit
0dd0f120-5b14-541c-b4b6-2162553b75e3 | note | NI = Not properly Identified
933c1064-707c-4dc6-9bda-ba3f231db7dd | checkpoint | 1)
60c7ee67-14b4-54a6-98e2-e6325c784e86 | textbox | Item ID:
e99dc020-6003-5dab-b19c-3b202f4e5069 | textbox | Item description:
2499553f-b94e-5e87-826a-c662dc1df600 | textbox | Units ordered:
a28ee37a-b432-511d-9089-738962c6708f | textbox | Units delivered:
da29fdd0-658f-5408-936e-0a755f60af20 | textbox | Special Storage/ Handling Requirements?
823b3756-f85d-534e-9a61-39b78e703b4d | note | The following is for completion by Fulton Hogan
1848bdb8-5c6b-53a0-b5fa-be7b93bee95f | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
748ca54e-6822-55b2-ac76-caefd2ad43fc | textbox | QA Docs Delivered?
4b6205d2-3f34-5df2-847d-9b2cbf205100 | textbox | Defective?
56bc6692-4a36-5fcb-9979-edfa3edea01a | textbox | Number Accepted / Number Rejected?
28b12607-d8f7-58f2-aa2a-a00e46b92c54 | button | Fault ID: | IN, MI, NI, QI, TD,OK
f044fe8d-534d-479c-be73-d68e049ffe50 | checkpoint | 2)
0a674aa5-7eed-501a-8350-8f3ac083ee27 | textbox | Item ID:
8cf00ba3-d74e-51c0-a1b8-f87074a63295 | textbox | Item description:
0a07cb38-3d99-5ffc-b2d6-d668e963be74 | textbox | Units ordered:
e203d50d-0872-527e-9168-c71fc8f94d26 | textbox | Units delivered:
94da1b72-f479-5d99-8010-9f4f10e41d03 | textbox | Special Storage/ Handling Requirements?
6fa28e6f-de05-5dd7-aa09-ab980dd4466c | note | The following is for completion by Fulton Hogan
87842268-d9a1-5c8d-8e53-dee79834bc18 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
c51712aa-4fd4-5b99-9a55-2f9e317f1c83 | textbox | QA Docs Delivered?
69c5bb0d-b562-515a-8002-27539378e8ec | textbox | Defective?
6cf59ac5-3234-50fe-b51c-410086099f51 | textbox | Number Accepted / Number Rejected?
94fc3a6c-6a55-56d6-81cb-c434ab2b74e6 | button | Fault ID: | IN, MI, NI, QI, TD,OK
315d25d8-4455-4cc4-bb7f-44bc19185156 | checkpoint | 3)
fff09420-6028-526e-a776-d363044cc599 | textbox | Item ID:
2ef171af-fb72-5984-9f2c-ea2be20ae685 | textbox | Item description:
f090fe5c-3455-5114-9808-3432cc1cfa10 | textbox | Units ordered:
e4f0b81f-d1d1-5182-a3af-0d4e8d0c6491 | textbox | Units delivered:
b5ea9870-e33b-5f53-8668-282d35cd4695 | textbox | Special Storage/ Handling Requirements?
5f531dc3-fca5-57e4-ac9f-afb77c34446f | note | The following is for completion by Fulton Hogan
0ac7625a-73d3-5e6c-a32e-1c19eabbdc6f | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
ad382e5d-b805-5b17-ac87-afd5c47bf814 | textbox | QA Docs Delivered?
54b2fdea-b623-59f4-801c-334251140b31 | textbox | Defective?
24fb0e9c-db3a-558f-9759-beb05fafc56a | textbox | Number Accepted / Number Rejected?
8091442b-c7db-55db-96a8-bb09ce73370c | button | Fault ID: | IN, MI, NI, QI, TD,OK
0b23fdf7-5704-435a-91bc-9a767ce0b7f1 | checkpoint | 4)
f93b93d0-556c-5e40-9621-c8efbffb759e | textbox | Item ID:
7f1c3a7c-e2ac-5966-9ecb-ffaefe755049 | textbox | Item description:
0fefb678-0e26-535f-a9a2-565f092f95c1 | textbox | Units ordered:
b7183b94-ba5c-51eb-accc-9c815b10abb1 | textbox | Units delivered:
a2d088ba-c3a2-551d-a9b5-b203c3f224a1 | textbox | Special Storage/ Handling Requirements?
1ec143a8-4560-598b-8a68-8e20239a1780 | note | The following is for completion by Fulton Hogan
b06db03d-2d94-5bd9-b5bb-bc8a7af97389 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
6efd3164-fc1b-51fd-825b-67debc4be56e | textbox | QA Docs Delivered?
11913bec-813f-5580-9ecb-63729e66b9a4 | textbox | Defective?
523d88ef-f392-5fc9-af78-f4cfded5cc7c | textbox | Number Accepted / Number Rejected?
a0e97e01-182d-5a92-b4c7-22709697d53b | button | Fault ID: | IN, MI, NI, QI, TD,OK
2e4f1c68-8840-4956-bde7-b0092af7e880 | checkpoint | 5)
ba418346-0a4d-5f34-88a3-675ee3a6de59 | textbox | Item ID:
990a7d19-4d3b-5ee0-aaf9-59d2501d3306 | textbox | Item description:
94ed7e63-f332-5f90-aa3b-52cd80da6cad | textbox | Units ordered:
1be8fe42-72e8-5369-b11a-f971fe73a635 | textbox | Units delivered:
e0e1daba-eb27-5847-be21-5eb32e45282f | textbox | Special Storage/ Handling Requirements?
8181c404-3901-5c3b-9488-adde459333df | note | The following is for completion by Fulton Hogan
29805a96-19c6-5450-9022-043779b6bfd6 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
d1992036-41a9-5489-8676-14cdd0e1d867 | textbox | QA Docs Delivered?
c61137ad-4ee9-54ee-9d22-6143986ee2dd | textbox | Defective?
c21f0840-01f2-55bd-8629-af866185cfe5 | textbox | Number Accepted / Number Rejected?
d7520235-f32a-5d00-92dd-8598eba39433 | button | Fault ID: | IN, MI, NI, QI, TD,OK
47957907-f6e0-4818-b6b4-62f7811bb2c9 | checkpoint | 6)
9c02582f-b889-5521-9ee7-b63e6a14c858 | textbox | Item ID:
5be92e56-f766-5d36-9a3d-f21baa4c2bf3 | textbox | Item description:
2184ae4b-3e82-5dfb-8d65-8d6607c31940 | textbox | Units ordered:
e7235e4e-6d75-590e-ab5b-2b8cde7405f2 | textbox | Units delivered:
d3f62b66-07d3-5d0f-8714-6d02a4bd5086 | textbox | Special Storage/ Handling Requirements?
565729e7-9c88-5e6f-8912-c855ffd9b05f | note | The following is for completion by Fulton Hogan
c88f3abe-88eb-5b3b-b7f0-aed97c1e5f98 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
247eacf7-a3e0-57ce-9521-3f2572d8e5ba | textbox | QA Docs Delivered?
b6462d65-0c35-54c0-825f-3df3f8a26e93 | textbox | Defective?
eb1a5141-2f61-5e02-8b65-7cfd42c4b1f0 | textbox | Number Accepted / Number Rejected?
0bf4a4fd-54e0-57eb-8a90-941fe2a45af3 | button | Fault ID: | IN, MI, NI, QI, TD,OK
49aa0f6b-0cab-4a9c-906c-a84d50d369fe | checkpoint | 7)
53ced6e8-952b-52ef-9dbe-cb75bf869ad6 | textbox | Item ID:
55ebe0bd-4802-5349-81d5-0aa12476bf96 | textbox | Item description:
1ac0554e-7186-564b-a8c0-b3558dbce543 | textbox | Units ordered:
e6bbf63b-e735-5931-8430-d76d57f75769 | textbox | Units delivered:
2dc3f935-dcd6-552c-b6a3-b9080f5295af | textbox | Special Storage/ Handling Requirements?
056e7615-ebac-583b-9d1d-98664c16034d | note | The following is for completion by Fulton Hogan
9d828777-038e-5369-a271-8c7402411acf | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
002a43da-fe34-58aa-a8b0-c62f7ef93163 | textbox | QA Docs Delivered?
aa623434-fb1c-509f-87f2-f0364476c18b | textbox | Defective?
dbe7365b-16ad-5974-83ca-66f818bbaaa9 | textbox | Number Accepted / Number Rejected?
b0b1a18c-aa97-5fb9-b076-3c68e1a74dc1 | button | Fault ID: | IN, MI, NI, QI, TD,OK
23fb09f2-d2fe-40b5-a445-c99b93b1f324 | checkpoint | 8)
7f738ee9-07bc-59c8-968e-bdaa7106461b | textbox | Item ID:
c1c207e8-1824-5229-96b2-d372f1317a37 | textbox | Item description:
18a94de2-e0ee-574a-9107-d94f6be23a8a | textbox | Units ordered:
e659dc05-bd2a-536d-ab9b-39dc96b84191 | textbox | Units delivered:
37fee92f-87ef-53cc-a5b6-1e92ab8da32a | textbox | Special Storage/ Handling Requirements?
a0c74ad0-17cb-5e08-bbdd-49dfb034d0b9 | note | The following is for completion by Fulton Hogan
a33c78da-d72b-547d-846a-11b6ad797933 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
6c956576-4baf-54c5-8784-f8444dc1e58d | textbox | QA Docs Delivered?
5aa9875c-58ab-5492-ac67-928b5e52f074 | textbox | Defective?
e8ad1df4-5b1f-583b-afba-0195b5a3fe07 | textbox | Number Accepted / Number Rejected?
54ea139e-cf5a-573b-aa75-bf565cef6133 | button | Fault ID: | IN, MI, NI, QI, TD,OK
058d2a28-689f-4cc2-acdc-9221d55c0360 | checkpoint | 9)
708e1d7e-537b-5289-8e39-45fe0877cc26 | textbox | Item ID:
8bc73834-cc2d-5605-a320-46bbafca77a8 | textbox | Item description:
a2b1834d-7dd7-5e62-aa3e-107e0adcbf9d | textbox | Units ordered:
b05a1525-8790-5314-ab7c-eb919eff5532 | textbox | Units delivered:
59e8bb72-9b7d-5edf-b06d-4258845d6a4e | textbox | Special Storage/ Handling Requirements?
9f0dc27a-a306-5653-9efa-aca0f4cb7f88 | note | The following is for completion by Fulton Hogan
05f7a5eb-4a27-54a7-95df-1625f818740d | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
860dd9cf-dd04-5a5d-9a4d-9602c9baa9dc | textbox | QA Docs Delivered?
0e565ce2-3b7d-5a8f-9873-892fface1009 | textbox | Defective?
6e582531-1e50-53cc-907a-6d1fa206adbc | textbox | Number Accepted / Number Rejected?
ba1daf16-ef60-55e9-9e9f-0fa2bc319155 | button | Fault ID: | IN, MI, NI, QI, TD,OK
2a53f88e-d97e-4527-ac90-b752e14f7384 | checkpoint | 10)
a6d7ee77-6755-5de9-af00-1a77bb523cc3 | textbox | Item ID:
16e9b6ed-c7ac-586c-ae5b-9f2efd8544d6 | textbox | Item description:
d824e899-7201-5fc6-ac3a-62b6638eed3f | textbox | Units ordered:
0932e6ba-548a-516c-8bc6-70748f72ea78 | textbox | Units delivered:
5bf2a793-6c96-5013-9c5a-ee98f6593402 | textbox | Special Storage/ Handling Requirements?
cb075035-959c-58a5-b5a4-6931e50321f5 | note | The following is for completion by Fulton Hogan
fc1e1244-4028-50ef-8691-870d492a0b80 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
57d83fbd-cf7b-5047-9274-1529dfc68c5e | textbox | QA Docs Delivered?
d99252ab-041a-5c06-a354-32e667844a45 | textbox | Defective?
cbb564e0-1b00-545f-8139-47d96a5370ec | textbox | Number Accepted / Number Rejected?
e1c315de-bbba-5fda-97c0-4069aa2a6acc | button | Fault ID: | IN, MI, NI, QI, TD,OK
76453c6b-0cac-4ed1-9953-d1f7f71d522b | section | Sign Off
076b93f7-ad09-4f1c-9d56-e07ed6ea468d | checkpoint | Accepted by Fulton Hogan
af79844a-8cde-4bf7-ad0a-7ee62e878716 | signoff | Sign Off