## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
f929064e-568a-44b8-9265-f24f2a8a1d28 | checklist | ITP-001 - Subgrade Preparation Rev2 | itp | ITP-001 - Subgrade Preparation
001dd911-d937-48b2-98d3-800d71131449 | section | 1 - Preliminary Works
08e0024d-231b-4647-9a6e-d43302fb49fd | checkpoint | 1.1 Prior to commencing any activity
62f9d2a2-eb0f-5668-a613-e424ef6d3bfc | note | FREQUENCY:
d1deab9c-1c5f-588a-bb14-8b70511a5ce7 | note | ACCEPTANCE CRITERIA:
1579c397-9798-5825-be1e-814e75f24c77 | note | • Ensure that all employees and subcontractors are:
106e3cdb-ff1c-54fb-9698-e73a571a32a1 | note | – using the correct and complete set of drawings
0734c511-b115-5d62-b9ac-44a90f4937f4 | note | – all drawings are the latest revision
0ddf6bb1-41dd-5e60-a227-f2fcb0938263 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
73a3f299-75e2-5df7-8a02-8f600426869a | note | INSPECTION/TEST METHOD: Visual inspection
da8a8733-2ce8-5f1f-86ee-e504c77e76f8 | note | RECORD OF CONFORMITY: This ITP signed off
4e76c56b-50ee-5eaa-89cd-a866be104203 | note | WP
e4bc8fea-7824-5a24-a472-3acf23feaf9d | note | RESPONSIBILITY: Fulton Hogan
77e8f216-8afd-5162-9926-208f3cdabaca | textbox | DATE:
e14f2d41-5934-4e94-b41a-356c38a4340d | checkpoint | 1.2 Implementation of all measures and controls
f122a68a-35cb-5b64-835c-26e7638f23d9 | note | FREQUENCY: Prior to commencing any activity
b59eee26-c887-5111-abe8-cc1f482e5c2e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
696a264e-24dc-5277-b46c-5dc95b4190fd | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e3c12262-f245-5553-b3c6-a36159b175f8 | note | INSPECTION/TEST METHOD: Visual Inspection
04fe345a-688b-56aa-ab33-7f70914e6bc5 | note | RECORD OF CONFORMITY: This ITP signed off
b5b255c7-1f7f-56ce-a8c9-3bffe07da55e | note | WP
e4fa5ec5-eb0d-58e6-8d7e-30f8176caa7b | note | RESPONSIBILITY: Fulton Hogan
8ea1ef1d-bca5-51a3-85fb-e223293bb64c | textbox | DATE:
89b1c2e3-80b1-415f-b4b7-f68a08c4ceb3 | checkpoint | 1.3 Selection and approval of Disposal Site
7892b0ae-154a-5f04-be8b-da8253677e7c | note | FREQUENCY: Prior to commencing any activity
e8301558-c3f3-5870-85ba-07ee8f58e5ca | note | ACCEPTANCE CRITERIA:
883c2214-a136-5332-820b-a871f747e7f8 | note | • Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
4294df9a-93f3-5892-a985-666f23a3d0ba | note | • It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
fa799b54-8fd5-5e73-a1cd-44bdb5a8768e | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019ST-0033 CL. 4.2.1.5.
c58f5fe8-4d8b-57aa-9c7c-68f2f7415a23 | note | INSPECTION/TEST METHOD: Verify
78b91ef3-1683-5bab-a89f-5f19cda169d5 | note | RECORD OF CONFORMITY: This ITP signed off
782a07ef-35f7-563c-98a6-13a22cc9a8be | note | WP
96f78f6a-d6d1-5547-9ea1-f0b7cd36ddb1 | note | RESPONSIBILITY: Fulton Hogan
ee8f6c8a-c918-5fd9-8091-a94761fe2b6a | textbox | DATE:
165cd49f-4c12-478d-8bd3-99ed859ad1aa | section | 2 - Construction Works
6ead4c3d-1f76-4041-98b9-735797e5e66a | checkpoint | 2.1 Excavation
04a24fd2-5b00-51d7-a9ca-c9aa717f319a | note | FREQUENCY: Each lot
efb94f2e-cd37-5320-8a6e-d0de104247e9 | note | ACCEPTANCE CRITERIA:
baa863f2-d1c9-5a5c-b146-8343f22e29d3 | note | • Plant and equipment shall be appropriate for the task.
9c40d5dd-dc67-5291-82d7-3ee417c0d39d | note | • Excavation operations shall not disturb areas outside the limit of works
c2d626ef-e9a1-518f-a3de-79624e2d314e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3., 4.2.4. Subgrade Preparation Work Procedure
0f3001c4-d5be-5e9c-9fd3-8d6ee43abf80 | note | INSPECTION/TEST METHOD: Verify
06a955ff-b6d8-5e17-96cf-92e5f236b8ac | note | RECORD OF CONFORMITY: This ITP Signed Off
f026da7f-121b-5bdc-8149-f050f061d70a | note | IP
2635c1b0-40d0-53fe-bb25-835a7dc906e3 | note | RESPONSIBILITY: Fulton Hogan
2fc52efc-3c8d-503c-8f9c-dbaaafb5fa9e | textbox | DATE:
802ca758-3ed1-49cc-b623-d176b80ca889 | checkpoint | 2.2 Reinstatement of bonds
b2f18abf-29ff-5c3c-8b2b-617b0b15d20d | note | FREQUENCY: –
1611c3e7-3fd9-5250-835c-4f5d3dabcb40 | note | ACCEPTANCE CRITERIA:
c56f39e4-6f45-57e0-82a0-4e725de86474 | note | • Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
ba86160b-c645-526a-818d-babb46b3cb50 | note | • All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
2db21435-71e8-55f6-94ff-0ae774c83bed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
b05afce8-1d41-5aef-9b80-4cb06cea6376 | note | INSPECTION/TEST METHOD: Verify
47abd4dc-af42-5443-a15b-f395a277951a | note | RECORD OF CONFORMITY: This ITP Signed Off
7b78c6ce-2524-5562-b24a-7198fd2e4651 | note | IP
1b1bf03c-2c0a-5a77-ac2b-045cbe47602a | note | RESPONSIBILITY: Fulton Hogan
21166443-ea74-569e-900e-144e71da9eae | textbox | DATE:
aa819b0f-1537-40ff-8ff0-f28640a7253e | checkpoint | 2.3 Inspection of Subgrade Material
9e19d421-f547-5b12-b685-5339217907b1 | note | FREQUENCY: Each lot
6db22b10-27f3-59ce-acd5-9ca5c8f8ba01 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
5da3edb5-abe4-565e-bd14-4f32ee34d3e7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
cfa6d697-5076-5877-9dfb-4d1e1f694f91 | note | INSPECTION/TEST METHOD: Verify
fe75f356-711b-5278-84ba-856975c88e52 | note | RECORD OF CONFORMITY: This ITP Signed Off
2f4cbba4-8165-5e31-89fd-9360b2b07247 | note | HP
5514190b-9b13-5929-a8da-70c531b745c0 | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
d6d7c255-3e25-5623-841c-ba0fdb9c2169 | textbox | DATE:
8d227978-c3fd-4821-9092-b79b3a2a723d | signoff | HOLD POINT AUTHORITY
de70ef90-206d-417a-bbae-d4a027f4aa30 | checkpoint | 2.4 Width and Level conformity
a94a2e99-32c1-5406-8109-bec445d72519 | note | FREQUENCY: Each Lot
5b68f9bf-3a2e-5301-8d68-fa6d3f28eaaa | note | ACCEPTANCE CRITERIA:
37e97c70-0483-572a-8ed3-d3d8f2f8a989 | note | • The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings.
bb29ddde-bd63-5bba-bac4-9e4b46f82e37 | note | • No point in the general surface shall vary more than 12mm from a 3m straight edge.
1525af19-3354-5a0b-aa93-4625836b8e10 | note | • Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
78c26b8d-8d93-5c84-a9b7-4d659afd965f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
05b5309a-e090-5069-8281-6f28f3100869 | note | INSPECTION/TEST METHOD: Survey Report
2b4df271-387b-5333-9d89-792db466b974 | note | RECORD OF CONFORMITY: Survey Record
d69316af-172f-51cd-9f5d-29ae147e860e | note | IP
e31c514f-1589-5939-a702-b18e3976e687 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
91b5070b-f523-5c2f-86b4-837a5523bdf6 | textbox | DATE:
9354554c-477f-46cc-80f3-fd6152b7dbb3 | checkpoint | Final Inspection
982e8627-7db0-5628-bc49-d17e69663b91 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e0019a79-27e0-597e-a9f1-a27028318fe2 | textbox | Print Name:
9af4c584-2dc1-5ed8-900b-5cacb3c76a9e | textbox | Position:
240943ab-196e-5849-a9b3-471e09479da2 | textbox | Date:
4bd53acd-6405-4e3e-a599-dc5d4aa54a1a | checklist | ITP-002 - Feeder Conduits and Pits Rev2 | itp | ITP-002 - Feeder Conduits and Pits
c0fdca6c-9fb3-4ae7-913f-6a4b051a60ac | section | 1 - Preliminary Works
a46884c7-852b-4bc8-8107-83cbce107959 | checkpoint | 1.1 Check for correct documentation
1dd02b6f-cb20-50b0-af91-29c941336207 | note | FREQUENCY: Prior to commencing any activity
74d3e9ed-67fe-5385-abae-33733cce56ae | note | ACCEPTANCE CRITERIA:
cb06cb9c-ec2f-56c7-ac67-68dc8af70f95 | note | • Ensure that all employees and subcontractors are:
7edbdd30-85f5-5bb3-a6ff-93580d65be30 | note | – using the correct and complete set of drawings
ef193c2a-8d93-5c32-8590-d75b06db3c49 | note | – all drawings are the latest revision
930331f8-238c-59e6-b164-afd483b350d6 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
62de1c25-2d66-5785-ab8b-edb723f6c9b6 | note | INSPECTION/TEST METHOD: Visual inspection
3796e4e2-e520-5904-8cbe-3c6218e6ca9a | note | RECORD OF CONFORMITY: This ITP signed off
c9939422-5637-5878-93db-86a8bc3de6e3 | note | HP*
bb638971-8de7-5b83-a139-01a79b71c691 | note | RESPONSIBILITY: Fulton Hogan Engineer
5abb1941-da2c-5861-bb51-10776769e729 | textbox | DATE:
9b0cad6e-a5d1-45a0-b1c4-0af4c94088a4 | checkpoint | 1.2 Implementation of all measures and controls
0c73006f-2171-5f13-8e75-af39e9451324 | note | FREQUENCY: Prior to commencing any activity
db30c66d-9b03-55e2-8fd0-49c81aa634fa | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
ea979269-855e-5d61-8c31-93defbcadb3c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
ff0a736e-cf31-5f75-84c3-90ef359b193d | note | INSPECTION/TEST METHOD: Visual Inspection
6d4bc889-2df9-52f1-b3df-66d87db0aa9b | note | RECORD OF CONFORMITY: This ITP signed off
50a3cc96-050f-5cd9-bd0d-ada92a712982 | note | HP*
03e3e14d-2f87-5273-91ed-600a1dc081d5 | note | RESPONSIBILITY: Fulton Hogan Engineer
3510f2fe-8b18-5c80-8b30-7f212bd7ed29 | textbox | DATE:
51127dad-de18-408a-b4b8-8c4bd7cead89 | checkpoint | 1.3 Materials
cd71f4d7-f62a-5521-909e-683d75311c6f | note | FREQUENCY: Per Batch
89cbbdc6-5627-5fa3-abb7-de1601ef85a0 | note | ACCEPTANCE CRITERIA:
477fe3bc-18c4-5c50-8a8e-77ecbab99503 | note | • Electrical supply conduit to be Orange
0187fab5-714c-5479-9541-206fb528cfdf | note | • Heavy Duty 100mm diameter UPVC
31a6bd62-579b-5e79-b740-9ef6d5e62d9b | note | • Modula Stakka pits to be used for feeder pit, entry for conduits to be cut with hole saw
e17d7cc9-f5ca-55bb-9df5-8e91e376ff4b | note | • All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
695bf958-fdf2-568a-a789-be08fcfd8844 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4AS 2053
f76b0ca7-4bf5-5269-b265-69d34d90254a | note | INSPECTION/TEST METHOD: Verify
6c41a7b2-6e51-5498-ba67-cad5a1b5f70c | note | RECORD OF CONFORMITY: This ITP signed
a4ec63bf-b7cf-5bf3-a7ae-33cca2f6165f | note | HP*
dc835441-3994-5f4b-9d73-a8281cf2e1c4 | note | RESPONSIBILITY: Fulton Hogan Engineer
d567f42e-33df-5466-af48-b2c30a899760 | textbox | DATE:
1033c23c-c402-49ae-b26d-ec1c7717fbb5 | section | 2 - Construction Works
5ba0b3f0-ba25-4425-9842-d89ba5ecff7b | checkpoint | 2.1 Survey set-out
f4301acb-d642-58c3-9c91-54e6dda108bf | note | FREQUENCY: As required
c9e86ae9-3028-5f15-91c5-41e83d3d343c | note | ACCEPTANCE CRITERIA:
3a1642b3-eb16-54a4-8bef-8a45a510c6c1 | note | • Work is set out in accordance with drawings.
34f1a8d2-dc7e-58c9-87a8-3f5712644582 | note | • Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
c501af14-d912-57c5-9578-d28bcac86dc4 | note | REFERENCE DOCUMENTS: Work procedure
37426b98-c29d-5140-aaf8-33c6a9350155 | note | INSPECTION/TEST METHOD: Verify
0444e3f3-2ca7-5856-bdfd-0454c0f20988 | note | RECORD OF CONFORMITY: This ITP signed
a8e1d7fc-d755-5fc0-b698-932d2cb53031 | note | HP*
60e27b74-8d7f-50a1-9694-994558cbde7b | note | RESPONSIBILITY: Fulton Hogan Engineer
4a9e3882-895f-517a-b27f-0902b2a0e8bc | textbox | DATE:
e149b514-72a0-41c2-bc41-44211afed155 | checkpoint | 2.2 Excavation and Trenching
d257f2e6-1587-54ce-b5a0-e39009ff8322 | note | FREQUENCY: Prior to Installation
4ca53c3d-c27e-5042-9cb5-a1d5afcdb073 | note | ACCEPTANCE CRITERIA:
65eb0d15-fb8e-518a-a50c-9181451805e3 | note | • Minimum cover for underground conduits shall be 600mm
617eee52-1727-5330-a011-7de41c7b7a95 | note | • Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
7c9fcdfe-8631-5290-9ac2-4cdf29b46ba0 | note | • Trench shall maintain a minimum clearance of 300mm from all existing services where possible
137dc1b8-5945-5b7f-85a8-c2bfcf127aaf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
551c3555-25ba-52c0-a31b-a904f3b38f4e | note | INSPECTION/TEST METHOD: Verify
3d12bbcf-bf4e-5aee-8b23-40657afa4424 | note | RECORD OF CONFORMITY: This ITP signed
6df89054-41bc-5053-b592-6943742e5374 | note | WP
9628fea1-0b93-57d6-9347-e9177e8555da | note | RESPONSIBILITY: Fulton Hogan Engineer
9b6da768-b289-544b-9893-e07ad0d1c3bb | textbox | DATE:
7225e839-da4a-45a2-948a-60d6e7fb480b | checkpoint | 2.3 Installation of Conduits and pits
c832c8ba-8e13-5576-b77e-7d707229268e | note | FREQUENCY: Each Lot
c099495d-eafe-56ac-8c2f-54a3d87f2750 | note | ACCEPTANCE CRITERIA:
8bbddfbc-3ff5-5233-93c7-ddab287bdaab | note | • Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
1dda2e31-5566-53b8-b178-5c4c90ba0066 | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
b77f9ef5-236e-5f41-b82a-107c9789d2df | note | • Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
25cb1706-cb3c-5884-826d-79b4c50b6512 | note | • Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
63a37aaf-930b-52fd-9b3f-71e527be293f | note | • Conduits shall not be subject to construction loadings
44ac61d9-f53d-58e7-bfcc-cf22ed64914e | note | • Pits shall be constructed as to allow for class D rated covers
d7ca8d42-7294-50a1-bec9-a00e641e6864 | note | • Bottom of lowest conduit shall maintain a minimum 100mm above pit floor, a 50mm gap between conduits shall be maintained as they enter pit face.
86a38c3b-55b5-5563-a9b5-85eb1a3ca008 | note | • Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mmbeyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
1693d599-26a2-5db9-bcea-e91a55976d89 | note | • Conduits shal be placed a minimum of 100mm above pit floor
4a76aea0-ab91-5d46-97d4-b73b3d27525d | note | • Conduits installed for future connections shall be installed to the track Margin
6de82dee-719c-50e1-adff-3adc0e3a5481 | note | • 100mm of concrete around and under pit lid
f6c9a846-0382-5487-84d3-383deda05fa8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
73ca6c71-6ee6-5294-9efa-9ecd1ef6bd36 | note | INSPECTION/TEST METHOD: Visual inspection
b15e974f-0393-5c44-a5a9-c666a7888569 | note | RECORD OF CONFORMITY: This ITP signed
aacf2caa-b99c-581d-8649-036b5c2f9696 | note | WP
342950e6-b2ad-50ad-81a3-93406401b868 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
50280934-0bb4-5a28-bae4-e322d738a3ee | textbox | DATE:
037ee90b-47cd-42e5-b832-d64d6cf4d41b | checkpoint | 2.4 Inspection of conduit installation
680d57be-c1a2-5bee-bc0d-b26d7dea7497 | note | FREQUENCY: Each Lot
4ab9713a-916a-5125-b601-5df2b9f9db40 | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
50502878-4ef2-51e2-86aa-35a7391036bc | note | REFERENCE DOCUMENTS: Work procedure
77266c6f-dbf5-53db-8d4f-02ade1712c3e | note | INSPECTION/TEST METHOD: Visual Inspection
6a65f469-134c-52c1-9015-f83457acf783 | note | RECORD OF CONFORMITY: This ITP Signed
f9e33d29-3934-5a49-8280-75a3730388fc | note | HP*
44ea229e-2696-590a-8891-6c3ec09cf3e1 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
e58453ef-ea0a-56a5-82e5-d0d577fd9df4 | textbox | DATE:
0460ee88-5f82-4f99-8d42-74966ffdabe9 | checkpoint | 2.5 Back Fill of Trenches
38e9b78a-16b7-5fde-af32-b7769317baad | note | FREQUENCY: Each Lot
884f29c0-fcad-5d0b-9059-07402f3ad160 | note | ACCEPTANCE CRITERIA:
6ff2836d-94f8-52fb-8f48-92a0277edb60 | note | • Backfilling (Only to be used for road crossing trenches)
05b9fd81-93a7-5f3b-9473-b7510d25335c | note | – conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
cb73b548-e6f7-5136-9398-1cd7b2baa95f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
b2852812-e46c-58d7-bc73-e4fb38df8f1f | note | INSPECTION/TEST METHOD: Verify
16e3ab25-2e01-53a0-ac5c-89c16803e07c | note | RECORD OF CONFORMITY: This ITP signed
9e89c5b6-a8fc-5ba9-a9d7-ba483bb284ea | note | WP
c3c2a196-db26-574b-9c63-29c835e28373 | note | RESPONSIBILITY: Fulton Hogan Engineer
fa22bae2-4241-5ca1-aad0-5315d4ef74da | textbox | DATE:
7c08edda-a5ad-4374-8060-88d932440622 | checkpoint | 2.6 Installation of Draw Cords
c267afaa-f569-5831-b99c-9af873e02a53 | note | FREQUENCY: Each Lot
14ae882d-8c13-517a-abf4-9d30b6d45ae9 | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'
207eecf7-9b02-50bc-82f9-f09b75523e68 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
44b04b8f-37b1-5cf7-9709-4e339847763b | note | INSPECTION/TEST METHOD: Verify
01a3ef3d-2436-5787-ac79-7c0574dcdc79 | note | RECORD OF CONFORMITY: This ITP signed
4ca78694-0202-5ed5-a302-b5be118da294 | note | WP
0259af1f-8864-555e-b3a6-f5844ebef30e | note | RESPONSIBILITY: Fulton Hogan Engineer
4d65725d-06e0-5a21-9c13-792fcc4ff712 | textbox | DATE:
5d7709fb-6c38-465e-848f-7c16d40450d5 | checkpoint | 2.7 Compaction
d7d9a326-831e-5775-b3da-348c1bffcae0 | note | FREQUENCY: Each Lot
9807efd3-112e-593f-b589-1dff7bb37bb2 | note | ACCEPTANCE CRITERIA: Bedding and backfill material to be compacted using mechanical plant During compaction optimum moisture content of bedding and select fill is within 85% to 115%
c34562e0-142d-5685-a626-26cc94b2c679 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
aee163b4-25cc-5e10-b899-03b7c19b3c93 | note | INSPECTION/TEST METHOD: Verify
0d3c485b-a2a1-54f3-84df-3308a9f41e1e | note | RECORD OF CONFORMITY: This ITP signed
2162a43f-01ce-5819-861f-91f4860501a9 | note | IP
898fb964-89ac-50e9-abb3-f20b564b9095 | note | RESPONSIBILITY: Fulton Hogan Engineer
3eaea696-d67b-5800-82ff-271f3f19d4a6 | textbox | DATE:
81757977-3546-4c59-9538-3d82d7ecce0b | checkpoint | 2.8 Feeder Pits & Pit Lids
c50215c1-1617-561d-bb94-f0fd734cde58 | note | FREQUENCY: Each Lot
43ef3cfd-e862-5fbe-b64d-e4e707668cac | note | ACCEPTANCE CRITERIA:
71c052cd-dd63-5c3a-80cb-1054046c039f | note | • Feeder Pits constructed and installed as per drawings
7b82e055-38aa-5ef6-be3a-fb7831423ff8 | note | • All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar
222acd19-d724-5a6d-aa9e-6d288a7e831b | note | • Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
ca0a7b13-836d-5154-ab69-03806ad53bbb | note | • Gatic pit lids shall be filled with structural grade concrete
f82b7bf3-9e96-5151-b848-2e2cce6ad230 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
0cd1206e-f5b9-5de5-a0fa-7f4eb70a1b28 | note | INSPECTION/TEST METHOD: Verify
0c6f21e3-2390-5f81-9378-5a8f9999ae3f | note | RECORD OF CONFORMITY: This ITP signed
b0fdb187-67b6-59c7-9072-db596abf1337 | note | WP
89ae9fbd-0fc5-5489-b2a4-1c3553c6b966 | note | RESPONSIBILITY: Fulton Hogan Engineer
79ade2eb-391a-5102-8175-d1d419475791 | textbox | DATE:
78da752a-3eb2-409b-ad7c-09e0da86c9fe | checkpoint | Final Inspection
4889b1e6-cdf7-5283-836b-dff8808bd0b4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4adbe82e-a0db-58fb-8417-21fd7ca999a6 | textbox | Print Name:
a6714e63-3953-5b7b-9188-a6f235fc564a | textbox | Position:
81671e29-e7a6-5830-b391-36e62c60ca03 | textbox | Date:
5c9dd9ae-5d73-40a9-950e-78a5209e1f91 | checklist | ITP-004a - Class 2 Base Course Placement Rev2 | itp | ITP-004a - Class 2 Base Course Placement
a58d392b-8507-40de-9d14-3b67c45a49a7 | section | 1 - Preliminary Works
a0bc2d42-8bdf-4ec6-9419-cfdd9492eb6b | checkpoint | 1.1 Check for correct documentation
cfc7655d-31c0-5ef5-9b85-4c1b13e35450 | note | FREQUENCY: Prior to commencing any activity
877f7fa9-4440-5784-a2c8-ff7bac9f47b6 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
f8b78a94-e4ac-588c-ad41-0a17b533ea6b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8fbb0231-0f9f-5ada-97dd-09062d57d0cc | note | INSPECTION/TEST METHOD: Visual inspection
3c2e8f40-9c97-5315-9a51-b2f35bc9a093 | note | RECORD OF CONFORMITY: This ITP signed
b244c56e-594d-5115-9d53-662078c07aff | note | HP*
69edf44d-eea9-5f41-927a-da07444e7b58 | note | RESPONSIBILITY: FH Engineer
fd19d9fc-3881-54d1-b8a9-b70957a4ef5e | textbox | DATE:
8ba63960-72ad-4383-bedc-6a5e1372d6dc | checkpoint | 1.2 Implementation of all measures and controls
81499de5-c2ea-54ff-99a6-394c122a494c | note | FREQUENCY: Prior to commencing any activity
f033dcb3-ab7a-5857-9b95-9f5491bff488 | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
99004b8b-70de-5e30-b481-efc1041a83f0 | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
29e229c9-c2c9-544b-8d0c-b05f2a97423e | note | INSPECTION/TEST METHOD: Verify
f0511825-d3d7-5f4f-b8fe-9ad6cfbfe248 | note | RECORD OF CONFORMITY: This ITP signed
41f03478-21c6-5aef-be12-bc84ae2bafd3 | note | HP*
03436fbc-38f6-558e-9495-f3e9bd2c4017 | note | RESPONSIBILITY: FH Engineer
1b6845b7-a41d-5132-951b-8b9701356648 | textbox | DATE:
87d949dc-2830-48c0-b747-8a917df29c15 | checkpoint | 1.3 Material Compliance
ebc0ad7e-0456-551e-9108-304475bfac37 | note | FREQUENCY: Prior to commencing any activity
1a030818-daf6-5f04-848e-55bf6e19538e | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
28a65559-40f7-5ad3-aafa-c956e08804c7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
bf9ca5f6-e30c-535b-ba40-7ce54b6e4a11 | note | INSPECTION/TEST METHOD: Document Review
6641289e-a7c0-5286-8c12-94256845e0a2 | note | RECORD OF CONFORMITY: Test Reports from supplier
33e4dd9c-9921-59e2-9e88-06b30e17a1e6 | note | HP*
ebcda4f4-0f98-51b0-9118-753cf1627287 | note | RESPONSIBILITY: FH Engineer
b30d4ba7-737b-5463-81db-08d011866f06 | textbox | DATE:
c172d805-d207-43d4-aed3-7c9670e3552f | section | 2 - Construction Works
c42f5f2d-b785-411e-8046-58394baa62b5 | checkpoint | 2.1 Sub Base
1931267d-5f09-547f-b16c-5da4aba88d9b | note | FREQUENCY: Each Lot
12dc0943-5075-5493-98ec-9a0913072a6d | note | ACCEPTANCE CRITERIA:
48c7c843-5094-5515-b8cc-3eb2160e7b27 | note | • Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
256db458-d0da-582d-8e25-aaed8a6e205f | note | • ITP-001 HP for subgrade inspection signed off
b03c7a17-7d05-569d-99c2-6439ed0c4630 | note | REFERENCE DOCUMENTS: VicRoads 173.03
6da3be09-e99e-52cf-a3b3-c5e6a1efaf31 | note | INSPECTION/TEST METHOD: Inspection / Test Method
03092c90-505a-5fa3-9c1b-dab4a78237a0 | note | RECORD OF CONFORMITY: This ITP signed
983dc9a8-2f1a-55ed-99f7-ca07a0918aea | note | HP*
94dedd20-06df-5e6b-a341-25b18c15719e | note | RESPONSIBILITY: Fulton Hogan Engineer
41ad4f56-063a-58ac-acc0-296ceaf1b53e | textbox | DATE:
a1a5d84c-f77d-4e4e-ae09-f4a9321a5261 | checkpoint | 2.2 Spreading material
84ac2692-cdef-5671-9456-e16195efb4bd | note | FREQUENCY: Each lot
ceff4e8b-e578-54d7-b1c8-3b6f36615167 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
3eae7764-84fd-5b6c-b1d2-126190303569 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
c34e6c29-1c2b-519c-9410-96334de72c6c | note | INSPECTION/TEST METHOD: Visual Inspection
ac44c65a-3739-5c7c-bc54-763cdfc87946 | note | RECORD OF CONFORMITY: This ITP signed off
c7644079-7a2e-5d70-9010-a355eb42c336 | note | IP
516c3949-346f-595e-9d89-48ba7a4c3687 | note | RESPONSIBILITY: FH Engineer
5156023a-c1c9-5204-bdf4-53c2d98ad483 | textbox | DATE:
572e7028-e482-4943-ad91-e52782625161 | checkpoint | 2.3 Compaction
673e7657-0522-55cd-a622-dc41073ef5dd | note | FREQUENCY: Each lot
c8f0e426-c1dc-5ec0-9fc3-e492f4cb10c9 | note | ACCEPTANCE CRITERIA:
a509639f-6459-5ddb-b58e-5c9952d38def | note | • Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
bb9dbfae-479a-520a-8638-eaac678a6126 | note | • Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
5960acb8-3e6c-505b-a1ac-336eaf54b8ef | note | • Compaction testing shall be carried out once per days production and shall comprise of three samples
86fce273-ce6e-52b3-aaa2-0d6835f03983 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
dfd3fdd1-1332-55f5-8912-2467ce47fdd5 | note | INSPECTION/TEST METHOD: Visual Inspection
9ebae320-ea6d-5604-a88e-aadcff2b330e | note | RECORD OF CONFORMITY: Test Results
4b82f3d3-37bd-57f5-90f0-c99c7edbed38 | note | TP
944594dd-90fe-5726-b182-d9c206975c1f | note | RESPONSIBILITY: FH Engineer
21f839e9-dbe8-50d9-905e-787b53f5424e | textbox | DATE:
e6117e45-8595-44e6-ae79-c6b1c18d4864 | checkpoint | 2.4 Level Checking and Conformance
d56a8dd0-cbc5-5337-b8d8-43e4f2d86673 | note | FREQUENCY: –
5575175d-22d6-5214-a176-e98f03bdc4cd | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
e611c6f5-4751-5c2d-b9ad-a8cdd69b68b0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
985d9c8a-91ca-5086-a6a3-09396f04505a | note | INSPECTION/TEST METHOD: Verify
cd98ffe2-3de9-57d7-aaf0-52996d1b5ea5 | note | RECORD OF CONFORMITY: This ITP signed off
7a325358-5e60-5ce0-8540-8ae1c855f6ff | note | IP
aa6504a8-6c3d-55cd-beab-9345ff21957b | note | RESPONSIBILITY: FH Engineer
f6cc034f-6986-54d4-8344-9de2cb47192e | textbox | DATE:
f182fe4e-a413-4ec4-82d3-d06dc37b9fbb | checkpoint | 2.5 Finished surface
4693e9a1-a7ce-5bfc-8da9-072d7c390a86 | note | FREQUENCY: Each lot
4d20fba5-5d41-5dcd-9a95-4ac8e377977d | note | ACCEPTANCE CRITERIA:
925c6e80-b4c8-5971-a3fd-20af26a5da0e | note | • Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
a199d8d7-19d3-5b31-a4fc-e1592c050bee | note | • Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
6b76877c-f125-582a-9763-1d9b46a8f714 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.2.8, Contract drawings
a6146de9-63ab-5fd8-b760-dcb3f722a84b | note | INSPECTION/TEST METHOD: Visual inspection
c00f6a9f-01d2-5e18-ab68-4473fb53beb9 | note | RECORD OF CONFORMITY: This ITP signed off
ec355f4a-79fe-55d0-bcd5-fcceb0d0e493 | note | SCP
aed36dce-5bc9-5fe9-9e63-ed0dca903c81 | note | RESPONSIBILITY: Surveyor / FH Engineer
dfe46485-20a0-5e51-b688-aec1711188c8 | textbox | DATE:
93e27ce4-99e1-4d66-9166-5e0ee7344ec8 | checkpoint | Final Inspection
5bc85d36-b360-5cf7-b83b-e172be71d23c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e6de64b2-703b-5106-b870-c404047499c8 | textbox | Print Name:
a0b9fbd1-9a45-56f2-87d0-e2fb12b7ffee | textbox | Position:
ccf506c9-7755-5475-bbb8-b581f86b8f59 | textbox | Date:
a563a155-1a21-45f9-8d21-358c5ace7ef7 | checklist | ITP-005 -Track Drains | itp | ITP-005 -Track Drains
28dc7dd8-264a-4baf-94a8-6c3cca55f804 | section | 1 - Preliminary Works
2ed9b094-7e3d-4e4b-a438-ffa3fd5fd2f5 | checkpoint | 1.1 Check for correct documentation
2a0a260e-6f85-54a1-b1f1-969b5fd32fd0 | note | FREQUENCY: Prior to commencing any activity
33e51d44-8297-5ae9-a818-bbafe2bf426d | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent
56fb834a-49d5-59c4-8002-fc1f95cb00d1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
304930ed-bcea-539e-b8e6-55b6ff33ff22 | note | INSPECTION/TEST METHOD: Visual inspection
6ec65096-2e14-549b-aa84-2b724d3b3705 | note | RECORD OF CONFORMITY: This ITP signed off
1a3b062d-70da-52df-bcd7-7497a61f0ac9 | note | HP*
b954a024-da7a-5989-90a0-3e1fa0ede1d4 | note | RESPONSIBILITY: Fulton Hogan Engineer
4b8c11da-f012-5919-8e0b-f24482093151 | textbox | DATE:
7e8efe72-068d-49e9-8653-35d95f5b1d04 | checkpoint | 1.3 Materials Check
906c90ea-da5c-593f-bf60-408cfccb9e67 | note | FREQUENCY: Prior to commencing any activity
20eafd1e-d5c3-56db-97b3-0a87e06016a1 | note | ACCEPTANCE CRITERIA:
f8bb0c34-0b1b-5a29-83ec-3d0dbcb7082c | note | • Ensure drainage pipes are of correct classification and are without damage
f33c625d-53e8-5b08-80a2-75b15f8f9e3b | note | • Check triangle drains are of adequate quality, and are design according Ri57A rail profile
56667528-cb83-53f7-ac1b-7c2536921ffc | note | • Ensure lid and j-bolts being used are in accordance with STD T9022
5061905d-9d55-53a3-b634-c9ebbe7a3f63 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
542479bf-95f8-5fa1-b429-16c4b3a77099 | note | INSPECTION/TEST METHOD: Visual inspection, Inspection Checklist
cb7a08f9-ab79-5a60-b022-4be9e12f4aa9 | note | RECORD OF CONFORMITY: This ITP signed off, Recievable Inspection Checklist
bcde4652-4b49-56fe-8e0a-3a1692f04803 | note | HP*
c84eb8e7-1a88-50f0-a790-3cfd616c7124 | note | RESPONSIBILITY: Fulton Hogan Engineer
415d66c1-303a-5c31-80ef-c7faf3554bd5 | textbox | DATE:
ef9ed69c-d7b7-45f5-88dd-6e7debe8c2c9 | checkpoint | 1.4 Bedding Sand
84dab116-e1ff-5ad1-aa75-9f915b5d9032 | note | FREQUENCY: Prior to commencing any activity
2bd41323-99ad-538c-b021-3fe39762ba9c | note | ACCEPTANCE CRITERIA:
48cdd688-0a69-5eb7-82ec-a606456d5a0f | note | • The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following:
d9a59f6e-51c3-512c-ab59-bd97e8974560 | note | • Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities,Consisting of hard durable particles, and well graded.
aba81991-e612-57e1-86c5-635c65519828 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
6befffa5-90e7-5588-a927-eba9460a63c8 | note | INSPECTION/TEST METHOD: Visual inspection
e6f64653-3e60-5ffa-be8a-67f4222e33ee | note | RECORD OF CONFORMITY: This ITP signed off
1f5d64e5-5d39-5ef4-a94d-349fde006fd2 | note | HP*
577ea088-0746-5502-8e15-027ca5ce09bb | note | RESPONSIBILITY: Fulton Hogan Engineer
ee763750-562b-5de5-a5cc-fdedd8845aba | textbox | DATE:
910fd00a-c512-4cf8-ab84-4e9e9220d618 | section | 2 - Construction Works
fa4c2b33-3d57-442b-a957-fa512a32278b | checkpoint | 2.1 Set out drainage
853356a7-92b8-5218-87f7-e87b8bfee7de | note | FREQUENCY: Prior to commencing any activity
c41b2925-f8d2-5312-8d5b-20515c2f21c9 | note | ACCEPTANCE CRITERIA:
83a4a16c-f976-5002-b3ac-a5171040a192 | note | • The position of all drainage lines are to be confirmed with the superintendent
6eb2a5f5-9bb0-586a-9f44-f44326f7347a | note | • Track drain locations are to be identified and based off IFC drawings and sections.
75ed57c2-6252-571a-b0e7-af5f895204ab | note | REFERENCE DOCUMENTS: Design Drawings and Register
69f4ce93-ea1e-52af-a99d-0a9eda1bf4e8 | note | INSPECTION/TEST METHOD: Visual inspection
f531681e-e2a3-5f9c-bb53-162909c23ebe | note | RECORD OF CONFORMITY: This ITP signed off
d772f973-5a24-5b53-a101-454d05f2a4bf | note | HP*
51399e3d-3c46-5807-ba7e-de163b685560 | note | RESPONSIBILITY: Fulton Hogan Engineer
8112d44c-c88b-5c3d-a177-6f8059e339eb | textbox | DATE:
8299c231-888a-4272-a7c9-81bb40e4d403 | checkpoint | 2.2 Excavation (pipes)
8950d38c-76b7-5c14-9d88-ddc030b68b58 | note | FREQUENCY: Each Trench
1429795c-1eeb-5be8-91a5-8d9fdadc059f | note | ACCEPTANCE CRITERIA:
3fb56a77-318c-532f-b85b-e8ee46e2447c | note | • Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe
4ebbaa4c-c42c-54c7-b109-ebc80719164a | note | • Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
b062b583-0b18-5d09-a042-28cf4b43ef64 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
cd0a65d9-dce0-52d8-870b-7a4aa5dd78cd | note | INSPECTION/TEST METHOD: Visual Inspection
398beb1e-f81e-54dc-949e-a28635ea31a4 | note | RECORD OF CONFORMITY: This ITP signed off
c6185d67-229c-58cb-9145-db87c36af4ee | note | IP
d1821562-2541-5373-aee7-1f4dd13c4a89 | note | RESPONSIBILITY: Fulton Hogan Engineer
64ba9bfa-190a-5b8f-88f5-a570a075c2d2 | textbox | DATE:
255e607e-f341-462b-b452-021c3b2da001 | checkpoint | 2.3 Bedding
88c3073d-04ce-502a-9197-b1132fa421cb | note | FREQUENCY: Each lot
2589139a-7c1d-5317-94b0-9cdc03fdc1b5 | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
204cf9dd-513b-52a4-a1c7-640a2a1d00d8 | note | REFERENCE DOCUMENTS: STD T9021A
5467c70d-e4a6-5390-80b9-f82d2fd9611a | note | INSPECTION/TEST METHOD: Visual inspection
1e527b60-b87c-527c-97bf-d857784e4fbc | note | RECORD OF CONFORMITY: This ITP signed off
3fc05fe8-7c31-59ba-9e56-afef071590f3 | note | IP
31027811-b127-5672-b6e8-ac3c565b29b4 | note | RESPONSIBILITY: Fulton Hogan Engineer
e314e674-2629-5c33-bd21-8d5e2deb4e88 | textbox | DATE:
72ce173f-77a8-4d30-b261-c7a426d4d5ff | checkpoint | 2.4 Joining
5c138dab-ca1d-5ac9-a0b1-9bc218860f2b | note | FREQUENCY: Each lot
624876a9-09a6-5e44-9e9c-ccb7082d79f8 | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
b0fafc96-de50-519f-a749-44b6cb444b97 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
3a1fc85b-fd08-5174-97d1-b4f00aa6db5c | note | INSPECTION/TEST METHOD: Verify
04777b75-4fa9-5fc6-a5f4-69dbe409e97a | note | RECORD OF CONFORMITY: This ITP signed off
47f35d09-7ff7-5eaa-a30c-ae2f9f586f99 | note | IP
85c9fc51-5e91-5431-a7ba-d7dfeefc7c83 | note | RESPONSIBILITY: Fulton Hogan Engineer
9c3f1e18-dc23-5a99-b6e8-2d523d3c187c | textbox | DATE:
0ad4a57d-4d96-4fc3-811e-0db2c72500c5 | checkpoint | 2.5 Track Drain Installation
fa567ec2-c404-5998-8677-ef7dca4f8a4e | note | FREQUENCY: Each Lot
585b8830-c34c-5b46-9102-c7c9b3e6a091 | note | ACCEPTANCE CRITERIA:
0fa3b107-ba7d-538f-bd68-430095306a49 | note | • Track drains shall be welded to designated positions, and cleaned of all weld splatter.
44b8d623-5c93-5b15-bd95-b9f2f672cf85 | note | • Weld shall be sealed after installation
25f6c6c9-aa36-5c2e-abb0-3a3d44b900e7 | note | • Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
e8e30589-8a5f-530c-a402-cc09989ef5b1 | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
7b43a569-19a4-51eb-ab58-507d7a9c7a3f | note | INSPECTION/TEST METHOD: Visual inspection
9fc9f5b5-4e0c-5ba7-b012-b3f4856f1f8c | note | RECORD OF CONFORMITY: This ITP signed off
b19e20c6-21ed-5542-9cb9-27d5282540ff | note | IP
f13e9ec9-0eb7-5f19-92ea-61291c57ec08 | note | RESPONSIBILITY: Fulton Hogan Engineer
a6bd4a4a-74e5-539e-ad39-903f17514487 | textbox | DATE:
46272b0d-a0d3-4eee-b599-58644dacbb70 | checkpoint | 2.6 Points Drainage
0e03d372-e268-53aa-8d19-1aa9e6327cf6 | note | FREQUENCY: Where required
f7d685ed-19d0-5722-bca6-3f23169618b6 | note | ACCEPTANCE CRITERIA:
4af86203-361a-5c80-a9bf-6c8cee24b3fa | note | • The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit.
2378823b-00c0-5549-af0b-7350a03c7cad | note | • Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
800785e3-b21d-5606-84b5-91514bca3080 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
3888db01-39d5-5ce8-8293-48ea687e193c | note | INSPECTION/TEST METHOD: Visual inspection
efc5dd61-cd5c-57d2-a0c5-79e1f2a55bab | note | RECORD OF CONFORMITY: This ITP signed off
1c09bc8f-dded-5684-a09f-164ed984eb7f | note | IP
3858509a-cddb-520c-9ec8-a9ffd2cb7e53 | note | RESPONSIBILITY: Fulton Hogan Engineer
d37fff4d-dc20-58e6-9e7a-06e0c0c04619 | textbox | DATE:
715fd835-37e2-4788-a02d-c536cdfa267d | checkpoint | 2.7 Concrete Pour
bc65749f-5d22-5acf-b46e-78bd14e77465 | note | FREQUENCY: Each Lot
6159f91a-e058-5999-bd7e-81333448e0f6 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
6646ae7a-f64b-55ba-b79d-71bea1993102 | note | REFERENCE DOCUMENTS: STD T9021A
a6921e60-ce42-5711-9889-89274e2fc93a | note | INSPECTION/TEST METHOD: Visual inspection
26b79637-5ad5-5e52-99c6-061997fdeb83 | note | RECORD OF CONFORMITY: This ITP Signed off
05eada67-20d0-5171-a708-bc0da3b7e2e6 | note | IP
bd5cf79e-5cdb-5839-805b-b1545aefa149 | note | RESPONSIBILITY: Fulton Hogan Engineer
343c186d-13ae-5f08-a25d-aeaa9673c0df | textbox | DATE:
568099d6-d37d-4100-a6fc-5ce443174c2c | checkpoint | 2.8 Connection to local drainage
0030c7e6-62da-5f04-adbd-d0e3221ee40e | note | FREQUENCY: Each Lot
e538a49e-be64-51da-9781-6c34d22606c1 | note | ACCEPTANCE CRITERIA:
3ce4c5b2-64c8-5fdb-b24e-53eb6a2dc4bb | note | • Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority.
7f4ea20f-b504-5bac-b679-ce2a283306ff | note | • The minimum pipe size shall be 150 mm.
fcf19655-ceec-5163-aec1-7a0db975991a | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
a0974d67-6578-5657-a2b0-74252a9189b6 | note | INSPECTION/TEST METHOD: Visual inspection
93c019b4-134c-53f3-b6ca-850c377fbf46 | note | RECORD OF CONFORMITY: This ITP Signed off
a8d3c658-952e-5b5d-b4c4-6c996ea2b627 | note | IP
2c0d0166-dd87-57e1-a419-519f73b4db5f | note | RESPONSIBILITY: Fulton Hogan Engineer
78f0b8b2-aff0-581b-8ed4-2883b6164769 | textbox | DATE:
f2d50830-b040-477d-b00c-23ff20d32a6f | checkpoint | Final Inspection
de7e82da-bde4-5df6-a0b5-10ae36eab927 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb65f8cc-1c7b-5d1d-8040-42a0d013f749 | textbox | Print Name:
1ce0ef8b-9490-5619-a354-392eff6531f7 | textbox | Position:
cc45c789-89ae-5dd4-9119-ec911347a826 | textbox | Date:
1ab0257c-0850-40e9-9843-d5785dd440b2 | checklist | ITP-006 - Track Placement Rev3 | itp | ITP-006 - Track Placement
24667aaa-d1b7-4d25-9b62-4e0bc150964b | section | 1 - Preliminary Works
9c400344-52c6-40bf-ae01-913f3a4e1f54 | checkpoint | 1.1 Check for Correct Documentation
db8224fe-760d-56e8-be3f-c35ea8bd6134 | note | FREQUENCY: Prior to Commencing Works
9423663b-e936-5294-a2f3-3ac475e8c971 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
8cfe857e-68ea-5096-8ff8-45a81ebb2f9a | note | REFERENCE DOCUMENTS: Design Drawings and Register
055f4d45-66c5-54ef-9cda-6836c07f498d | note | INSPECTION/TEST METHOD: Visual Inspection
b2372165-6cba-5731-abf8-af5f1c863197 | note | RECORD OF CONFORMITY: This ITP Signed Off
02123363-0acd-59ee-9137-113d159cee59 | note | HP*
6f060038-265e-56a0-861f-b91ac57541bb | note | RESPONSIBILITY: Fulton Hogan Engineer
43adeb5b-d86e-5ad3-b13b-aeda88a4b9db | textbox | DATE:
193e432a-536f-44c3-884a-3963203868d2 | checkpoint | 1.2 Check Materials
a33d4c53-1966-59d5-a266-07e334632c55 | note | FREQUENCY: Prior to Commencing Works
bb2e6fb8-a026-5d7b-95ad-76854b956eb4 | note | ACCEPTANCE CRITERIA:
fff18da3-e323-55ba-9ef0-23aa9e6a5374 | note | • Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
b55ad6b1-6a87-5cce-8f85-daa58cf74914 | note | • Check condition of rail sleepers
db4294a7-e1fb-5645-be23-ea9e9add3a6d | note | • Ensure rail jewellery is of sound condition
5ababb39-93a8-571e-898b-90b94814edc8 | note | REFERENCE DOCUMENTS: AS 1085
f51ffe29-45a2-51b8-8c6f-4da578e5a6b3 | note | INSPECTION/TEST METHOD: Visual Inspection
de76202f-68bd-5bca-bebc-00212cfb8d02 | note | RECORD OF CONFORMITY: This ITP Signed Off
3d7eb362-050d-5c19-ae55-0950b30216bd | note | HP*
ff3d44c7-42d6-5789-b2c4-e9b7d7a96aca | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
73e8a78e-d3b9-58cf-8c05-dcd8acff29c8 | textbox | DATE:
aecea445-dfed-42c3-a1b4-de7166e36fb1 | checkpoint | 1.3 Check Special Works Components
94067da2-367d-503a-af89-dea921692605 | note | FREQUENCY: Prior to Commencing Works
83941dd3-dc82-5358-b210-d34b19cc1275 | note | ACCEPTANCE CRITERIA:
2e8d3510-6927-5946-bf6d-93bff793a30e | note | • Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
75e97d9d-2e85-59f5-b507-a5df256ba356 | note | • Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails.
414b2b05-36d2-592a-b5bc-ea5becacc100 | note | • Superintendent to visit yard from intial inspection of the rail and fabrication plans.
35c1abb2-75ce-581d-85f5-db5dfca4bc0e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
f094d12f-8c56-5208-b838-f7d38e67b6c2 | note | INSPECTION/TEST METHOD: Verify
ff91bfc6-c048-5881-9d18-575874c85f37 | note | RECORD OF CONFORMITY: This ITP Signed Off
4f25c9bc-71eb-53bb-84a7-58ae68e6dee6 | note | IP
70c0613f-e26f-5594-9625-86e5d3f2581c | note | RESPONSIBILITY: Fulton Hogan Engineer
32a88e8f-4fce-5e8b-8cfb-d245d70b9bf7 | textbox | DATE:
a5606e24-0038-4bd0-b861-5a7366e7015e | checkpoint | 1.4 Check Curved rail
c058526c-5c98-5411-8a56-a2d740193281 | note | FREQUENCY: Prior to Commencing Works
bbd5e121-bab7-5248-91f5-8e022c3f67a1 | note | ACCEPTANCE CRITERIA:
2ebbd81c-f77e-57bb-bc95-6b9af228feb0 | note | • Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
8891fbd4-0b67-569d-b5fc-d09ffa63e667 | note | • Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
e911eb58-f044-5937-985a-f49f2ce005ed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
592300eb-d6bf-5453-baec-33a454cea07f | note | INSPECTION/TEST METHOD: Verify
d6ee1093-f56f-5c36-a439-a41af172a325 | note | RECORD OF CONFORMITY: This ITP Signed Off
a13a2365-5f7d-5244-a8bd-df7434f4e280 | note | HP*
32fefc3e-5e15-5c45-a40d-5dc8b811498e | note | RESPONSIBILITY: Fulton Hogan Engineer
ccacca26-b530-5b18-b3e0-ea05bf8a00eb | textbox | DATE:
d8c01044-dd90-44be-bb29-42ba8278bf1a | checkpoint | 1.5 Welders Qualifications
edfec91f-1ea0-5aec-97bd-79fcbf128874 | note | FREQUENCY: Prior to Commencing Works
ba6d92c1-b3b2-5b5b-83ff-53a4a05687d0 | note | ACCEPTANCE CRITERIA:
a94592f9-da4c-5165-a2f2-292bcde76179 | note | • Welders shall be trained and compliant in Aluminothermic Welding Requirements;
2f9cad02-1224-596e-b9d9-e49e601914d1 | note | ○ TLIW2012 Grind Rails
60d0ad60-d686-5926-bfe4-41e005636176 | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
591a803b-d2a2-5748-9aaa-eefa8371ad0b | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
b1a92464-e928-5305-b51d-a98f6f8870a6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
03542f16-2868-5594-b7d4-9dcabcacfe4d | note | INSPECTION/TEST METHOD: Verify
f3ffbbd6-1937-5756-a196-921cf681142f | note | RECORD OF CONFORMITY: This ITP Signed Off
b365a5df-a9ea-5518-82a6-9bb3241cded2 | note | HP*
7e914d8f-b698-5186-90bf-a9ce64f0772c | note | RESPONSIBILITY: Fulton Hogan Engineer
4286c1d7-57a7-548c-88c5-70991556e4a8 | textbox | DATE:
54af46ea-156e-45de-9eb3-a499855d7f10 | checkpoint | 1.6 Ultrasonic Testers Qualifications
3363028e-acec-5dee-88e8-fe30f11a9d9b | note | FREQUENCY: Prior to Commencing Works
932e5319-d770-56a6-8f35-cab15629edb7 | note | ACCEPTANCE CRITERIA:
a6c8458f-b0ca-541c-82ec-56aa38922076 | note | • Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing.
a6bda1e3-a65f-5c6f-b83d-559f1f018293 | note | • Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
90448311-3bc3-5945-9cbc-d51a111df8d1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
8777db36-6b6e-5665-923c-d05ab2d1058f | note | INSPECTION/TEST METHOD: Verify
559a73ce-948e-5a92-83d6-534682e95d79 | note | RECORD OF CONFORMITY: This ITP Signed Off
6c095786-6c4a-549c-880c-2cfca1d3be29 | note | HP*
b0e7b29d-8377-5c49-9b81-ce4955221abc | note | RESPONSIBILITY: Fulton Hogan Engineer
7c86e8bb-232b-56fd-a3ff-bfaf2b0b7ce3 | textbox | DATE:
10de851d-eb4d-4d46-8f9e-0fc4f0a1cf20 | section | 2 - Construction Works
e10da0a0-f38f-4d02-a895-424b5d96c307 | checkpoint | 2.1 Installation of Sleeper
1ce74de5-67fc-5aa4-a6e9-f5c4adf264c0 | note | FREQUENCY: Each Lot
db80831e-5ee3-510d-9134-97411297b1b0 | note | ACCEPTANCE CRITERIA:
612e7b95-78a2-50f9-975d-faf46fa6051d | note | • Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
cf3aeee1-b20a-5f3c-be94-c7d8af589f02 | note | • Dual block sleepers shall also comply with the design offsets at each chainage
aa4387e1-01ff-59aa-801f-bcd7b396dad3 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
421af280-dace-5577-a813-afdbdb145ff6 | note | INSPECTION/TEST METHOD: Visual Inspection
b56d6101-d15c-5be6-8059-49678a55f52c | note | RECORD OF CONFORMITY: This ITP Signed Off
ed9a27b0-9a1d-5888-9bf4-c6a5bf5cac2e | note | IP
a1f91dad-7952-50b0-9bf6-439f2efe63a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a419f03-c656-5ff1-a660-5023ddf22fc5 | textbox | DATE:
1c631e1e-578a-43ef-9bb8-9f44fd09889f | checkpoint | 2.2 Placement of Rail
db1d57cf-0e11-5374-80c7-a7ba90d2a275 | note | FREQUENCY: Each Lot
d3f8a0aa-8c67-55e7-929a-5cf2b700bae1 | note | ACCEPTANCE CRITERIA:
4894d7a2-86b0-564b-81a1-86ffa9434541 | note | Ensure rail strings conform to rail plan
f712775d-8d7f-50a1-96c5-b78b606e0aaa | note | • All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
d55813af-cae5-501c-bc0a-6ab2190e63d3 | note | • Bottom of rail and bearing surface shall be clean of foreign materials before laying
670ba4e6-6238-59a1-b025-e19c343112b9 | note | • Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
36079b7d-6d25-545f-832d-6b78d4761da8 | note | • Geometry tolerances as follows:
782b0f96-c951-59d7-9594-bf8026a11248 | note | – Centreline location: +/- 3mm
ee655657-83dd-59fa-917e-fb7c9ec9db5a | note | – Level: +/- 3mm - Line measured (>10m chord): +/- 3mm
541946f4-b7fb-5e46-b071-6072e7bb9314 | note | – Twist (3.5m chord): +/- 2mm
2260fa2e-dd2f-5acc-89ac-e7c7d194f052 | note | – Cant: +/- 3mm
38b7db40-024b-56bf-887a-a6deab3b235e | note | – Gauge (open track): +3mm, -0mm
efddf516-1a37-5eca-82f4-5b7597159fef | note | – Gauge,Turnouts (opposite crossings): +2, -0mm
e52b8cef-b120-5919-adba-e0e37d89bff3 | note | – Gauge, Diamonds and ‘H’ Crossings: +2, -0mm
ea42293a-bed3-5118-b5e9-11f7b95603a6 | note | • Note: Cant shall be applied uniformly over transitions
4c6f2b9f-c165-5600-acff-5327e064e8b7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
4476a817-b081-5068-a678-14898f87b369 | note | INSPECTION/TEST METHOD: Visual Inspection
8a20974e-bd51-5d75-a9db-6eb184b665b4 | note | RECORD OF CONFORMITY: Completion of track charts
36f89d78-cc91-5acb-ada4-5f2a70f2ad13 | note | HP*
a7003db7-c302-538e-9180-23998c856924 | note | RESPONSIBILITY: Fulton Hogan Engineer
c66b666f-32f4-5e2b-9510-3d367f0f5136 | textbox | DATE:
21e36e42-f22a-40eb-a09e-e8d1e04982aa | checkpoint | 2.3 Placement of Jewellery
fd7a3ea0-aeeb-5a28-9518-3738346b0f19 | note | FREQUENCY: Each Lot
592104b9-8cc9-5648-b134-6f54d88bc7df | note | ACCEPTANCE CRITERIA:
75e5d90e-452d-5d22-a131-cfad40516ad5 | note | • Each sleeper shall be fastened to track with approved jewellery and rail clips
81949c41-e487-5f95-9517-8ccf6e4b21ff | note | • Clips shall be installed with panpuller or equivalent
7c9790e7-c26a-512e-bc3f-366cffcedf28 | note | • All fasteners shall be sealed as per agreed method with Yarra Trams
0cd89289-0778-527f-8e99-9e2d27d9941d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
39fc205c-9506-5761-b65e-8c4518e5f66c | note | INSPECTION/TEST METHOD: Visual Inspection
c100f020-fb1e-52c4-a391-692b959cb1ad | note | RECORD OF CONFORMITY: This ITP Signed Off
7a67c57d-5ce5-5d60-a351-99fd18695342 | note | WP
9ffb41b1-a7c0-5a84-afa0-5514cd5d4d2b | note | RESPONSIBILITY: Fulton Hogan Engineer
d64984af-80d8-53ec-b33e-4e58039aee4d | textbox | DATE:
fa5d72bf-fb56-4eb7-9442-6c2338c7854a | checkpoint | 2.4 Rail End Preparation
6520c8ed-7ab8-563b-8f2c-ac945f8dc478 | note | FREQUENCY: Each Lot
eb701765-5fe5-5491-9b9e-1bd08af6956e | note | ACCEPTANCE CRITERIA:
ef3331be-a510-5387-b4f9-6415b2cf9844 | note | • Rails shall be saw cut or flame cut
66bd05d9-f613-5830-a604-21a78692ddfa | note | • Minimum closure length from proximity of welds shall be 2m
934b1414-12e8-5e09-a0c0-ce37eb444450 | note | • Rail end conditions shall match (i.e flame cut - flame cut)
c04748f7-8cce-54a7-8775-f32c80b92977 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
6a48df45-8a34-5166-a989-2042be7b853e | note | INSPECTION/TEST METHOD: Visual Inspection
6031e11b-0735-5134-b4f5-cb8ab933f613 | note | RECORD OF CONFORMITY: This ITP Signed Off
ee50323e-f388-57f6-8c90-a0de7c663324 | note | WP
70fe89bd-c591-5b4e-92f3-23293c731f10 | note | RESPONSIBILITY: Fulton Hogan Engineer
ba1d898b-2636-51ef-9bb1-f65fb15dda48 | textbox | DATE:
9ebcb9ac-c985-4ab6-9049-366d01d1884c | checkpoint | 2.5 Welding of Rail
24bf2b42-4070-5626-838d-78d45fcd2128 | note | FREQUENCY: Each Weld
541bd01d-1feb-5613-8c5f-43ce15772ae8 | note | ACCEPTANCE CRITERIA:
b12593f0-3af1-5833-8141-c9d7ca9d51ab | note | • Joints shall be square across the track
84aea222-77e5-5d86-9af9-e710a3b38a1e | note | • Maximum skew at square joints shall be 65mm
9cf9638c-dab5-529b-9a49-73bba91bb8c4 | note | • Portions shall match rail type (i.e HHR, Ordinary)
5a89bb8d-7e8a-51b1-991d-b75313913907 | note | • Welds shall not be within:
fd4cd6ed-779d-5d6d-a063-b257535e0c67 | note | – 3m of another weld
32626221-d20e-5c1b-89e9-a5cfe89c6743 | note | – 3m of a rail end
aa20ba8f-dff0-5f1a-bfbc-b3b7bcd854ac | note | – 1.5m of a glued insulation joint assembly
8c5c9ff3-1401-5c5a-98f8-02a2749c102b | note | • Field welds shall be +/- 50mm from centre of bay between sleepers
30ce5beb-d597-5e3e-9f00-522f8bcf4a34 | note | • Weld Return forms shall be completed by qualified welder
bf67bd38-06c4-5d00-9c25-aafcce3f6581 | note | • Welds shall be grinded after 1 hour
7b331555-43a0-5379-bf48-0aeebb0a4c26 | note | • Welds shall be free of water
986ee10a-179f-56fe-a3ec-1455c1126e2b | note | • Post grinding, welds shall be cleaned for visual inspection
2cc9d23d-e78e-530a-8a4f-5aa8140adc78 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
e872a7d9-795e-5aab-b7ea-63a064dd4686 | note | INSPECTION/TEST METHOD: Visual Inspection
4d49d749-afd8-537e-a737-d968f5a8375c | note | RECORD OF CONFORMITY: This ITP Signed Off
09b1bd1a-5f80-51b0-8ca2-ebaf820f6469 | note | TP
f6187a2e-41fb-54ab-a7be-8f41f09c70df | note | RESPONSIBILITY: Fulton Hogan Engineer
bac10196-6c3a-5187-a312-5ef1b01f00a9 | textbox | DATE:
08e68919-3478-4a68-91d6-cac2113a1dc3 | checkpoint | 2.6 Grinding & Cleaning Welds
8c376fa6-863a-5156-a7ef-d4eae4f599ad | note | FREQUENCY: Each Weld
184cc1b9-2c97-5049-940b-9f8747228089 | note | ACCEPTANCE CRITERIA:
93b122d2-3a90-524f-bf44-af176b1f6692 | note | • The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring).
1058848f-292a-5c08-9fb1-6b8d3c9274de | note | • The grinding stroke should not exceed 500 mm to each side of the weld.Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
deee0f02-5705-53be-818d-0c1718e980ac | note | • The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
155f370c-c196-5a7a-8feb-ad6ab362e309 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
f3f12c43-2a88-58f0-ad8d-7d8584177fef | note | INSPECTION/TEST METHOD: Visual Inspection
d8930176-742e-5622-9fdf-36bde22fe704 | note | RECORD OF CONFORMITY: This ITP Signed Off
8fd45468-447d-5a93-9c76-ff56f557ad09 | note | IP
768a09bc-3c5e-5936-96af-464b698aabb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
f44b95d1-7ecf-510c-af69-4ad1dfe9c4d4 | textbox | DATE:
c26bfe7a-6a22-407b-8870-72b1570bb1ba | checkpoint | 2.7 Track Adjustment
d4b177aa-0861-555f-9b41-cec52507672e | note | FREQUENCY: When required
98921c26-2e06-5cea-87f8-c5edfe2f680d | note | ACCEPTANCE CRITERIA:
4a1be384-751e-5f25-824c-88d89503b7ea | note | Allowance must be made for expansion and contraction of rail to control stress.
aae339f6-bace-52f9-b449-e58058d5ef62 | note | The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with anapproved type of thermometer.
74961083-62c0-514e-817a-adef213000ff | note | In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
5655633e-6686-5b15-8c2c-0a116bb43efe | note | Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
d5e6d340-1153-5291-8bec-b77ef0eca6e5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
f60878cd-6883-5b28-9074-a571cbb383bd | note | INSPECTION/TEST METHOD: Visual Inspection
9447dec2-76d3-5b5f-bdfe-e1e22d04dd95 | note | RECORD OF CONFORMITY: This ITP Signed Off
9eef05a8-f497-500a-9143-87594b3c6309 | note | IP
b6f508e8-321b-52c5-ae3e-9a839c255180 | note | RESPONSIBILITY: Fulton Hogan Engineer
b96bb69d-444a-5a8d-9f56-5a555cc464c5 | textbox | DATE:
fe33f82d-7e03-4fb2-b2d6-c80e19557ab3 | checkpoint | 2.8 Track Bonds
00a27bb3-586f-5449-b5b5-6dc6cf6c73aa | note | FREQUENCY: Each Lot
ae55cb6b-b78b-547e-9107-08d7fc5c9078 | note | ACCEPTANCE CRITERIA:
0410b825-7510-56ab-92e9-c77a0329a1c4 | note | • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
0044ca8c-04cb-561c-96c7-752ff464134d | note | • Ensure bonds are sealed as per agreed method with Yarra Trams
f2d93732-9a9e-580a-8496-0919974899e5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
bb18a3a4-8b0e-5222-b868-00e08979b99e | note | INSPECTION/TEST METHOD: Inspection / Test Method
891b6129-4acc-550c-bbbb-42dafc22d734 | note | RECORD OF CONFORMITY: This ITP Signed Off
b2a76721-f678-5889-bcca-fbdc3548a495 | note | IP
6017e730-13e3-5926-99f2-eacd803b9fb0 | note | RESPONSIBILITY: Fulton Hogan Engineer
09b73312-724f-5a13-bf0d-b2d1a2faf039 | textbox | DATE:
1fc1df1f-deda-4b40-a8e7-a7bb49c2d9ee | section | 3 - Testing
d97e47ed-12b8-4f7d-be16-5072be6d98a7 | checkpoint | 3.1 Track Testing
380b4d38-59cf-53fb-a49c-2b9491893d69 | note | FREQUENCY: Each Weld
fd992515-0e55-5955-842c-71eae10e2a10 | note | ACCEPTANCE CRITERIA:
faee323b-e8b6-5acd-939a-11aac6280f34 | note | • All welds shall be tested by qualified NDT operator
a0bd9fb3-9aff-585d-8400-b816ebd21228 | note | • Failed welds shall be cut out and replaced
c029a1ec-cd28-5bbe-9168-8ae818e25ac4 | note | • Testing documentation shall be recorded and supplied to the superintendent
de2ce446-c03e-56f0-872c-20407c42cbcd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
e4a23fa8-2d96-528f-ba2e-0b0c6f115e81 | note | INSPECTION/TEST METHOD: Inspection / Test Method
2d757200-529f-5817-aa52-42d5309e51f8 | note | RECORD OF CONFORMITY: This ITP Signed Off
591f49e3-969c-5b62-b10f-77ba34675571 | note | TP
ed141fcf-1eb5-5874-9ac7-2c6bb18214fc | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
0c07b41e-cff9-5fe6-9173-31b457431926 | textbox | DATE:
0bd4e755-898a-4fc4-bff9-7a97cfa4176f | checkpoint | Final Inspection
bb6075ab-180b-52c5-902d-6756af51a345 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
74e77242-1f9f-5fc4-9208-4edecd1f318f | textbox | Print Name:
88b50e03-f51f-52fe-9531-42434547c4af | textbox | Position:
e0d81f1e-7814-59f6-a4c0-7160da1ee96a | textbox | Date:
392e700a-0e07-457f-9d5c-6df20c50074a | checklist | ITP-007 - Concrete Track Slab Pour Rev2 | itp | ITP-007 - Concrete Track Slab Pour
d816c0f7-b1df-4e84-a8b0-135f87e77d72 | section | 1 - Preliminary Works
8b7e3a7a-1c26-4ff2-9e3d-b88692e4e2f6 | checkpoint | 1.1 Check for correct documentation
da623a02-195d-5cc8-bb9d-848331945cc4 | note | FREQUENCY: Prior to commencing any activity
f882b465-7c94-5aec-b8ee-33997dc9c117 | note | ACCEPTANCE CRITERIA:
f408d9bf-dcee-5c86-b16a-c77f6d24a881 | note | • Ensure that all employees and subcontractors are:
07da9231-eee4-5b47-a1f1-920f74869379 | note | – using the correct and complete set of drawings
76ee42f3-06f4-5018-9769-b91c289112dd | note | – all drawings are the latest revision
cfd01961-9ffe-56d1-9452-ef808917cc2c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
946e2740-ba09-5632-ba3c-bf96e55b36c9 | note | INSPECTION/TEST METHOD: Visual inspection
6f1f4114-0319-5626-99fd-bf5db0bc2eb2 | note | RECORD OF CONFORMITY: This ITP signed off
967f66c5-e4bb-591f-a1fd-2e73f009434d | note | HP*
b2295147-3511-5691-bfc4-c858941ca5b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
22b1cb72-cace-58ce-a249-9da547c11856 | textbox | DATE:
5e2a8c67-ec8b-4d54-a1c6-56724d1f16e6 | checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
9e7cbbc3-deb9-5d2c-b288-476c67ad6887 | note | FREQUENCY: Prior to first concrete pour
876d56d7-f0e8-502e-bfbf-d0708b8cd6f3 | note | ACCEPTANCE CRITERIA:
763ac6cb-11fd-56bb-8510-da1da35c21a7 | note | • Concrete mix design submitted and approved at least 2 weeks prior to first pour.
b278e546-eac7-56c2-a0ed-ccde8d41f7ec | note | • Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
c08540de-a400-5764-81bb-ac6dedfac803 | note | • Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
4645dd56-daf8-50df-892e-85711f4f113b | note | REFERENCE DOCUMENTS: CE-019-ST-0033
4631ee45-28af-5cd8-beb5-cbbdf5a256b1 | note | INSPECTION/TEST METHOD: Verify
7d087f2a-2a5e-5a5c-bbbc-0815514632c3 | note | RECORD OF CONFORMITY: Mix Design ITP
7b246dee-1224-5866-95c8-51c40c6aed60 | note | HP*
3c5e65be-e60a-53a8-8a2e-433dc9c19324 | note | RESPONSIBILITY: FH Engineer / Superintendent
ebe9b3f8-4a6d-523d-b547-996c1ded0cc4 | textbox | DATE:
92c47959-556f-4807-addc-9a82406769ec | section | 2 - Construction Works
006a8104-c40f-46e1-acb8-3d6a85b22956 | checkpoint | 2.1 Weather Monitoring
fddb9bfd-4543-52a3-8e6f-191e7be8abfd | note | FREQUENCY: Prior to start
55b8c580-ab2b-564c-ab22-bfe758771e0f | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
ed39fe34-09a6-5d64-b875-ab3dd0356dcb | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
c49a9b1d-00c1-5a8c-8517-9c1fd5f2aec4 | note | INSPECTION/TEST METHOD: Verify
5106412f-fbd9-5e03-a469-66135b61bf61 | note | RECORD OF CONFORMITY: This ITP signed off
83c43ccf-7ee7-50df-b8ad-602ccc848cf7 | note | HP
11a32ef4-f50e-5d14-9c82-f9c84224ed48 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
539404fe-b6bc-54d4-9d00-e759eeab1aa8 | textbox | DATE:
d606af13-4759-4ec2-8eb5-6aa035b281d6 | signoff | HOLD POINT AUTHORITY
c56e2f7c-82ff-4a0e-aa6b-3d3f1391d877 | checkpoint | 2.2 Surface Preparation
37688fb9-01cb-5f20-bdb0-02d4c6798c4d | note | FREQUENCY: Prior to start
bb317480-2244-5caa-b798-48a1fafe88f9 | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
22fa3543-3552-56b7-bb25-efe05579f137 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
a46a1075-61a5-51c5-b1c8-313be48630fe | note | INSPECTION/TEST METHOD: Verify
f08cd20b-844d-50c4-8aac-694308b9449d | note | RECORD OF CONFORMITY: This ITP signed off
a75415ee-dfa4-5092-a748-406277451f6f | note | IP
4f2d9fdc-980b-5036-9d80-b9478fad958d | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
b19bc243-4421-554c-9514-bf1668d505e6 | textbox | DATE:
47762765-f5e6-4c3e-9ac9-e096cea3f90f | checkpoint | 2.3 Setting Out
4e5e43e8-7781-599f-b838-b8277d13b927 | note | FREQUENCY: Prior to start
f1b64c0d-9356-5b29-926d-42c39cc2fdfe | note | ACCEPTANCE CRITERIA:
e0cd6f89-a9d2-53f6-8213-7b062a19d3ea | note | • Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications.
9a1e3697-6d44-5451-8a22-658ef3467b4e | note | • No survey/level pegs to be removed by any persons until completion of works.
4fedf475-9254-5a15-b380-aaf49045ba73 | note | • Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
6230c80e-ea0f-596a-ba5c-fbf5b24ce1e2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
abd73cbd-5e19-5981-9fee-5d93fff9a9c2 | note | INSPECTION/TEST METHOD: Verify
2fa26f37-f158-545c-8763-be1eab7b873d | note | RECORD OF CONFORMITY: This ITP signed off
bdb64609-9cda-53a1-bb8b-30172e514263 | note | IP
87f8c103-7267-51df-8188-75e3985aa519 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
296e2bdc-daf3-554f-94df-3e039c1451ff | textbox | DATE:
434802ee-7f89-48ff-94e8-17d63f3e9a34 | checkpoint | 2.4 Preliminary Works Formwork
153d5e8c-d557-5ef7-9880-83b89f44b6cc | note | FREQUENCY: Prior to start
713d571c-6c9e-5d13-bf51-8cf7221ab080 | note | ACCEPTANCE CRITERIA:
bb00d26f-429a-554a-9c9a-9ce7316a5e50 | note | • Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
f9a94a03-c76e-50cf-b0df-36bcf6931dd9 | note | • The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
6ddbf664-6c32-5a3c-9cda-bc0990cc3147 | note | • Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent
d42e7ba5-4bea-59b9-b39b-621a6f4f5ba8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
c552fec3-4493-5072-bca4-2f18a730d038 | note | INSPECTION/TEST METHOD: Verify
d750bf38-c787-561f-ad2d-1a5edf5a3f8c | note | RECORD OF CONFORMITY: This ITP signed off
19062975-285c-5996-9688-b417bbe8f845 | note | WP
2a0157b1-c14e-5a11-9f11-2cca112767fd | note | RESPONSIBILITY: Fulton Hogan Engineer
4e9a9be5-1145-53a4-9b33-b00c24a1015f | textbox | DATE:
30bc8d5e-205e-4995-bc52-5f5d5144c140 | checkpoint | 2.5 Reinforcement
856bd8c7-e33c-52d6-bddd-85689f08d4d0 | note | FREQUENCY: Where Required
df6f01ee-0fcf-5253-aea0-54c3ac6de1eb | note | ACCEPTANCE CRITERIA:
d91bf87d-479c-592c-84a1-9ac20857af4c | note | • Ensure that all reinforcement is placed as specified by construction drawings.
66d6de07-1770-5556-bd4a-b03dd698cd66 | note | • All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
caa48137-23de-53ff-8fc3-21e8d23cd09c | note | • Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
82956558-82f3-5a1a-a994-21c63912c62d | note | • Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
abb464fe-4f91-5d27-9262-78eb8aa2c18c | note | • Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
cc829126-1fcc-57fe-a87e-baf1ab2aeb43 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
f0b61a55-2605-5326-b034-601edeb7a63a | note | INSPECTION/TEST METHOD: Verify
4737760f-13f7-51b9-87d0-5b744eb58534 | note | RECORD OF CONFORMITY: This ITP signed off
2e2de00e-ab16-5e60-af2f-575a811abac4 | note | IP
a4b7e142-4e05-5a91-aa57-eab8b47b1ebc | note | RESPONSIBILITY: Fulton Hogan Engineer
9d83033c-eb95-571c-98a2-84893f92c4d0 | textbox | DATE:
63f86f0c-1482-4685-9c0a-140565c7ae05 | checkpoint | 2.6 Dowels
349486b6-e4e7-50c8-a1cb-31c41dbe5253 | note | FREQUENCY: Where Required
7867be7c-34b4-50a4-9eaa-0d6c423c5f15 | note | ACCEPTANCE CRITERIA:
dc056be6-9217-5328-aa5a-1ed33f172472 | note | • Ensure that all dowels are placed as specified in the construction drawings
ce22260d-04d1-56f5-a4c2-1926042e548e | note | • All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
78fcc105-07c2-5aff-a3f6-c929d2d1f693 | note | • Dowels shall be clean and free from mill scale, loose rust or oil.
74ec8d08-789c-53ca-8b42-b7e7facdefba | note | • Ensure that all dowels are securely held in their correct position until the concrete has set.
2503dc0f-4aaa-5412-ad7e-5b015de3d0c9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
0b05ab62-1d5f-544b-8fd8-85bc940b83de | note | INSPECTION/TEST METHOD: Verify
fd78a592-ab0d-5f0a-a76d-5c5a93dd3a20 | note | RECORD OF CONFORMITY: This ITP signed off
dd0907e0-c0a2-55fd-89de-2d2c3c75bcde | note | IP
b8ec194e-1712-5993-81b5-6993cd7207e2 | note | RESPONSIBILITY: Fulton Hogan Engineer
b1de681e-10f0-55c8-9f0b-e62fe852c84c | textbox | DATE:
5d934988-df15-4410-a1ca-034f4ea45192 | checkpoint | 2.7 Pre Pour Inspection
7595135b-396d-505f-ae92-6320721c15df | note | FREQUENCY: Prior to start
659aba80-27e9-5dd0-8d62-d20285dec797 | note | ACCEPTANCE CRITERIA:
e9504930-7c77-51e3-a4a2-693ec9532f34 | note | • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
725c6e83-7006-5a8e-b9a5-0b038837d244 | note | • Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
65e348ec-dec3-5a90-a011-e0b1a3c5afa5 | note | • Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
94f17f36-ed9d-5ff2-9a79-3bfdbe3531ab | note | REFERENCE DOCUMENTS: CE-019-ST-0033
ada6659c-594f-5d81-be3a-7ed7a3f07654 | note | INSPECTION/TEST METHOD: Inspection / Test Method
79e187bd-7595-585a-8e16-b197ed6e52d4 | note | RECORD OF CONFORMITY: FH Track Inspection
54eb841d-2db9-5602-9a04-752a0ee465de | note | HP
8de0f025-2f32-5053-97a8-d3cf035f4c21 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
dc1a95ec-479e-5c23-ac5e-97f08fd9ea05 | textbox | DATE:
c4382ff7-3a48-4c7e-8bd2-7f2021aa803c | signoff | HOLD POINT AUTHORITY
fa63ce95-3aed-4d3a-a055-8d4bcac337e8 | checkpoint | 2.8 Preliminary Works Carry out sampling of concrete
d159a2bc-5aac-5449-bb8a-8d4d3343f10e | note | FREQUENCY: Each concrete pour
1f30f459-5a24-5518-b00a-a088134d6393 | note | ACCEPTANCE CRITERIA:
9ffa275e-8d3a-5aa8-8a71-a14e795dbcfb | note | Slump:
f409e95f-c07d-5c4e-8e1a-9a3263569342 | note | ○ Concrete Slump shall be 100mm +/-20 Compressive Strength:
4e44b77c-5857-5309-b38a-e898230b572e | note | • Shall be measured in accordance with CE-019-ST-0033
c5f4928e-5b27-5d83-b47b-310285ca6264 | note | ○ Testing frquency =
44ea80fb-8dc9-5cfe-9333-98e0372b6abe | note | • 0-50m3, 1 sample
8ca6b213-a325-5985-b91d-9615e8b97ddc | note | • 50-100m3, 2 samples
cde820e1-2a0c-5648-a32b-bfd0888c232a | note | • 100m3+, 3 samples
986eb4ea-7c00-5ecd-a258-e1c233bd318a | note | ○ Each sample shall consist of 4 cylinders
3241dcda-10a7-5934-be2e-c1e8b37e6dd0 | note | ○ Test Results will be provided to the Superintendent
13b94abf-7fd3-52a3-80d7-5e0a69e98b83 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
de9850df-9041-5612-b276-ef41528c4ea5 | note | INSPECTION/TEST METHOD: Verify
62581a55-6557-5ee4-95fd-64ebcc6e3691 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
f0d43b75-2edd-5cc1-b4bb-0e2e47692fbc | note | TP
38d1d668-55ac-5d8e-8505-031ff829f4b1 | note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
5f647234-cacc-5b1e-aaff-ed348591ca7c | textbox | DATE:
7eafd0ec-1291-4ee4-bfb7-512d7c759ce6 | checkpoint | 2.9 Concrete Placement
3c08400f-9400-5e1e-ab2d-9dc240edb6fd | note | FREQUENCY: Each Lot
5cbecd56-7670-5f98-b726-065385798e07 | note | ACCEPTANCE CRITERIA:
8845c671-f94c-5580-b9ec-34c8213704d5 | note | • Ensure formwork is clean
206657ef-5c13-5523-9e73-7126dc3b2ddd | note | • Concrete shall be entirely discharged 60 minutes after batching,
208ad92a-1d76-56f2-bf2b-6f0649e187d3 | note | • Ensure that pouring does not occur from a height greater than 1200mm
f2e86bb6-d059-56c9-95b3-d7046a15efbf | note | • Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
be961c01-332b-543e-acee-630f893d4b56 | note | • The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
bd35c7f8-d0be-5867-8233-61127d9d3662 | note | • There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
16ab02f2-09a6-5e20-8a5a-f3f5d1df8165 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
62800ce3-632d-5dce-8a23-32ecacfc30d2 | note | INSPECTION/TEST METHOD: Visual Inspection
47563973-c16d-5f5f-b7de-651d33c24491 | note | RECORD OF CONFORMITY: This ITP signed off
db5f3109-d899-5a59-be9a-78e29f029edd | note | WP
cbc36dd6-0a73-5e50-b2f3-64fcd23a302f | note | RESPONSIBILITY: Fulton Hogan Engineer
35835311-a566-58aa-913b-4e552bab9069 | textbox | DATE:
26d17f9e-6baa-4b63-b6d9-68a597b576c0 | checkpoint | 2.10 Compaction
8b13d60d-c330-5f73-b3c3-3e14310ed98b | note | FREQUENCY: Each Lot
5885daa7-199c-510c-a5bb-fe063e0481a8 | note | ACCEPTANCE CRITERIA:
c20c1eba-c2fa-553c-aafe-91693f4ebd52 | note | • Immediately after concrete placement, compaction shall take place with an approved vibrator
ecc22a7a-8dbe-57e0-b0b0-895c39d2b690 | note | • Vibration shall take place until exposed concrete surface is free from air voids
4b494ffa-a72e-56db-b40d-069a24251e4e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
e5858f3f-236f-5c08-b0c0-1f2ce70f4188 | note | INSPECTION/TEST METHOD: Visual inspection
d1605d42-c5d4-5102-ae1a-1967989600ab | note | RECORD OF CONFORMITY: This ITP signed off
88ad8298-5a10-5bee-a40d-3fb341c8d9e8 | note | IP
9beffd52-9583-5ddf-965b-c458a4c3cad0 | note | RESPONSIBILITY: Fulton Hogan Engineer
501786d5-ca93-5ee2-9765-d90e7142d879 | textbox | DATE:
6f92c0b7-735c-4982-a5a2-f440acea19c8 | checkpoint | 2.11 Record location of each batch
70d70acd-8207-5329-8e68-7600e1b29aa1 | note | FREQUENCY: Each concrete pour
112f16cc-ddbd-5eaa-a154-4d810a190998 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
feb02ac8-b29e-5163-86eb-09acaccd4dfa | note | REFERENCE DOCUMENTS: CE-019-ST-0033
7232cf55-53ba-5eba-b3fc-20626c5f919a | note | INSPECTION/TEST METHOD: Checklist
4753f193-32bd-50a1-bb37-b2257fb1d81d | note | RECORD OF CONFORMITY: This ITP signed off
c5ee5368-2364-5820-a653-e4fc3ade8046 | note | IP
6a86f560-a93c-5db8-9f2c-d650218e3a8e | note | RESPONSIBILITY: Fulton Hogan Engineer
4cc23669-ac84-5129-b07d-daef6535af47 | textbox | DATE:
2d9cd346-e83e-4142-aab9-a19329541ebe | checkpoint | 2.12 Curing
6bfaa850-068b-5dcd-9833-02d2d73bcbf0 | note | FREQUENCY: Each concrete pour
17512eee-e017-5452-95d0-bd62f6c4484c | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
6adbe97b-53ef-5d46-a35a-f1259a524738 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
67e712b0-628e-5c34-98db-6d2000a9dd93 | note | INSPECTION/TEST METHOD: Checklist
8180e0f6-b57a-551a-8db4-d1a8541565c5 | note | RECORD OF CONFORMITY: This ITP signed off
22cb404f-29b7-5015-891d-4ee040fa6292 | note | IP
f96b1205-7cb3-55e1-8a5b-4da3684320ba | note | RESPONSIBILITY: Fulton Hogan Engineer
a9b60ca8-df1a-5567-8615-1635e7f2c441 | textbox | DATE:
10920819-ce05-4179-b156-c6a446b7299b | checkpoint | 2.13 Tolerances
0fa08a55-052c-510e-9105-0dbb57771722 | note | FREQUENCY: Each concrete pour
eb004f46-277e-595a-afd2-ae47b4338426 | note | ACCEPTANCE CRITERIA:
b2ec4ce1-33d3-59a4-b407-3fb971642faa | note | All concrete shall finish true to the dimensions, the following tolerances apply:
ab1c3bc0-00c4-5c78-8368-0914bbf79c16 | note | • Plan dimension of slab +10,-10mm
fa48bcd0-cdd8-5079-b9cb-323f9c3265e1 | note | • Thickness of slab +10,-10mm
57f1a84b-f3d7-55a1-aeae-590d49927334 | note | • Cover to reinforcement +5,-3mm
146eab0c-742e-57fa-a966-20aec350999a | note | • Finished level of slab +3,-3mm
6de3f730-a467-5833-849d-a29e4fc0f138 | note | • Foundation level of slab +0,-20mm
6066ab88-55f0-50c7-bdfc-d1c575695eaf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
299389a4-7b61-580c-9302-b9356e1e7011 | note | INSPECTION/TEST METHOD: Checklist
ce112561-7635-59d0-b861-a044885f2a6e | note | RECORD OF CONFORMITY: This ITP signed off
5bc2968a-49dd-5986-baad-d5c1f1690ce1 | note | IP
b09a8220-c6f1-5395-a29e-8e6bd286f632 | note | RESPONSIBILITY: Fulton Hogan Engineer
feb85f66-767c-597d-9611-44ae8534457b | textbox | DATE:
4d8cdc57-0afb-46d5-8450-bdcac4062ed5 | checkpoint | 2.14 Preliminary Works Slab finish
a49027b5-2cbc-5251-b501-ffd78a4a67cd | note | FREQUENCY: Where appilcable - if track is Type 1 structure
55ad13b4-cb53-5ab2-8946-5123810cb490 | note | ACCEPTANCE CRITERIA:
95c70e0b-c629-5cd7-a4ee-a5d271149273 | note | • Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities.
3ff4d398-f8db-5993-97f8-b92ff262f903 | note | • All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
7afe6cd7-fdd5-588d-91cf-dc0309b30b12 | note | • A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
301f4cb5-0010-5914-8fe5-02ee74d084b4 | note | • The slab surfaces shall be broomed to provide a non-slip finish.
f2e00634-77b8-5c6f-9f33-2c33e833d074 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
7d309d11-93c6-5d8a-8ff4-bba0213368b8 | note | INSPECTION/TEST METHOD: Checklist
93e50471-263a-56a7-9cfe-5279bb19f529 | note | RECORD OF CONFORMITY: This ITP signed off
afcfcec0-5ab6-5bf9-9283-5e0193f267a1 | note | IP
8a2b2c2e-3e65-52e3-ac7e-b6194afa542b | note | RESPONSIBILITY: Fulton Hogan Engineer
6162f3e6-c690-55a7-8c6a-f935fc047dbc | textbox | DATE:
68aecfe1-314d-4d5d-a9a6-6a2290bf9b3f | checkpoint | 2.15 Post Pour Inspection
4a428604-1531-5fcd-99c6-d38e8df125f9 | note | FREQUENCY: Each Lot
b3e8e416-092c-592a-a4e5-f61216c94943 | note | ACCEPTANCE CRITERIA:
329bfe77-5570-54bf-8313-35cff188c792 | note | • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
23355c68-cf73-5ce2-8b43-137d038aee28 | note | • Ensure no defects are present in slab
a131b245-0bd3-536f-92eb-bc703727ae65 | note | • Complete Fulton Hogan Post Pour Checklist
38c2d995-2db9-5b12-8ea4-8ae1d95726da | note | REFERENCE DOCUMENTS: CE-019-ST-0033
214e0585-5d53-5ff8-a22f-d5729219a9e2 | note | INSPECTION/TEST METHOD: Visual Inspection
7fe7b8fb-b935-5d26-bb04-5250966bba34 | note | RECORD OF CONFORMITY: Post pour checklist
194f6ab8-1f58-5aba-a251-51a0aa209822 | note | IP
3a0f0283-bf4d-5f48-81bf-2f6ca4ff36d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
c4b69e3b-9706-5051-9d93-c80795b2096e | textbox | DATE:
4acfc0c9-64a1-4788-8713-f05d45a50594 | checkpoint | Final Inspection
358805e0-7c71-5807-8bc9-7011d48e1b06 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications
627f3738-85c9-53b3-b153-c6eefd37139a | textbox | Print Name:
eaeba2eb-ec3a-5cfc-b9b9-b6d1a5219dea | textbox | Position:
fc212994-23a9-5008-9855-74fad5260c98 | textbox | Date:
f3edb058-0f89-482e-ad4a-ea66af7d1fdd | checklist | ITP-008 - Hot Mix Asphalt Rev2 | itp | ITP-008 - Hot Mix Asphalt
52c1fe73-6c81-4067-8a95-47f415a0d055 | section | 1 - Construction Works
9ce87d74-9207-444e-8bcf-478ea75136e1 | checkpoint | 1.1 Submission of Mix Design
3c7d5a74-4fa9-59cc-b9de-2a80b0f383f6 | note | FREQUENCY: Prior to commencing paving
1e8ccf90-9d35-5559-bf28-bb356cfe1d92 | note | ACCEPTANCE CRITERIA: Ensure the correct mix design has been registered and is approved by Superintendent prior to laying mix according to standard track structure drawings
5c7aa9f0-26d2-5590-bd78-09776ebea4ac | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
db931383-e7a0-5379-86b3-051bd78e569c | note | INSPECTION/TEST METHOD: Correspondance of receival of mix design
5b75cd4b-2bd0-5209-8903-09c18f817fba | note | RECORD OF CONFORMITY: Superintendent approval Completed ITP
b9c2944f-c129-56bc-9747-6cfaca3e3017 | note | HP
681e9169-fb4d-59a2-ac70-e855b1d7230b | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor / Superintendent
4097e28c-0cb4-5d37-9db1-07704948aa00 | textbox | DATE:
ead1f852-1d69-4ebd-8233-6587e73d8bce | signoff | HOLD POINT AUTHORITY
5aafd120-be26-4304-9984-ace39ef74d78 | checkpoint | 1.2 Site Inspection and Base Condition
9d5137ff-87ac-5abc-9ef2-96264a988ee8 | note | FREQUENCY: Prior to commencing paving
c29d74a8-2484-5201-80a0-2016aa74496e | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
adc4ec6d-9cc2-54dc-a95a-5f1369633022 | note | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
0c8acdf1-c13f-574d-a43a-e1d086153683 | note | INSPECTION/TEST METHOD: Visual Inspection
d04b131a-8a80-57ff-b388-0485a90d9eba | note | RECORD OF CONFORMITY: ITP Signed
baf0933a-54a9-5603-be57-6d2d55cdd5ae | note | WP
4729ad8d-cdfc-5a9a-88d3-f9677ea78522 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
993126bd-393c-5ad3-9c75-77dea26b88bb | textbox | DATE:
e2163b8e-eb5f-4e4b-bf0c-8b5399ec4e18 | checkpoint | 1.3 Ambient Conditions for Placing
4a59601e-8715-54be-b076-e5b72c37a001 | note | FREQUENCY: Prior to commencing paving
9aac1bae-69c4-5a58-a82a-31693a7cb3d5 | note | ACCEPTANCE CRITERIA:
44bbd0ab-b0b0-5a36-99d2-3bf816fbca3a | note | • The majority of the surface area to be paved has a temperature greater than or equal to the following:
32f1c26b-c835-552a-9719-e286532ae680 | note | – Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
2456e870-6136-5671-a9fd-c9f4ab091e32 | note | – Wearing Courses: 10°C for conventional binders or 15°C for PMBs
6f9dcb72-d89a-5990-9869-b9508e45b70b | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
099f250d-9dda-59ff-aa00-ae70547bf988 | note | INSPECTION/TEST METHOD: Verify
3b11cf6f-fdbf-5482-bb46-3eddb72f122a | note | RECORD OF CONFORMITY: Thermometer
6db2748c-3c28-5f14-ab62-d3e5b12ac71c | note | IP
1828ad3f-627d-55e3-a51a-b08e30f8393f | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
37ee4f90-ed9e-54e7-aea5-4ed3f04c92b3 | textbox | DATE:
747e67b6-7683-453d-8e95-d5b520d49c15 | checkpoint | 1.4 Planning of Joints
28c924f4-7be5-582b-9f7e-5287d4dcbe61 | note | FREQUENCY: Prior to commencing paving
5a728779-ca49-54c9-9108-993b6806df4d | note | ACCEPTANCE CRITERIA:
ce1e8a2d-1704-582c-9469-cfb8163e6122 | note | ○ Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
d84b83d1-0a6d-557d-86be-e543fa2a4383 | note | • Transverse Joints Offset from layer to layer by at least 2m
4aadf958-2d35-576d-a8e3-4aa677ffabe3 | note | • Longitudinal Joints Offset from layer to layer by at least
02e4d722-fd84-55b0-889b-168020443efe | note | • 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
ec22bb5a-716a-5d81-b536-0d5493e0da13 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c) Pavement Drawings
b21775d5-9d48-5864-8249-6493685ba5e5 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
c1116d1c-18fa-540c-9567-9f0400f2a953 | note | RECORD OF CONFORMITY: Paving Plan
db96e033-dd2b-5026-bdda-4bda1d7d7065 | note | WP
0316f915-0495-537a-badf-8ea1775b97af | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
ec8187e5-22ec-56bf-8638-bfb24e68289e | textbox | DATE:
eb90047d-9f8b-4dc9-bf88-d2504d15494f | checkpoint | 1.5 Longitudinal Joints with existing Pavement
4f6a5bb9-c6c6-517f-9c58-48b8783ec6c2 | note | FREQUENCY: Prior to commencing paving
e9925f27-870c-5163-9293-0bdd69332a5e | note | ACCEPTANCE CRITERIA:
dfb7fbd5-cf01-5b23-a0bb-2abfe6299a9d | note | • Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
30bf793a-98b5-5869-b6bb-7de148cb49e5 | note | • Depth of step to be cut to the full depth of each indiviual layer.
7e763025-4b35-5c62-b08e-5f0c67cc404c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c) Project Specs. Section 3040.06 (d)(vii)
5cea51ad-2677-5c38-87d9-f5d96987afcf | note | INSPECTION/TEST METHOD: Visual Inspection
c96f4c6b-f27d-56d9-9a35-da52c0ae432e | note | RECORD OF CONFORMITY: ITP Signed
00b37b54-eb4a-5e61-8c1f-3a4d4077aad8 | note | WP
3c358c4d-c12e-5ac5-a4fb-e9ce7ce8e1c5 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
9718ba3f-737d-5022-9a2d-d42b8779c5d1 | textbox | DATE:
4831288f-8945-46e7-8d57-6587f1a4b64c | section | 2 - Asphalt Placement works
09e92ab4-48e4-493d-bb70-5a03f96bb317 | checkpoint | 2.1 Commencement of Placing
ef707d7e-1250-5ca3-aa31-f9ccb1db8783 | note | FREQUENCY: Prior to commencing Paving
78aca2a6-d74b-546f-a119-21a0bc0954e0 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
1a015b04-4c4d-5ac8-941a-c7617191de0e | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
19af8369-53b9-5a6e-92f5-76fe112922fb | note | INSPECTION/TEST METHOD: Visual Inspection
90236489-3370-5a72-82a7-57c529964cf6 | note | RECORD OF CONFORMITY: ITP Signed
f6e42286-5ddb-5091-b2e9-ea68365f703e | note | HP
b083fd84-1907-560e-a93e-685aff53ac02 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor / Superintendent
af4060a4-596d-5372-a85e-20691fa00488 | textbox | DATE:
5a76f65d-30a8-4373-a427-a1546a24cf18 | signoff | HOLD POINT AUTHORITY
066a912c-a82a-42bb-8f7c-ddf7a099727e | checkpoint | 2.2 Mix Design Confirmation
715e22b3-4876-5ced-860b-a76c1a9da9b8 | note | FREQUENCY: Each lot
aa987ecc-fc8f-5fc9-ad80-8f470f679eab | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt wearing and base layer mixes must abide to IFC drawings and be as specified in standard tram track drawings.
5f542931-f966-57da-a2c5-a62d0803da1f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09 STD_T9010
12e9bca9-dead-5adf-ba97-2ce68d67e260 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
4699e5cb-8de3-569f-b2e3-09933d42d623 | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
0088de17-89b8-56e9-8f81-95ae6287921f | note | HP*
c2acdf6d-a0da-585b-ab9b-8b5dfedbabc6 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
e37aea2c-893e-5084-a964-e0aebda7e992 | textbox | DATE:
043fa327-10a1-4a6a-bfff-b90e3f477410 | checkpoint | 2.3 Delivery of Mix
b16415b0-8a45-5cde-980d-05bf0c6371d7 | note | FREQUENCY: Each load
adbf83cf-e747-5ade-8641-6399b78ce5f3 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
037911d7-b282-5e44-adda-8b36f75b7e7a | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20 Table 407.111
56da7d1b-503d-529a-bcd6-847d2d68b8a5 | note | INSPECTION/TEST METHOD: Visual Inspection
52bf561f-44b0-5dc0-94fc-a61c96e11244 | note | RECORD OF CONFORMITY: Delivery Docket
9d12eb23-7832-50c1-a4dd-6dcd69b0b542 | note | WP
bc975bc8-d075-51c6-986f-ff99795438a4 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
8b021180-8e8f-57fe-902d-4a7dc5bf9af8 | textbox | DATE:
49595050-ad01-4523-a671-32948ea8d721 | checkpoint | 2.4 Traceability
9c8f22d0-0447-5953-9767-6165801a46a8 | note | FREQUENCY: Each lot
3391f3e9-c684-5d67-a89e-7eb61abee7cf | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
1d8be6b9-f383-59fc-aa4c-3750eb310dc8 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ddf03f5c-38a1-5b12-be0c-1dc60024eb47 | note | INSPECTION/TEST METHOD: Verify
e8589e75-6a45-5918-b419-c91c5e69d166 | note | RECORD OF CONFORMITY: Daily Lot Record
638ec7d6-40b3-5c10-acf2-8fa4598b3477 | note | IP
5f48aa88-93c8-5b6d-b756-fac2335086b7 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
064b67c7-0496-5c45-b8b4-5fa331be88d1 | textbox | DATE:
5912eb0f-17a7-44d8-8b50-be513abef043 | checkpoint | 2.5 Layer Thickness and Level Control
42451787-e5a8-5b28-b767-b58019b7bbfc | note | FREQUENCY: Regularly during paving
de8e04a8-391a-5bdd-87e5-923883369bd5 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
6eaee0eb-cd40-5564-865f-c01dc1611e4c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
1c5f88c7-3782-5eb6-8918-7ca0782c9822 | note | INSPECTION/TEST METHOD: Verify
0f624a6d-a677-58d6-a46d-120becbbedaf | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
a78ad95d-8482-5702-9a5a-b375e303ab4c | note | WP
646f6144-9150-55d1-a4d4-975c895a738f | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
4d290aef-d3a5-5713-96d4-435f8a5580f0 | textbox | DATE:
f1a38348-088c-4fba-b5e0-4c6b9298569b | checkpoint | 2.6 Surface Finish of Wearing Course
5f131282-68de-50bd-af0e-549f2abd3c66 | note | FREQUENCY: During paving and after final roll
b7da6a97-2ada-56b3-8c07-194b5a6f9e4e | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
b8336e7b-9f43-5eb6-bd8d-19d2ef71c37b | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
4bccd4ad-2665-52a2-b70c-eddcafecc099 | note | INSPECTION/TEST METHOD: Visual Inspection
d7c10bb5-6a00-5aea-8cd7-b95eed1f0fa8 | note | RECORD OF CONFORMITY: ITP Signed
6734527b-4359-5e6d-8eb7-06325a0302ac | note | WP
c9be4ce0-ab45-519c-8a7b-dce677132269 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
ee616819-cf06-53a7-8dfd-515b73037f5c | textbox | DATE:
22a3125f-689a-43a9-b9c5-7973bb6ca2da | checkpoint | 2.7 Alignment of layers not placed against concrete edge
c09a4929-7c0f-5eb9-9548-68c6cf0e88fa | note | FREQUENCY: During paving and at completion of work
0266c7c7-1aae-5983-b465-5127774c9832 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
c42fb1d3-ac8b-56e5-8dd3-dcb127bc3ff4 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv) Drawings
89612f37-d736-5e3f-8720-c6ef5143caa2 | note | INSPECTION/TEST METHOD: Visual Inspection
1a5b5df4-5976-5cec-a4ed-18bc3987afe4 | note | RECORD OF CONFORMITY: ITP Signed
b1d56df3-ea54-5775-8083-183378ae93c4 | note | IP
d10374cb-5788-5aab-a878-cc6017024869 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
2d822e83-42ef-50d8-90da-8e2793c594d3 | textbox | DATE:
ccc0c08e-f085-480c-89ac-70c5b1b17251 | section | 3 - Testing
ecb0fa6b-b1fd-4949-b869-c429ab9604e1 | checkpoint | 3.1 Compaction
eda76481-15a8-569c-8990-a78165b7ed0e | note | FREQUENCY: Per Lot
08eeaa51-d591-5112-96f3-3e79d8be703e | note | ACCEPTANCE CRITERIA:
507bc64e-dccc-59d2-8857-6f111eb74042 | note | ○ For wearing course layers <50mm, if characteristic density ratio is:
5401ebd9-629e-5b58-9516-af62d15f23c3 | note | • 94.0% or greater Accept lot
67387c2e-1808-5690-9237-651d2308efe6 | note | • 91.0% to 93.9% Lot may be accepted at reduced rate
3bc015ad-87e4-54e0-a80c-b57523bb1bd4 | note | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
376f3c0a-8999-5cbb-bd6e-75fb048fc7c9 | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
826fe862-ff3a-5cc0-836d-aa2540a4cf60 | note | INSPECTION/TEST METHOD: Verify
1438ce9a-eb69-5b53-91c5-6435103b618a | note | RECORD OF CONFORMITY: Test Report
e380982a-7db1-5167-b9cd-6304241043a4 | note | TP
e230ff84-9551-5dee-bade-15ce892b5a32 | note | RESPONSIBILITY: Site Engineer / FH Lab Technician
aeaf60f0-6800-5f3d-94c9-116ba20e94cb | textbox | DATE:
4179d23b-9e72-4a95-8e7a-eb7db415a594 | checkpoint | Final Inspection
9fd87725-abe5-54e0-8a2f-e60b9be13cdf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb5845a4-d4a9-5bbf-ba05-fbd8fff3d6f3 | textbox | Print Name:
a2110f3e-62fc-5b40-b807-ec9e1a5e159a | textbox | Position:
631a2c99-5ff5-546f-9bff-2a670c9deb04 | textbox | Date:
53b5bd12-b8f5-40dc-8e4e-c89205d23345 | checklist | ITP-019 - Line Marking Rev3 | itp | ITP-019 - Line Marking
c333197b-4b37-4bc2-877c-63e7e2a5cb41 | section | 1 - Preliminary Works
39c7a9a2-59cb-4f63-8560-f8486361a183 | checkpoint | 1.1 Check for correct documentation
859b73a0-bb32-5974-b0c6-d9d67f1fa0d3 | note | FREQUENCY: Prior to commencing any activity
d0838437-d108-5786-9497-c05f4d766c7b | note | ACCEPTANCE CRITERIA:
6a145315-a5e5-5db2-90ce-fad45952c11c | note | • Ensure that all employees and subcontractors are:
8aef68cd-e8b0-5e1e-87e2-73e420f34b8e | note | – using the correct and complete set of drawings
8c1930a7-e415-5626-820e-e58dd45dc675 | note | – all drawings are the latest revision
b0dc9599-008b-5f47-9369-08a4d13f483c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2ea4ddd7-0112-5561-b304-c2944702fae4 | note | INSPECTION/TEST METHOD: Visual inspection
42e68f4c-2741-5276-87ef-6a6de3c2de8c | note | RECORD OF CONFORMITY: This ITP signed off
b4d485c2-fa68-534e-bb3a-e6b6254c45ee | note | WP
88cdf8b4-4f5b-5031-93bd-da94e76d7eec | note | RESPONSIBILITY: Fulton Hogan Engineer
046ff6c9-c27c-53b6-9181-6e0935abf205 | textbox | DATE:
0c96f5de-02c3-4a3e-849a-fe73262a6e5b | checkpoint | 1.2 Implementation of all measures and controls
bd9b69b4-f21a-59e7-8154-ea5cd36a5d77 | note | FREQUENCY: Prior to commencing any activity
3d2459ae-44a9-5df3-aedc-ab19d2ef48a6 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
f46301e4-a551-52a9-a7b1-fb9c9180eac3 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
8e3a1bdb-7d37-50a5-893c-b29e23288035 | note | INSPECTION/TEST METHOD: Visual Inspection
dc4e04f8-7007-589b-af7d-c4e3dce91b8b | note | RECORD OF CONFORMITY: This ITP signed off
bd3d7976-870f-56d3-9a99-4fceb5868d93 | note | WP
35510ca2-e6c6-54d6-aeb8-aa8d63f4b6b0 | note | RESPONSIBILITY: Fulton Hogan Engineer
72da6511-8a34-5ec4-8b84-145ee0b32eab | textbox | DATE:
89e25256-b4c0-4d80-b4a6-6094e849c6e3 | section | 2 - Construction Works
5870b843-cc7a-4fc4-9150-be2cf80d4c5b | checkpoint | 2.1 Setting Out
f341e104-e201-593f-9fd1-a17703555d2a | note | FREQUENCY: Prior to start
b757428a-1625-5409-ba59-50fc03a95dc4 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
4f4c2d95-a2cd-5f02-8112-dbe090d7ff80 | note | REFERENCE DOCUMENTS: Drawings
e422bb76-cd07-5f33-8942-cb04ecb28c41 | note | INSPECTION/TEST METHOD: Visual Inspection
89345a0f-e9eb-5d01-a958-c90f2651cf8e | note | RECORD OF CONFORMITY: This ITP signed off
348a6e69-f992-5f66-9671-ac080920bf74 | note | IP
8fe8e4e9-f145-5aaf-b584-fed18f17f2b1 | note | RESPONSIBILITY: Fulton Hogan Engineer
fbb819ec-315d-5a4d-9d1d-ce3e2ac8400c | textbox | DATE:
37eba590-7fa1-4cb5-8683-d63c651990f8 | checkpoint | 2.2 Position of Markings
bbce3099-a8c8-57b5-9581-36cd8b505698 | note | FREQUENCY: Prior to application
86383220-3eab-5ee2-855a-c0ba8079d857 | note | ACCEPTANCE CRITERIA:
f6a719cd-21bc-5d68-9a84-99b1ffcd8052 | note | • Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
cea0e6b5-6a28-5590-8470-4533954f1014 | note | • Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the
6358ced7-3a5f-53cb-8abc-7a8a189932c5 | note | • VicRoads Traffic Engineering Manual Volume 2.
5ed37d5f-18ec-5b0b-9ee6-c75d7f36eeb4 | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010
7352d7f8-91f2-50a5-a8a7-8220cf01a711 | note | INSPECTION/TEST METHOD: Visual inspection
4184de50-1be8-5a76-a7e5-618fd096da49 | note | RECORD OF CONFORMITY: This ITP signed off
b5c2afaf-7649-5e55-ad84-192dcd35fff8 | note | HP
a20a64d8-d371-544b-9a54-1228b159095b | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
f64d78f6-79c1-5196-a095-a50b0156a94d | textbox | DATE:
c4566728-7da1-4a5d-9a47-e7075787ce14 | signoff | HOLD POINT AUTHORITY
6d4c6efd-67ed-489b-8563-115c6239bf6d | checkpoint | 2.3 Tolerance of Pavement Markings
76dc4ee0-089b-5893-93a9-9704e9cf481b | note | FREQUENCY: Each lot
9d54a281-1f70-5c82-afbe-587d39a8a758 | note | ACCEPTANCE CRITERIA:
4d5c504a-ca79-5ba5-9d4c-473e1e8ef371 | note | • The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings.
8fae1102-ee25-53ae-a9ad-bee2451b3334 | note | • The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
e033d5b3-cb1a-5eeb-8454-376b356ca3f6 | note | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
f761846c-b9a2-5750-89aa-1669f8ec15f2 | note | INSPECTION/TEST METHOD: Visual inspection
7970d78b-83a6-5968-bb55-40558571685e | note | RECORD OF CONFORMITY: This ITP signed off
715e19a1-deef-59d9-b73b-3a5779534036 | note | IP
740745fb-9631-5d49-9532-57967d40e0a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
777503a4-d222-5fec-ae4a-2d9750961ba2 | textbox | DATE:
2d277e33-31c2-4b77-adc0-5958fc38477b | checkpoint | 2.4 Preliminary Works Raised Pavement Markings
241b9a85-89d0-5959-aa2c-d2483ebb8513 | note | FREQUENCY: Each lot
0361b2a6-cda3-53f8-8fe0-d23d4f785fc9 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
48896ac9-5801-59dc-a96f-cc90d27fbb29 | note | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
d2057a55-517c-549c-aa45-c5f6533b68de | note | INSPECTION/TEST METHOD: Visual inspection
7f81f35b-d7d5-5362-8778-d0d0f497aeb7 | note | RECORD OF CONFORMITY: This ITP signed off
b58dbf16-9343-56a0-8125-5b583dea5ff7 | note | IP
2be56757-8984-552f-abb0-f80f1986575d | note | RESPONSIBILITY: Fulton Hogan Engineer
41d835c4-ab0d-5556-90c8-2ced6a32cbd9 | textbox | DATE:
85a9ea44-5e21-4d2b-833e-1c97cfc16f77 | checkpoint | Final Inspection
cfc8c898-358d-54e5-9d9d-fae1071d6f5d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d0932b43-5f8b-5a89-add2-9a92bbaeeb88 | textbox | Print Name:
45ce201c-9503-5812-b105-cbef59e45401 | textbox | Position:
f2db0e07-d575-5cda-a2b9-d2542156b444 | textbox | Date: