## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
f929064e-568a-44b8-9265-f24f2a8a1d28 | checklist | ITP-001 - Subgrade Preparation Rev2 | itp | ITP-001 - Subgrade Preparation
001dd911-d937-48b2-98d3-800d71131449 | section | 1 - Preliminary Works
08e0024d-231b-4647-9a6e-d43302fb49fd | checkpoint | 1.1 Prior to commencing any activity
62f9d2a2-eb0f-5668-a613-e424ef6d3bfc | note | FREQUENCY:
d1deab9c-1c5f-588a-bb14-8b70511a5ce7 | note | ACCEPTANCE CRITERIA:
1579c397-9798-5825-be1e-814e75f24c77 | note | • Ensure that all employees and subcontractors are:
106e3cdb-ff1c-54fb-9698-e73a571a32a1 | note | – using the correct and complete set of drawings
0734c511-b115-5d62-b9ac-44a90f4937f4 | note | – all drawings are the latest revision
0ddf6bb1-41dd-5e60-a227-f2fcb0938263 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
73a3f299-75e2-5df7-8a02-8f600426869a | note | INSPECTION/TEST METHOD: Visual inspection
da8a8733-2ce8-5f1f-86ee-e504c77e76f8 | note | RECORD OF CONFORMITY: This ITP signed off
4e76c56b-50ee-5eaa-89cd-a866be104203 | note | WP
e4bc8fea-7824-5a24-a472-3acf23feaf9d | note | RESPONSIBILITY: Fulton Hogan
77e8f216-8afd-5162-9926-208f3cdabaca | textbox | DATE:
e14f2d41-5934-4e94-b41a-356c38a4340d | checkpoint | 1.2 Implementation of all measures and controls
f122a68a-35cb-5b64-835c-26e7638f23d9 | note | FREQUENCY: Prior to commencing any activity
b59eee26-c887-5111-abe8-cc1f482e5c2e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
696a264e-24dc-5277-b46c-5dc95b4190fd | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
e3c12262-f245-5553-b3c6-a36159b175f8 | note | INSPECTION/TEST METHOD: Visual Inspection
04fe345a-688b-56aa-ab33-7f70914e6bc5 | note | RECORD OF CONFORMITY: This ITP signed off
b5b255c7-1f7f-56ce-a8c9-3bffe07da55e | note | WP
e4fa5ec5-eb0d-58e6-8d7e-30f8176caa7b | note | RESPONSIBILITY: Fulton Hogan
8ea1ef1d-bca5-51a3-85fb-e223293bb64c | textbox | DATE:
89b1c2e3-80b1-415f-b4b7-f68a08c4ceb3 | checkpoint | 1.3 Selection and approval of Disposal Site
7892b0ae-154a-5f04-be8b-da8253677e7c | note | FREQUENCY: Prior to commencing any activity
e8301558-c3f3-5870-85ba-07ee8f58e5ca | note | ACCEPTANCE CRITERIA:
883c2214-a136-5332-820b-a871f747e7f8 | note | • Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
4294df9a-93f3-5892-a985-666f23a3d0ba | note | • It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
fa799b54-8fd5-5e73-a1cd-44bdb5a8768e | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019ST-0033 CL. 4.2.1.5.
c58f5fe8-4d8b-57aa-9c7c-68f2f7415a23 | note | INSPECTION/TEST METHOD: Verify
78b91ef3-1683-5bab-a89f-5f19cda169d5 | note | RECORD OF CONFORMITY: This ITP signed off
782a07ef-35f7-563c-98a6-13a22cc9a8be | note | WP
96f78f6a-d6d1-5547-9ea1-f0b7cd36ddb1 | note | RESPONSIBILITY: Fulton Hogan
ee8f6c8a-c918-5fd9-8091-a94761fe2b6a | textbox | DATE:
165cd49f-4c12-478d-8bd3-99ed859ad1aa | section | 2 - Construction Works
6ead4c3d-1f76-4041-98b9-735797e5e66a | checkpoint | 2.1 Excavation
04a24fd2-5b00-51d7-a9ca-c9aa717f319a | note | FREQUENCY: Each lot
efb94f2e-cd37-5320-8a6e-d0de104247e9 | note | ACCEPTANCE CRITERIA:
baa863f2-d1c9-5a5c-b146-8343f22e29d3 | note | • Plant and equipment shall be appropriate for the task.
9c40d5dd-dc67-5291-82d7-3ee417c0d39d | note | • Excavation operations shall not disturb areas outside the limit of works
c2d626ef-e9a1-518f-a3de-79624e2d314e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3., 4.2.4. Subgrade Preparation Work Procedure
0f3001c4-d5be-5e9c-9fd3-8d6ee43abf80 | note | INSPECTION/TEST METHOD: Verify
06a955ff-b6d8-5e17-96cf-92e5f236b8ac | note | RECORD OF CONFORMITY: This ITP Signed Off
f026da7f-121b-5bdc-8149-f050f061d70a | note | IP
2635c1b0-40d0-53fe-bb25-835a7dc906e3 | note | RESPONSIBILITY: Fulton Hogan
2fc52efc-3c8d-503c-8f9c-dbaaafb5fa9e | textbox | DATE:
802ca758-3ed1-49cc-b623-d176b80ca889 | checkpoint | 2.2 Reinstatement of bonds
b2f18abf-29ff-5c3c-8b2b-617b0b15d20d | note | FREQUENCY: –
1611c3e7-3fd9-5250-835c-4f5d3dabcb40 | note | ACCEPTANCE CRITERIA:
c56f39e4-6f45-57e0-82a0-4e725de86474 | note | • Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
ba86160b-c645-526a-818d-babb46b3cb50 | note | • All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
2db21435-71e8-55f6-94ff-0ae774c83bed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
b05afce8-1d41-5aef-9b80-4cb06cea6376 | note | INSPECTION/TEST METHOD: Verify
47abd4dc-af42-5443-a15b-f395a277951a | note | RECORD OF CONFORMITY: This ITP Signed Off
7b78c6ce-2524-5562-b24a-7198fd2e4651 | note | IP
1b1bf03c-2c0a-5a77-ac2b-045cbe47602a | note | RESPONSIBILITY: Fulton Hogan
21166443-ea74-569e-900e-144e71da9eae | textbox | DATE:
aa819b0f-1537-40ff-8ff0-f28640a7253e | checkpoint | 2.3 Inspection of Subgrade Material
9e19d421-f547-5b12-b685-5339217907b1 | note | FREQUENCY: Each lot
6db22b10-27f3-59ce-acd5-9ca5c8f8ba01 | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
5da3edb5-abe4-565e-bd14-4f32ee34d3e7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
cfa6d697-5076-5877-9dfb-4d1e1f694f91 | note | INSPECTION/TEST METHOD: Verify
fe75f356-711b-5278-84ba-856975c88e52 | note | RECORD OF CONFORMITY: This ITP Signed Off
2f4cbba4-8165-5e31-89fd-9360b2b07247 | note | HP
5514190b-9b13-5929-a8da-70c531b745c0 | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
d6d7c255-3e25-5623-841c-ba0fdb9c2169 | textbox | DATE:
8d227978-c3fd-4821-9092-b79b3a2a723d | signoff | HOLD POINT AUTHORITY
de70ef90-206d-417a-bbae-d4a027f4aa30 | checkpoint | 2.4 Width and Level conformity
a94a2e99-32c1-5406-8109-bec445d72519 | note | FREQUENCY: Each Lot
5b68f9bf-3a2e-5301-8d68-fa6d3f28eaaa | note | ACCEPTANCE CRITERIA:
37e97c70-0483-572a-8ed3-d3d8f2f8a989 | note | • The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings.
bb29ddde-bd63-5bba-bac4-9e4b46f82e37 | note | • No point in the general surface shall vary more than 12mm from a 3m straight edge.
1525af19-3354-5a0b-aa93-4625836b8e10 | note | • Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
78c26b8d-8d93-5c84-a9b7-4d659afd965f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
05b5309a-e090-5069-8281-6f28f3100869 | note | INSPECTION/TEST METHOD: Survey Report
2b4df271-387b-5333-9d89-792db466b974 | note | RECORD OF CONFORMITY: Survey Record
d69316af-172f-51cd-9f5d-29ae147e860e | note | IP
e31c514f-1589-5939-a702-b18e3976e687 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
91b5070b-f523-5c2f-86b4-837a5523bdf6 | textbox | DATE:
9354554c-477f-46cc-80f3-fd6152b7dbb3 | checkpoint | Final Inspection
982e8627-7db0-5628-bc49-d17e69663b91 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e0019a79-27e0-597e-a9f1-a27028318fe2 | textbox | Print Name:
9af4c584-2dc1-5ed8-900b-5cacb3c76a9e | textbox | Position:
240943ab-196e-5849-a9b3-471e09479da2 | textbox | Date: