## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
5c9dd9ae-5d73-40a9-950e-78a5209e1f91 | checklist | ITP-004a - Class 2 Base Course Placement Rev2 | itp | ITP-004a - Class 2 Base Course Placement
a58d392b-8507-40de-9d14-3b67c45a49a7 | section | 1 - Preliminary Works
a0bc2d42-8bdf-4ec6-9419-cfdd9492eb6b | checkpoint | 1.1 Check for correct documentation
cfc7655d-31c0-5ef5-9b85-4c1b13e35450 | note | FREQUENCY: Prior to commencing any activity
877f7fa9-4440-5784-a2c8-ff7bac9f47b6 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
f8b78a94-e4ac-588c-ad41-0a17b533ea6b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8fbb0231-0f9f-5ada-97dd-09062d57d0cc | note | INSPECTION/TEST METHOD: Visual inspection
3c2e8f40-9c97-5315-9a51-b2f35bc9a093 | note | RECORD OF CONFORMITY: This ITP signed
b244c56e-594d-5115-9d53-662078c07aff | note | HP*
69edf44d-eea9-5f41-927a-da07444e7b58 | note | RESPONSIBILITY: FH Engineer
fd19d9fc-3881-54d1-b8a9-b70957a4ef5e | textbox | DATE:
8ba63960-72ad-4383-bedc-6a5e1372d6dc | checkpoint | 1.2 Implementation of all measures and controls
81499de5-c2ea-54ff-99a6-394c122a494c | note | FREQUENCY: Prior to commencing any activity
f033dcb3-ab7a-5857-9b95-9f5491bff488 | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
99004b8b-70de-5e30-b481-efc1041a83f0 | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
29e229c9-c2c9-544b-8d0c-b05f2a97423e | note | INSPECTION/TEST METHOD: Verify
f0511825-d3d7-5f4f-b8fe-9ad6cfbfe248 | note | RECORD OF CONFORMITY: This ITP signed
41f03478-21c6-5aef-be12-bc84ae2bafd3 | note | HP*
03436fbc-38f6-558e-9495-f3e9bd2c4017 | note | RESPONSIBILITY: FH Engineer
1b6845b7-a41d-5132-951b-8b9701356648 | textbox | DATE:
87d949dc-2830-48c0-b747-8a917df29c15 | checkpoint | 1.3 Material Compliance
ebc0ad7e-0456-551e-9108-304475bfac37 | note | FREQUENCY: Prior to commencing any activity
1a030818-daf6-5f04-848e-55bf6e19538e | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
28a65559-40f7-5ad3-aafa-c956e08804c7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
bf9ca5f6-e30c-535b-ba40-7ce54b6e4a11 | note | INSPECTION/TEST METHOD: Document Review
6641289e-a7c0-5286-8c12-94256845e0a2 | note | RECORD OF CONFORMITY: Test Reports from supplier
33e4dd9c-9921-59e2-9e88-06b30e17a1e6 | note | HP*
ebcda4f4-0f98-51b0-9118-753cf1627287 | note | RESPONSIBILITY: FH Engineer
b30d4ba7-737b-5463-81db-08d011866f06 | textbox | DATE:
c172d805-d207-43d4-aed3-7c9670e3552f | section | 2 - Construction Works
c42f5f2d-b785-411e-8046-58394baa62b5 | checkpoint | 2.1 Sub Base
1931267d-5f09-547f-b16c-5da4aba88d9b | note | FREQUENCY: Each Lot
12dc0943-5075-5493-98ec-9a0913072a6d | note | ACCEPTANCE CRITERIA:
48c7c843-5094-5515-b8cc-3eb2160e7b27 | note | • Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
256db458-d0da-582d-8e25-aaed8a6e205f | note | • ITP-001 HP for subgrade inspection signed off
b03c7a17-7d05-569d-99c2-6439ed0c4630 | note | REFERENCE DOCUMENTS: VicRoads 173.03
6da3be09-e99e-52cf-a3b3-c5e6a1efaf31 | note | INSPECTION/TEST METHOD: Inspection / Test Method
03092c90-505a-5fa3-9c1b-dab4a78237a0 | note | RECORD OF CONFORMITY: This ITP signed
983dc9a8-2f1a-55ed-99f7-ca07a0918aea | note | HP*
94dedd20-06df-5e6b-a341-25b18c15719e | note | RESPONSIBILITY: Fulton Hogan Engineer
41ad4f56-063a-58ac-acc0-296ceaf1b53e | textbox | DATE:
a1a5d84c-f77d-4e4e-ae09-f4a9321a5261 | checkpoint | 2.2 Spreading material
84ac2692-cdef-5671-9456-e16195efb4bd | note | FREQUENCY: Each lot
ceff4e8b-e578-54d7-b1c8-3b6f36615167 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
3eae7764-84fd-5b6c-b1d2-126190303569 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
c34e6c29-1c2b-519c-9410-96334de72c6c | note | INSPECTION/TEST METHOD: Visual Inspection
ac44c65a-3739-5c7c-bc54-763cdfc87946 | note | RECORD OF CONFORMITY: This ITP signed off
c7644079-7a2e-5d70-9010-a355eb42c336 | note | IP
516c3949-346f-595e-9d89-48ba7a4c3687 | note | RESPONSIBILITY: FH Engineer
5156023a-c1c9-5204-bdf4-53c2d98ad483 | textbox | DATE:
572e7028-e482-4943-ad91-e52782625161 | checkpoint | 2.3 Compaction
673e7657-0522-55cd-a622-dc41073ef5dd | note | FREQUENCY: Each lot
c8f0e426-c1dc-5ec0-9fc3-e492f4cb10c9 | note | ACCEPTANCE CRITERIA:
a509639f-6459-5ddb-b58e-5c9952d38def | note | • Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
bb9dbfae-479a-520a-8638-eaac678a6126 | note | • Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
5960acb8-3e6c-505b-a1ac-336eaf54b8ef | note | • Compaction testing shall be carried out once per days production and shall comprise of three samples
86fce273-ce6e-52b3-aaa2-0d6835f03983 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
dfd3fdd1-1332-55f5-8912-2467ce47fdd5 | note | INSPECTION/TEST METHOD: Visual Inspection
9ebae320-ea6d-5604-a88e-aadcff2b330e | note | RECORD OF CONFORMITY: Test Results
4b82f3d3-37bd-57f5-90f0-c99c7edbed38 | note | TP
944594dd-90fe-5726-b182-d9c206975c1f | note | RESPONSIBILITY: FH Engineer
21f839e9-dbe8-50d9-905e-787b53f5424e | textbox | DATE:
e6117e45-8595-44e6-ae79-c6b1c18d4864 | checkpoint | 2.4 Level Checking and Conformance
d56a8dd0-cbc5-5337-b8d8-43e4f2d86673 | note | FREQUENCY: –
5575175d-22d6-5214-a176-e98f03bdc4cd | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
e611c6f5-4751-5c2d-b9ad-a8cdd69b68b0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
985d9c8a-91ca-5086-a6a3-09396f04505a | note | INSPECTION/TEST METHOD: Verify
cd98ffe2-3de9-57d7-aaf0-52996d1b5ea5 | note | RECORD OF CONFORMITY: This ITP signed off
7a325358-5e60-5ce0-8540-8ae1c855f6ff | note | IP
aa6504a8-6c3d-55cd-beab-9345ff21957b | note | RESPONSIBILITY: FH Engineer
f6cc034f-6986-54d4-8344-9de2cb47192e | textbox | DATE:
f182fe4e-a413-4ec4-82d3-d06dc37b9fbb | checkpoint | 2.5 Finished surface
4693e9a1-a7ce-5bfc-8da9-072d7c390a86 | note | FREQUENCY: Each lot
4d20fba5-5d41-5dcd-9a95-4ac8e377977d | note | ACCEPTANCE CRITERIA:
925c6e80-b4c8-5971-a3fd-20af26a5da0e | note | • Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
a199d8d7-19d3-5b31-a4fc-e1592c050bee | note | • Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
6b76877c-f125-582a-9763-1d9b46a8f714 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.2.8, Contract drawings
a6146de9-63ab-5fd8-b760-dcb3f722a84b | note | INSPECTION/TEST METHOD: Visual inspection
c00f6a9f-01d2-5e18-ab68-4473fb53beb9 | note | RECORD OF CONFORMITY: This ITP signed off
ec355f4a-79fe-55d0-bcd5-fcceb0d0e493 | note | SCP
aed36dce-5bc9-5fe9-9e63-ed0dca903c81 | note | RESPONSIBILITY: Surveyor / FH Engineer
dfe46485-20a0-5e51-b688-aec1711188c8 | textbox | DATE:
93e27ce4-99e1-4d66-9166-5e0ee7344ec8 | checkpoint | Final Inspection
5bc85d36-b360-5cf7-b83b-e172be71d23c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e6de64b2-703b-5106-b870-c404047499c8 | textbox | Print Name:
a0b9fbd1-9a45-56f2-87d0-e2fb12b7ffee | textbox | Position:
ccf506c9-7755-5475-bbb8-b581f86b8f59 | textbox | Date: