## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
a563a155-1a21-45f9-8d21-358c5ace7ef7 | checklist | ITP-005 -Track Drains | itp | ITP-005 -Track Drains
28dc7dd8-264a-4baf-94a8-6c3cca55f804 | section | 1 - Preliminary Works
2ed9b094-7e3d-4e4b-a438-ffa3fd5fd2f5 | checkpoint | 1.1 Check for correct documentation
2a0a260e-6f85-54a1-b1f1-969b5fd32fd0 | note | FREQUENCY: Prior to commencing any activity
33e51d44-8297-5ae9-a818-bbafe2bf426d | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwaded to the superintendent
56fb834a-49d5-59c4-8002-fc1f95cb00d1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
304930ed-bcea-539e-b8e6-55b6ff33ff22 | note | INSPECTION/TEST METHOD: Visual inspection
6ec65096-2e14-549b-aa84-2b724d3b3705 | note | RECORD OF CONFORMITY: This ITP signed off
1a3b062d-70da-52df-bcd7-7497a61f0ac9 | note | HP*
b954a024-da7a-5989-90a0-3e1fa0ede1d4 | note | RESPONSIBILITY: Fulton Hogan Engineer
4b8c11da-f012-5919-8e0b-f24482093151 | textbox | DATE:
7e8efe72-068d-49e9-8653-35d95f5b1d04 | checkpoint | 1.3 Materials Check
906c90ea-da5c-593f-bf60-408cfccb9e67 | note | FREQUENCY: Prior to commencing any activity
20eafd1e-d5c3-56db-97b3-0a87e06016a1 | note | ACCEPTANCE CRITERIA:
f8bb0c34-0b1b-5a29-83ec-3d0dbcb7082c | note | • Ensure drainage pipes are of correct classification and are without damage
f33c625d-53e8-5b08-80a2-75b15f8f9e3b | note | • Check triangle drains are of adequate quality, and are design according Ri57A rail profile
56667528-cb83-53f7-ac1b-7c2536921ffc | note | • Ensure lid and j-bolts being used are in accordance with STD T9022
5061905d-9d55-53a3-b634-c9ebbe7a3f63 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
542479bf-95f8-5fa1-b429-16c4b3a77099 | note | INSPECTION/TEST METHOD: Visual inspection, Inspection Checklist
cb7a08f9-ab79-5a60-b022-4be9e12f4aa9 | note | RECORD OF CONFORMITY: This ITP signed off, Recievable Inspection Checklist
bcde4652-4b49-56fe-8e0a-3a1692f04803 | note | HP*
c84eb8e7-1a88-50f0-a790-3cfd616c7124 | note | RESPONSIBILITY: Fulton Hogan Engineer
415d66c1-303a-5c31-80ef-c7faf3554bd5 | textbox | DATE:
ef9ed69c-d7b7-45f5-88dd-6e7debe8c2c9 | checkpoint | 1.4 Bedding Sand
84dab116-e1ff-5ad1-aa75-9f915b5d9032 | note | FREQUENCY: Prior to commencing any activity
2bd41323-99ad-538c-b021-3fe39762ba9c | note | ACCEPTANCE CRITERIA:
48cdd688-0a69-5eb7-82ec-a606456d5a0f | note | • The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following:
d9a59f6e-51c3-512c-ab59-bd97e8974560 | note | • Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities,Consisting of hard durable particles, and well graded.
aba81991-e612-57e1-86c5-635c65519828 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
6befffa5-90e7-5588-a927-eba9460a63c8 | note | INSPECTION/TEST METHOD: Visual inspection
e6f64653-3e60-5ffa-be8a-67f4222e33ee | note | RECORD OF CONFORMITY: This ITP signed off
1f5d64e5-5d39-5ef4-a94d-349fde006fd2 | note | HP*
577ea088-0746-5502-8e15-027ca5ce09bb | note | RESPONSIBILITY: Fulton Hogan Engineer
ee763750-562b-5de5-a5cc-fdedd8845aba | textbox | DATE:
910fd00a-c512-4cf8-ab84-4e9e9220d618 | section | 2 - Construction Works
fa4c2b33-3d57-442b-a957-fa512a32278b | checkpoint | 2.1 Set out drainage
853356a7-92b8-5218-87f7-e87b8bfee7de | note | FREQUENCY: Prior to commencing any activity
c41b2925-f8d2-5312-8d5b-20515c2f21c9 | note | ACCEPTANCE CRITERIA:
83a4a16c-f976-5002-b3ac-a5171040a192 | note | • The position of all drainage lines are to be confirmed with the superintendent
6eb2a5f5-9bb0-586a-9f44-f44326f7347a | note | • Track drain locations are to be identified and based off IFC drawings and sections.
75ed57c2-6252-571a-b0e7-af5f895204ab | note | REFERENCE DOCUMENTS: Design Drawings and Register
69f4ce93-ea1e-52af-a99d-0a9eda1bf4e8 | note | INSPECTION/TEST METHOD: Visual inspection
f531681e-e2a3-5f9c-bb53-162909c23ebe | note | RECORD OF CONFORMITY: This ITP signed off
d772f973-5a24-5b53-a101-454d05f2a4bf | note | HP*
51399e3d-3c46-5807-ba7e-de163b685560 | note | RESPONSIBILITY: Fulton Hogan Engineer
8112d44c-c88b-5c3d-a177-6f8059e339eb | textbox | DATE:
8299c231-888a-4272-a7c9-81bb40e4d403 | checkpoint | 2.2 Excavation (pipes)
8950d38c-76b7-5c14-9d88-ddc030b68b58 | note | FREQUENCY: Each Trench
1429795c-1eeb-5be8-91a5-8d9fdadc059f | note | ACCEPTANCE CRITERIA:
3fb56a77-318c-532f-b85b-e8ee46e2447c | note | • Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe
4ebbaa4c-c42c-54c7-b109-ebc80719164a | note | • Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
b062b583-0b18-5d09-a042-28cf4b43ef64 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
cd0a65d9-dce0-52d8-870b-7a4aa5dd78cd | note | INSPECTION/TEST METHOD: Visual Inspection
398beb1e-f81e-54dc-949e-a28635ea31a4 | note | RECORD OF CONFORMITY: This ITP signed off
c6185d67-229c-58cb-9145-db87c36af4ee | note | IP
d1821562-2541-5373-aee7-1f4dd13c4a89 | note | RESPONSIBILITY: Fulton Hogan Engineer
64ba9bfa-190a-5b8f-88f5-a570a075c2d2 | textbox | DATE:
255e607e-f341-462b-b452-021c3b2da001 | checkpoint | 2.3 Bedding
88c3073d-04ce-502a-9197-b1132fa421cb | note | FREQUENCY: Each lot
2589139a-7c1d-5317-94b0-9cdc03fdc1b5 | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
204cf9dd-513b-52a4-a1c7-640a2a1d00d8 | note | REFERENCE DOCUMENTS: STD T9021A
5467c70d-e4a6-5390-80b9-f82d2fd9611a | note | INSPECTION/TEST METHOD: Visual inspection
1e527b60-b87c-527c-97bf-d857784e4fbc | note | RECORD OF CONFORMITY: This ITP signed off
3fc05fe8-7c31-59ba-9e56-afef071590f3 | note | IP
31027811-b127-5672-b6e8-ac3c565b29b4 | note | RESPONSIBILITY: Fulton Hogan Engineer
e314e674-2629-5c33-bd21-8d5e2deb4e88 | textbox | DATE:
72ce173f-77a8-4d30-b261-c7a426d4d5ff | checkpoint | 2.4 Joining
5c138dab-ca1d-5ac9-a0b1-9bc218860f2b | note | FREQUENCY: Each lot
624876a9-09a6-5e44-9e9c-ccb7082d79f8 | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
b0fafc96-de50-519f-a749-44b6cb444b97 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
3a1fc85b-fd08-5174-97d1-b4f00aa6db5c | note | INSPECTION/TEST METHOD: Verify
04777b75-4fa9-5fc6-a5f4-69dbe409e97a | note | RECORD OF CONFORMITY: This ITP signed off
47f35d09-7ff7-5eaa-a30c-ae2f9f586f99 | note | IP
85c9fc51-5e91-5431-a7ba-d7dfeefc7c83 | note | RESPONSIBILITY: Fulton Hogan Engineer
9c3f1e18-dc23-5a99-b6e8-2d523d3c187c | textbox | DATE:
0ad4a57d-4d96-4fc3-811e-0db2c72500c5 | checkpoint | 2.5 Track Drain Installation
fa567ec2-c404-5998-8677-ef7dca4f8a4e | note | FREQUENCY: Each Lot
585b8830-c34c-5b46-9102-c7c9b3e6a091 | note | ACCEPTANCE CRITERIA:
0fa3b107-ba7d-538f-bd68-430095306a49 | note | • Track drains shall be welded to designated positions, and cleaned of all weld splatter.
44b8d623-5c93-5b15-bd95-b9f2f672cf85 | note | • Weld shall be sealed after installation
25f6c6c9-aa36-5c2e-abb0-3a3d44b900e7 | note | • Rectangular 300 x 450mm junction pit & lid shall be used with 4 x j-bolts secured as per STD T9022
e8e30589-8a5f-530c-a402-cc09989ef5b1 | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
7b43a569-19a4-51eb-ab58-507d7a9c7a3f | note | INSPECTION/TEST METHOD: Visual inspection
9fc9f5b5-4e0c-5ba7-b012-b3f4856f1f8c | note | RECORD OF CONFORMITY: This ITP signed off
b19e20c6-21ed-5542-9cb9-27d5282540ff | note | IP
f13e9ec9-0eb7-5f19-92ea-61291c57ec08 | note | RESPONSIBILITY: Fulton Hogan Engineer
a6bd4a4a-74e5-539e-ad39-903f17514487 | textbox | DATE:
46272b0d-a0d3-4eee-b599-58644dacbb70 | checkpoint | 2.6 Points Drainage
0e03d372-e268-53aa-8d19-1aa9e6327cf6 | note | FREQUENCY: Where required
f7d685ed-19d0-5722-bca6-3f23169618b6 | note | ACCEPTANCE CRITERIA:
4af86203-361a-5c80-a9bf-6c8cee24b3fa | note | • The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit.
2378823b-00c0-5549-af0b-7350a03c7cad | note | • Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
800785e3-b21d-5606-84b5-91514bca3080 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
3888db01-39d5-5ce8-8293-48ea687e193c | note | INSPECTION/TEST METHOD: Visual inspection
efc5dd61-cd5c-57d2-a0c5-79e1f2a55bab | note | RECORD OF CONFORMITY: This ITP signed off
1c09bc8f-dded-5684-a09f-164ed984eb7f | note | IP
3858509a-cddb-520c-9ec8-a9ffd2cb7e53 | note | RESPONSIBILITY: Fulton Hogan Engineer
d37fff4d-dc20-58e6-9e7a-06e0c0c04619 | textbox | DATE:
715fd835-37e2-4788-a02d-c536cdfa267d | checkpoint | 2.7 Concrete Pour
bc65749f-5d22-5acf-b46e-78bd14e77465 | note | FREQUENCY: Each Lot
6159f91a-e058-5999-bd7e-81333448e0f6 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
6646ae7a-f64b-55ba-b79d-71bea1993102 | note | REFERENCE DOCUMENTS: STD T9021A
a6921e60-ce42-5711-9889-89274e2fc93a | note | INSPECTION/TEST METHOD: Visual inspection
26b79637-5ad5-5e52-99c6-061997fdeb83 | note | RECORD OF CONFORMITY: This ITP Signed off
05eada67-20d0-5171-a708-bc0da3b7e2e6 | note | IP
bd5cf79e-5cdb-5839-805b-b1545aefa149 | note | RESPONSIBILITY: Fulton Hogan Engineer
343c186d-13ae-5f08-a25d-aeaa9673c0df | textbox | DATE:
568099d6-d37d-4100-a6fc-5ce443174c2c | checkpoint | 2.8 Connection to local drainage
0030c7e6-62da-5f04-adbd-d0e3221ee40e | note | FREQUENCY: Each Lot
e538a49e-be64-51da-9781-6c34d22606c1 | note | ACCEPTANCE CRITERIA:
3ce4c5b2-64c8-5fdb-b24e-53eb6a2dc4bb | note | • Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority.
7f4ea20f-b504-5bac-b679-ce2a283306ff | note | • The minimum pipe size shall be 150 mm.
fcf19655-ceec-5163-aec1-7a0db975991a | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
a0974d67-6578-5657-a2b0-74252a9189b6 | note | INSPECTION/TEST METHOD: Visual inspection
93c019b4-134c-53f3-b6ca-850c377fbf46 | note | RECORD OF CONFORMITY: This ITP Signed off
a8d3c658-952e-5b5d-b4c4-6c996ea2b627 | note | IP
2c0d0166-dd87-57e1-a419-519f73b4db5f | note | RESPONSIBILITY: Fulton Hogan Engineer
78f0b8b2-aff0-581b-8ed4-2883b6164769 | textbox | DATE:
f2d50830-b040-477d-b00c-23ff20d32a6f | checkpoint | Final Inspection
de7e82da-bde4-5df6-a0b5-10ae36eab927 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb65f8cc-1c7b-5d1d-8040-42a0d013f749 | textbox | Print Name:
1ce0ef8b-9490-5619-a354-392eff6531f7 | textbox | Position:
cc45c789-89ae-5dd4-9119-ec911347a826 | textbox | Date: