## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
1ab0257c-0850-40e9-9843-d5785dd440b2 | checklist | ITP-006 - Track Placement Rev3 | itp | ITP-006 - Track Placement
24667aaa-d1b7-4d25-9b62-4e0bc150964b | section | 1 - Preliminary Works
9c400344-52c6-40bf-ae01-913f3a4e1f54 | checkpoint | 1.1 Check for Correct Documentation
db8224fe-760d-56e8-be3f-c35ea8bd6134 | note | FREQUENCY: Prior to Commencing Works
9423663b-e936-5294-a2f3-3ac475e8c971 | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
8cfe857e-68ea-5096-8ff8-45a81ebb2f9a | note | REFERENCE DOCUMENTS: Design Drawings and Register
055f4d45-66c5-54ef-9cda-6836c07f498d | note | INSPECTION/TEST METHOD: Visual Inspection
b2372165-6cba-5731-abf8-af5f1c863197 | note | RECORD OF CONFORMITY: This ITP Signed Off
02123363-0acd-59ee-9137-113d159cee59 | note | HP*
6f060038-265e-56a0-861f-b91ac57541bb | note | RESPONSIBILITY: Fulton Hogan Engineer
43adeb5b-d86e-5ad3-b13b-aeda88a4b9db | textbox | DATE:
193e432a-536f-44c3-884a-3963203868d2 | checkpoint | 1.2 Check Materials
a33d4c53-1966-59d5-a266-07e334632c55 | note | FREQUENCY: Prior to Commencing Works
bb2e6fb8-a026-5d7b-95ad-76854b956eb4 | note | ACCEPTANCE CRITERIA:
fff18da3-e323-55ba-9ef0-23aa9e6a5374 | note | • Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
b55ad6b1-6a87-5cce-8f85-daa58cf74914 | note | • Check condition of rail sleepers
db4294a7-e1fb-5645-be23-ea9e9add3a6d | note | • Ensure rail jewellery is of sound condition
5ababb39-93a8-571e-898b-90b94814edc8 | note | REFERENCE DOCUMENTS: AS 1085
f51ffe29-45a2-51b8-8c6f-4da578e5a6b3 | note | INSPECTION/TEST METHOD: Visual Inspection
de76202f-68bd-5bca-bebc-00212cfb8d02 | note | RECORD OF CONFORMITY: This ITP Signed Off
3d7eb362-050d-5c19-ae55-0950b30216bd | note | HP*
ff3d44c7-42d6-5789-b2c4-e9b7d7a96aca | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
73e8a78e-d3b9-58cf-8c05-dcd8acff29c8 | textbox | DATE:
aecea445-dfed-42c3-a1b4-de7166e36fb1 | checkpoint | 1.3 Check Special Works Components
94067da2-367d-503a-af89-dea921692605 | note | FREQUENCY: Prior to Commencing Works
83941dd3-dc82-5358-b210-d34b19cc1275 | note | ACCEPTANCE CRITERIA:
2e8d3510-6927-5946-bf6d-93bff793a30e | note | • Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
75e97d9d-2e85-59f5-b507-a5df256ba356 | note | • Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails.
414b2b05-36d2-592a-b5bc-ea5becacc100 | note | • Superintendent to visit yard from intial inspection of the rail and fabrication plans.
35c1abb2-75ce-581d-85f5-db5dfca4bc0e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
f094d12f-8c56-5208-b838-f7d38e67b6c2 | note | INSPECTION/TEST METHOD: Verify
ff91bfc6-c048-5881-9d18-575874c85f37 | note | RECORD OF CONFORMITY: This ITP Signed Off
4f25c9bc-71eb-53bb-84a7-58ae68e6dee6 | note | IP
70c0613f-e26f-5594-9625-86e5d3f2581c | note | RESPONSIBILITY: Fulton Hogan Engineer
32a88e8f-4fce-5e8b-8cfb-d245d70b9bf7 | textbox | DATE:
a5606e24-0038-4bd0-b861-5a7366e7015e | checkpoint | 1.4 Check Curved rail
c058526c-5c98-5411-8a56-a2d740193281 | note | FREQUENCY: Prior to Commencing Works
bbd5e121-bab7-5248-91f5-8e022c3f67a1 | note | ACCEPTANCE CRITERIA:
2ebbd81c-f77e-57bb-bc95-6b9af228feb0 | note | • Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
8891fbd4-0b67-569d-b5fc-d09ffa63e667 | note | • Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
e911eb58-f044-5937-985a-f49f2ce005ed | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
592300eb-d6bf-5453-baec-33a454cea07f | note | INSPECTION/TEST METHOD: Verify
d6ee1093-f56f-5c36-a439-a41af172a325 | note | RECORD OF CONFORMITY: This ITP Signed Off
a13a2365-5f7d-5244-a8bd-df7434f4e280 | note | HP*
32fefc3e-5e15-5c45-a40d-5dc8b811498e | note | RESPONSIBILITY: Fulton Hogan Engineer
ccacca26-b530-5b18-b3e0-ea05bf8a00eb | textbox | DATE:
d8c01044-dd90-44be-bb29-42ba8278bf1a | checkpoint | 1.5 Welders Qualifications
edfec91f-1ea0-5aec-97bd-79fcbf128874 | note | FREQUENCY: Prior to Commencing Works
ba6d92c1-b3b2-5b5b-83ff-53a4a05687d0 | note | ACCEPTANCE CRITERIA:
a94592f9-da4c-5165-a2f2-292bcde76179 | note | • Welders shall be trained and compliant in Aluminothermic Welding Requirements;
2f9cad02-1224-596e-b9d9-e49e601914d1 | note | ○ TLIW2012 Grind Rails
60d0ad60-d686-5926-bfe4-41e005636176 | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
591a803b-d2a2-5748-9aaa-eefa8371ad0b | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
b1a92464-e928-5305-b51d-a98f6f8870a6 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
03542f16-2868-5594-b7d4-9dcabcacfe4d | note | INSPECTION/TEST METHOD: Verify
f3ffbbd6-1937-5756-a196-921cf681142f | note | RECORD OF CONFORMITY: This ITP Signed Off
b365a5df-a9ea-5518-82a6-9bb3241cded2 | note | HP*
7e914d8f-b698-5186-90bf-a9ce64f0772c | note | RESPONSIBILITY: Fulton Hogan Engineer
4286c1d7-57a7-548c-88c5-70991556e4a8 | textbox | DATE:
54af46ea-156e-45de-9eb3-a499855d7f10 | checkpoint | 1.6 Ultrasonic Testers Qualifications
3363028e-acec-5dee-88e8-fe30f11a9d9b | note | FREQUENCY: Prior to Commencing Works
932e5319-d770-56a6-8f35-cab15629edb7 | note | ACCEPTANCE CRITERIA:
a6c8458f-b0ca-541c-82ec-56aa38922076 | note | • Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing.
a6bda1e3-a65f-5c6f-b83d-559f1f018293 | note | • Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
90448311-3bc3-5945-9cbc-d51a111df8d1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
8777db36-6b6e-5665-923c-d05ab2d1058f | note | INSPECTION/TEST METHOD: Verify
559a73ce-948e-5a92-83d6-534682e95d79 | note | RECORD OF CONFORMITY: This ITP Signed Off
6c095786-6c4a-549c-880c-2cfca1d3be29 | note | HP*
b0e7b29d-8377-5c49-9b81-ce4955221abc | note | RESPONSIBILITY: Fulton Hogan Engineer
7c86e8bb-232b-56fd-a3ff-bfaf2b0b7ce3 | textbox | DATE:
10de851d-eb4d-4d46-8f9e-0fc4f0a1cf20 | section | 2 - Construction Works
e10da0a0-f38f-4d02-a895-424b5d96c307 | checkpoint | 2.1 Installation of Sleeper
1ce74de5-67fc-5aa4-a6e9-f5c4adf264c0 | note | FREQUENCY: Each Lot
db80831e-5ee3-510d-9134-97411297b1b0 | note | ACCEPTANCE CRITERIA:
612e7b95-78a2-50f9-975d-faf46fa6051d | note | • Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
cf3aeee1-b20a-5f3c-be94-c7d8af589f02 | note | • Dual block sleepers shall also comply with the design offsets at each chainage
aa4387e1-01ff-59aa-801f-bcd7b396dad3 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
421af280-dace-5577-a813-afdbdb145ff6 | note | INSPECTION/TEST METHOD: Visual Inspection
b56d6101-d15c-5be6-8059-49678a55f52c | note | RECORD OF CONFORMITY: This ITP Signed Off
ed9a27b0-9a1d-5888-9bf4-c6a5bf5cac2e | note | IP
a1f91dad-7952-50b0-9bf6-439f2efe63a5 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a419f03-c656-5ff1-a660-5023ddf22fc5 | textbox | DATE:
1c631e1e-578a-43ef-9bb8-9f44fd09889f | checkpoint | 2.2 Placement of Rail
db1d57cf-0e11-5374-80c7-a7ba90d2a275 | note | FREQUENCY: Each Lot
d3f8a0aa-8c67-55e7-929a-5cf2b700bae1 | note | ACCEPTANCE CRITERIA:
4894d7a2-86b0-564b-81a1-86ffa9434541 | note | Ensure rail strings conform to rail plan
f712775d-8d7f-50a1-96c5-b78b606e0aaa | note | • All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
d55813af-cae5-501c-bc0a-6ab2190e63d3 | note | • Bottom of rail and bearing surface shall be clean of foreign materials before laying
670ba4e6-6238-59a1-b025-e19c343112b9 | note | • Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
36079b7d-6d25-545f-832d-6b78d4761da8 | note | • Geometry tolerances as follows:
782b0f96-c951-59d7-9594-bf8026a11248 | note | – Centreline location: +/- 3mm
ee655657-83dd-59fa-917e-fb7c9ec9db5a | note | – Level: +/- 3mm - Line measured (>10m chord): +/- 3mm
541946f4-b7fb-5e46-b071-6072e7bb9314 | note | – Twist (3.5m chord): +/- 2mm
2260fa2e-dd2f-5acc-89ac-e7c7d194f052 | note | – Cant: +/- 3mm
38b7db40-024b-56bf-887a-a6deab3b235e | note | – Gauge (open track): +3mm, -0mm
efddf516-1a37-5eca-82f4-5b7597159fef | note | – Gauge,Turnouts (opposite crossings): +2, -0mm
e52b8cef-b120-5919-adba-e0e37d89bff3 | note | – Gauge, Diamonds and ‘H’ Crossings: +2, -0mm
ea42293a-bed3-5118-b5e9-11f7b95603a6 | note | • Note: Cant shall be applied uniformly over transitions
4c6f2b9f-c165-5600-acff-5327e064e8b7 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
4476a817-b081-5068-a678-14898f87b369 | note | INSPECTION/TEST METHOD: Visual Inspection
8a20974e-bd51-5d75-a9db-6eb184b665b4 | note | RECORD OF CONFORMITY: Completion of track charts
36f89d78-cc91-5acb-ada4-5f2a70f2ad13 | note | HP*
a7003db7-c302-538e-9180-23998c856924 | note | RESPONSIBILITY: Fulton Hogan Engineer
c66b666f-32f4-5e2b-9510-3d367f0f5136 | textbox | DATE:
21e36e42-f22a-40eb-a09e-e8d1e04982aa | checkpoint | 2.3 Placement of Jewellery
fd7a3ea0-aeeb-5a28-9518-3738346b0f19 | note | FREQUENCY: Each Lot
592104b9-8cc9-5648-b134-6f54d88bc7df | note | ACCEPTANCE CRITERIA:
75e5d90e-452d-5d22-a131-cfad40516ad5 | note | • Each sleeper shall be fastened to track with approved jewellery and rail clips
81949c41-e487-5f95-9517-8ccf6e4b21ff | note | • Clips shall be installed with panpuller or equivalent
7c9790e7-c26a-512e-bc3f-366cffcedf28 | note | • All fasteners shall be sealed as per agreed method with Yarra Trams
0cd89289-0778-527f-8e99-9e2d27d9941d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
39fc205c-9506-5761-b65e-8c4518e5f66c | note | INSPECTION/TEST METHOD: Visual Inspection
c100f020-fb1e-52c4-a391-692b959cb1ad | note | RECORD OF CONFORMITY: This ITP Signed Off
7a67c57d-5ce5-5d60-a351-99fd18695342 | note | WP
9ffb41b1-a7c0-5a84-afa0-5514cd5d4d2b | note | RESPONSIBILITY: Fulton Hogan Engineer
d64984af-80d8-53ec-b33e-4e58039aee4d | textbox | DATE:
fa5d72bf-fb56-4eb7-9442-6c2338c7854a | checkpoint | 2.4 Rail End Preparation
6520c8ed-7ab8-563b-8f2c-ac945f8dc478 | note | FREQUENCY: Each Lot
eb701765-5fe5-5491-9b9e-1bd08af6956e | note | ACCEPTANCE CRITERIA:
ef3331be-a510-5387-b4f9-6415b2cf9844 | note | • Rails shall be saw cut or flame cut
66bd05d9-f613-5830-a604-21a78692ddfa | note | • Minimum closure length from proximity of welds shall be 2m
934b1414-12e8-5e09-a0c0-ce37eb444450 | note | • Rail end conditions shall match (i.e flame cut - flame cut)
c04748f7-8cce-54a7-8775-f32c80b92977 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
6a48df45-8a34-5166-a989-2042be7b853e | note | INSPECTION/TEST METHOD: Visual Inspection
6031e11b-0735-5134-b4f5-cb8ab933f613 | note | RECORD OF CONFORMITY: This ITP Signed Off
ee50323e-f388-57f6-8c90-a0de7c663324 | note | WP
70fe89bd-c591-5b4e-92f3-23293c731f10 | note | RESPONSIBILITY: Fulton Hogan Engineer
ba1d898b-2636-51ef-9bb1-f65fb15dda48 | textbox | DATE:
9ebcb9ac-c985-4ab6-9049-366d01d1884c | checkpoint | 2.5 Welding of Rail
24bf2b42-4070-5626-838d-78d45fcd2128 | note | FREQUENCY: Each Weld
541bd01d-1feb-5613-8c5f-43ce15772ae8 | note | ACCEPTANCE CRITERIA:
b12593f0-3af1-5833-8141-c9d7ca9d51ab | note | • Joints shall be square across the track
84aea222-77e5-5d86-9af9-e710a3b38a1e | note | • Maximum skew at square joints shall be 65mm
9cf9638c-dab5-529b-9a49-73bba91bb8c4 | note | • Portions shall match rail type (i.e HHR, Ordinary)
5a89bb8d-7e8a-51b1-991d-b75313913907 | note | • Welds shall not be within:
fd4cd6ed-779d-5d6d-a063-b257535e0c67 | note | – 3m of another weld
32626221-d20e-5c1b-89e9-a5cfe89c6743 | note | – 3m of a rail end
aa20ba8f-dff0-5f1a-bfbc-b3b7bcd854ac | note | – 1.5m of a glued insulation joint assembly
8c5c9ff3-1401-5c5a-98f8-02a2749c102b | note | • Field welds shall be +/- 50mm from centre of bay between sleepers
30ce5beb-d597-5e3e-9f00-522f8bcf4a34 | note | • Weld Return forms shall be completed by qualified welder
bf67bd38-06c4-5d00-9c25-aafcce3f6581 | note | • Welds shall be grinded after 1 hour
7b331555-43a0-5379-bf48-0aeebb0a4c26 | note | • Welds shall be free of water
986ee10a-179f-56fe-a3ec-1455c1126e2b | note | • Post grinding, welds shall be cleaned for visual inspection
2cc9d23d-e78e-530a-8a4f-5aa8140adc78 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
e872a7d9-795e-5aab-b7ea-63a064dd4686 | note | INSPECTION/TEST METHOD: Visual Inspection
4d49d749-afd8-537e-a737-d968f5a8375c | note | RECORD OF CONFORMITY: This ITP Signed Off
09b1bd1a-5f80-51b0-8ca2-ebaf820f6469 | note | TP
f6187a2e-41fb-54ab-a7be-8f41f09c70df | note | RESPONSIBILITY: Fulton Hogan Engineer
bac10196-6c3a-5187-a312-5ef1b01f00a9 | textbox | DATE:
08e68919-3478-4a68-91d6-cac2113a1dc3 | checkpoint | 2.6 Grinding & Cleaning Welds
8c376fa6-863a-5156-a7ef-d4eae4f599ad | note | FREQUENCY: Each Weld
184cc1b9-2c97-5049-940b-9f8747228089 | note | ACCEPTANCE CRITERIA:
93b122d2-3a90-524f-bf44-af176b1f6692 | note | • The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring).
1058848f-292a-5c08-9fb1-6b8d3c9274de | note | • The grinding stroke should not exceed 500 mm to each side of the weld.Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
deee0f02-5705-53be-818d-0c1718e980ac | note | • The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
155f370c-c196-5a7a-8feb-ad6ab362e309 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
f3f12c43-2a88-58f0-ad8d-7d8584177fef | note | INSPECTION/TEST METHOD: Visual Inspection
d8930176-742e-5622-9fdf-36bde22fe704 | note | RECORD OF CONFORMITY: This ITP Signed Off
8fd45468-447d-5a93-9c76-ff56f557ad09 | note | IP
768a09bc-3c5e-5936-96af-464b698aabb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
f44b95d1-7ecf-510c-af69-4ad1dfe9c4d4 | textbox | DATE:
c26bfe7a-6a22-407b-8870-72b1570bb1ba | checkpoint | 2.7 Track Adjustment
d4b177aa-0861-555f-9b41-cec52507672e | note | FREQUENCY: When required
98921c26-2e06-5cea-87f8-c5edfe2f680d | note | ACCEPTANCE CRITERIA:
4a1be384-751e-5f25-824c-88d89503b7ea | note | Allowance must be made for expansion and contraction of rail to control stress.
aae339f6-bace-52f9-b449-e58058d5ef62 | note | The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with anapproved type of thermometer.
74961083-62c0-514e-817a-adef213000ff | note | In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
5655633e-6686-5b15-8c2c-0a116bb43efe | note | Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
d5e6d340-1153-5291-8bec-b77ef0eca6e5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
f60878cd-6883-5b28-9074-a571cbb383bd | note | INSPECTION/TEST METHOD: Visual Inspection
9447dec2-76d3-5b5f-bdfe-e1e22d04dd95 | note | RECORD OF CONFORMITY: This ITP Signed Off
9eef05a8-f497-500a-9143-87594b3c6309 | note | IP
b6f508e8-321b-52c5-ae3e-9a839c255180 | note | RESPONSIBILITY: Fulton Hogan Engineer
b96bb69d-444a-5a8d-9f56-5a555cc464c5 | textbox | DATE:
fe33f82d-7e03-4fb2-b2d6-c80e19557ab3 | checkpoint | 2.8 Track Bonds
00a27bb3-586f-5449-b5b5-6dc6cf6c73aa | note | FREQUENCY: Each Lot
ae55cb6b-b78b-547e-9107-08d7fc5c9078 | note | ACCEPTANCE CRITERIA:
0410b825-7510-56ab-92e9-c77a0329a1c4 | note | • Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
0044ca8c-04cb-561c-96c7-752ff464134d | note | • Ensure bonds are sealed as per agreed method with Yarra Trams
f2d93732-9a9e-580a-8496-0919974899e5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
bb18a3a4-8b0e-5222-b868-00e08979b99e | note | INSPECTION/TEST METHOD: Inspection / Test Method
891b6129-4acc-550c-bbbb-42dafc22d734 | note | RECORD OF CONFORMITY: This ITP Signed Off
b2a76721-f678-5889-bcca-fbdc3548a495 | note | IP
6017e730-13e3-5926-99f2-eacd803b9fb0 | note | RESPONSIBILITY: Fulton Hogan Engineer
09b73312-724f-5a13-bf0d-b2d1a2faf039 | textbox | DATE:
1fc1df1f-deda-4b40-a8e7-a7bb49c2d9ee | section | 3 - Testing
d97e47ed-12b8-4f7d-be16-5072be6d98a7 | checkpoint | 3.1 Track Testing
380b4d38-59cf-53fb-a49c-2b9491893d69 | note | FREQUENCY: Each Weld
fd992515-0e55-5955-842c-71eae10e2a10 | note | ACCEPTANCE CRITERIA:
faee323b-e8b6-5acd-939a-11aac6280f34 | note | • All welds shall be tested by qualified NDT operator
a0bd9fb3-9aff-585d-8400-b816ebd21228 | note | • Failed welds shall be cut out and replaced
c029a1ec-cd28-5bbe-9168-8ae818e25ac4 | note | • Testing documentation shall be recorded and supplied to the superintendent
de2ce446-c03e-56f0-872c-20407c42cbcd | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
e4a23fa8-2d96-528f-ba2e-0b0c6f115e81 | note | INSPECTION/TEST METHOD: Inspection / Test Method
2d757200-529f-5817-aa52-42d5309e51f8 | note | RECORD OF CONFORMITY: This ITP Signed Off
591f49e3-969c-5b62-b10f-77ba34675571 | note | TP
ed141fcf-1eb5-5874-9ac7-2c6bb18214fc | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
0c07b41e-cff9-5fe6-9173-31b457431926 | textbox | DATE:
0bd4e755-898a-4fc4-bff9-7a97cfa4176f | checkpoint | Final Inspection
bb6075ab-180b-52c5-902d-6756af51a345 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
74e77242-1f9f-5fc4-9208-4edecd1f318f | textbox | Print Name:
88b50e03-f51f-52fe-9531-42434547c4af | textbox | Position:
e0d81f1e-7814-59f6-a4c0-7160da1ee96a | textbox | Date: