## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
392e700a-0e07-457f-9d5c-6df20c50074a | checklist | ITP-007 - Concrete Track Slab Pour Rev2 | itp | ITP-007 - Concrete Track Slab Pour
d816c0f7-b1df-4e84-a8b0-135f87e77d72 | section | 1 - Preliminary Works
8b7e3a7a-1c26-4ff2-9e3d-b88692e4e2f6 | checkpoint | 1.1 Check for correct documentation
da623a02-195d-5cc8-bb9d-848331945cc4 | note | FREQUENCY: Prior to commencing any activity
f882b465-7c94-5aec-b8ee-33997dc9c117 | note | ACCEPTANCE CRITERIA:
f408d9bf-dcee-5c86-b16a-c77f6d24a881 | note | • Ensure that all employees and subcontractors are:
07da9231-eee4-5b47-a1f1-920f74869379 | note | – using the correct and complete set of drawings
76ee42f3-06f4-5018-9769-b91c289112dd | note | – all drawings are the latest revision
cfd01961-9ffe-56d1-9452-ef808917cc2c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
946e2740-ba09-5632-ba3c-bf96e55b36c9 | note | INSPECTION/TEST METHOD: Visual inspection
6f1f4114-0319-5626-99fd-bf5db0bc2eb2 | note | RECORD OF CONFORMITY: This ITP signed off
967f66c5-e4bb-591f-a1fd-2e73f009434d | note | HP*
b2295147-3511-5691-bfc4-c858941ca5b9 | note | RESPONSIBILITY: Fulton Hogan Engineer
22b1cb72-cace-58ce-a249-9da547c11856 | textbox | DATE:
5e2a8c67-ec8b-4d54-a1c6-56724d1f16e6 | checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
9e7cbbc3-deb9-5d2c-b288-476c67ad6887 | note | FREQUENCY: Prior to first concrete pour
876d56d7-f0e8-502e-bfbf-d0708b8cd6f3 | note | ACCEPTANCE CRITERIA:
763ac6cb-11fd-56bb-8510-da1da35c21a7 | note | • Concrete mix design submitted and approved at least 2 weeks prior to first pour.
b278e546-eac7-56c2-a0ed-ccde8d41f7ec | note | • Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
c08540de-a400-5764-81bb-ac6dedfac803 | note | • Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
4645dd56-daf8-50df-892e-85711f4f113b | note | REFERENCE DOCUMENTS: CE-019-ST-0033
4631ee45-28af-5cd8-beb5-cbbdf5a256b1 | note | INSPECTION/TEST METHOD: Verify
7d087f2a-2a5e-5a5c-bbbc-0815514632c3 | note | RECORD OF CONFORMITY: Mix Design ITP
7b246dee-1224-5866-95c8-51c40c6aed60 | note | HP*
3c5e65be-e60a-53a8-8a2e-433dc9c19324 | note | RESPONSIBILITY: FH Engineer / Superintendent
ebe9b3f8-4a6d-523d-b547-996c1ded0cc4 | textbox | DATE:
92c47959-556f-4807-addc-9a82406769ec | section | 2 - Construction Works
006a8104-c40f-46e1-acb8-3d6a85b22956 | checkpoint | 2.1 Weather Monitoring
fddb9bfd-4543-52a3-8e6f-191e7be8abfd | note | FREQUENCY: Prior to start
55b8c580-ab2b-564c-ab22-bfe758771e0f | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
ed39fe34-09a6-5d64-b875-ab3dd0356dcb | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
c49a9b1d-00c1-5a8c-8517-9c1fd5f2aec4 | note | INSPECTION/TEST METHOD: Verify
5106412f-fbd9-5e03-a469-66135b61bf61 | note | RECORD OF CONFORMITY: This ITP signed off
83c43ccf-7ee7-50df-b8ad-602ccc848cf7 | note | HP
11a32ef4-f50e-5d14-9c82-f9c84224ed48 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
539404fe-b6bc-54d4-9d00-e759eeab1aa8 | textbox | DATE:
d606af13-4759-4ec2-8eb5-6aa035b281d6 | signoff | HOLD POINT AUTHORITY
c56e2f7c-82ff-4a0e-aa6b-3d3f1391d877 | checkpoint | 2.2 Surface Preparation
37688fb9-01cb-5f20-bdb0-02d4c6798c4d | note | FREQUENCY: Prior to start
bb317480-2244-5caa-b798-48a1fafe88f9 | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
22fa3543-3552-56b7-bb25-efe05579f137 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
a46a1075-61a5-51c5-b1c8-313be48630fe | note | INSPECTION/TEST METHOD: Verify
f08cd20b-844d-50c4-8aac-694308b9449d | note | RECORD OF CONFORMITY: This ITP signed off
a75415ee-dfa4-5092-a748-406277451f6f | note | IP
4f2d9fdc-980b-5036-9d80-b9478fad958d | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
b19bc243-4421-554c-9514-bf1668d505e6 | textbox | DATE:
47762765-f5e6-4c3e-9ac9-e096cea3f90f | checkpoint | 2.3 Setting Out
4e5e43e8-7781-599f-b838-b8277d13b927 | note | FREQUENCY: Prior to start
f1b64c0d-9356-5b29-926d-42c39cc2fdfe | note | ACCEPTANCE CRITERIA:
e0cd6f89-a9d2-53f6-8213-7b062a19d3ea | note | • Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications.
9a1e3697-6d44-5451-8a22-658ef3467b4e | note | • No survey/level pegs to be removed by any persons until completion of works.
4fedf475-9254-5a15-b380-aaf49045ba73 | note | • Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
6230c80e-ea0f-596a-ba5c-fbf5b24ce1e2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
abd73cbd-5e19-5981-9fee-5d93fff9a9c2 | note | INSPECTION/TEST METHOD: Verify
2fa26f37-f158-545c-8763-be1eab7b873d | note | RECORD OF CONFORMITY: This ITP signed off
bdb64609-9cda-53a1-bb8b-30172e514263 | note | IP
87f8c103-7267-51df-8188-75e3985aa519 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
296e2bdc-daf3-554f-94df-3e039c1451ff | textbox | DATE:
434802ee-7f89-48ff-94e8-17d63f3e9a34 | checkpoint | 2.4 Preliminary Works Formwork
153d5e8c-d557-5ef7-9880-83b89f44b6cc | note | FREQUENCY: Prior to start
713d571c-6c9e-5d13-bf51-8cf7221ab080 | note | ACCEPTANCE CRITERIA:
bb00d26f-429a-554a-9c9a-9ce7316a5e50 | note | • Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
f9a94a03-c76e-50cf-b0df-36bcf6931dd9 | note | • The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
6ddbf664-6c32-5a3c-9cda-bc0990cc3147 | note | • Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent
d42e7ba5-4bea-59b9-b39b-621a6f4f5ba8 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
c552fec3-4493-5072-bca4-2f18a730d038 | note | INSPECTION/TEST METHOD: Verify
d750bf38-c787-561f-ad2d-1a5edf5a3f8c | note | RECORD OF CONFORMITY: This ITP signed off
19062975-285c-5996-9688-b417bbe8f845 | note | WP
2a0157b1-c14e-5a11-9f11-2cca112767fd | note | RESPONSIBILITY: Fulton Hogan Engineer
4e9a9be5-1145-53a4-9b33-b00c24a1015f | textbox | DATE:
30bc8d5e-205e-4995-bc52-5f5d5144c140 | checkpoint | 2.5 Reinforcement
856bd8c7-e33c-52d6-bddd-85689f08d4d0 | note | FREQUENCY: Where Required
df6f01ee-0fcf-5253-aea0-54c3ac6de1eb | note | ACCEPTANCE CRITERIA:
d91bf87d-479c-592c-84a1-9ac20857af4c | note | • Ensure that all reinforcement is placed as specified by construction drawings.
66d6de07-1770-5556-bd4a-b03dd698cd66 | note | • All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
caa48137-23de-53ff-8fc3-21e8d23cd09c | note | • Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
82956558-82f3-5a1a-a994-21c63912c62d | note | • Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
abb464fe-4f91-5d27-9262-78eb8aa2c18c | note | • Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
cc829126-1fcc-57fe-a87e-baf1ab2aeb43 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
f0b61a55-2605-5326-b034-601edeb7a63a | note | INSPECTION/TEST METHOD: Verify
4737760f-13f7-51b9-87d0-5b744eb58534 | note | RECORD OF CONFORMITY: This ITP signed off
2e2de00e-ab16-5e60-af2f-575a811abac4 | note | IP
a4b7e142-4e05-5a91-aa57-eab8b47b1ebc | note | RESPONSIBILITY: Fulton Hogan Engineer
9d83033c-eb95-571c-98a2-84893f92c4d0 | textbox | DATE:
63f86f0c-1482-4685-9c0a-140565c7ae05 | checkpoint | 2.6 Dowels
349486b6-e4e7-50c8-a1cb-31c41dbe5253 | note | FREQUENCY: Where Required
7867be7c-34b4-50a4-9eaa-0d6c423c5f15 | note | ACCEPTANCE CRITERIA:
dc056be6-9217-5328-aa5a-1ed33f172472 | note | • Ensure that all dowels are placed as specified in the construction drawings
ce22260d-04d1-56f5-a4c2-1926042e548e | note | • All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
78fcc105-07c2-5aff-a3f6-c929d2d1f693 | note | • Dowels shall be clean and free from mill scale, loose rust or oil.
74ec8d08-789c-53ca-8b42-b7e7facdefba | note | • Ensure that all dowels are securely held in their correct position until the concrete has set.
2503dc0f-4aaa-5412-ad7e-5b015de3d0c9 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
0b05ab62-1d5f-544b-8fd8-85bc940b83de | note | INSPECTION/TEST METHOD: Verify
fd78a592-ab0d-5f0a-a76d-5c5a93dd3a20 | note | RECORD OF CONFORMITY: This ITP signed off
dd0907e0-c0a2-55fd-89de-2d2c3c75bcde | note | IP
b8ec194e-1712-5993-81b5-6993cd7207e2 | note | RESPONSIBILITY: Fulton Hogan Engineer
b1de681e-10f0-55c8-9f0b-e62fe852c84c | textbox | DATE:
5d934988-df15-4410-a1ca-034f4ea45192 | checkpoint | 2.7 Pre Pour Inspection
7595135b-396d-505f-ae92-6320721c15df | note | FREQUENCY: Prior to start
659aba80-27e9-5dd0-8d62-d20285dec797 | note | ACCEPTANCE CRITERIA:
e9504930-7c77-51e3-a4a2-693ec9532f34 | note | • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
725c6e83-7006-5a8e-b9a5-0b038837d244 | note | • Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
65e348ec-dec3-5a90-a011-e0b1a3c5afa5 | note | • Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
94f17f36-ed9d-5ff2-9a79-3bfdbe3531ab | note | REFERENCE DOCUMENTS: CE-019-ST-0033
ada6659c-594f-5d81-be3a-7ed7a3f07654 | note | INSPECTION/TEST METHOD: Inspection / Test Method
79e187bd-7595-585a-8e16-b197ed6e52d4 | note | RECORD OF CONFORMITY: FH Track Inspection
54eb841d-2db9-5602-9a04-752a0ee465de | note | HP
8de0f025-2f32-5053-97a8-d3cf035f4c21 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
dc1a95ec-479e-5c23-ac5e-97f08fd9ea05 | textbox | DATE:
c4382ff7-3a48-4c7e-8bd2-7f2021aa803c | signoff | HOLD POINT AUTHORITY
fa63ce95-3aed-4d3a-a055-8d4bcac337e8 | checkpoint | 2.8 Preliminary Works Carry out sampling of concrete
d159a2bc-5aac-5449-bb8a-8d4d3343f10e | note | FREQUENCY: Each concrete pour
1f30f459-5a24-5518-b00a-a088134d6393 | note | ACCEPTANCE CRITERIA:
9ffa275e-8d3a-5aa8-8a71-a14e795dbcfb | note | Slump:
f409e95f-c07d-5c4e-8e1a-9a3263569342 | note | ○ Concrete Slump shall be 100mm +/-20 Compressive Strength:
4e44b77c-5857-5309-b38a-e898230b572e | note | • Shall be measured in accordance with CE-019-ST-0033
c5f4928e-5b27-5d83-b47b-310285ca6264 | note | ○ Testing frquency =
44ea80fb-8dc9-5cfe-9333-98e0372b6abe | note | • 0-50m3, 1 sample
8ca6b213-a325-5985-b91d-9615e8b97ddc | note | • 50-100m3, 2 samples
cde820e1-2a0c-5648-a32b-bfd0888c232a | note | • 100m3+, 3 samples
986eb4ea-7c00-5ecd-a258-e1c233bd318a | note | ○ Each sample shall consist of 4 cylinders
3241dcda-10a7-5934-be2e-c1e8b37e6dd0 | note | ○ Test Results will be provided to the Superintendent
13b94abf-7fd3-52a3-80d7-5e0a69e98b83 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
de9850df-9041-5612-b276-ef41528c4ea5 | note | INSPECTION/TEST METHOD: Verify
62581a55-6557-5ee4-95fd-64ebcc6e3691 | note | RECORD OF CONFORMITY: Concrete supplier test sheet
f0d43b75-2edd-5cc1-b4bb-0e2e47692fbc | note | TP
38d1d668-55ac-5d8e-8505-031ff829f4b1 | note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
5f647234-cacc-5b1e-aaff-ed348591ca7c | textbox | DATE:
7eafd0ec-1291-4ee4-bfb7-512d7c759ce6 | checkpoint | 2.9 Concrete Placement
3c08400f-9400-5e1e-ab2d-9dc240edb6fd | note | FREQUENCY: Each Lot
5cbecd56-7670-5f98-b726-065385798e07 | note | ACCEPTANCE CRITERIA:
8845c671-f94c-5580-b9ec-34c8213704d5 | note | • Ensure formwork is clean
206657ef-5c13-5523-9e73-7126dc3b2ddd | note | • Concrete shall be entirely discharged 60 minutes after batching,
208ad92a-1d76-56f2-bf2b-6f0649e187d3 | note | • Ensure that pouring does not occur from a height greater than 1200mm
f2e86bb6-d059-56c9-95b3-d7046a15efbf | note | • Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
be961c01-332b-543e-acee-630f893d4b56 | note | • The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
bd35c7f8-d0be-5867-8233-61127d9d3662 | note | • There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
16ab02f2-09a6-5e20-8a5a-f3f5d1df8165 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
62800ce3-632d-5dce-8a23-32ecacfc30d2 | note | INSPECTION/TEST METHOD: Visual Inspection
47563973-c16d-5f5f-b7de-651d33c24491 | note | RECORD OF CONFORMITY: This ITP signed off
db5f3109-d899-5a59-be9a-78e29f029edd | note | WP
cbc36dd6-0a73-5e50-b2f3-64fcd23a302f | note | RESPONSIBILITY: Fulton Hogan Engineer
35835311-a566-58aa-913b-4e552bab9069 | textbox | DATE:
26d17f9e-6baa-4b63-b6d9-68a597b576c0 | checkpoint | 2.10 Compaction
8b13d60d-c330-5f73-b3c3-3e14310ed98b | note | FREQUENCY: Each Lot
5885daa7-199c-510c-a5bb-fe063e0481a8 | note | ACCEPTANCE CRITERIA:
c20c1eba-c2fa-553c-aafe-91693f4ebd52 | note | • Immediately after concrete placement, compaction shall take place with an approved vibrator
ecc22a7a-8dbe-57e0-b0b0-895c39d2b690 | note | • Vibration shall take place until exposed concrete surface is free from air voids
4b494ffa-a72e-56db-b40d-069a24251e4e | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
e5858f3f-236f-5c08-b0c0-1f2ce70f4188 | note | INSPECTION/TEST METHOD: Visual inspection
d1605d42-c5d4-5102-ae1a-1967989600ab | note | RECORD OF CONFORMITY: This ITP signed off
88ad8298-5a10-5bee-a40d-3fb341c8d9e8 | note | IP
9beffd52-9583-5ddf-965b-c458a4c3cad0 | note | RESPONSIBILITY: Fulton Hogan Engineer
501786d5-ca93-5ee2-9765-d90e7142d879 | textbox | DATE:
6f92c0b7-735c-4982-a5a2-f440acea19c8 | checkpoint | 2.11 Record location of each batch
70d70acd-8207-5329-8e68-7600e1b29aa1 | note | FREQUENCY: Each concrete pour
112f16cc-ddbd-5eaa-a154-4d810a190998 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
feb02ac8-b29e-5163-86eb-09acaccd4dfa | note | REFERENCE DOCUMENTS: CE-019-ST-0033
7232cf55-53ba-5eba-b3fc-20626c5f919a | note | INSPECTION/TEST METHOD: Checklist
4753f193-32bd-50a1-bb37-b2257fb1d81d | note | RECORD OF CONFORMITY: This ITP signed off
c5ee5368-2364-5820-a653-e4fc3ade8046 | note | IP
6a86f560-a93c-5db8-9f2c-d650218e3a8e | note | RESPONSIBILITY: Fulton Hogan Engineer
4cc23669-ac84-5129-b07d-daef6535af47 | textbox | DATE:
2d9cd346-e83e-4142-aab9-a19329541ebe | checkpoint | 2.12 Curing
6bfaa850-068b-5dcd-9833-02d2d73bcbf0 | note | FREQUENCY: Each concrete pour
17512eee-e017-5452-95d0-bd62f6c4484c | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
6adbe97b-53ef-5d46-a35a-f1259a524738 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
67e712b0-628e-5c34-98db-6d2000a9dd93 | note | INSPECTION/TEST METHOD: Checklist
8180e0f6-b57a-551a-8db4-d1a8541565c5 | note | RECORD OF CONFORMITY: This ITP signed off
22cb404f-29b7-5015-891d-4ee040fa6292 | note | IP
f96b1205-7cb3-55e1-8a5b-4da3684320ba | note | RESPONSIBILITY: Fulton Hogan Engineer
a9b60ca8-df1a-5567-8615-1635e7f2c441 | textbox | DATE:
10920819-ce05-4179-b156-c6a446b7299b | checkpoint | 2.13 Tolerances
0fa08a55-052c-510e-9105-0dbb57771722 | note | FREQUENCY: Each concrete pour
eb004f46-277e-595a-afd2-ae47b4338426 | note | ACCEPTANCE CRITERIA:
b2ec4ce1-33d3-59a4-b407-3fb971642faa | note | All concrete shall finish true to the dimensions, the following tolerances apply:
ab1c3bc0-00c4-5c78-8368-0914bbf79c16 | note | • Plan dimension of slab +10,-10mm
fa48bcd0-cdd8-5079-b9cb-323f9c3265e1 | note | • Thickness of slab +10,-10mm
57f1a84b-f3d7-55a1-aeae-590d49927334 | note | • Cover to reinforcement +5,-3mm
146eab0c-742e-57fa-a966-20aec350999a | note | • Finished level of slab +3,-3mm
6de3f730-a467-5833-849d-a29e4fc0f138 | note | • Foundation level of slab +0,-20mm
6066ab88-55f0-50c7-bdfc-d1c575695eaf | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
299389a4-7b61-580c-9302-b9356e1e7011 | note | INSPECTION/TEST METHOD: Checklist
ce112561-7635-59d0-b861-a044885f2a6e | note | RECORD OF CONFORMITY: This ITP signed off
5bc2968a-49dd-5986-baad-d5c1f1690ce1 | note | IP
b09a8220-c6f1-5395-a29e-8e6bd286f632 | note | RESPONSIBILITY: Fulton Hogan Engineer
feb85f66-767c-597d-9611-44ae8534457b | textbox | DATE:
4d8cdc57-0afb-46d5-8450-bdcac4062ed5 | checkpoint | 2.14 Preliminary Works Slab finish
a49027b5-2cbc-5251-b501-ffd78a4a67cd | note | FREQUENCY: Where appilcable - if track is Type 1 structure
55ad13b4-cb53-5ab2-8946-5123810cb490 | note | ACCEPTANCE CRITERIA:
95c70e0b-c629-5cd7-a4ee-a5d271149273 | note | • Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities.
3ff4d398-f8db-5993-97f8-b92ff262f903 | note | • All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
7afe6cd7-fdd5-588d-91cf-dc0309b30b12 | note | • A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
301f4cb5-0010-5914-8fe5-02ee74d084b4 | note | • The slab surfaces shall be broomed to provide a non-slip finish.
f2e00634-77b8-5c6f-9f33-2c33e833d074 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
7d309d11-93c6-5d8a-8ff4-bba0213368b8 | note | INSPECTION/TEST METHOD: Checklist
93e50471-263a-56a7-9cfe-5279bb19f529 | note | RECORD OF CONFORMITY: This ITP signed off
afcfcec0-5ab6-5bf9-9283-5e0193f267a1 | note | IP
8a2b2c2e-3e65-52e3-ac7e-b6194afa542b | note | RESPONSIBILITY: Fulton Hogan Engineer
6162f3e6-c690-55a7-8c6a-f935fc047dbc | textbox | DATE:
68aecfe1-314d-4d5d-a9a6-6a2290bf9b3f | checkpoint | 2.15 Post Pour Inspection
4a428604-1531-5fcd-99c6-d38e8df125f9 | note | FREQUENCY: Each Lot
b3e8e416-092c-592a-a4e5-f61216c94943 | note | ACCEPTANCE CRITERIA:
329bfe77-5570-54bf-8313-35cff188c792 | note | • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
23355c68-cf73-5ce2-8b43-137d038aee28 | note | • Ensure no defects are present in slab
a131b245-0bd3-536f-92eb-bc703727ae65 | note | • Complete Fulton Hogan Post Pour Checklist
38c2d995-2db9-5b12-8ea4-8ae1d95726da | note | REFERENCE DOCUMENTS: CE-019-ST-0033
214e0585-5d53-5ff8-a22f-d5729219a9e2 | note | INSPECTION/TEST METHOD: Visual Inspection
7fe7b8fb-b935-5d26-bb04-5250966bba34 | note | RECORD OF CONFORMITY: Post pour checklist
194f6ab8-1f58-5aba-a251-51a0aa209822 | note | IP
3a0f0283-bf4d-5f48-81bf-2f6ca4ff36d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
c4b69e3b-9706-5051-9d93-c80795b2096e | textbox | DATE:
4acfc0c9-64a1-4788-8713-f05d45a50594 | checkpoint | Final Inspection
358805e0-7c71-5807-8bc9-7011d48e1b06 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications
627f3738-85c9-53b3-b153-c6eefd37139a | textbox | Print Name:
eaeba2eb-ec3a-5cfc-b9b9-b6d1a5219dea | textbox | Position:
fc212994-23a9-5008-9855-74fad5260c98 | textbox | Date: