## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
f3edb058-0f89-482e-ad4a-ea66af7d1fdd | checklist | ITP-008 - Hot Mix Asphalt Rev2 | itp | ITP-008 - Hot Mix Asphalt
52c1fe73-6c81-4067-8a95-47f415a0d055 | section | 1 - Construction Works
9ce87d74-9207-444e-8bcf-478ea75136e1 | checkpoint | 1.1 Submission of Mix Design
3c7d5a74-4fa9-59cc-b9de-2a80b0f383f6 | note | FREQUENCY: Prior to commencing paving
1e8ccf90-9d35-5559-bf28-bb356cfe1d92 | note | ACCEPTANCE CRITERIA: Ensure the correct mix design has been registered and is approved by Superintendent prior to laying mix according to standard track structure drawings
5c7aa9f0-26d2-5590-bd78-09776ebea4ac | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
db931383-e7a0-5379-86b3-051bd78e569c | note | INSPECTION/TEST METHOD: Correspondance of receival of mix design
5b75cd4b-2bd0-5209-8903-09c18f817fba | note | RECORD OF CONFORMITY: Superintendent approval Completed ITP
b9c2944f-c129-56bc-9747-6cfaca3e3017 | note | HP
681e9169-fb4d-59a2-ac70-e855b1d7230b | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor / Superintendent
4097e28c-0cb4-5d37-9db1-07704948aa00 | textbox | DATE:
ead1f852-1d69-4ebd-8233-6587e73d8bce | signoff | HOLD POINT AUTHORITY
5aafd120-be26-4304-9984-ace39ef74d78 | checkpoint | 1.2 Site Inspection and Base Condition
9d5137ff-87ac-5abc-9ef2-96264a988ee8 | note | FREQUENCY: Prior to commencing paving
c29d74a8-2484-5201-80a0-2016aa74496e | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
adc4ec6d-9cc2-54dc-a95a-5f1369633022 | note | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
0c8acdf1-c13f-574d-a43a-e1d086153683 | note | INSPECTION/TEST METHOD: Visual Inspection
d04b131a-8a80-57ff-b388-0485a90d9eba | note | RECORD OF CONFORMITY: ITP Signed
baf0933a-54a9-5603-be57-6d2d55cdd5ae | note | WP
4729ad8d-cdfc-5a9a-88d3-f9677ea78522 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
993126bd-393c-5ad3-9c75-77dea26b88bb | textbox | DATE:
e2163b8e-eb5f-4e4b-bf0c-8b5399ec4e18 | checkpoint | 1.3 Ambient Conditions for Placing
4a59601e-8715-54be-b076-e5b72c37a001 | note | FREQUENCY: Prior to commencing paving
9aac1bae-69c4-5a58-a82a-31693a7cb3d5 | note | ACCEPTANCE CRITERIA:
44bbd0ab-b0b0-5a36-99d2-3bf816fbca3a | note | • The majority of the surface area to be paved has a temperature greater than or equal to the following:
32f1c26b-c835-552a-9719-e286532ae680 | note | – Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
2456e870-6136-5671-a9fd-c9f4ab091e32 | note | – Wearing Courses: 10°C for conventional binders or 15°C for PMBs
6f9dcb72-d89a-5990-9869-b9508e45b70b | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
099f250d-9dda-59ff-aa00-ae70547bf988 | note | INSPECTION/TEST METHOD: Verify
3b11cf6f-fdbf-5482-bb46-3eddb72f122a | note | RECORD OF CONFORMITY: Thermometer
6db2748c-3c28-5f14-ab62-d3e5b12ac71c | note | IP
1828ad3f-627d-55e3-a51a-b08e30f8393f | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
37ee4f90-ed9e-54e7-aea5-4ed3f04c92b3 | textbox | DATE:
747e67b6-7683-453d-8e95-d5b520d49c15 | checkpoint | 1.4 Planning of Joints
28c924f4-7be5-582b-9f7e-5287d4dcbe61 | note | FREQUENCY: Prior to commencing paving
5a728779-ca49-54c9-9108-993b6806df4d | note | ACCEPTANCE CRITERIA:
ce1e8a2d-1704-582c-9469-cfb8163e6122 | note | ○ Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
d84b83d1-0a6d-557d-86be-e543fa2a4383 | note | • Transverse Joints Offset from layer to layer by at least 2m
4aadf958-2d35-576d-a8e3-4aa677ffabe3 | note | • Longitudinal Joints Offset from layer to layer by at least
02e4d722-fd84-55b0-889b-168020443efe | note | • 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
ec22bb5a-716a-5d81-b536-0d5493e0da13 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c) Pavement Drawings
b21775d5-9d48-5864-8249-6493685ba5e5 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
c1116d1c-18fa-540c-9567-9f0400f2a953 | note | RECORD OF CONFORMITY: Paving Plan
db96e033-dd2b-5026-bdda-4bda1d7d7065 | note | WP
0316f915-0495-537a-badf-8ea1775b97af | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
ec8187e5-22ec-56bf-8638-bfb24e68289e | textbox | DATE:
eb90047d-9f8b-4dc9-bf88-d2504d15494f | checkpoint | 1.5 Longitudinal Joints with existing Pavement
4f6a5bb9-c6c6-517f-9c58-48b8783ec6c2 | note | FREQUENCY: Prior to commencing paving
e9925f27-870c-5163-9293-0bdd69332a5e | note | ACCEPTANCE CRITERIA:
dfb7fbd5-cf01-5b23-a0bb-2abfe6299a9d | note | • Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
30bf793a-98b5-5869-b6bb-7de148cb49e5 | note | • Depth of step to be cut to the full depth of each indiviual layer.
7e763025-4b35-5c62-b08e-5f0c67cc404c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c) Project Specs. Section 3040.06 (d)(vii)
5cea51ad-2677-5c38-87d9-f5d96987afcf | note | INSPECTION/TEST METHOD: Visual Inspection
c96f4c6b-f27d-56d9-9a35-da52c0ae432e | note | RECORD OF CONFORMITY: ITP Signed
00b37b54-eb4a-5e61-8c1f-3a4d4077aad8 | note | WP
3c358c4d-c12e-5ac5-a4fb-e9ce7ce8e1c5 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
9718ba3f-737d-5022-9a2d-d42b8779c5d1 | textbox | DATE:
4831288f-8945-46e7-8d57-6587f1a4b64c | section | 2 - Asphalt Placement works
09e92ab4-48e4-493d-bb70-5a03f96bb317 | checkpoint | 2.1 Commencement of Placing
ef707d7e-1250-5ca3-aa31-f9ccb1db8783 | note | FREQUENCY: Prior to commencing Paving
78aca2a6-d74b-546f-a119-21a0bc0954e0 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
1a015b04-4c4d-5ac8-941a-c7617191de0e | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
19af8369-53b9-5a6e-92f5-76fe112922fb | note | INSPECTION/TEST METHOD: Visual Inspection
90236489-3370-5a72-82a7-57c529964cf6 | note | RECORD OF CONFORMITY: ITP Signed
f6e42286-5ddb-5091-b2e9-ea68365f703e | note | HP
b083fd84-1907-560e-a93e-685aff53ac02 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor / Superintendent
af4060a4-596d-5372-a85e-20691fa00488 | textbox | DATE:
5a76f65d-30a8-4373-a427-a1546a24cf18 | signoff | HOLD POINT AUTHORITY
066a912c-a82a-42bb-8f7c-ddf7a099727e | checkpoint | 2.2 Mix Design Confirmation
715e22b3-4876-5ced-860b-a76c1a9da9b8 | note | FREQUENCY: Each lot
aa987ecc-fc8f-5fc9-ad80-8f470f679eab | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt wearing and base layer mixes must abide to IFC drawings and be as specified in standard tram track drawings.
5f542931-f966-57da-a2c5-a62d0803da1f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09 STD_T9010
12e9bca9-dead-5adf-ba97-2ce68d67e260 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
4699e5cb-8de3-569f-b2e3-09933d42d623 | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
0088de17-89b8-56e9-8f81-95ae6287921f | note | HP*
c2acdf6d-a0da-585b-ab9b-8b5dfedbabc6 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
e37aea2c-893e-5084-a964-e0aebda7e992 | textbox | DATE:
043fa327-10a1-4a6a-bfff-b90e3f477410 | checkpoint | 2.3 Delivery of Mix
b16415b0-8a45-5cde-980d-05bf0c6371d7 | note | FREQUENCY: Each load
adbf83cf-e747-5ade-8641-6399b78ce5f3 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
037911d7-b282-5e44-adda-8b36f75b7e7a | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20 Table 407.111
56da7d1b-503d-529a-bcd6-847d2d68b8a5 | note | INSPECTION/TEST METHOD: Visual Inspection
52bf561f-44b0-5dc0-94fc-a61c96e11244 | note | RECORD OF CONFORMITY: Delivery Docket
9d12eb23-7832-50c1-a4dd-6dcd69b0b542 | note | WP
bc975bc8-d075-51c6-986f-ff99795438a4 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
8b021180-8e8f-57fe-902d-4a7dc5bf9af8 | textbox | DATE:
49595050-ad01-4523-a671-32948ea8d721 | checkpoint | 2.4 Traceability
9c8f22d0-0447-5953-9767-6165801a46a8 | note | FREQUENCY: Each lot
3391f3e9-c684-5d67-a89e-7eb61abee7cf | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
1d8be6b9-f383-59fc-aa4c-3750eb310dc8 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ddf03f5c-38a1-5b12-be0c-1dc60024eb47 | note | INSPECTION/TEST METHOD: Verify
e8589e75-6a45-5918-b419-c91c5e69d166 | note | RECORD OF CONFORMITY: Daily Lot Record
638ec7d6-40b3-5c10-acf2-8fa4598b3477 | note | IP
5f48aa88-93c8-5b6d-b756-fac2335086b7 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
064b67c7-0496-5c45-b8b4-5fa331be88d1 | textbox | DATE:
5912eb0f-17a7-44d8-8b50-be513abef043 | checkpoint | 2.5 Layer Thickness and Level Control
42451787-e5a8-5b28-b767-b58019b7bbfc | note | FREQUENCY: Regularly during paving
de8e04a8-391a-5bdd-87e5-923883369bd5 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
6eaee0eb-cd40-5564-865f-c01dc1611e4c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
1c5f88c7-3782-5eb6-8918-7ca0782c9822 | note | INSPECTION/TEST METHOD: Verify
0f624a6d-a677-58d6-a46d-120becbbedaf | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
a78ad95d-8482-5702-9a5a-b375e303ab4c | note | WP
646f6144-9150-55d1-a4d4-975c895a738f | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
4d290aef-d3a5-5713-96d4-435f8a5580f0 | textbox | DATE:
f1a38348-088c-4fba-b5e0-4c6b9298569b | checkpoint | 2.6 Surface Finish of Wearing Course
5f131282-68de-50bd-af0e-549f2abd3c66 | note | FREQUENCY: During paving and after final roll
b7da6a97-2ada-56b3-8c07-194b5a6f9e4e | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
b8336e7b-9f43-5eb6-bd8d-19d2ef71c37b | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
4bccd4ad-2665-52a2-b70c-eddcafecc099 | note | INSPECTION/TEST METHOD: Visual Inspection
d7c10bb5-6a00-5aea-8cd7-b95eed1f0fa8 | note | RECORD OF CONFORMITY: ITP Signed
6734527b-4359-5e6d-8eb7-06325a0302ac | note | WP
c9be4ce0-ab45-519c-8a7b-dce677132269 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
ee616819-cf06-53a7-8dfd-515b73037f5c | textbox | DATE:
22a3125f-689a-43a9-b9c5-7973bb6ca2da | checkpoint | 2.7 Alignment of layers not placed against concrete edge
c09a4929-7c0f-5eb9-9548-68c6cf0e88fa | note | FREQUENCY: During paving and at completion of work
0266c7c7-1aae-5983-b465-5127774c9832 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
c42fb1d3-ac8b-56e5-8dd3-dcb127bc3ff4 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv) Drawings
89612f37-d736-5e3f-8720-c6ef5143caa2 | note | INSPECTION/TEST METHOD: Visual Inspection
1a5b5df4-5976-5cec-a4ed-18bc3987afe4 | note | RECORD OF CONFORMITY: ITP Signed
b1d56df3-ea54-5775-8083-183378ae93c4 | note | IP
d10374cb-5788-5aab-a878-cc6017024869 | note | RESPONSIBILITY: Site Engineer / Asphalt Supervisor
2d822e83-42ef-50d8-90da-8e2793c594d3 | textbox | DATE:
ccc0c08e-f085-480c-89ac-70c5b1b17251 | section | 3 - Testing
ecb0fa6b-b1fd-4949-b869-c429ab9604e1 | checkpoint | 3.1 Compaction
eda76481-15a8-569c-8990-a78165b7ed0e | note | FREQUENCY: Per Lot
08eeaa51-d591-5112-96f3-3e79d8be703e | note | ACCEPTANCE CRITERIA:
507bc64e-dccc-59d2-8857-6f111eb74042 | note | ○ For wearing course layers <50mm, if characteristic density ratio is:
5401ebd9-629e-5b58-9516-af62d15f23c3 | note | • 94.0% or greater Accept lot
67387c2e-1808-5690-9237-651d2308efe6 | note | • 91.0% to 93.9% Lot may be accepted at reduced rate
3bc015ad-87e4-54e0-a80c-b57523bb1bd4 | note | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
376f3c0a-8999-5cbb-bd6e-75fb048fc7c9 | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
826fe862-ff3a-5cc0-836d-aa2540a4cf60 | note | INSPECTION/TEST METHOD: Verify
1438ce9a-eb69-5b53-91c5-6435103b618a | note | RECORD OF CONFORMITY: Test Report
e380982a-7db1-5167-b9cd-6304241043a4 | note | TP
e230ff84-9551-5dee-bade-15ce892b5a32 | note | RESPONSIBILITY: Site Engineer / FH Lab Technician
aeaf60f0-6800-5f3d-94c9-116ba20e94cb | textbox | DATE:
4179d23b-9e72-4a95-8e7a-eb7db415a594 | checkpoint | Final Inspection
9fd87725-abe5-54e0-8a2f-e60b9be13cdf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb5845a4-d4a9-5bbf-ba05-fbd8fff3d6f3 | textbox | Print Name:
a2110f3e-62fc-5b40-b807-ec9e1a5e159a | textbox | Position:
631a2c99-5ff5-546f-9bff-2a670c9deb04 | textbox | Date: