## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
53b5bd12-b8f5-40dc-8e4e-c89205d23345 | checklist | ITP-019 - Line Marking Rev3 | itp | ITP-019 - Line Marking
c333197b-4b37-4bc2-877c-63e7e2a5cb41 | section | 1 - Preliminary Works
39c7a9a2-59cb-4f63-8560-f8486361a183 | checkpoint | 1.1 Check for correct documentation
859b73a0-bb32-5974-b0c6-d9d67f1fa0d3 | note | FREQUENCY: Prior to commencing any activity
d0838437-d108-5786-9497-c05f4d766c7b | note | ACCEPTANCE CRITERIA:
6a145315-a5e5-5db2-90ce-fad45952c11c | note | • Ensure that all employees and subcontractors are:
8aef68cd-e8b0-5e1e-87e2-73e420f34b8e | note | – using the correct and complete set of drawings
8c1930a7-e415-5626-820e-e58dd45dc675 | note | – all drawings are the latest revision
b0dc9599-008b-5f47-9369-08a4d13f483c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2ea4ddd7-0112-5561-b304-c2944702fae4 | note | INSPECTION/TEST METHOD: Visual inspection
42e68f4c-2741-5276-87ef-6a6de3c2de8c | note | RECORD OF CONFORMITY: This ITP signed off
b4d485c2-fa68-534e-bb3a-e6b6254c45ee | note | WP
88cdf8b4-4f5b-5031-93bd-da94e76d7eec | note | RESPONSIBILITY: Fulton Hogan Engineer
046ff6c9-c27c-53b6-9181-6e0935abf205 | textbox | DATE:
0c96f5de-02c3-4a3e-849a-fe73262a6e5b | checkpoint | 1.2 Implementation of all measures and controls
bd9b69b4-f21a-59e7-8154-ea5cd36a5d77 | note | FREQUENCY: Prior to commencing any activity
3d2459ae-44a9-5df3-aedc-ab19d2ef48a6 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
f46301e4-a551-52a9-a7b1-fb9c9180eac3 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
8e3a1bdb-7d37-50a5-893c-b29e23288035 | note | INSPECTION/TEST METHOD: Visual Inspection
dc4e04f8-7007-589b-af7d-c4e3dce91b8b | note | RECORD OF CONFORMITY: This ITP signed off
bd3d7976-870f-56d3-9a99-4fceb5868d93 | note | WP
35510ca2-e6c6-54d6-aeb8-aa8d63f4b6b0 | note | RESPONSIBILITY: Fulton Hogan Engineer
72da6511-8a34-5ec4-8b84-145ee0b32eab | textbox | DATE:
89e25256-b4c0-4d80-b4a6-6094e849c6e3 | section | 2 - Construction Works
5870b843-cc7a-4fc4-9150-be2cf80d4c5b | checkpoint | 2.1 Setting Out
f341e104-e201-593f-9fd1-a17703555d2a | note | FREQUENCY: Prior to start
b757428a-1625-5409-ba59-50fc03a95dc4 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
4f4c2d95-a2cd-5f02-8112-dbe090d7ff80 | note | REFERENCE DOCUMENTS: Drawings
e422bb76-cd07-5f33-8942-cb04ecb28c41 | note | INSPECTION/TEST METHOD: Visual Inspection
89345a0f-e9eb-5d01-a958-c90f2651cf8e | note | RECORD OF CONFORMITY: This ITP signed off
348a6e69-f992-5f66-9671-ac080920bf74 | note | IP
8fe8e4e9-f145-5aaf-b584-fed18f17f2b1 | note | RESPONSIBILITY: Fulton Hogan Engineer
fbb819ec-315d-5a4d-9d1d-ce3e2ac8400c | textbox | DATE:
37eba590-7fa1-4cb5-8683-d63c651990f8 | checkpoint | 2.2 Position of Markings
bbce3099-a8c8-57b5-9581-36cd8b505698 | note | FREQUENCY: Prior to application
86383220-3eab-5ee2-855a-c0ba8079d857 | note | ACCEPTANCE CRITERIA:
f6a719cd-21bc-5d68-9a84-99b1ffcd8052 | note | • Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
cea0e6b5-6a28-5590-8470-4533954f1014 | note | • Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the
6358ced7-3a5f-53cb-8abc-7a8a189932c5 | note | • VicRoads Traffic Engineering Manual Volume 2.
5ed37d5f-18ec-5b0b-9ee6-c75d7f36eeb4 | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010
7352d7f8-91f2-50a5-a8a7-8220cf01a711 | note | INSPECTION/TEST METHOD: Visual inspection
4184de50-1be8-5a76-a7e5-618fd096da49 | note | RECORD OF CONFORMITY: This ITP signed off
b5c2afaf-7649-5e55-ad84-192dcd35fff8 | note | HP
a20a64d8-d371-544b-9a54-1228b159095b | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
f64d78f6-79c1-5196-a095-a50b0156a94d | textbox | DATE:
c4566728-7da1-4a5d-9a47-e7075787ce14 | signoff | HOLD POINT AUTHORITY
6d4c6efd-67ed-489b-8563-115c6239bf6d | checkpoint | 2.3 Tolerance of Pavement Markings
76dc4ee0-089b-5893-93a9-9704e9cf481b | note | FREQUENCY: Each lot
9d54a281-1f70-5c82-afbe-587d39a8a758 | note | ACCEPTANCE CRITERIA:
4d5c504a-ca79-5ba5-9d4c-473e1e8ef371 | note | • The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings.
8fae1102-ee25-53ae-a9ad-bee2451b3334 | note | • The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
e033d5b3-cb1a-5eeb-8454-376b356ca3f6 | note | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
f761846c-b9a2-5750-89aa-1669f8ec15f2 | note | INSPECTION/TEST METHOD: Visual inspection
7970d78b-83a6-5968-bb55-40558571685e | note | RECORD OF CONFORMITY: This ITP signed off
715e19a1-deef-59d9-b73b-3a5779534036 | note | IP
740745fb-9631-5d49-9532-57967d40e0a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
777503a4-d222-5fec-ae4a-2d9750961ba2 | textbox | DATE:
2d277e33-31c2-4b77-adc0-5958fc38477b | checkpoint | 2.4 Preliminary Works Raised Pavement Markings
241b9a85-89d0-5959-aa2c-d2483ebb8513 | note | FREQUENCY: Each lot
0361b2a6-cda3-53f8-8fe0-d23d4f785fc9 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
48896ac9-5801-59dc-a96f-cc90d27fbb29 | note | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
d2057a55-517c-549c-aa45-c5f6533b68de | note | INSPECTION/TEST METHOD: Visual inspection
7f81f35b-d7d5-5362-8778-d0d0f497aeb7 | note | RECORD OF CONFORMITY: This ITP signed off
b58dbf16-9343-56a0-8125-5b583dea5ff7 | note | IP
2be56757-8984-552f-abb0-f80f1986575d | note | RESPONSIBILITY: Fulton Hogan Engineer
41d835c4-ab0d-5556-90c8-2ced6a32cbd9 | textbox | DATE:
85a9ea44-5e21-4d2b-833e-1c97cfc16f77 | checkpoint | Final Inspection
cfc8c898-358d-54e5-9d9d-fae1071d6f5d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d0932b43-5f8b-5a89-add2-9a92bbaeeb88 | textbox | Print Name:
45ce201c-9503-5812-b105-cbef59e45401 | textbox | Position:
f2db0e07-d575-5cda-a2b9-d2542156b444 | textbox | Date: