## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP TC01 Pre-Pour Inspection |  | ITP TC01 Pre-Pour Inspection |  | e427a2f3-801e-490a-8275-16f2249dcd92
| section | Pre Pour / Post Pour
| checkpoint | Tendon installation as per approved drawings
| checkpoint | Anchor and dead-end setup
| checkpoint | Tendon chairing
| checkpoint | Grout hose installation
| checkpoint | Engineer inspection mark review and closeout
| checkpoint | Pour completed
| checkpoint | IR-01 (Interspan) Inspection Report (To be uploaded as reference)
| checkpoint | TC-01 (Interspan) Pre pour Inspection (To be uploaded as reference)
| checkpoint | TC-02 (Interspan) Watching Concrete Pour (To be uploaded as reference)
| section | Initial Stressing
| checkpoint | Safe access for initial stressing
| checkpoint | Concrete strength (should be more than 7 MPa)
| checkpoint | Anchorage and strands condition
| checkpoint | Jack Calibration, current
| checkpoint | Initial stressing completed
| section | Final Stressing
| checkpoint | Safe access for final stressing
| checkpoint | Concrete strength (should be more than 22 MPa)
| checkpoint | Anchorage and strands condition
| checkpoint | Jack Calibration, current
| checkpoint | Final stressing completed
| checkpoint | TC-03 (Interspan) Stressing Inspection (To be uploaded as reference)
| section | Grouting
| checkpoint | Safe access for grouting
| checkpoint | Anchor pockets cut and sealed
| checkpoint | Grout hoses condition
| checkpoint | Grouting completed
| checkpoint | TC-05 – (Interspan) Grouting (To be uploaded as reference)