## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - C1603A - Waikare Gorge Decent RW - Asphalt | itp |  |  |  |  | ITP - C1603A - Waikare Gorge Decent RW - Asphalt
section | 1 - Pre Construction
checkpoint | CPS Approver
textbox | Project Manager
textbox | Project Engineer
textbox | Site Engineer
checkpoint | Quality Approver
textbox | Quality Engineer
textbox | CPS Engineer
textbox | CPS Manager
checkpoint | 1.1 - Survey Setout - Milling
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out on site, confirmed by CPS Engineer
label | Conformance Criteria - Visual inspection, Survey
label | Records - Survey, Photos, COR
checkpoint | 1.2 - Paving Plan
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Construction team are to provide a paving plan detailing where joints are going and how the asphalt handled to ensure it arrives onsite at a suitable temperature
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Agreement on methodology and joint location
label | Conformance Criteria - Review
label | Records - Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Milling Existing AC
label | ACTION (Hold, Monitor, Witness) - MONITOR
label | Detail - Milling undertaken to correct depth of nominal thickness
label | Frequency - During operation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Design Report, depth of milling confirmed by CPS
label | Conformance Criteria - Visual Inspection
label | Records - COR
section | 2 - Material Compliance
checkpoint | 2.1 - Binder Penetration Grade
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with NZTA M01: 2020 - Table 6.1 and TNZ P11: 2007 - Table 5.2 Lab Mix
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NZTA M01: 2020 - Table 6.1
label | ○ TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
label | Conformance Criteria - Property Test
label | Records - Lab Report
checkpoint | 2.2 - Coarse Aggregate Source
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with TNZ P11: 2007
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - 230kN minimum Crushing Resistance AA or BA Weathering Quality Index
label | Conformance Criteria - Property Test
label | Records - IANZ Report
checkpoint | 2.3 - Blended Coarse Aggregate Production
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - To comply with TNZ P11: 2007
label | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - 2.25 Max Particle Shape 98% Broken Faces
label | ○ Report Value-5 minimum Cleanness Value
label | Conformance Criteria - Property Test
label | Records - IANZ Report
checkpoint | 2.4 - Asphalt Mix Design
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Mix Design approved including peer review
label | Frequency - 10 days minimum prior to paving
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Select approved mix design for use on this site and submit to CPS
label | Conformance Criteria - Testing
label | Records - JMF compiled with test records
section | 3 - Construction
checkpoint | 3.1 - Survey Setout - Paving
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Determine paving run start/stop locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure accurate survey setting out is in place.
label | Conformance Criteria - Survey, Visual Inspection
label | Records - Subcontractor QA
checkpoint | 3.2 - Weather Check
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Ensure weather conditions are acceptable for work to proceed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C
label | Conformance Criteria - Weather Forecast
label | Records - Subcontractor QA
checkpoint | 3.3 - Surface Preparation
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Ensure previous layer is broomed clean.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Truck broom to have been used and surface approved by CPS Engineer
label | Conformance Criteria - Visual inspection
label | Records - Photos
checkpoint | 3.4 - Membrane seal
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Application as per Design Requirements (Chip size / binder application rate)
label | Frequency - Prior to asphalt
label | ○ Spray sheet for everyday.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Application as per Design Requirements (Chip size / binder application rate)
label | Conformance Criteria - Spray sheet, QA records
label | Records - Spray sheet, QA records
checkpoint | 3.5 - Temperature of Asphalt for paving
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Check temperature of Asphalt for every truck entering the paver.
label | Frequency - Any truck load
label | Inspection / Test Method submission, visual inspection, testing, measure, review - The asphalt shall have a minimum temperature of 80 degrees Celsius on completion of compaction.
label | Conformance Criteria - Temperature Check
label | Records - Subcontractor QA
checkpoint | 3.6 - Thickness (Cores)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Layer thickness measured from core samples.
label | Frequency - Each core taken for density
label | Inspection / Test Method submission, visual inspection, testing, measure, review - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
label | Conformance Criteria - Core Test
label | Records - Lab test report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Compaction and air voids
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - To comply with NZTA M10: 2023 OR project specification
label | Frequency - As per specification
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NZTA M/10: 2020 - section 9.9.3
label | Conformance Criteria - NDM for Quality Control Only
label | Records - IANZ Report, QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Surface Finish and Roughness
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - No visible cracks, defects related to poorly constructed joints, water ponding,
label | Frequency - Post Construction Site walkover.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - No visible crack, no obvious defect related to poorly constructed joints. No areas with water ponding. Good ride quality.
label | Conformance Criteria - Visual inspection.
label | Records - COR
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Completed report
label | Conformance Criteria - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - All RFI, NCRs and site changes must be recorded.
label | ○ Signed and dated
label | Conformance Criteria - Drawings, Survey as-built
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - WITNESS
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all QA is uploaded into ConQA / Procore
label | Conformance Criteria - Document Review
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - HOLD
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all parties have signed and approved ITP
label | Conformance Criteria - Document Review
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT