## Construction ITP
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: |  |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | D2102A-ID1507 Maraetaha Bridge 5 |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-??-???? |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage: SH2 RS461 RP - 7.780
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1 : RECEIVING INSPECTIONS
1.1 | 2t Ecogreen/Kyowa bags | W | Consistency with Construction Specifications 2-U3436.BM(14) S02-S03 | Prior to commencement | Manufacturers certificate | Purchased from Bluemont or similar approved | Material cert, delivery dockets | Site Engineer
Traceability of all materials delivered to site
1.2 | Class D A39 Geotextile | W | Consistency with Construction Specifications 2-U3436.BM(14) S02-S03, TNZ F/7 | Prior to commencement | Manufacturers certificate | TNZ F/7 filtration class 1 strength Class D | Material cert, delivery dockets | Site Engineer
1.3 | Granular Backfill AP65 | W | SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2 | Prior to commencement | Material source property reports | AP65 shall be hard, durable, well graded, free draining material with maximum particle size of 65mm and not more than 5% by mass passing a 75-micron sieve | Material cert, delivery dockets | Site Engineer
1.4 | Rock Infill for Eco-Green Rock Bags | H | SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2 | Prior to commencement | Material source property reports | Sound, hard, durable rock resistant to weathering shall be used as rock bag infill material. Sized from 50mm up to 175mm but not exceeding 200mm. Should be round in shape and not flat. | Material cert, delivery dockets | Site Engineer | CPS Engineer
Section 2 : IN PROGRESS INSPECTIONS (Buttress)
2.1 | Survey Setout and joint site visit | H | Consistency with 2-U3436.BM(14) S01-S03 | Prior to commencement | Survey | CPS Engineer to confirm and agree the extent of works including rock bag placement and survey set-out | Survey receipt, CPS COR Report | Site Engineer | CPS Engineer
2.2 | Vegetation Clearance and removal of loose debris | W | 2-U3436.BM(14) S01-S03 | Prior to commencement | Visual inspection | Remove and clear the vegetation | Photo's | Site Engineer
2.3 | Subgrade Excavation | H | 2-U3436.BM(14) S01-S03 | During Construction | Visual inspection | CPS Engineer to inspect foundation level when required depth has been met. Scala check sheet (to 1.5 metres) | Scala Check sheet (CS-4000), CPS COR report | Site Engineer | CPS Engineer
2.4 | Ground Improvements | H | 2-U3436.BM(14) S01-S03 | Prior to commencement | Document Review | Any area that requires Ground Improvements (i.e. additional undercuts) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence | CPS COR report | Site Engineer | CPS Engineer
2.5 | Granular Backfill AP65 | H | Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03, TNZ F/1 | At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer | Clegg hammer or NDM testing | Comply with TNZ F/1. | Test Reports, Photo's | Site Engineer | CPS Engineer
Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
2.6 | Class D (A39) Geotextile | W | Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03 | During Construction | Visual Inspection | Installation between the AP65 fill and rock filled bags. | Photo's | Site Engineer
The fabric shall be laid and overlapped as per manufacturers recommendations
2.7 | Rock Bag installation | H | Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03 | During Construction | Visual Inspection | Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V. | Photo's, CPS COR report | Site Engineer | CPS Engineer
The final layer will be determined by the CPS Engineer on site
2.8 | Bulk Fill Placement access roads | M | Consistency with Construction Drawing 2-U3436.BM(14) S01-S03, NZS4431:2022, TNZ F/1 | During Construction | Visual Inspection | Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade | Bulk Fill Earthworks check sheet (CS-4020), Photo's | Site Engineer
2.9 | Topsoiling | W | 2-U3436.BM(14)-S03 | During Construction | Visual Inspection | Topsoil shall be spread out on the disturbed area at a nominal thickness of 100mm but not less than 50mm nor more than 120mm. Batter steeper than 2:1 are not to be topsoiled. | Photos | Site Engineer
2.1 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
2.11 | Grassing | W | 2-U3436.BM(14)-S03 | During Construction | Visual Inspection | Grassing should be superphosphate at a rate 50grams per square meter, Grass seed shall be sown at the rate of 25 grams per square metre bare seed weight | Photos | Site Engineer
Section 4 : Final Inspection and Handover
3.1 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
3.2 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date: