## Network Drainage
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | G1302A Culvert 33 – SH38 RS179 RP5.805 |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Network Drainage |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert SharePoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location: SH38 at RP179/5.805
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Setout inlet & outlet points with inverts as required by Contractor to construct to design | Prior to commencement | Survey (As agreed with Engineer) |  | Survey receipt | Site Engineer
2 | Locate existing services by hand digging | H | Ensure all services conflicting with the line of trench has been exposed by hand digging/hudro excavation | Prior to commencement | Potholing | All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services | As-built Drawings Doc. Review | Site Engineer
3 | Trenching and Excavation | W | Inspect trench profile and ensure it is correct to lines and levels to design | Daily | Visual/Inspection | Line and level is correct |  | Site Engineer
4 |  | W | Ensure trench width is sufficient to provide enough space on either side of the pipe | Daily | Visual/Inspection | D/6 or 150mm whichever is greater on either side of the pipe |  | Site Engineer
5 | Foundation Compliance | H | Test formation level on completion of excavation to check if undercut required | As stated | Visual Inspection by Designer | Designer to inspect formation level at outfalls / inlets. | CS-4025 Drainage Line Record Check Sheet | Site Engineer | Design Engineer
6 | Pipe Bedding Material Compliance | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Compliance with requirements from Specifications | Lab Test Report | Site Engineer
7 |  | H | Backfill Construction Material | 1 test per 50m | Lab Testing | Solid wall pipe – Pea Metal < 7mm | CS-4025 Drainage Line Record Check Sheet | Site Engineer
8 | Bedding | W | Bedding - Ensure correct thickness of bedding is placed | Daily | Visual/Inspection | Type 3 support as per drawing | CS-4025 Drainage Line Record Check Sheet | Site Engineer
9 | Pipes and Precast Units | H | Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Each delivery to site | Certification | Comply with Section 3 AS/NZS2566.2 | Delivery Dockets | Site Engineer
10 | Pipe Laying | W | Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm | Daily | Visual/Inspection | Line and level to follow existing pipe | CS-4025 Drainage Line Record Check Sheet | Site Engineer
11 |  | W | Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness | Prior to backfilling | Visual/Inspection | No defects/ gaps / pipes are aligned correctly | Photos | Site Engineer
12 |  | W | As-built survey of pipes installed | Once line is completed between 2 structures | Survey | Invert level <= 5mm and grade <= 3mm from design levels | Survey Receipt | Site Engineer
13 | Design Engineer Pre backfill Inspection | W | Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps. | Daily | Visual Inspection | Compliance with the Specification | CS-4025 Drainage Line Record Check Sheet | Site Engineer | Design Engineer
14 | Pipe Backfill Compliance | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40 | CS-4025 Drainage Line Record Check Sheet | Site Engineer
15 |  | H | Backfill Construction Material | 1 test per 100m | Lab Testing | Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40 | Lab Test Report | Site Engineer
16 | Backfilling | W | Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material. | 1 test per 20 m length of trench per 300mm lift | Testing | 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent | Lab test results | Site Engineer
17 | Structure installation (Manhole, Catchpit, Wingwall) | W | Structures to be installed to the design survey location and level | During structure construction | Visual/Inspection | As Built Survey | CS-4006 Manhole Catchpit Board Check Sheet and Survey receipt | Site Engineer
18 | Survey As Built | W | Arrange as-built survey of the structure and all invert levels | Once installed | Survey | As Built Survey | Survey Receipt | Site Engineer
20 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
21 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date:
Note on F16: Insert Frequency here
Note on H16: List Tests required from Spec & PRs here with criteria for a passing test - use multiple rows if required