## Subsoil Drainage
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004C White Pine Bush |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Subsoil Drainage |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: SH2 North – RS0608 RP14.530 |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location: ID:278
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | W | Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain. | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
2 | Material Compliance | H | Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter | Upon delivery to site | Ensure delivery docket matches materials delivered | 100mm diameter Drain flow TNZ F/2 Grade pipe | Delivery docket | Site Engineer
3 |  | H | Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip) |  | Visual inspection | Ensure clean drainage chip | Delivery docket | Site Engineer
4 |  | H | Ensure the bidim material is A14. A similar material maybe used but it must be approved | Upon delivery to site | Ensure delivery docket matches materials delivered | Ensure geotextile is approved for use | Delivery docket | Site Engineer
5 | Trenching | H | Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level. | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet | Photo / CS-4001 Subsoil Dipsheet Check Sheet | Site Engineer
6 |  | H | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | 10m intervals | Visual inspection and measurement | Ensure trench line and levels match the design drawings | Photo / CS-4001 Subsoil Dipsheet Check Sheet | Site Engineer
7 |  | H | Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works. | As required | Visual Inspection | Design Engineer to instruct action and record on dip sheet and as built drawing | Photo / CS-4001 Subsoil Dipsheet Check Sheet | Site Engineer
8 | Bedding, pipe installation and Backfill. | H | Upon completion of trenching Bidim 14 or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material | 10m intervals | Visual inspection | Ensure material covers the trench and is pinned in place | Photo / CS-4001 Subsoil Dipsheet Check Sheet | Site Engineer
9 |  | W | Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo / CS-4001 Subsoil Dipsheet Check Sheet | Site Engineer
10 |  | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
11 |  | H | As built Survey the Pipe before backfill | 10m intervals | Document review | Consistency with Subsoil Details | As-built receipt | Site Engineer
12 |  | W | Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench | - | Visual inspection | Ensure good coverage | Photos | Site Engineer
13 |  | W | Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place |  | Visual inspection |  |  | Site Engineer
14 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
[5 empty] | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: